## CR Log Jun-Jul 2026
JAL REKHA PROJECT — CHANGE REQUEST LOG (SIMPLE VIEW) ¦ June–July 2026
Plain-language summary of every CR – one line per point. Prepared by: Dheeraj Motiyani ¦ Reviewed by: Tapan Khandelwal
CR No. | CR Code | Raised By | Logging Date | CR Description (Simple) | Module | Sub-Module | Impact (Simple) | Status | Priority | Risk | Remarks
1 | OMB-JUN-2026-001 | MD Sir / Kapil Sir | 01-Jun-2026 | Make Submission Letter & Tax Invoice compulsory before Contractor can forward a draft bill to GM (PIU). | O&M Billing | Save as Draft – Mandatory Upload | Draft can still be saved anytime; only forwarding is blocked until documents are attached. | Open | High | Medium | Same rule as Cube Testing & Sahbhagita Save-as-Draft.
2 | OMB-MAY-2026-020 | MD Sir | 16-Jun-2026 | Update Residual Pressure report with District, Block, Village, Consumer, Pressure, Remark & penalty columns. | O&M Billing | Residual Pressure | New columns added as per the pressure-report format. | Open | Medium | Low | Follow OM_RA_Bill_Report.pdf format.
3 | OMB-JUN-2026-002 | MD Sir | 20-Jun-2026 | Add complaint dates, 48-hour flag, and penalty relaxation option to Complaint Redressal Sheet. | O&M Billing | Complaint Redressal Sheet | 48-hour flag is calculated automatically from the complaint dates. | Open | Medium | Low | Linked to Residual Pressure CR.
4 | OMB-MAY-2026-006 | MD Sir | 01-Jun-2026 | New O&M billing approval path: Firm → GM PIU → either direct to GM O&M, or full chain via TL SQC up to MD. | O&M Billing | Workflow Redesign | Two approval paths now available depending on the case. | In Progress | High | High | Use the new Manage Bill page.
5 | OMB-MAY-2026-002 | MD Sir / Kapil Sir | 22-May-2026 | Contractor selects a bill and the system auto-generates the Abstract, tagging all villages. | O&M Billing | Abstract Generation | No manual village selection needed. | In Progress | High | Medium | Linked to the 8th Bill.
6 | OMB-JUN-2026-003 | MD Sir | 18-Jun-2026 | Abstract report split into Village-wise and Combined activity views, same style as Sahbhagita. | O&M Billing | Abstract Bill – Category Filter | Same RA(1)–RA(12) bill numbering used. | Open | High | Medium | Reuses Sahbhagita filter logic.
7 | OMB-MAY-2026-005 | MD Sir | 22-May-2026 | Merge all ~20 bill documents into a single PDF and fix the landscape-page display issue. | O&M Billing | Bill PDF Merge | Static documents once per quarter; other documents refreshed monthly. | In Progress | High | Medium | Includes GM, SQC, Firm, Form 27A, MB, Abstract.
8 | OMB-MAY-2026-008 | MD Sir | 03-Jun-2026 | Show Contractor's mistakes to SQC, TL and GM across all logins. | O&M Billing | Mistake Visibility | Improves error tracking between roles. | Open | Medium | Medium | Related to Bill PDF Merge CR.
9 | OMB-MAY-2026-015 | MD Sir | 09-Jun-2026 | Redesign the document-upload screen into 3 sections: Firm, TL/SQC, GM PIU. | O&M Billing | Document Upload Screen | Each document gets Upload / Download / View buttons. | In Progress | High | Medium | Multiple uploads allowed for select documents.
10 | OMB-MAY-2026-003 | MD Sir / Kapil Sir | 22-May-2026 | Add a GST number field to the contractor/firm profile; show it on the bill and abstract. | O&M Billing | GST Integration | One-time master-data entry per contractor. | Open | Medium | Low | Confirm GST data source with Rakesh Sir.
11 | OMB-MAY-2026-001 | MD Sir / Kapil Sir | 22-May-2026 | Add CDAC e-Sign (Aadhaar-based) for Bill, Submission Letter and Tax Invoice on Web & Mobile. | O&M Billing | E-Sign Integration | Physical signature no longer required. | Open | High | High | Needs CDAC coordination.
12 | OMB-MAY-2026-004 | MD Sir | 22-May-2026 | Auto-generate the TL Recommendation Letter through the E-Office system. | O&M Billing | TL Letter – E-Office | Removes manual letter upload step. | Open | High | High | Needs E-Office integration.
13 | OMB-MAY-2026-014 | MD Sir | 08-Jun-2026 | Add 'View Pending Bills' and 'Manage Bill' screens for GM PIU and GM O&M. | O&M Billing (Aaklan) | Pending Bills View | Already-generated bills are shown in a table. | In Progress | High | Medium | Part of the Aaklan module.
14 | SHB-JUN-2026-004 | MD Sir | 18-Jun-2026 | Split Sahbhagita report into Village-wise (32) and Combined (22) activities with a V/C/A filter. | Sahbhagita | Activity Report Filter | Easier activity-wise reporting. | In Progress | High | Medium | Uses the master activity list.
15 | SHB-MAY-2026-007 | MD Sir | 01-Jun-2026 | Allow multi-select of RA bills (RA1–RA12) with a Withhold Bills option. | Sahbhagita | Multi-Select Bill Dropdown | Faster bill selection for the user. | Open | Medium | Low | —
16 | SHB-MAY-2026-013 | MD Sir | 04-Jun-2026 | Make the Village Name clickable to preview its uploaded activity document. | Sahbhagita | Hyperlink Preview | Quick document preview without leaving the report. | In Progress | Medium | Low | —
17 | SHB-MAY-2026-012 | MD Sir | 04-Jun-2026 | Future: AI photo/video check at CP Manager stage to catch duplicate proof photos. | Sahbhagita | AI Photo Verification | Prevents fake or reused proof photos. | Open | Low | High | Future scope, not immediate.
18 | CUBE-JUN-2026-005 | MD Sir | 16-Jun-2026 | Generate the Cube ID before photo upload; show rejected cubes back to the Contractor. | Cube Testing | Cube ID & Rejected Data | Faster ID creation and easier correction by Contractor. | Completed | Medium | Low | Already delivered (16-Jun-2026).
19 | MSTR-JUN-2026-006 | MD Sir | 18-Jun-2026 | Lock Scheme, Village and OHT master data once it is used in Dhara, O&M or Asset records. | Master | Master Data Lock | Prevents accidental edits to data already in live use. | Open | High | High | Extends the Dhara lock rule to Master data.
20 | DHARA-MAY-2026-009 | MD Sir | 03-Jun-2026 | Lock a Dhara report once GM approves it; only additions allowed after that, no edits. | Dhara | Approved Report Lock | Protects approved data from being changed later. | In Progress | High | High | GM can still add a penalty point.
21 | DHARA-MAY-2026-021 | MD Sir | 01-Jun-2026 | Make Remark, Photo Upload, Forward and Backward options optional on all logins. | Dhara | Non-Mandatory Options | Faster submission since these steps no longer block the user. | Completed | High | Low | Live since 19-Jun-2026.

## Summary
CR Summary – June–July 2026
Module | Total CRs | Completed | Still Pending
O&M Billing | 12 | 0 | 12
O&M Billing (Aaklan) | 1 | 0 | 1
Sahbhagita | 4 | 0 | 4
Cube Testing | 1 | 1 | 0
Master | 1 | 0 | 1
Dhara | 2 | 1 | 1
TOTAL | 21 | 2 | 19