## Cube Testing Code Review Defect
Internal Code Defects Review-Cube Testing
S.no. | CR | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Defects | Recommendation of Review | Compliance Status | Date
CYCLE -4
1 |  | JAL REKHA | CUBE TESTING | Contractor Login | ANAND GOUR | SUSHIL PATEL | 1.Contractor history pagination resets to the first page after applying filters or refreshing the data. | Verify that the current page number is retained after applying filters, searching, or refreshing the data. Perform regression testing with different record counts and ensure pagination behaves consistently across all scenarios. | Closed
2 | [6 empty] | 2.Duplicate Cube Inspection records are created when the same Contractor RFI is submitted multiple times. | Implement server-side duplicate validation based on unique business keys such as Contractor ID and RFI Number. Also, disable multiple clicks on the Submit button until the API response is received to prevent duplicate record creation. | Closed
3 |  |  |  | FE Login | ANAND GOUR | SUSHIL PATEL | 1.Inactive or disabled FE users are able to log in successfully through the Mobile FE Login API. | Validate the user's active status before generating the authentication token. Include regression testing for active, inactive, and blocked user accounts to ensure only authorized users can access the application. | Closed
4 | [6 empty] | 2.The system allows FE users to submit Cube Inspection before the configured 7-day or 28-day validation period. | Verify the date validation logic at both the application and database levels. Test all possible scenarios for 7-day and 28-day inspections to ensure inspections are allowed only within the configured timeline. | Closed
5 | [6 empty] | 3.Cube Testing reports displayed to SQC-TPIA users are missing recently completed FE inspection records. | Verify the report query, API response, and synchronization process to ensure all completed FE inspections are fetched correctly. Perform end-to-end validation by comparing report data with the database records to confirm data consistency. | Closed
6 |  |  |  | GM-SQC-TPIA Login | SUNIL THAKUR | NEHA SONI | 1.The Pending Action page displays records that do not match the configured 7-day or 28-day inspection criteria. | Review the business logic used to identify pending records for both inspection cycles. Validate the filtering criteria with different date combinations and ensure the pending list accurately reflects eligible records. | Closed
3 | [6 empty] | 2.The Summary Report continues to display the previous RFI status even after the GM updates the request status. | Verify that the status update is committed successfully and reflected in all report queries. Perform end-to-end validation to ensure report data remains synchronized with the latest database updates. | Closed
4 |  |  |  | CR | SUNIL THAKUR | NEHA SONI | 1.Users logged in with the SQC role can access TPIA-specific pages and APIs, resulting in unauthorized access to TPIA functionality. | Verify role-based authorization at both the UI and API levels to ensure users can access only the functionalities assigned to their roles. Perform regression testing for SQC, TPIA, GM, Contractor, and FE roles to confirm that access permissions are enforced consistently across the application. | Closed