## Scheme Month Tracker
S.No | Scheme ID | Scheme Name | Apr | May | Jun | Months Billed (Count) | Months Pending | Status | Bill Finalize / Save As Draft
1 | 4 | Aarniya Bahadur | Yes | Yes | Yes | 3 | None | Complete (Q1) | Save as Draft
2 | 20 | Begamganj-Gairatganj | Yes | Yes | Yes | 3 | None | Complete (Q1) | Save as Draft
3 | 32 | Dampoh - Patera | Yes | No | No | 1 | May, Jun | Pending | Save as Draft
4 | 46 | Ganga Bavdi | Yes | Yes | Yes | 3 | None | Complete (Q1) | Save as Draft
5 | 56 | Gunawad | Yes | Yes | Yes | 3 | None | Complete (Q1) | Save as Draft
6 | 69 | Karanpura -1 | Yes | Yes | Yes | 3 | None | Complete (Q1) | Save as Draft
7 | 90 | Majoli | Yes | Yes | Yes | 3 | None | Complete (Q1) | Save as Draft
8 | 96 | Mohkhed | Yes | No | No | 1 | May, Jun | Pending | Save as Draft
9 | 98 | Nagda | Yes | Yes | Yes | 3 | None | Complete (Q1) | Save as Draft
10 | 99 | Narhela | Yes | Yes | Yes | 3 | None | Complete (Q1) | Save as Draft
11 | 104 | Neelkhanth - Nasrullaganj | Yes | Yes | No | 2 | Jun | Pending | Save as Draft
12 | 119 | Punjapura | Yes | Yes | Yes | 3 | None | Complete (Q1) | Save as Draft
13 | 121 | Rajond | Yes | No | No | 1 | May, Jun | Pending | Save as Draft
14 | 126 | Sagad-Hinotiya Mali | Yes | No | No | 1 | May, Jun | Pending | Save as Draft
15 | 144 | Udgawan | Yes | No | No | 1 | May, Jun | Pending | Save as Draft
Total Schemes: | 15
Complete (Apr+May+Jun): | 9
Pending (Incomplete): | 6
Bill Finalize / Save as Draft | Save as Draft

## Pending Schemes
Scheme ID | Scheme Name | Bill Started In | Pending Months | Remarks
32 | Dampoh - Patera | Apr | May, Jun | Follow-up required for RA bill submission
96 | Mohkhed | Apr | May, Jun | Follow-up required for RA bill submission
104 | Neelkhanth - Nasrullaganj | Apr, May | Jun | Follow-up required for RA bill submission
121 | Rajond | Apr | May, Jun | Follow-up required for RA bill submission
126 | Sagad-Hinotiya Mali | Apr | May, Jun | Follow-up required for RA bill submission
144 | Udgawan | Apr | May, Jun | Follow-up required for RA bill submission