## Sheet1
Date Wise Time Sheet
Time Sheet entry Date From : 01/06/2026 To 30/09/2026 Current Date & Time : October 6, 2026 at 03:16:48 PM
Sr.No | Resource Name | Resource_Location | Project Name | Sprint Name | Sprint Start Date ¦ End date | Module Name | Activity Name | Task Assign Date | TimeSheet Entry date | Task Name | Assign Hours | Consumed Hrs | Work Status By Resource | Work Status By PM | Action Performed by Resource
1 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Documents | Documentation of CMMI and Attneding Audit meeting | 01/06/2026 | 01/06/2026 | CMMI documents preparation and show casing to audit team | 16.00 | 6.00 | WIP | Yet To Update | Estimation, User stories creation of Cycle 4 jal rekha
2 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Sprint 2: Parakh Customization for Mandir Nayas and Asset Survey for Indore MC | 18/05/2026 ¦ 17/06/2026 | Gwalior Collectorate-School, Hostel, Anganwadi, Health Center | Requirement Gathering School, Hostel, Anganwadi, Health Ceter | 01/06/2026 | 01/06/2026 | Review and Changes in Gwalior form and Hospital Patient feedback form | 6.00 | 2.00 | WIP | Yet To Update | Minor column level field changes into the form of Gwalior Anganwadi school and hostel forms
3 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Sprint 2: Parakh Customization for Mandir Nayas and Asset Survey for Indore MC | 18/05/2026 ¦ 17/06/2026 | Guna Collectorate | Patient feedback & QR Code integration functionality in Form of Parakh | 01/06/2026 | 02/06/2026 | Guna Hospital Patient feedback form Requirement analysis and Changes | 6.00 | 3.00 | WIP | Yet To Update | Patient feedback form creation and testing
4 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Sprint 2: Parakh Customization for Mandir Nayas and Asset Survey for Indore MC | 18/05/2026 ¦ 17/06/2026 | Gwalior Collectorate-School, Hostel, Anganwadi, Health Center | Requirement Gathering School, Hostel, Anganwadi, Health Ceter | 01/06/2026 | 02/06/2026 | Review and Changes in Gwalior form and Hospital Patient feedback form | 6.00 | 2.00 | Completed | Yet To Update | Gwalior forms and reports moved to the production environment
5 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Sprint 2: Parakh Customization for Mandir Nayas and Asset Survey for Indore MC | 18/05/2026 ¦ 17/06/2026 | Ujjain Collectorate | School Infrastructure, Bhawan & Toilet Survey form | 01/06/2026 | 02/06/2026 | Changes in Ujjain School Infra Inspection form | 3.00 | 1.00 | Completed | Yet To Update | Deployed to prod the ujjain form
6 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Sprint 2: Parakh Customization for Mandir Nayas and Asset Survey for Indore MC | 18/05/2026 ¦ 17/06/2026 | Ujjain Collectorate | School Infrastructure, Bhawan & Toilet Survey form | 01/06/2026 | 02/06/2026 | Changes in Ujjain School Infra Inspection form | 3.00 | 2.00 | WIP | Yet To Update | Ujjain school infrastructure bhavan and toilet form creation
7 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Documents | Documentation of CMMI and Attneding Audit meeting | 01/06/2026 | 03/06/2026 | CMMI documents preparation and show casing to audit team | 16.00 | 5.00 | WIP | Yet To Update | Documentation Data Model Data collection and Date wise timesheet extraction for Jal rekha project & Flaws discussion with Satyart & rajat for Parakh. There are 2 things required to be added into the promot 1) Date filter required in the Activity wise timesheet and Project milestone timesheet 2) Creation of Sub module column in the Modules section ( under Project list > Modules > In below modules list ) ================================================================================================== 1). If you have created a Module with its Sub module in the previous cycle then if you create an activity again because of some change then you have to filter it down with the required date. 2) same goes with sub module column creation so that going forward you don't have to explicitly mention it in your data collection sheet ( as it is done in Date Collection activity wise sheet ) but it should also be available ( under Project list > Modules > in the below modules list )
8 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Sprint 2: Parakh Customization for Mandir Nayas and Asset Survey for Indore MC | 18/05/2026 ¦ 17/06/2026 | Guna Collectorate | Patient feedback & QR Code integration functionality in Form of Parakh | 01/06/2026 | 03/06/2026 | Guna Hospital Patient feedback form Requirement analysis and Changes | 6.00 | 3.00 | Completed | Yet To Update | Deployed changes suggested by Guna and Gwalior into the Patient QR feedback form
9 | Dheeraj Motiyani | BHOPAL | ICMIS - RCS Portal | SPRINT-28/JUNE-28A | 01/06/2026 ¦ 15/06/2026 | Inspection Module | BRD documentation of Inspection and ICMIS functionality Integration | 08/06/2026 | 04/06/2026 | BRD documentation and meeting with department for updation if any required | 8.00 | 3.00 | WIP | Yet To Update | department meeting on business rules
10 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Documents | Documentation of CMMI and Attneding Audit meeting | 01/06/2026 | 04/06/2026 | CMMI documents preparation and show casing to audit team | 16.00 | 5.00 | Completed | Yet To Update | data collection updated and Minitab account set up
11 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Documents | Data Collection Estimation & Model Minitab | 08/06/2026 | 05/06/2026 | Documentation of Estimation, Data Collection & data Model using Minitab | 16.00 | 8.00 | WIP | Yet To Update | Working data collection user stories PSR MoM and internal meetings
12 | Dheeraj Motiyani | BHOPAL | ICMIS - RCS Portal | SPRINT-28/JUNE-28A | 01/06/2026 ¦ 15/06/2026 | Inspection Module | BRD documentation of Inspection and ICMIS functionality Integration | 08/06/2026 | 08/06/2026 | BRD documentation and meeting with department for updation if any required | 8.00 | 5.00 | Completed | Yet To Update | sent BRD document to department for review and feedback
13 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Documents | Data Collection Estimation & Model Minitab | 08/06/2026 | 08/06/2026 | Documentation of Estimation, Data Collection & data Model using Minitab | 16.00 | 3.00 | WIP | Yet To Update | Estimation and department meeting on user stories, MoM, PSR and promot key milestones and modules preparation and updations
14 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Documents | Data Collection Estimation & Model Minitab | 08/06/2026 | 09/06/2026 | Documentation of Estimation, Data Collection & data Model using Minitab | 16.00 | 5.00 | Completed | Yet To Update | Estimation and department meeting on user stories, MoM, PSR and promot key milestones and modules preparation and updations
15 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | SVS Water Supply Monitoring | Development of Web pages and Database functions | 10/06/2026 | 09/06/2026 | Creation of Reports and Column Names updation & Testing | 16.00 | 3.00 | WIP | Yet To Update | Development of reports and dwsr svs forms
16 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | SVS Water Supply Monitoring | SVS Daily Water Supply Wireframe | 10/06/2026 | 10/06/2026 | SVS Production release Demo to the department Jal Nigam PHE | 3.00 | 3.00 | Completed | Yet To Update | Creation of Reports and Column Names updation & Testing SVS production release demo to the department jal nigam PHE
17 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Sprint 2: Parakh Customization for Mandir Nayas and Asset Survey for Indore MC | 18/05/2026 ¦ 17/06/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 09/06/2026 | 10/06/2026 | Meeting with department to streamline & analysis of Inspection form requirement | 10.00 | 5.00 | WIP | Yet To Update | Working on Betul 6 inspectin forms
18 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | SVS Water Supply Monitoring | Development of Web pages and Database functions | 10/06/2026 | 11/06/2026 | Creation of Reports and Column Names updation & Testing | 16.00 | 4.00 | WIP | Yet To Update | working on Estimation sheet of jal rekha and change request document
19 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | O&M Billing Workflow b/w O&M GM & Higher officials | O&M Billing Workflow preparation & requirement gathering | 15/06/2026 | 12/06/2026 | Processflow preparation for O&M Billing WorkFlow Module | 10.00 | 2.00 | WIP | Yet To Update | attended workflow of O&M creation & its implementation
20 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | SVS Water Supply Monitoring | Development of Web pages and Database functions | 10/06/2026 | 12/06/2026 | Creation of Reports and Column Names updation & Testing | 16.00 | 4.00 | WIP | Yet To Update | Deployed the SVS form and report updated
21 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Sprint 2: Parakh Customization for Mandir Nayas and Asset Survey for Indore MC | 18/05/2026 ¦ 17/06/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 09/06/2026 | 12/06/2026 | Meeting with department to streamline & analysis of Inspection form requirement | 10.00 | 2.00 | WIP | Yet To Update | explanation of betul 6 forms to internal team for implementation
22 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Statistical Analysis | Minitab Data Modeling - PPM Prod, PPM CT and DRE | 15/06/2026 | 15/06/2026 | T test F test Cp Cpk Test of Statistical Models | 12.00 | 4.00 | WIP | Yet To Update | t test f test cp cpk analysis x factor y factor ppm productivity cycle time DRE creation
23 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | O&M Billing Workflow b/w O&M GM & Higher officials | O&M Billing Workflow preparation & requirement gathering | 15/06/2026 | 17/06/2026 | Processflow preparation for O&M Billing WorkFlow Module | 10.00 | 3.00 | WIP | Yet To Update | Meeting with department on workflow of aaklan implementation, checklist of activities to be performed at each role of workflow, final bill generated should have which all document ( approx 18 documents)
24 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | Sahbhagita Change Request | Sahbhagita Activities Addition & Abstract Report Creation | 18/06/2026 | 17/06/2026 | Requirement gathering for Activities category & Abstract report creation & Master data of Activity changes | 16.00 | 4.00 | WIP | Yet To Update | Requirement gathering for Activities category & Abstract report creation & Master data of Activity changes
25 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Statistical Analysis | Minitab Data Modeling - PPM Prod, PPM CT and DRE | 15/06/2026 | 18/06/2026 | T test F test Cp Cpk Test of Statistical Models | 12.00 | 4.00 | WIP | Yet To Update | Github repository centralized documents of jal rekha
26 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | Sahbhagita Change Request | Sahbhagita Activities Addition & Abstract Report Creation | 18/06/2026 | 18/06/2026 | Requirement gathering for Activities category & Abstract report creation & Master data of Activity changes | 16.00 | 4.00 | WIP | Yet To Update | internal team meeting for the addition of additional master activities for sahbhagita module and abstract report creation
27 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Statistical Analysis | Minitab Data Modeling - PPM Prod, PPM CT and DRE | 15/06/2026 | 25/06/2026 | T test F test Cp Cpk Test of Statistical Models | 12.00 | 2.00 | WIP | Yet To Update | working on updating documents
28 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | SVS Water Supply Monitoring | Development of Web pages and Database functions | 10/06/2026 | 25/06/2026 | Creation of Reports and Column Names updation & Testing | 16.00 | 5.00 | Completed | Yet To Update | Completed the changes and deployed by the development team to the prod environment
29 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | Sahbhagita Change Request | Sahbhagita Activities Addition & Abstract Report Creation | 18/06/2026 | 26/06/2026 | Requirement gathering for Activities category & Abstract report creation & Master data of Activity changes | 16.00 | 3.00 | WIP | Yet To Update | Gathered the updated information from the department
30 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 23/06/2026 | 26/06/2026 | Training and workshop on PM Poshan demonstrated to team at Walmi Campus | 5.00 | 5.00 | Completed | Yet To Update | Completed the Day 1 Training for Users ( Further 01st July and 03rd July Scheduled)
31 | Dheeraj Motiyani | BHOPAL | ICMIS - RCS Portal | SPRINT-29/JUNE-28B | 16/06/2026 ¦ 30/06/2026 | Inspection Module | Demonstration of MP Cooperative Society Inspection Form to Department | 23/06/2026 | 29/06/2026 | Demonstration of Inspection form, Rooster, Schedule, & User hierarchy to Department | 3.00 | 3.00 | Completed | Yet To Update | Completed Demonstration
32 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | O&M Billing Workflow b/w O&M GM & Higher officials | O&M Billing Workflow preparation & requirement gathering | 26/06/2026 | 29/06/2026 | Bill Generation flow Validation and Abstract Generation Analysis | 4.00 | 4.00 | Completed | Yet To Update | Revisited the changes mentioned by the department on O&M Billing and its workflow impact
33 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | CMMI Statistical Analysis | Minitab Data Modeling - PPM Prod, PPM CT and DRE | 15/06/2026 | 30/06/2026 | T test F test Cp Cpk Test of Statistical Models | 12.00 | 2.00 | Completed | Yet To Update | Documenting Code review and design review updation in document, 5 Why analysis of Cycle 4 model
34 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/17 | 01/06/2026 ¦ 30/06/2026 | Sahbhagita Change Request | Sahbhagita Activities Addition & Abstract Report Creation | 18/06/2026 | 30/06/2026 | Requirement gathering for Activities category & Abstract report creation & Master data of Activity changes | 16.00 | 3.00 | WIP | Yet To Update | Checking changes done on the UAT for Abstract of Sahbhagita
35 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing Workflow b/w O&M GM & Higher officials | Worflow Functionality at each login for O&M Billing | 01/07/2026 | 01/07/2026 | Department Meeting with Stakeholders for O&M Billing Workflow & Modficaitions in O&M Bill | 6.00 | 6.00 | Completed | Yet To Update | Modification at contractor login and approval body O&M GM login Further Workflow creations steps discussed
36 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 01/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 2.00 | WIP | Yet To Update | Requirement on Mining form , aadhar form and school form
37 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 01/07/2026 | 02/07/2026 | Enhancements & Change Request documentation of O&M Billing & it's Workflow module | 16.00 | 5.00 | WIP | Yet To Update | Attended meeting for O&M Billing enhancements
38 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 01/07/2026 | 02/07/2026 | Training and workshop 2nd and 3rd day PM Poshan demonstrated to team at Walmi Campus | 8.00 | 3.00 | WIP | Yet To Update | 2nd day training of PM Poshan on social audit
39 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 03/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 3.00 | WIP | Yet To Update | Contant discussion with external stakeholder for requirement enhancements and communicate those requirement upgrades to internal team
40 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 01/07/2026 | 03/07/2026 | Training and workshop 2nd and 3rd day PM Poshan demonstrated to team at Walmi Campus | 8.00 | 5.00 | Completed | Yet To Update | Completed 3rd day training on PM Poshan social audit in walmi campus
41 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 06/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 6.00 | WIP | Yet To Update | guided team to onboard betul forms according to master data and verified correct master data for Betul collectorate to finalize
42 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 07/07/2026 | 06/07/2026 | Requirement gathering for Jabalpur Building Inspection Form | 4.00 | 2.00 | WIP | Yet To Update | Taken requirement from Jabalpur Building Inspection form
43 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 01/07/2026 | 07/07/2026 | Enhancements & Change Request documentation of O&M Billing & it's Workflow module | 16.00 | 4.00 | WIP | Yet To Update | Updated enhancements for O&M workflow and its implementation
44 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 07/07/2026 | 07/07/2026 | Requirement gathering from Chhindwara Collectorate | 12.00 | 4.00 | WIP | Yet To Update | Requirement gathered from Chhindwara collectorate and did the departmental external meeting
45 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | Cycle 4 Documentation from Jan to June 2026 | 06/07/2026 | 08/07/2026 | Jan to May 2026 Data Collection, Action Plan, And RCA 5 Why analysis | 16.00 | 3.00 | WIP | Yet To Update | Pushing documents to centralized repository - and CMMI standards followed
46 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 01/07/2026 | 08/07/2026 | Enhancements & Change Request documentation of O&M Billing & it's Workflow module | 16.00 | 2.00 | WIP | Yet To Update | enhancements - on contractor login - 1) complaint redressal 2) Residual Pressure 3) additional facilities
47 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 07/07/2026 | 08/07/2026 | Requirement gathering from Chhindwara Collectorate | 12.00 | 3.00 | WIP | Yet To Update | Internal team discussion on Chhindwara 6 forms - गोदाम निरीक्षण प्रपत्र आंगनवाड़ी केन्द्र का निरीक्षण प्रपत्र स्वास्थ्य केंद्र निरीक्षण प्रतिवेदन विद्यालय निरीक्षण प्रपत्र is already there, tribal hostel inspection form
48 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | Cycle 4 Documentation from Jan to June 2026 | 06/07/2026 | 09/07/2026 | Jan to May 2026 Data Collection, Action Plan, And RCA 5 Why analysis | 16.00 | 3.00 | WIP | Yet To Update | Further Documenting O&M billing Wireframe dynamic html file
49 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | Cycle 4 Documentation from Jan to June 2026 | 06/07/2026 | 09/07/2026 | Jan to May 2026 Data Collection, Action Plan, And RCA 5 Why analysis | 16.00 | 4.00 | WIP | Yet To Update | CMMI Code review design review and action plan with 5 why outlier creation
50 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 10/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 3.00 | WIP | Yet To Update | The Betul credentials are created for the state admin level and shared with the Betul collectorate to verify them at UAT environment
51 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 07/07/2026 | 10/07/2026 | Requirement gathering from Chhindwara Collectorate | 12.00 | 3.00 | WIP | Yet To Update | Chhindwara Master data and form finalized by comparison with other district collectorate forms
52 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | Cycle 4 Documentation from Jan to June 2026 | 06/07/2026 | 14/07/2026 | Jan to May 2026 Data Collection, Action Plan, And RCA 5 Why analysis | 16.00 | 4.00 | WIP | Yet To Update | CMMI Cycle 4 documents completed - Code review and Release note is in progress
53 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 14/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 2.00 | Completed | Yet To Update | All forms created at UAT and Betul Collectorate is checking it
54 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 07/07/2026 | 14/07/2026 | Requirement gathering for Jabalpur Building Inspection Form | 4.00 | 2.00 | Completed | Yet To Update | Jabalpur unused building inspection form - team has created it after Master data and updated inspection form received
55 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 01/07/2026 | 15/07/2026 | Enhancements & Change Request documentation of O&M Billing & it's Workflow module | 16.00 | 3.00 | WIP | Yet To Update | Team has updated contractor pages - residual and complaint additional facilities pages and added UFW also and supporting document upload workflow on contractor firm side working on it
56 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 07/07/2026 | 15/07/2026 | Requirement gathering from Chhindwara Collectorate | 12.00 | 2.00 | Completed | Yet To Update | All forms updated and moved to UAT and chhindwara collectorate is checking on it
57 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 14/07/2026 | 15/07/2026 | Unused Building Jabalpur Inspection - Department meeting & Internal Meeting Form & Master data | 4.00 | 2.00 | WIP | Yet To Update | Updated and mailed them to verify the status of Form on UAT
58 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 15/07/2026 | 16/07/2026 | Cycle 5 CR log creation for all modules | 12.00 | 3.00 | WIP | Yet To Update | Change request documents added and created activity for it. Department meeting on documents
59 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 01/07/2026 | 16/07/2026 | Enhancements & Change Request documentation of O&M Billing & it's Workflow module | 16.00 | 2.00 | Completed | Yet To Update | Department meeting to discuss on Approval report changes and O&M workflow upload documents pages and its impact
60 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 14/07/2026 | 16/07/2026 | PM Poshan video creation and atttended meeting for Buf fix from fields ( Block officer & VSA Inspector Issues ) Resolutions | 16.00 | 3.00 | WIP | Yet To Update | PM Poshan Bug fixing and video & department meeting & report creation
61 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | Cycle 4 Documentation from Jan to June 2026 | 06/07/2026 | 17/07/2026 | Jan to May 2026 Data Collection, Action Plan, And RCA 5 Why analysis | 16.00 | 2.00 | Completed | Yet To Update | Cycle 4 documents are completed Excluding BRTM
62 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 14/07/2026 | 17/07/2026 | PM Poshan video creation and atttended meeting for Buf fix from fields ( Block officer & VSA Inspector Issues ) Resolutions | 16.00 | 6.00 | WIP | Yet To Update | Resolved issues of PM Poshan inspection form - from VSA BO level in hierarchy users. Created video and updated it on group to complete inspection and connected with development team in meetings
63 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 15/07/2026 | 20/07/2026 | Requirement gathered for Reinspection loop in (Cube/Material Testing modules) | 3.00 | 3.00 | Completed | Yet To Update | Requirement gathered for reinspectionloop and wireframe it out for - Cube testing, material testing and reate activity to create it for sahbhagita enhancements also
64 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 15/07/2026 | 20/07/2026 | Requirement gathered for Reinspection loop in (Cube/Material Testing modules) | 3.00 | 3.00 | WIP | Yet To Update | Requirement gathered for reinspectionloop and wireframe it out for - Cube testing, material testing and reate activity to create it for sahbhagita enhancements also
65 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 15/07/2026 | 20/07/2026 | Chhindwara Report corrections | 2.00 | 2.00 | Completed | Yet To Update | Moved the forms to production
66 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 15/07/2026 | 21/07/2026 | Cycle 5 CR log creation for all modules | 12.00 | 3.00 | WIP | Yet To Update | Updating release note and other brtm document
67 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 14/07/2026 | 21/07/2026 | Change request in requirement | 4.00 | 4.00 | Completed | Yet To Update | Shared data of changes to team and discussed with external department for correcting the remaining changes shared by them
68 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 21/07/2026 | 22/07/2026 | Requirement Enhancements Changes Contractor Bill generation pages | 8.00 | 4.00 | WIP | Yet To Update | Department meeting and O&M separate Meeting with Kapil GM from Jal Nigam for O&M Billing , Reports and Complete analysis on Enhancements and Changes
69 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 14/07/2026 | 22/07/2026 | PM Poshan video creation and atttended meeting for Buf fix from fields ( Block officer & VSA Inspector Issues ) Resolutions | 16.00 | 4.00 | WIP | Yet To Update | Attended meeting and discussed with department about bug in forms
70 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 21/07/2026 | 23/07/2026 | Requirement Enhancements Changes Contractor Bill generation pages | 8.00 | 3.00 | WIP | Yet To Update | Requirement finalized and developed functions by database side procedures and functions. Front end developer working on logic and implementation of logic
71 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 14/07/2026 | 23/07/2026 | Unused Building Jabalpur Inspection - Department meeting & Internal Meeting Form & Master data | 4.00 | 2.00 | Completed | Yet To Update | Discussed changes with department and questions & units sqft and other details of photo issue fixed and moved form to prod by dev team
72 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 14/07/2026 | 23/07/2026 | PM Poshan video creation and atttended meeting for Buf fix from fields ( Block officer & VSA Inspector Issues ) Resolutions | 16.00 | 3.00 | Completed | Yet To Update | PM Poshan issues resolved
73 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 15/07/2026 | 24/07/2026 | Cycle 5 CR log creation for all modules | 12.00 | 2.00 | WIP | Yet To Update | noted the further CRs for June july month
74 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 15/07/2026 | 24/07/2026 | Cycle 5 CR log creation for all modules | 12.00 | 3.00 | WIP | Yet To Update | Documented CRs and MoM for June and July
75 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 24/07/2026 | 24/07/2026 | Requirement Enhancements Changes Contractor Bill generation pages - (Continue remaining Points) | 9.00 | 3.00 | WIP | Yet To Update | Formula & calculations are corrected as per the stakeholders
76 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 15/07/2026 | 27/07/2026 | Cycle 5 CR log creation for all modules | 12.00 | 1.00 | Completed | Yet To Update | Completed and reviewed from project manager
77 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 21/07/2026 | 27/07/2026 | Requirement Enhancements Changes Contractor Bill generation pages | 8.00 | 1.00 | Completed | Yet To Update | Added these points in the requirements
78 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 24/07/2026 | 27/07/2026 | Requirement Enhancements Changes Contractor Bill generation pages - (Continue remaining Points) | 9.00 | 3.00 | WIP | Yet To Update | Formula based calculations are applied into the O&M Bill generated procedures at database side
79 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 27/07/2026 | 27/07/2026 | Chhindwara forms and reports uat and prod forms & incorporation of changes | 5.00 | 3.00 | WIP | Yet To Update | Forms changes deployed and Master data corrections incorporated
80 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate - Property Inspection | Property Inspection form | 27/07/2026 | 28/07/2026 | Indore Property form & apk deployment followup | 5.00 | 3.00 | WIP | Yet To Update | Changes into Property form Apk modification - select correct patch and deployment of and geofencing implementaion proper or not
81 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | MP Cooperative | Inspection form for Mp Cooperative society | 27/07/2026 | 28/07/2026 | MP Cooperative work on change request shared from department Nirikshan form and meeting | 8.00 | 3.00 | WIP | Yet To Update | MP cooperative Nirikshan old and new form comparison and created changes incorporated document and further implement them
82 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 24/07/2026 | 29/07/2026 | Requirement Enhancements Changes Contractor Bill generation pages - (Continue remaining Points) | 9.00 | 3.00 | Completed | Yet To Update | 5) Gross O&M Bill - Amount of Village (in Rs) (V1 (Census) / Summation of Villages (Census)) * ( Monthly O&M Amount - Amount for Bulk Supply) 6) Deduction as per agreement norms ( Save as Draft) - Data Visible 7) Gross Amount Monthly O&M amount = Sum ( amount for Bulk supply users and amount of villages gross o&m bill amount) 8) Net Payable Bill Gross amount : Gross Amount(in Rs) = Summation ( amount of village considering water supply days + amount for Bulk supply gross in Rs) Net payable - Deduction for UFW (in Rs) => is zero for not visible = (UFW Calculated % - Allowable UFW ) * Gross Amount allowable ufw is taken from abstract contract details 9) Refer CMMI docs
83 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | SVS Water Supply Monitoring | SVS Daily Water Supply Wireframe | 23/07/2026 | 29/07/2026 | SVS Village water suply wireframe preparation and Report Dashboard creation & Mockup | 10.00 | 2.00 | WIP | Yet To Update | SVS Dashboard created
84 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 27/07/2026 | 29/07/2026 | Betul 6 forms changes incorporated and resolved issues of form submissions & virtual calls | 5.00 | 3.00 | WIP | Yet To Update | Betul collectorate in UAT - able to fill all the forms just, school monitoring form, that was not able to submit other than that every form is working properly now and questions are also fine.
85 | Dheeraj Motiyani | BHOPAL | ICMIS - RCS Portal | SPRINT-31/JULY-30 | 16/07/2026 ¦ 31/07/2026 | Inspection Module | MP Cooperative Inspection Form & Flow Changes | 29/07/2026 | 30/07/2026 | Change Comparison summarized between Old and New Nirikshan form | 8.00 | 3.00 | WIP | Yet To Update | changes suggested by department in new nirikshan form are documented and shared dcoument with development team and department for confirmation
86 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/18 | 01/07/2026 ¦ 31/07/2026 | SVS Water Supply Monitoring | SVS Daily Water Supply Wireframe | 23/07/2026 | 30/07/2026 | SVS Village water suply wireframe preparation and Report Dashboard creation & Mockup | 10.00 | 2.00 | WIP | Yet To Update | reviewed by department and suggested changes in SVS dashboard village water supply
87 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 24/07/2026 | 30/07/2026 | Jabalpur Unused building inspepction form changes and tracking UAT and prod | 3.00 | 3.00 | Completed | Yet To Update | Live Jabalpur form and report generated and corrected with changes
88 | Dheeraj Motiyani | BHOPAL | ICMIS - RCS Portal | SPRINT-31/JULY-30 | 16/07/2026 ¦ 31/07/2026 | Inspection Module | MP Cooperative Inspection Form & Flow Changes | 29/07/2026 | 31/07/2026 | Change Comparison summarized between Old and New Nirikshan form | 8.00 | 5.00 | Completed | Yet To Update | BRD and change summary document shared with department and they are finalizing on that and update us.
89 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 27/07/2026 | 31/07/2026 | Chhindwara forms and reports uat and prod forms & incorporation of changes | 5.00 | 2.00 | Completed | Yet To Update | Chhindwara reports are developed by team and is getting reviewed
90 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 05/08/2026 | 03/08/2026 | Betul Inspection form follow up | 3.00 | 1.00 | WIP | Yet To Update | Forms to be released in production
91 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 27/07/2026 | 03/08/2026 | Betul 6 forms changes incorporated and resolved issues of form submissions & virtual calls | 5.00 | 2.00 | Completed | Yet To Update | Betul 5 forms verified on UAT and discussing it with department so that we can onboard them to production
92 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | MP Cooperative | Inspection form for Mp Cooperative society | 27/07/2026 | 03/08/2026 | MP Cooperative work on change request shared from department Nirikshan form and meeting | 8.00 | 5.00 | Completed | Yet To Update | BRD and change summary documents created and sent to department for verification
93 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 04/08/2026 | Cycle 5 documentation of July and June | 10.00 | 2.00 | WIP | Yet To Update | Documented CR , MOM and PSR - June July
94 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 05/08/2026 | 04/08/2026 | Changes for Meter Reading MF, MNF and NWS documented | 5.00 | 2.00 | WIP | Yet To Update | Changes taken from department. Discussed and understood analysed the Meter reading logics
95 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 04/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 2.00 | WIP | Yet To Update | Nirmal SVS requirement gathered and discussed with internal team and PM.
96 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate - Property Inspection | Property Inspection form | 27/07/2026 | 04/08/2026 | Indore Property form & apk deployment followup | 5.00 | 2.00 | Completed | Yet To Update | Internal meeting to get new structured inspection form question deparmtnet wise from external Indore collectorate
97 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS dashboard Creation | 04/08/2026 | 05/08/2026 | Mock Up created for Dashboard and updated features suggested by Department | 4.00 | 4.00 | WIP | Yet To Update | SVS Dashboard mock up created and suggested changes to the development team
98 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 04/08/2026 | 05/08/2026 | Requirement gathering meeting with Team & Indore Collectorate & finalize inspection forms | 16.00 | 4.00 | WIP | Yet To Update | Internal meeting and External stakeholders discussion on Phase 1 and Phase 2 of Indore inspection implementation and BRD and mock up of forms to team and external stakeholders
99 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 05/08/2026 | 06/08/2026 | Changes for Meter Reading MF, MNF and NWS documented | 5.00 | 2.00 | WIP | Yet To Update | connected with OIC rakesh sir for dhara meter reading chnages and fixes
100 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS dashboard Creation | 06/08/2026 | 06/08/2026 | review with Tejas for SVS dashboard | 3.00 | 3.00 | Completed | Yet To Update | review svs dashboard chnages with tejas
101 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 04/08/2026 | 06/08/2026 | Requirement gathering meeting with Team & Indore Collectorate & finalize inspection forms | 16.00 | 3.00 | WIP | Yet To Update | Connecting with internal team to finalize Divisional level hierarchy in parakh and Action taken report building in parakh
102 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 07/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase | 10.00 | 3.00 | WIP | Yet To Update | Workflow meeting and further work requirement gathering meeting with Kapil department jal nigam
103 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 07/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 3.00 | WIP | Yet To Update | Nirmal SVS water quality checks and FTK kit requirement analysis and finalizing acceptable and rejectable range & criteria with stakeholders department and internal team and PM
104 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 05/08/2026 | 07/08/2026 | Chhindwara Inspection form follow up | 2.00 | 2.00 | Completed | Yet To Update | Chhindwara inspection reprot building by team and production release
105 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 10/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase | 10.00 | 3.00 | WIP | Yet To Update | SQC Edit and GM Edit functionality needs to be provided as suggested by department jal nigam
106 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Guna Collectorate | Guna Ayush health inspection form | 12/08/2026 | 10/08/2026 | Requirement understanding and analysis & gathered Guna Ayush health inspection form and master data | 4.00 | 2.00 | WIP | Yet To Update | Master data and requirement analysis of Ayush inspection forms and formatting of the form
107 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 11/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 2.00 | WIP | Yet To Update | Requirement gathered - Dhara Meter reading MF MNF M Replaceable FE entry only when meter functional and entries are not approved. GM approves entries and are final. Then start and end reading will not change
108 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 11/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 3.00 | WIP | Yet To Update | Team implementing Nirmal range of FTK kit water quality of village water supply
109 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 11/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 3.00 | WIP | Yet To Update | Requirement gathered from damoh collectorate on 12 forms and understanding and analysis with team
110 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 12/08/2026 | Cycle 5 documentation of July and June | 10.00 | 2.50 | WIP | Yet To Update | Attended and presented CMMI cycle 4 review points with Satyarth Tapan and ranjana in the meeting
111 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 12/08/2026 | 12/08/2026 | User manual creation for Phase 1 and Phase 2 implementation for INdore inspecction 17 forms | 14.00 | 5.00 | WIP | Yet To Update | User manual creation for phase 1
112 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 13/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase | 10.00 | 2.00 | WIP | Yet To Update | O&M SQC Edit further functionlity on --- different pages payment, residual, complaint, facilties, final net and abtract payment page
113 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 05/08/2026 | 13/08/2026 | Betul Inspection form follow up | 3.00 | 2.00 | WIP | Yet To Update | deployed and changes & issues fixed for betul forms - mining form gram panchayt not visible and other changes in the forms for the question changes
114 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 13/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 3.00 | WIP | Yet To Update | Constant follow up and creation of master data and deployment of Inspecion forms through team meetings
115 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 14/08/2026 | Cycle 5 documentation of July and June | 10.00 | 2.00 | WIP | Yet To Update | Reviewed and discussed changes with team and satyarth for documents
116 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 14/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 3.00 | WIP | Yet To Update | Updating Wireframe with new requirements and changes in the previous screens developed -MVS contractor, Gram sachiv and CEO Block
117 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 14/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 3.00 | WIP | Yet To Update | Conected with department for forms questions and Asset upload bulk upload method and add asset for each form
118 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 17/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 3.00 | WIP | Yet To Update | Updated requirement and wireframe and connected with tteam folr overview of nirmal SVS
119 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 04/08/2026 | 17/08/2026 | Requirement gathering meeting with Team & Indore Collectorate & finalize inspection forms | 16.00 | 2.00 | WIP | Yet To Update | Indore sharing new forms to be implemented. After Phase 2 - Divisional officer login and View feature to divisional officer. Updated User Manual
120 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 18/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 2.00 | WIP | Yet To Update | Documented these requirements and team implemented.
121 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 18/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 4.00 | WIP | Yet To Update | Added details
122 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 18/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 2.00 | WIP | Yet To Update | following up on damoh forms work - general inspection forms
123 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 19/08/2026 | Cycle 5 documentation of July and June | 10.00 | 2.00 | WIP | Yet To Update | document review and cycle 5 started june july and august docs
124 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 19/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 2.00 | Completed | Yet To Update | implemented nirmal fit functionlaity
125 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 20/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 3.00 | WIP | Yet To Update | Meter reading survey intake wtp oht and bulk web and mobile view
126 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 04/08/2026 | 20/08/2026 | Requirement gathering meeting with Team & Indore Collectorate & finalize inspection forms | 16.00 | 5.00 | Completed | Yet To Update | Understood meeting gathering from indore and communicated with them
127 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | Cycle 4 Documentation from Jan to June 2026 | 12/08/2026 | 21/08/2026 | CMMI review meeting for Cycle 4 data - https://docs.google.com/spreadsheets/d/1I5mSYQsKy9NE_Bpvi1KwrNQY7fstHskR1z57EtfsjnU/edit?gid=0#gid=0 | 4.00 | 4.00 | Completed | Yet To Update | Updated cycle 5 cmmi docs in jal rekha and parakh
128 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Project Module Initiation Meeting and Requirement gathering | 14/08/2026 | 21/08/2026 | SVS module like Vistrit module of dhara for MVS villages Requirement understanding & analysis | 4.00 | 4.00 | Completed | Yet To Update | Nirmal SVS details and reports FTK Kit finalized and shared
129 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | CMMI Documentation | CMMI Level Documents | 18/08/2026 | 24/08/2026 | BRDs generic and add on with new enhancements | 12.00 | 5.00 | WIP | Yet To Update | BRDs according to changes and enhancement updated and created specific docs Generic also created
130 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 12/08/2026 | 24/08/2026 | User manual creation for Phase 1 and Phase 2 implementation for INdore inspecction 17 forms | 14.00 | 3.00 | WIP | Yet To Update | Created manuals - Indore inspection and District GIS parakh manual updated with enhancements
131 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 25/08/2026 | Cycle 5 documentation of July and June | 10.00 | 1.50 | Completed | Yet To Update | updated docs for augist month as well
132 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 24/08/2026 | 25/08/2026 | Water supply during construction phase requirement gathered | 8.00 | 3.50 | WIP | Yet To Update | Meeting with MD sir for reviewing details
133 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 25/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 3.00 | Completed | Yet To Update | Shared master data from Damoh should be updated in all 12 CM Jan vishwas
134 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Parinam Enhancements | Parinam Dashboard | 20/08/2026 | 26/08/2026 | Requirement gathered for Parinam dashboard | 4.00 | 3.00 | WIP | Yet To Update | Dashboard updates
135 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 27/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 3.00 | WIP | Yet To Update | Alignment of Dhara meter for all roles
136 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 27/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase | 10.00 | 2.00 | WIP | Yet To Update | WSDCP steps to wireframe and updates in flow
137 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 05/08/2026 | 28/08/2026 | Changes for Meter Reading MF, MNF and NWS documented | 5.00 | 1.00 | Completed | Yet To Update | updated the tasks
138 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Parinam Enhancements | Parinam Dashboard | 20/08/2026 | 28/08/2026 | Requirement gathered for Parinam dashboard | 4.00 | 1.00 | Completed | Yet To Update | Parinam dashboard updated
139 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 24/08/2026 | 28/08/2026 | Water supply during construction phase requirement gathered | 8.00 | 4.50 | Completed | Yet To Update | Enhancments completed
140 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Department Meetings | VC with MD sir and training session | 28/08/2026 | 31/08/2026 | Meeting and finalizing O&M billing | 8.00 | 8.00 | Completed | Yet To Update | department and internal meeting
141 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Anusharavan at Gram Panchanyat level | 01/09/2026 | 01/09/2026 | Reguirement gathering understanding and meeting with MD sir and internal meeting | 10.00 | 3.00 | WIP | Yet To Update | meeting adone and gathered the requirement
142 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | CMMI Documentation | CMMI Level Documents | 31/08/2026 | 01/09/2026 | Business Analyst documentation for District GIS Parakh | 16.00 | 3.00 | WIP | Yet To Update | Documentation done for CMMI for District gis parakh
143 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | District GIS - CM Jan Vishwas Abhiyan | Requirement gathering & meetings | 28/08/2026 | 01/09/2026 | Requirement gathering & meetings and forms finalization with department (12 forms) | 16.00 | 2.00 | WIP | Yet To Update | Gathering of requirement from Damoh
144 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Requirement gathering, meetings and Wireframe | 01/09/2026 | 02/09/2026 | Wireframe of Anusharavan GP for SVS | 8.00 | 3.00 | WIP | Yet To Update | Designing wireframe and adding requirements
145 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | CMMI Documentation | CMMI Level Documents | 31/08/2026 | 02/09/2026 | Business Analyst documentation for District GIS Parakh | 16.00 | 2.00 | WIP | Yet To Update | User stories, BRD, manuals, estimation, MoM PSR updations, release notes emails
146 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | District GIS - CM Jan Vishwas Abhiyan | Requirement gathering & meetings | 28/08/2026 | 02/09/2026 | Requirement gathering & meetings and forms finalization with department (12 forms) | 16.00 | 3.00 | WIP | Yet To Update | clarification on questions format and logic of questions in that form
147 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Requirement gathering, meetings and Wireframe | 01/09/2026 | 04/09/2026 | Wireframe of Anusharavan GP for SVS | 8.00 | 3.00 | WIP | Yet To Update | Updated Wireframe with BR CR FR in the separate workflow
148 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Anusharavan at Gram Panchanyat level | 01/09/2026 | 07/09/2026 | Reguirement gathering understanding and meeting with MD sir and internal meeting | 10.00 | 3.00 | WIP | Yet To Update | Anusharavan RFI at GP level and Sub engineer level role based screen creation
149 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | CMMI Documentation | CMMI Level Documents | 31/08/2026 | 08/09/2026 | Business Analyst documentation for District GIS Parakh | 16.00 | 4.00 | WIP | Yet To Update | CMMMI Documentationa and preparing further
150 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | District GIS - CM Jan Vishwas Abhiyan | Requirement gathering & meetings | 28/08/2026 | 08/09/2026 | Requirement gathering & meetings and forms finalization with department (12 forms) | 16.00 | 4.00 | WIP | Yet To Update | Coordinating with team to implement changes and new forms under CM jan vishwas
151 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Nirmal GP | Requirement gathering, meetings and wireframe | 01/09/2026 | 09/09/2026 | Wireframe updation and addition of range in FTK kit for Nirmal SVS | 6.00 | 2.00 | WIP | Yet To Update | Gathered requirement through meeting and analysis of ranges for ftk water quality kit
152 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Anusharavan at Gram Panchanyat level | 01/09/2026 | 09/09/2026 | Reguirement gathering understanding and meeting with MD sir and internal meeting | 10.00 | 3.00 | WIP | Yet To Update | Edited details for Wireframe workflow and Meeting with department
153 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 01/09/2026 | 09/09/2026 | Nirmal wireframe BR FR CR updation | 4.00 | 3.00 | WIP | Yet To Update | Updated Wireframe with new changes and shared BR FR and CR with team
154 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | District GIS - CM Jan Vishwas Abhiyan | Requirement gathering & meetings | 07/09/2026 | 10/09/2026 | Dhar, Damoh, Indore Chhindwara requirement gathering for CM Jan vishwas forms | 16.00 | 8.00 | WIP | Yet To Update | Enhancements and updates in shared forms and suggested new forms from department according to their requirement
155 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | District GIS - CM Jan Vishwas Abhiyan | Requirement gathering & meetings | 07/09/2026 | 11/09/2026 | Dhar, Damoh, Indore Chhindwara requirement gathering for CM Jan vishwas forms | 16.00 | 4.00 | WIP | Yet To Update | Reports check on UAT and Prod
156 | Dheeraj Motiyani | BHOPAL | ICMIS - RCS Portal | SPRINT-33/Sep-2026 | 01/09/2026 ¦ 30/09/2026 | Inspection Module | Requirement gathering and Enhancement in Inspection Module & Meetings | 08/09/2026 | 14/09/2026 | Stakeholder Meetings with Requirement gathering and Enhancement in Inspection Module by further changes & Documentation | 16.00 | 4.00 | WIP | Yet To Update | MP Cooperative changes discussed with department and BRD dcoumented and Nirikshan format master data update required from department
157 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | CMMI Documentation | CMMI Level Documents | 31/08/2026 | 15/09/2026 | Business Analyst documentation for District GIS Parakh | 16.00 | 7.00 | Completed | Yet To Update | first phase document updated and completed till august
158 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | District GIS - CM Jan Vishwas Abhiyan | Requirement gathering & meetings | 28/08/2026 | 16/09/2026 | Requirement gathering & meetings and forms finalization with department (12 forms) | 16.00 | 7.00 | Completed | Yet To Update | Created and updated new forms
159 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | MP Metro | Requirement gathering and Meetings | 08/09/2026 | 17/09/2026 | MP Metro MD Sir Meeting and VC call with MP Metro team & Coordinate with Internal team | 8.00 | 8.00 | Completed | Yet To Update | Discussion and forms creation asset entry form, survey form. analysis of requriement emails and meeting with department and internal teams
160 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Nirmal GP | Requirement gathering, meetings and wireframe | 01/09/2026 | 18/09/2026 | Wireframe updation and addition of range in FTK kit for Nirmal SVS | 6.00 | 4.00 | Completed | Yet To Update | updated wireframe with Nirmal SVS details
161 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Anusharavan at Gram Panchanyat level | 01/09/2026 | 18/09/2026 | Reguirement gathering understanding and meeting with MD sir and internal meeting | 10.00 | 1.00 | Completed | Yet To Update | Discussed with internal about SVS Anusharavan requirement
162 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 01/09/2026 | 18/09/2026 | Nirmal wireframe BR FR CR updation | 4.00 | 1.00 | Completed | Yet To Update | Nirmal wireframe BR FR CR created and shared with tester
163 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | District GIS - CM Jan Vishwas Abhiyan | Requirement gathering & meetings | 07/09/2026 | 22/09/2026 | Dhar, Damoh, Indore Chhindwara requirement gathering for CM Jan vishwas forms | 16.00 | 4.00 | Completed | Yet To Update | Jan Vishwas forms created and deployed to UAT
164 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 15/09/2026 | 22/09/2026 | Meeting and Requirement discussion with stakeholders and Updating documents | 16.00 | 4.00 | WIP | Yet To Update | Documented Division specific forms, requirement taken from department for few forms
165 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Requirement gathering, meetings and Wireframe | 04/09/2026 | 23/09/2026 | Wireframe update and Master & RFI screen updates | 8.00 | 4.00 | WIP | Yet To Update | Meeting with department and internal team to implement module
166 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | CM Jan Vishwas Forms and enhancements for Division level access/role | 24/08/2026 ¦ 23/09/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 15/09/2026 | 23/09/2026 | Meeting and Requirement discussion with stakeholders and Updating documents | 16.00 | 4.00 | WIP | Yet To Update | Documented Division specific forms, requirement taken from department for few forms
167 | Dheeraj Motiyani | BHOPAL | Waterbodies Management System - MIS Reports | New CM Scheme Addition and Enhancement in Reports | 21/09/2026 ¦ 21/10/2026 | Mukhya Mantri Machhua Samriddhi Yojna - Enhancement | Enhancements and Add New Programme details | 23/09/2026 | 24/09/2026 | Requirement gathering & Department meeting about new request to add new programme | 16.00 | 5.00 | WIP | Yet To Update | ENhancement - add new programme Requirement gathering
168 | Dheeraj Motiyani | BHOPAL | Waterbodies Management System - MIS Reports | New CM Scheme Addition and Enhancement in Reports | 21/09/2026 ¦ 21/10/2026 | Mukhya Mantri Machhua Samriddhi Yojna - Enhancement | Enhancements and Add New Programme details | 24/09/2026 | 24/09/2026 | Documentation & Technocommercial with wireframe on new module build | 12.00 | 2.50 | WIP | Yet To Update | technocommerical
169 | Dheeraj Motiyani | BHOPAL | ICMIS - RCS Portal | SPRINT-33/Sep-2026 | 01/09/2026 ¦ 30/09/2026 | Inspection Module | Requirement gathering and Enhancement in Inspection Module & Meetings | 08/09/2026 | 28/09/2026 | Stakeholder Meetings with Requirement gathering and Enhancement in Inspection Module by further changes & Documentation | 16.00 | 3.50 | WIP | Yet To Update | Priya Jyoti mam from Mp cooperative offline meeting and demo presented to department
170 | Dheeraj Motiyani | BHOPAL | Waterbodies Management System - MIS Reports | New CM Scheme Addition and Enhancement in Reports | 21/09/2026 ¦ 21/10/2026 | Mukhya Mantri Machhua Samriddhi Yojna - Enhancement | Enhancements and Add New Programme details | 24/09/2026 | 28/09/2026 | Documentation & Technocommercial with wireframe on new module build | 12.00 | 4.50 | WIP | Yet To Update | documented and checked the flow of new programme added
171 | Dheeraj Motiyani | BHOPAL | Waterbodies Management System - MIS Reports | New CM Scheme Addition and Enhancement in Reports | 21/09/2026 ¦ 21/10/2026 | Mukhya Mantri Machhua Samriddhi Yojna - Enhancement | Enhancements and Add New Programme details | 23/09/2026 | 29/09/2026 | Requirement gathering & Department meeting about new request to add new programme | 16.00 | 2.00 | WIP | Yet To Update | UAT verification of new programe addition and check new additions required
172 | Dheeraj Motiyani | BHOPAL | Waterbodies Management System - MIS Reports | New CM Scheme Addition and Enhancement in Reports | 21/09/2026 ¦ 21/10/2026 | Mukhya Mantri Machhua Samriddhi Yojna - Enhancement | Enhancements and Add New Programme details | 23/09/2026 | 29/09/2026 | Requirement gathering & Department meeting about new request to add new programme | 16.00 | 6.00 | WIP | Yet To Update | Requirement gathered and multiple calls and meetings with fisheries department & internal approval of technocommercial & wireframe
173 | Dheeraj Motiyani | BHOPAL | ICMIS - RCS Portal | SPRINT-33/Sep-2026 | 01/09/2026 ¦ 30/09/2026 | Inspection Module | Requirement gathering and Enhancement in Inspection Module & Meetings | 08/09/2026 | 30/09/2026 | Stakeholder Meetings with Requirement gathering and Enhancement in Inspection Module by further changes & Documentation | 16.00 | 4.00 | WIP | Yet To Update | UAT Testing of Cooperative Nirikshan form
174 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Requirement gathering, meetings and Wireframe | 04/09/2026 | 30/09/2026 | Wireframe update and Master & RFI screen updates | 8.00 | 4.00 | Completed | Yet To Update | Meeting attended in Jal nigam for SVS PHE Anusharavan module integration with SIPRI and Collect master data from department to hand it over SIPRI team through mulitple meeting