# Proposal

## Integrated Digital Platform for Handpumps, Single Village Schemes (SVS) and Multi-Village Schemes (MVS)

### Jal Rekha | Jal Samadhan | GHAN 2.0 | Jal Darpan (Common Domain)

Prepared for: Public Health Engineering Department (PHED), Government of Madhya Pradesh

In coordination with: Madhya Pradesh Jal Nigam (MPJN)

Submitted by: Madhya Pradesh State Electronics Development Corporation (MPSEDC)

Reference: Minutes of the meeting held on 12.10.2026 under the chairmanship of the Additional Chief Secretary, PHED |

Submission date: 19.10.2026

## Contents

- Introduction

- About MPSEDC

- About PHED and MPJN

- Background and Directions of the ACS, PHED

- Objective of the Project

- Existing Platforms and Current State

- Proposed Integrated Solution Architecture

- Scope of Work (Module-wise Functionality)

- Complaint Registration, Routing and Escalation Mechanism

- Roles and Responsibilities of Stakeholders

- Methodology and Approach

- Deliverables

- Implementation Plan and Timeline

- Assumptions

- Expectations and Dependencies from the Department

- Contact Details

## 1. Introduction

The Public Health Engineering Department implements drinking water supply schemes to provide safe and potable water across rural Madhya Pradesh through handpumps, Single Village Schemes (SVS) and Multi-Village Schemes (MVS). The Department has digitalised its operations in stages and now operates several independent digital platforms: the GHAN 2.0 application for handpumps, geotagged SVS data and the Jal Rekha application of MPJN, which supports MVS operations through 12 operational modules including Dhara and Nirmal.

In the review meeting held on 12.10.2026, the Additional Chief Secretary, PHED, directed that these platforms be brought together into one unified system so that citizens have a single point of access, grievances are resolved faster, and the Department, MPJN and field functionaries coordinate better.

## 2. About MPSEDC

MPSEDC is a corporation under the Companies Act 1956, entrusted with developing the Software Technology Parks at Indore, Bhopal, Jabalpur and Gwalior under the guidance of the Department of Science & Technology, Government of Madhya Pradesh. It works towards the promotion, implementation and investment in IT, ITeS and ESDM sectors and the implementation of the State IT Policy. MPSEDC is the nodal agency of the state for Remote Sensing, GIS and drone-based solutions for government departments.

## 3. About PHED and MPJN

Public Health Engineering Department. PHED is an independent department of the Government of Madhya Pradesh. Its major activities include:

- Survey, investigation, preparation and execution of water supply schemes for villages.

- Maintenance and conservation of rural handpump schemes.

- Water supply from alternative sources in quality-affected habitations.

- Drinking water arrangements in tribal ashram-hostels, anganwadis and rural schools.

- Groundwater recharge, rainwater harvesting and renewal of conventional water sources.

- Water supply and sewage disposal schemes in urban areas on request of urban bodies.

Madhya Pradesh Jal Nigam (MPJN). MPJN is responsible for Multi-Village Schemes and manages MVS information through the Jal Rekha integrated application.

## 4. Background and Directions of the ACS, PHED

The meeting of 12.10.2026 was chaired by the ACS, PHED, in the presence of the Managing Director, MPJN, and MPSEDC representatives. MPSEDC briefed that geotagging details of handpumps and SVS are already incorporated in the GHAN portal and MP Geoportal and presented GHAN 2.0, the citizen-centric complaint platform. The MD, MPJN, informed that MVS information is available through Jal Rekha with 12 modules. The ACS issued the following directions, and the table shows where this proposal addresses each.

| # | Direction of the ACS, PHED | Addressed in |
| --- | --- | --- |
| 1 | Develop an integrated digital platform covering Handpumps, SVS and MVS, with information and services for all three on a common platform | Sections 7 and 8 |
| 2 | Incorporate a dedicated module, Jal Samadhan, into Jal Rekha for raising and tracking complaints for Handpumps, SVS and MVS | Section 8.C and 9 |
| 3 | Examine the feasibility of a common domain, Jal Darpan, integrating Jal Rekha, Jal Samadhan and GHAN 2.0 as a single point of access for citizens | Section 8.D |
| 4 | Coordinate with the State Call Centre (181) so that O&M complaints for Handpumps, SVS and MVS are routed to the designated departmental helpline or team | Section 8.E and 9 |
| 5 | Prepare a comprehensive proposal covering integration of existing portals, module-wise functionality, complaint registration and escalation, roles and responsibilities, and the implementation plan | This document |
| 6 | Submit the proposal on 19.10.2026 | Submitted |

## 5. Objective of the Project

The objective is to create a unified, citizen-centric and process-driven digital ecosystem for rural drinking water assets in Madhya Pradesh by:

- Extending Jal Rekha to PHED for Single Village Schemes through role-based modules for user management, asset mapping, data visualisation, tap connection validation (Parinam), water quantity (Dhara), water quality (Nirmal) and community participation (Sahbhagita).

- Integrating the GHAN 2.0 web portal and mobile application with Jal Rekha.

- Introducing Jal Samadhan as the single complaint registration, tracking and grievance redressal module for Handpumps, SVS and MVS.

- Establishing Jal Darpan as a common domain and single entry point for citizens, subject to the feasibility study.

- Connecting the State Call Centre (181) to the complaint workflow for O&M complaints.

## 6. Existing Platforms and Current State

| Platform | Owner | Coverage | Current status |
| --- | --- | --- | --- |
| GHAN portal | PHED / MPSEDC | Geotagged handpump | Non-operational, one time activity for geotagging assets. |
| GHAN 2.0 (web and mobile) | PHED / MPSEDC | Citizen complaint registration, technician workflow, handpump maintenance and survey update | Live on web, Google Play Store and Apple App Store |
| Jal Rekha | MPJN / MPSEDC | MVS information; 12 operational modules including Dhara and Nirmal | Operational for MVS; to be extended to PHED for SVS |
| State Call Centre (181) | State Government | Citizen helpline | Operational; not yet linked to O&M complaint workflow for water assets |

The main gaps are that citizens must know which portal or application applies to their asset, SVS and MVS have no common complaint channel, and complaints received at 181 are not routed systematically to the responsible water-supply team.

## 7. Proposed Integrated Solution Architecture

.

| Layer | Components | Purpose |
| --- | --- | --- |
| Access layer | Jal Darpan common domain; GHAN 2.0 and Jal Rekha mobile apps; web portals; State Call Centre (181) | Single point of access for citizens, field staff and officers |
| Application layer | Jal Rekha (PHED-SVS modules, existing MVS modules); Jal Samadhan; GHAN 2.0 handpump modules | Module-wise functionality |
| Integration layer | Single sign-on and common user directory; common asset and scheme master; complaint API; Samagra ID integration; SMS and WhatsApp gateway; 181 call centre integration | Data exchange and common services between platforms |
| Data and GIS layer | Common database of handpumps, SVS and MVS assets; GIS data layers and satellite imagery from MPSEDC; MIS and dashboards | Single source of truth and analytics |

Design principles

- Reuse the complaint engine, technician workflow and geo-tagged photo capability already live in GHAN 2.0 instead of rebuilding them.

- One user identity per person across Jal Darpan, Jal Rekha, Jal Samadhan and GHAN 2.0.

- One asset master so that every complaint is linked to a handpump, SVS or MVS asset, scheme, village and responsible officer.

- Role-based access for EE, AE, SE, TPI-A, TPI-TL, ISA, technicians, MPJN officers and citizens.

## 8. Scope of Work (Module-wise Functionality)

The scope is grouped into five components. Component A follows the high-level FRS for Jalrekha and PHED SVS; Component B covers the GHAN 2.0 integration; Components C, D and E implement the directions of the ACS.

### A. Jal Rekha for PHED – Single Village Scheme (SVS)

User roles and access

| Role | Description | Access |
| --- | --- | --- |
| EE (Executive Engineer) | Administers schemes and users | Web |
| AE | Monitoring and supervision | Web and Mobile |
| SE | Field-level supervision; asset and validation review | Web and Mobile |
| TPI-A / TPI-TL | Third-party inspection agency staff and team leads | Mobile (as per HLD; Web access for TPI to be confirmed with the Department) |
| ISA | Implementation Support Agency (Sahbhagita) | Web and Mobile |

A1. User Management Module

- User registration and role-based login for EE, AE, SE, TPI-A and TPI-TL.

- EE creates users, activates or deactivates them, and assigns schemes to users.

- Role-based menus, dashboards and data visibility by scheme, block, district and division.

- Import of the User Master and Scheme Master provided by the Department.

- Audit log of user creation, status changes and scheme assignments.

A2. Asset Mapping Module

- Display and maintain already-mapped assets: distribution pipeline, OHT (overhead tank) and tubewell.

- Mapping of pending assets: sump well and pump line.

- Asset upload facility on the web portal; geo-location and attribute capture through the mobile app.

- Every asset linked to its scheme and village.

- Asset mapping report (scheme-wise, district-wise, mapped versus pending) with export.

A3. Data Visualisation

- Scheme-wise and district-wise visualisation of SVS asset data.

- Map and chart views with drill-down from district to scheme to asset.

A4. Parinam – Tap Connection Validation

- Mobile function to validate household tap connections in the field, with AI-assisted validation as per the FRS.

- Integration with Samagra ID for beneficiary identification.

- Web report of validation status (validated, pending, not found) by scheme, village and district.

A5. Dhara – Water Quantity

- Make the existing Jal Rekha Dhara web module available to PHED users on a role basis.

- Mobile app for meter reading where a water meter is installed: reading entry, photo capture, geo-tag and timestamp.

- Validation of readings, for example flagging a reading lower than the previous one.

- Web reports on consumption and reading status.

A6. Nirmal – Water Quality

- Make the existing Nirmal web module for water sample testing available to PHED users.

- Mobile app for geofenced sample collection (allowed only within a defined radius of the asset) from OHTs, tubewells and beneficiaries.

- Recording of sample details, test results and status, with flags for results outside permissible limits.

- Web reports.

A7. Sahbhagita – Community Participation

- Web and mobile modules for community participation activities.

- Scheme-wise mapping of ISAs using the list provided by the Department.

- Activity capture, monitoring and reports by ISA, scheme and district.

### B. GHAN 2.0 Integration with Jal Rekha

- Integration of the GHAN 2.0 web portal with Jal Rekha, with single sign-on and a common user directory.

- Integration of the GHAN 2.0 mobile application with the Jal Rekha mobile application, so a user can reach both services from one app session.

- Common asset master so handpump, SVS and MVS assets can be viewed together on the map and in dashboards.

- Shared reports and a consolidated PHED dashboard covering handpump complaints and maintenance alongside SVS and MVS status.

- Existing handpump complaint, maintenance and survey-update functionality of GHAN 2.0 continues without disruption.

### C. Jal Samadhan – Unified Complaint and Grievance Module

Jal Samadhan is incorporated into Jal Rekha as the single module for raising and tracking complaints for Handpumps, SVS and MVS.

Complaint registration

- Citizen registration and OTP-based login.

- Complaint categories for Handpump (not working, low discharge, contaminated water, damaged platform), SVS and MVS (no supply, low pressure, pipeline leakage, quality issue, meter issue, others).

- Asset selection by map, asset ID or nearest-asset search; geo-tagged photo upload; location capture.

- Unique complaint ID generated for every complaint, whichever channel it comes from.

Processing and tracking

- Automatic routing to the responsible officer or team based on asset type, scheme and location. Handpump and SVS complaints go to PHED field functionaries; MVS complaints go to MPJN-designated officers.

- Assignment to technicians or field staff, with status updates, before and after geo-tagged photos, and maintenance or repair details.

- Real-time status tracking for the citizen, with SMS or WhatsApp notifications at registration, assignment and closure.

- Citizen feedback on closure, with the option to reopen a complaint.

Escalation and monitoring

- Time-bound, level-wise escalation as described in Section 9.

- Dashboards for the ACS, MPJN, Engineers-in-Chief, SE, EE and AE covering complaints received, pending, resolved, escalated and breaching the timeline.

- Reports by district, scheme, asset type, channel, category and officer; export to Excel and PDF.

### D. Jal Darpan – Common Domain (Feasibility and Implementation)

As directed, the feasibility of a common domain under the name Jal Darpan will be examined first and, on the Department's approval, implemented.

D1. Feasibility study

- Study of domain, hosting, branding, URL structure and the existing domains (including jalrekha.mp.gov.in).

- Technical options for single sign-on, common user directory, API integration and a unified mobile app versus linked apps.

- Impact on existing users, and migration and communication plan.

- A feasibility report with recommendation, to be shared with the Department for decision.

D2. Implementation (subject to approval of the feasibility report)

- Common landing page and single entry point for citizens covering Jal Rekha, Jal Samadhan and GHAN 2.0.

- Common citizen login and one-time registration across all services.

- Services directory: raise a complaint, track a complaint, view scheme or asset information, and water quality and quantity information as approved for public display.

- Redirection of existing portals and application links to Jal Darpan to avoid confusion about which portal or app to use.

- Public dashboard and bilingual (Hindi and English) interface.

### E. Integration with State Call Centre (181)

- Coordination with the officials managing the State Call Centre (181) to define the process for complaints on O&M of Handpumps, SVS and MVS.

- API integration so that complaints taken at 181 are registered in Jal Samadhan with a unique complaint ID, and the caller is given the ID and status updates.

- Routing of each complaint to the designated departmental helpline or team, and a two-way status update (closure in Jal Samadhan is reflected at 181).

- A call-centre agent screen or script flow covering complaint categories and mandatory fields, and a call-back and reopen process.

- Reports on complaints received through 181 and their resolution.

## 9. Complaint Registration, Routing and Escalation Mechanism

Channels: Jal Darpan portal, GHAN 2.0 mobile app, Jal Rekha mobile app, State Call Centre (181), and officer-assisted entry on behalf of citizens.

Flow: Complaint received → unique ID generated and asset identified → auto-routed to the responsible officer or team (PHED or MPJN) → assigned to technician or field functionary → resolved with before and after geo-tagged photos → closed with citizen feedback → reopened if the citizen is not satisfied.

Proposed escalation matrix (levels and timelines are indicative and to be finalised by the Department and MPJN):

| Level | Responsible | Action time (proposed) | Escalates to |
| --- | --- | --- | --- |
| L1 | Technician / field functionary | Within 48 hours of assignment | AE |
| L2 | AE | A further 24 hours | EE |
| L3 | EE | A further 48 hours | SE |
| L4 | SE | A further 72 hours | Chief Engineer / MPJN nominated officer |
| L5 | Chief Engineer / MPJN officer | Monitoring and review | PHED / MD, MPJN dashboard alert |

The system sends automatic alerts at each escalation, shows breached complaints on the dashboards, and keeps a complete audit trail. For MVS complaints, the equivalent MPJN officers are mapped at each level.

## 10. Roles and Responsibilities of Stakeholders

| Stakeholder | Responsibilities |
| --- | --- |
| ACS, PHED | Overall direction and approvals; chairing periodic review of the integrated platform |
| PHED (Nodal officer, EE/SE/AE) | Designate a Single Point of Contact; provide User Master, Scheme Master and scheme-wise ISA list; confirm requirements, escalation matrix and SLAs; participate in UAT; field-level use and training of functionaries |
| MPJN | Provide MVS data, Jal Rekha module access and API details; nominate MVS officers for complaint routing and escalation; support integration of Jal Rekha with Jal Samadhan and Jal Darpan; participate in UAT |
| MPSEDC | Solution design, development, integration, testing and deployment; GIS data and satellite imagery; hosting coordination; training, user manuals and one year of post go-live support |
| State Call Centre (181) team | Share API and process details; train agents; route and update complaints as per the agreed process |
| TPI agencies / ISAs | Use the mobile and web modules for validation, sampling and community activities as per assigned roles |
| Citizens | Register and track complaints and give feedback through Jal Darpan, the mobile apps or 181 |

## 11. Methodology and Approach

Development follows the same life cycle as the GHAN 2.0 engagement:

- Requirement collection and analysis: workshops with PHED, MPJN and the 181 team; confirmation of the FRS for each component.

- Feasibility study: the Jal Darpan feasibility report and integration feasibility with Jal Rekha and GHAN 2.0.

- Design: system architecture, database design, API specifications, UI/UX and the Functional Requirement Specification.

- Coding: module-wise development in parallel tracks, following coding and security guidelines.

- Testing: unit, integration and regression testing in a testing environment.

- User Acceptance Testing (UAT): by PHED, MPJN and 181 representatives.

- Deployment: release to production and go-live support, with training of field functionaries.

- Maintenance: bug fixing, upgrades and enhancements, with one year of support after go-live.

## 12. Deliverables

- Jal Rekha modules for PHED SVS: User Management, Asset Mapping, Data Visualisation, Parinam, Dhara, Nirmal and Sahbhagita (web and mobile, role-wise).

- GHAN 2.0 web and mobile integration with Jal Rekha.

- Jal Samadhan unified complaint management module (web and mobile).

- Jal Darpan feasibility report and, after approval, the common domain and landing portal.

- State Call Centre (181) integration with Jal Samadhan.

- Consolidated dashboards and MIS reports.

- Functional Requirement Specification, system design document and test reports.

- User manuals for web and mobile applications, and training of Department, MPJN and call-centre users.

- One year of support and maintenance after go-live.

## 13. Implementation Plan and Timeline

Effort estimate (working days of development effort)

| # | Component / Module | Effort (days) |
| --- | --- | --- |
| A1 | User Management | 15 |
| A2 | Asset Mapping | 15 |
| A3 | Data Visualisation | 5 |
| A4 | Parinam | 10 |
| A5 | Dhara | 18 |
| A6 | Nirmal | 15 |
| A7 | Sahbhagita | 12 |
| B | GHAN 2.0 Integration | 12 |
| C | Jal Samadhan | 25 |
| D | Jal Darpan (feasibility 5 + implementation 15) | 20 |
| E | State Call Centre (181) Integration | 10 |
|  | Total effort | 157 |

Proposed schedule with three parallel development tracks (working days)

| Days | Track A | Track B | Track C |
| --- | --- | --- | --- |
| 1–15 | User Management (1–15) | Asset Mapping (1–15) | Jal Darpan feasibility (1–5); Jal Samadhan (6–30) |
| 16–30 | Parinam (16–25); Dhara starts (26–) | Data Visualisation (16–20); Nirmal starts (21–) | Jal Samadhan continues |
| 31–45 | Dhara (26–43); Sahbhagita starts (44–) | Nirmal (21–35); GHAN 2.0 Integration (36–47) | 181 Integration (31–40); Jal Darpan implementation (41–55) |
| 46–55 | Sahbhagita (44–55) | Cross-module integration testing (48–55) | Jal Darpan implementation continues |
| 56–67 | UAT, bug fixing and Department feedback | UAT, bug fixing and Department feedback | UAT, bug fixing and Department feedback |
| 68–72 | Go-live preparation, training and deployment | Go-live preparation, training and deployment | Go-live preparation, training and deployment |

With three parallel tracks, the build completes in about 55 working days (around 11 weeks) and go-live in about 72 working days (around 14 to 15 weeks) from project initiation. Timelines exclude Department-side delays in data or approvals. Jal Darpan implementation starts only after the Department approves the feasibility report. Efforts for Components C, D and E are MPSEDC's estimates and will be firmed up after requirement workshops.

## 14 Assumptions

- The scope is based on the minutes of 12.10.2026 and the high-level FRS, and will change only by mutual agreement between PHED, MPJN and MPSEDC.

- The Department provides the User Master, Scheme Master and scheme-wise ISA list before development of the related modules.

- Dhara mobile meter reading applies only where water meters are installed.

- Existing Jal Rekha modules (including Dhara and Nirmal) are reused for PHED users; no re-development of the 12 MVS modules is included.

- Timelines are in working days of development effort, exclude Department-side delays in data or approvals, and exclude UAT unless stated.

- GIS data layers and satellite imagery available with MPSEDC are provided free of cost.

- The cost of security audit, SMS, WhatsApp, hosting, domain registration, and 181 telephony or call-centre agent charges is not included and, if applicable, will be as per actuals.

- Escalation levels, timelines and complaint categories are indicative and will be finalised with PHED and MPJN.

- Future technology updates are assumed to be manageable through regular maintenance and support.

## 15. Expectations and Dependencies from the Department

- Clear requirements: PHED and MPJN designate a Single Point of Contact each and provide clear and detailed requirements.

- Regular communication: Prompt feedback, answers to queries and resolution of concerns with the MPSEDC Project Manager.

- Timely decision-making: Timely decisions on priorities, scope changes, the Jal Darpan feasibility report, the escalation matrix and approval of deliverables.

- Resource allocation: Access to subject matter experts of PHED, MPJN and the 181 team for requirement gathering for each module.

- Coordination: Introductions and approvals needed for 181 integration and for API access to Jal Rekha modules.

- Quality assurance: Participation in UAT before deployment.

- Adherence to deadlines: Timely review of deliverables and grant of approvals.

## 16 Contact Details

The following professionals are the key points of contact for this project.

From PHED:

- Name of the person: Mr. Rakesh Dawar

- Designation:EE

- Contact No:

- Email address:

From MPJN:

- Name of the person:

- Designation:

- Contact No:

- Email address:

From MPSEDC:

- Name of the person: Dr. Rakesh Dubey

- Designation: Head MPSSDI, OIC GIS

- Contact No:

- Email address: rakesh.dubey1@mpsedc.mp.gov.in