## Sheet1
Date Wise Time Sheet
Time Sheet entry Date From : 01/09/2026 To 30/09/2026 Current Date & Time : October 1, 2026 at 12:10:53 PM
Sr.No | Resource Name | Resource_Location | Project Name | Sprint Name | Sprint Start Date ¦ End date | Module Name | Activity Name | Task Assign Date | TimeSheet Entry date | Task Name | Assign Hours | Consumed Hrs | Work Status By Resource | Work Status By PM | Action Performed by Resource
1 | Aasheesh Gupta | INDORE | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Change Request Contractor | O&M Billing Contractor Summary Page changes | 15/09/2026 | 16/09/2026 | UI Update and Bug Fixes in Frm Bill Tracking Page | 16.00 | 8.00 | WIP | Yet To Update | Updated and restored the Jal Rekha database in pgAdmin to ensure the latest database changes were properly synchronized and available for development. Worked on the alignment and overall UI design of the Frm Bill Tracking page under the Aakalan module. Updated and refined the Search Bar input field on the Frm Bill Tracking page for improved usability and consistent styling. Fixed the alignment of Search Bar buttons and select input fields to maintain a clean and structured layout. Refined the overall spacing, alignment, and UI consistency of the Bill Tracking page. Checked and updated the mobile responsive layout to ensure proper display across different screen sizes. Conducted UI testing to cross-check the updated search components, alignment, page layout, and responsive behavior.
2 | Aasheesh Gupta | INDORE | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Change Request Contractor | O&M Billing Contractor Summary Page changes | 15/09/2026 | 17/09/2026 | UI Update and Bug Fixes in Frm Bill Tracking Page | 16.00 | 8.00 | Completed | Yet To Update | Continued work on the Frm Bill Tracking page under the Aakalan module and enhanced the overall UI design and alignment. Updated and refined the data table to improve its structure, presentation, and overall UI consistency. Fixed the TR/TD alignment within the data table to ensure proper positioning and readability of table content. Updated and refined the popup design inside the data table with improved layout, spacing, alignment, and styling. Ensured consistency between the data table and popup components as per the overall module design. Checked and updated the mobile-responsive layout of the Frm Bill Tracking page for different screen sizes. Conducted UI testing to cross-check the table alignment, popup design, layout, and responsive behavior.
3 | Aasheesh Gupta | INDORE | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Dashboard | Requirement Gathering | 18/09/2026 | 18/09/2026 | UI Update and Bug Fixes in login page and forgot page | 16.00 | 8.00 | WIP | Yet To Update | Updated and restored the Jal Rekha database to ensure the latest project data and changes were properly maintained. Completely redesigned the Login Tab on the Jal Rekha Login Page with updated UI components and styling. Worked on the alignment and layout of the Login Tab to improve spacing, positioning, and overall visual consistency. Designed and refined the Forgot Password popup with a structured layout, improved styling, and proper component alignment. Updated the overall Login and Forgot Password UI to maintain consistency with the latest design requirements. Implemented and verified mobile responsiveness for the updated Login Tab and Forgot Password popup. Conducted UI testing to cross-check the updated design, alignment, popup layout, and responsive behavior across different screen sizes.
4 | Aasheesh Gupta | INDORE | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Dashboard | Requirement Gathering | 18/09/2026 | 21/09/2026 | UI Update and Bug Fixes in login page and forgot page | 16.00 | 8.00 | Completed | Yet To Update | Updated and refined the complete Login Tab design on the Jal Rekha Login Page as per the latest UI requirements. Fixed and optimized the left sidebar layout for mobile devices to ensure proper positioning, visibility, and usability on smaller screens. Designed and refined the Terms & Conditions popup on the Login Page with proper layout, spacing, alignment, and styling. Updated the related UI components and styling to maintain consistency across the Login Page. Merged and updated the completed code changes into the Development Branch for further integration and testing. Implemented and verified mobile responsiveness for the updated Login Page, sidebar, and popup components. Conducted UI testing and cross-checking to validate the updated design, alignment, popup behavior, mobile layout, and overall page consistency.
5 | Aasheesh Gupta | INDORE | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Change Request Contractor | Contractor Bill generation flow and update Approved Reports | 22/09/2026 | 22/09/2026 | UI Update and Bug Fixes and bill create in Aaklan module | 16.00 | 8.00 | WIP | Yet To Update | Worked on the Aakalan Module and enhanced the overall page layout and UI design. Conducted R&D on the Abstract Bill design flow to understand the required structure, user flow, and UI implementation. Created and designed reusable CSS components for the Abstract Bill interface to maintain consistent styling and improve UI reusability. Fixed and refined the Bill Generate Table design with proper alignment, spacing, and overall layout consistency. Improved the overall UI structure and visual consistency of the Abstract Bill and Bill Generate sections. Implemented and verified mobile responsiveness for the updated Aakalan module pages and components. Conducted UI testing and cross-checking to validate the updated CSS components, table design, alignment, and responsive behavior.
6 | Aasheesh Gupta | INDORE | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Change Request Contractor | Contractor Bill generation flow and update Approved Reports | 22/09/2026 | 23/09/2026 | UI Update and Bug Fixes and bill create in Aaklan module | 16.00 | 8.00 | Completed | Yet To Update | Worked on the Abstract Bill design under the Jal Rekha Aakalan module. Designed and refined the Abstract Bill interface with proper layout, spacing, alignment, and styling. Created and implemented reusable CSS components for the Abstract Bill design and integrated them into the Bill Generate functionality. Created and designed the Bill Generate Data Table with a structured layout, proper alignment, and consistent styling. Refined the overall UI components and table layout to maintain design consistency across the Aakalan module. Implemented and verified mobile responsiveness for the Abstract Bill and Bill Generate sections. Conducted UI testing to cross-check the bill design, CSS components, table layout, alignment, and responsive behavior.
7 | Aasheesh Gupta | INDORE | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Change Request Contractor | CR in Contractor - Summary page Abstract Report | 24/09/2026 | 24/09/2026 | UI Update and Bug Fixes in Abstract bill in Aaklan module | 16.00 | 8.00 | WIP | Yet To Update | Worked on the Print/PDF design of the Abstract Bill under the Jal Rekha Aakalan module. Designed and refined the Abstract Bill Print/PDF layout to ensure proper presentation and print-friendly formatting. Created and implemented reusable CSS components specifically for the Abstract Bill Print/PDF design. Fixed the table alignment and content positioning in the Abstract Bill Print/PDF layout for improved readability and consistency. Refined the overall spacing, typography, borders, and alignment of the Print/PDF content. Implemented and verified mobile responsiveness for the updated Abstract Bill design. Conducted Print/PDF and UI testing to cross-check table layout, content alignment, formatting, and responsive behavior.
8 | Aasheesh Gupta | INDORE | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Change Request Contractor | CR in Contractor - Summary page Abstract Report | 24/09/2026 | 25/09/2026 | UI Update and Bug Fixes in Abstract bill in Aaklan module | 16.00 | 8.00 | Completed | Yet To Update | Continued work on the Abstract Bill Print/PDF design under the Jal Rekha Aakalan module. Identified and fixed various Print/PDF design and formatting issues to improve the overall output. Fixed the page-wise alignment and layout of the Abstract Bill to ensure proper content placement across multiple PDF pages. Refined the design of the Final Abstract Bill section with improved layout, spacing, alignment, and formatting. Fixed the table and inner section alignment within the Abstract Bill Print/PDF layout for better readability and consistency. Optimized the page breaks, spacing, and content positioning to maintain a clean and structured Print/PDF output. Implemented and verified mobile responsiveness for the updated Abstract Bill interface. Conducted Print/PDF testing to cross-check page-wise alignment, table structure, inner sections, formatting, and overall output consistency.
9 | Aasheesh Gupta | INDORE | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing GM | UI update in existing page | 28/09/2026 | 28/09/2026 | UI Update and Bug Fixes in Abstract Report PDF | 8.00 | 8.00 | Completed | Yet To Update | Worked on the O&M Billing Abstract Bill Print/PDF design under the Jal Rekha Aakalan module. Identified and fixed various Print/PDF design and formatting issues in the O&M Billing Abstract Bill. Fixed the page-wise alignment and layout to ensure proper content placement across different PDF pages. Fixed the table and inner section alignment within the O&M Billing Abstract Bill Print/PDF layout for improved readability and consistency. Refined the overall spacing, content positioning, page breaks, and formatting to achieve a clean and structured Print/PDF output. Ensured consistent layout and styling across all sections of the O&M Billing Abstract Bill. Implemented and verified mobile responsiveness for the updated O&M Billing Abstract Bill interface. Conducted Print/PDF testing to cross-check page-wise alignment, tables, inner sections, formatting, and overall output consistency.
10 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Project Module Initiation Meeting and Requirement gathering | 01/09/2026 | 01/09/2026 | GP User Module requirement and analysis | 8.00 | 8.00 | Completed | Yet To Update | DONE
11 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Anusharavan at Gram Panchanyat level | 02/09/2026 | 02/09/2026 | GP Select User Type and citizen login UI for mobile | 8.00 | 8.00 | Completed | Yet To Update | New screens for GP module
12 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Mobile Development | 07/09/2026 | 07/09/2026 | GP User login screen and api integration | 8.00 | 8.00 | Completed | Yet To Update | GP Login functionality and GP User RFI form
13 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Mobile Development | 08/09/2026 | 08/09/2026 | GP User RFI form and Sync data for offline functionality | 16.00 | 8.00 | WIP | Yet To Update | sync api call and local db
14 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Mobile Development | 08/09/2026 | 09/09/2026 | GP User RFI form and Sync data for offline functionality | 16.00 | 8.00 | Completed | Yet To Update | Save Offline RFI
15 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | Crash Analytics & Issue Fixes | 10/09/2026 | 10/09/2026 | Play store crashlytics fix | 16.00 | 8.00 | WIP | Yet To Update | Working on crashlytics fix
16 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | Crash Analytics & Issue Fixes | 10/09/2026 | 11/09/2026 | Play store crashlytics fix | 16.00 | 8.00 | Completed | Yet To Update | bug fixing
17 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Mobile Development | 15/09/2026 | 15/09/2026 | Submit RFI api integration & Offline Draft list screen | 8.00 | 8.00 | Completed | Yet To Update | DONE
18 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Mobile Development | 16/09/2026 | 16/09/2026 | UI Enhancement | 16.00 | 8.00 | WIP | Yet To Update | App UI Enhancement
19 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Mobile Development | 16/09/2026 | 17/09/2026 | UI Enhancement | 16.00 | 8.00 | Completed | Yet To Update | App UI Enhancement
20 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | FHTC Parinam Enhancements | Parinam Dashboard | 18/09/2026 | 18/09/2026 | UI Enhancement | 8.00 | 8.00 | Completed | Yet To Update | UI Enhancement
21 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Mobile Development | 21/09/2026 | 21/09/2026 | History Page and api integration with details page | 16.00 | 8.00 | WIP | Yet To Update | Working on history page
22 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Mobile Development | 21/09/2026 | 22/09/2026 | History Page and api integration with details page | 16.00 | 8.00 | Completed | Yet To Update | DONE
23 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Dhara | UI update in existing page | 23/09/2026 | 23/09/2026 | Dhara UI Changes | 16.00 | 8.00 | WIP | Yet To Update | Dhara component list page UI changes
24 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Dhara | UI update in existing page | 23/09/2026 | 24/09/2026 | Dhara UI Changes | 16.00 | 8.00 | Completed | Yet To Update | Dhara meter reading form ui upgradation
25 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | Mobile/Web- Enhancement and Regression Testing | 28/09/2026 | 28/09/2026 | UI Enhancement for different modules | 16.00 | 8.00 | WIP | Yet To Update | Material UI theme integration
26 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | Mobile/Web- Enhancement and Regression Testing | 28/09/2026 | 29/09/2026 | UI Enhancement for different modules | 16.00 | 8.00 | Completed | Yet To Update | Material UI theme integration
27 | AWINASH KHARE | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 01/09/2026 | 01/09/2026 | Contractor/GM Login O&M Bill Generation & Approval Enhancements | 16.00 | 8.00 | WIP | Yet To Update | Implemented stage-wise approval workflow enhancements for O&M Billing. Added role-based authorization for TL (SQC) and GM (PIU), dynamic document upload fields, remarks validation, target-stage forwarding, and approval-stage document visibility on the Bill Submission page. Performed integration testing and fixed workflow access issues.
28 | AWINASH KHARE | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 01/09/2026 | 02/09/2026 | Contractor/GM Login O&M Bill Generation & Approval Enhancements | 16.00 | 8.00 | Completed | Yet To Update | Worked on Jal Rekha O&M Billing enhancements, including analysis and implementation of required billing-related changes.
29 | AWINASH KHARE | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 03/09/2026 | 03/09/2026 | Scheme-wise GM, Contractor & TL_SQC Mapping Update | 16.00 | 8.00 | Completed | Yet To Update | Verified scheme-wise GM, Contractor and TL_SQC mapping details. Identified the existing TL_SQC for Scheme 13, validated the replacement user details, and updated the existing TL_SQC assignment in the database as per the requirement.
30 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Anusharavan at Gram Panchanyat level | 01/09/2026 | 01/09/2026 | Reguirement gathering understanding and meeting with MD sir and internal meeting | 10.00 | 3.00 | WIP | Yet To Update | meeting adone and gathered the requirement
31 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Requirement gathering, meetings and Wireframe | 01/09/2026 | 02/09/2026 | Wireframe of Anusharavan GP for SVS | 8.00 | 3.00 | WIP | Yet To Update | Designing wireframe and adding requirements
32 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Requirement gathering, meetings and Wireframe | 01/09/2026 | 04/09/2026 | Wireframe of Anusharavan GP for SVS | 8.00 | 3.00 | WIP | Yet To Update | Updated Wireframe with BR CR FR in the separate workflow
33 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Anusharavan at Gram Panchanyat level | 01/09/2026 | 07/09/2026 | Reguirement gathering understanding and meeting with MD sir and internal meeting | 10.00 | 3.00 | WIP | Yet To Update | Anusharavan RFI at GP level and Sub engineer level role based screen creation
34 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Nirmal GP | Requirement gathering, meetings and wireframe | 01/09/2026 | 09/09/2026 | Wireframe updation and addition of range in FTK kit for Nirmal SVS | 6.00 | 2.00 | WIP | Yet To Update | Gathered requirement through meeting and analysis of ranges for ftk water quality kit
35 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Anusharavan at Gram Panchanyat level | 01/09/2026 | 09/09/2026 | Reguirement gathering understanding and meeting with MD sir and internal meeting | 10.00 | 3.00 | WIP | Yet To Update | Edited details for Wireframe workflow and Meeting with department
36 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 01/09/2026 | 09/09/2026 | Nirmal wireframe BR FR CR updation | 4.00 | 3.00 | WIP | Yet To Update | Updated Wireframe with new changes and shared BR FR and CR with team
37 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Nirmal GP | Requirement gathering, meetings and wireframe | 01/09/2026 | 18/09/2026 | Wireframe updation and addition of range in FTK kit for Nirmal SVS | 6.00 | 4.00 | Completed | Yet To Update | updated wireframe with Nirmal SVS details
38 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Anusharavan at Gram Panchanyat level | 01/09/2026 | 18/09/2026 | Reguirement gathering understanding and meeting with MD sir and internal meeting | 10.00 | 1.00 | Completed | Yet To Update | Discussed with internal about SVS Anusharavan requirement
39 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 01/09/2026 | 18/09/2026 | Nirmal wireframe BR FR CR updation | 4.00 | 1.00 | Completed | Yet To Update | Nirmal wireframe BR FR CR created and shared with tester
40 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Requirement gathering, meetings and Wireframe | 04/09/2026 | 23/09/2026 | Wireframe update and Master & RFI screen updates | 8.00 | 4.00 | WIP | Yet To Update | Meeting with department and internal team to implement module
41 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Requirement gathering, meetings and Wireframe | 04/09/2026 | 30/09/2026 | Wireframe update and Master & RFI screen updates | 8.00 | 4.00 | Completed | Yet To Update | Meeting attended in Jal nigam for SVS PHE Anusharavan module integration with SIPRI and Collect master data from department to hand it over SIPRI team through mulitple meeting
42 | Mukesh Singh | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Cube Testing CR | New Stage Changes - Mobile App, DB, API & Web level | 09/09/2026 | 10/09/2026 | Worked on resolving a database-level issue on the live production server and implemented the required changes successfully. | 8.00 | 8.00 | Completed | Yet To Update | Fixed SQL syntax, type mismatch, and join-related issues.
43 | Mukesh Singh | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Material Testing Change Request | Database functions Updation & API Web and Mobile Services | 15/09/2026 | 15/09/2026 | Material and Cube Module – New Stage Database Changes & Function Updates as per Requirement | 8.00 | 8.00 | Completed | Yet To Update | Developed reusable SQL scripts for developer.
44 | Mukesh Singh | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 18/09/2026 | 21/09/2026 | CR: Clarify and Implement Required Database Changes | 8.00 | 8.00 | Completed | Yet To Update | Implemented database changes for new application features.
45 | Mukesh Singh | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Master Enhancements | Survey data of Intake Master | 24/09/2026 | 24/09/2026 | Work on Intake Master update/insert — Source (Dam/River), Name of Source, and Capacity of Intake Well. | 8.00 | 8.00 | Completed | Yet To Update | Supported application team with DB-level troubleshooting.
46 | Neha Soni | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Master Enhancements | Survey data of Intake Master | 21/09/2026 | 21/09/2026 | Creation of web page and API Survey data of Intake Master | 8.00 | 8.00 | Completed | Yet To Update | Creation of web page and API Survey data of Intake Master
47 | Neha Soni | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Master Enhancements | Survey data of OHT Master | 22/09/2026 | 22/09/2026 | Creation of web page and API Survey data of OHT Master | 8.00 | 8.00 | Completed | Yet To Update | Creation of web page and API Survey data of OHT Master
48 | Neha Soni | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Master Enhancements | Survey data of WTP Master | 23/09/2026 | 23/09/2026 | Creation of web page and API Survey data of WTP Master | 8.00 | 8.00 | Completed | Yet To Update | Creation of web page and API Survey data of WTP Master
49 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 02/09/2026 | 02/09/2026 | SVS Nirmal- Test Scenario Creation | 8.00 | 8.00 | Completed | Yet To Update | Started working on test scenario creation and its in progress.
50 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | 2 Factor Authentication Implementation | 03/09/2026 | 03/09/2026 | Testing | 4.00 | 4.00 | Completed | Yet To Update | Performed testing on 2FA functionality.
51 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | 2 Factor Authentication Implementation | 03/09/2026 | 03/09/2026 | Understanding on 2FA | 4.00 | 4.00 | Completed | Yet To Update | 2FA requirement gathering completed, including authentication flow, OTP validation, security scenarios, and suggestions for appropriate popup/alert messages.
52 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Nirmal GP | Internal Testing | 07/09/2026 | 07/09/2026 | Testing | 4.00 | 4.00 | Completed | Yet To Update | Testing Nirmal module.
53 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | User & Role Management | Automation with Selenium | 07/09/2026 | 07/09/2026 | Automation Script | 4.00 | 4.00 | Completed | Yet To Update | Worked on script creation
54 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Nirmal GP | Internal Testing | 08/09/2026 | 08/09/2026 | NIRMAL-Testing | 4.00 | 4.00 | Completed | Yet To Update | Testing and re-testing of bugs have been completed.
55 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Nirmal GP | Requirement gathering, meetings and wireframe | 08/09/2026 | 08/09/2026 | NIRMAL – Requirement Understanding for Reports | 4.00 | 4.00 | Completed | Yet To Update | Understanding on Nirmal Report View. Also prepare report section table for reference to team member.
56 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | User & Role Management | Automation with Selenium | 09/09/2026 | 09/09/2026 | Automation Script updated till User Access Mapping | 8.00 | 8.00 | Completed | Yet To Update | Update the script
57 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Cube Testing CR | New Stage Changes - Mobile App, DB, API & Web level | 10/09/2026 | 10/09/2026 | Cube Testing- Change Request where Contractor re-inspection document/Photo in option | 4.00 | 4.00 | Completed | Yet To Update | Testing has been completed.
58 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Material Testing Change Request | New Stage Changes - Mobile App, DB, API & Web level | 10/09/2026 | 10/09/2026 | Material Testing- Change Request where Contractor re-inspection document/Photo in option | 4.00 | 4.00 | Completed | Yet To Update | Testing has been completed. And moved to prod.
59 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Dhara | UAT/Prod/CR Testing | 16/09/2026 | 16/09/2026 | Prod Issue Validation | 2.00 | 2.00 | Completed | Yet To Update | Validated the issue on prod
60 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Material Testing Change Request | Loop Functionality | 16/09/2026 | 16/09/2026 | Test Plan Document | 8.00 | 4.00 | WIP | Yet To Update | Started working on Test Plan document for loop functionality
61 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Sahbhagita GM | UAT/Prod/CR Testing | 16/09/2026 | 16/09/2026 | Prod Issue Validation- CP Manager | 2.00 | 2.00 | Completed | Yet To Update | Issue Validated on Prod
62 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 17/09/2026 | 17/09/2026 | Test Plan Document | 8.00 | 4.00 | Completed | Yet To Update | Started working on Cube testing test plan document for loop functionality
63 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Material Testing Change Request | Loop Functionality | 16/09/2026 | 17/09/2026 | Test Plan Document | 8.00 | 4.00 | Completed | Yet To Update | Document has been completed
64 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Dhara | UAT/Prod/CR Testing | 18/09/2026 | 18/09/2026 | Testing | 4.00 | 4.00 | Completed | Yet To Update | Validated prod issue
65 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 21/09/2026 | 21/09/2026 | Test Plan Document- Update and Completion | 8.00 | 8.00 | Completed | Yet To Update | Test Plan Document has been completed for cube testing Loop Functionality.
66 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | Training/Walkthrough | 22/09/2026 | 22/09/2026 | Jal Rekha application training | 3.00 | 3.00 | Completed | Yet To Update | Walkthrough given to the team members.
67 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | FHTC Change request FHTC | FHTC Loop functionality implementation | 22/09/2026 | 22/09/2026 | Test Plan Document-FHTC | 5.00 | 5.00 | Completed | Yet To Update | Worked on test plan document
68 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 28/09/2026 | 28/09/2026 | Update and completion of Test Plan | 8.00 | 8.00 | Completed | Yet To Update | Test Plan document has been completed.
69 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | Mobile/Web- Enhancement and Regression Testing | 29/09/2026 | 29/09/2026 | Mobile App UI and Regression Testing | 8.00 | 8.00 | Completed | Yet To Update | Verified UI changes and performed regression on mobile app.
70 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | Mobile/Web- Enhancement and Regression Testing | 30/09/2026 | 30/09/2026 | Retesting of bugs and regression | 8.00 | 8.00 | Completed | Yet To Update | Bug retesting has been completed and closed.
71 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 01/09/2026 | 01/09/2026 | O&M Bill Approval Workflow – Stage-wise Routing, Document Management & Role-based Review Modification | 16.00 | 8.00 | WIP | Yet To Update | Enhanced the Approval Stage Review Popup to dynamically determine and display the next workflow action based on the selected Target Stage, clearly distinguishing between Forward and Send Back actions. Implemented Target Stage-based workflow routing by integrating allowed route information with the approval process, ensuring that users can select only the valid next stages configured for the current approval stage. Analyzed and corrected the Previous Approval History mapping to ensure that the correct stage and action information is displayed according to the actual workflow transition. Analyzed and corrected the Previous Approval Attached Documents mapping to ensure that approval documents are displayed against their respective workflow stages and approval actions.
72 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 07/09/2026 | 07/09/2026 | Contractor Monthly Bill PDF & Bill Sheet Modification | 8.00 | 8.00 | Completed | Yet To Update | Fixed the issue of the Monthly Bill PDF Download button not displaying for Contractor users, including submitted bills. Modified Lodder.js to display Additional Addition along with Additional Deduction in the Monthly Bill PDF. Removed the Action column from the Additional Addition table in PDF export. Updated OMBillPrint.js to keep the Download PDF button available in both Draft and Submitted modes. Tested PDF generation and verified the required tables and download functionality.
73 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 08/09/2026 | 08/09/2026 | Billing GM & Contractor Page UI and Loading Improvements | 8.00 | 8.00 | Completed | Yet To Update | Fixed Scheme Status issue on the Billing GM Page and updated OMContractDetails.js field handling. Fixed Contractor Page month-change button state so buttons refresh correctly for the selected month. Improved Contractor Page initial loading to ensure all page components load properly. Enhanced loader.js with a counter-based loading mechanism to handle multiple pending operations. Tested month-wise button behavior and page loading functionality.
74 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 09/09/2026 | 09/09/2026 | Bill Tracking & History Page Modification | 8.00 | 8.00 | Completed | Yet To Update | Modified the Bill Tracking page to display additional required details in the Bill History Timeline as per the updated requirements. Updated the Timeline information and fields to ensure relevant bill-related details are displayed correctly. Worked on the Contractor Bill submission/details section to resolve issues faced by contractors while adding the required details. Modified DataTable names, column names, and displayed fields as per the latest department requirements. Reviewed and adjusted the Bill Tracking and History UI to maintain consistency with the updated column structure and naming conventions. Performed functional testing of the modified sections and verified the updated data display and workflow.
75 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 10/09/2026 | 10/09/2026 | Fix Lodder of the Contractor Page Issue | 8.00 | 8.00 | Completed | Yet To Update | Issue Reported: On the O&M Billing page, certain dropdowns and dependent data occasionally became interactive before the page had fully finished loading, allowing users to begin entering data prematurely. Additionally, the loading indicator was found to disappear before background data fetches (e.g., Power Consumption sheet, month-change data) had actually completed. Root Cause Analysis: Investigated the shared loader utility (loader.js) used across the application. The ShowSendingProgress() / StopProgress() functions were implemented as a simple show/hide toggle rather than a reference-counted mechanism. As a result, whenever multiple asynchronous (AJAX) calls executed in parallel, the loader was dismissed as soon as the first call completed — even while other calls were still in progress. Work Completed: Refactored loader.js to implement a counter-based (reference-counted) loading indicator, ensuring the loader remains visible until all concurrently active requests have completed. Conducted a full audit of OMBillPrint.js to verify consistency between ShowSendingProgress() and StopProgress() calls across all functions. Identified 21 functions where StopProgress() was invoked without a corresponding ShowSendingProgress() call — a pattern that would undermine the new counter-based logic and cause the loader to close prematurely. Applied corrective fixes to 17 of the 21 identified functions, adding the missing ShowSendingProgress() calls and, where required, adding missing StopProgress() calls in success/error/exception handlers to prevent the loader from getting stuck indefinitely. Each fix was tagged with a // LOADER-FIX comment for easy traceability and future auditing. Functions fixed: GetComplaintRedressalSheet, submitPressureFinal, submitComplaintRedressalSheetFinal, GetManpowerByContractSchemeID, GetManpowerVehicleByContractSchemeID, GetManpowerLandLineByContractSchemeID, ManpowerDataFinal, PowerConsuptionStart, GetPowerConsuptionSheetList, submitPowerConsuptionSheetFinal, GetUFWReport, GetYearlyFactorSummary, GetCPIWSummary, GetSummaryBulkUserList, GetSummaryGrossList, GetSummaryDeductionList, GetNetPayableBillList, GetAdditionaldeduction, submitDeductionSummarySheet
76 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 01/09/2026 | 11/09/2026 | O&M Bill Approval Workflow – Stage-wise Routing, Document Management & Role-based Review Modification | 16.00 | 8.00 | Completed | Yet To Update | Due to not fill on 02-09-2026 , so complete this task. Modified the approval-stage document upload functionality to support multiple stage-wise document attachments, with the required document fields dynamically generated based on the current approval stage and configured upload requirements. Implemented role/stage-based document requirements, allowing different approval roles such as GM (PIU) and TL (SQC) to have different document attachment requirements depending on the workflow stage. Enhanced the document upload UI to dynamically display the Document Name/Label for each attachment field, making it easier for users to identify and upload the appropriate supporting documents. Modified the approval workflow access logic to allow all authorized roles to view the complete approval flow, while restricting the Review/Process functionality to the role responsible for the current approval stage. Updated the GetStageReviewPage, GetPendingApprovals, GetAllowedRoutes, and ProcessApprovalStage service integration and related JavaScript logic to support the modified workflow, routing, document upload, and role-based processing requirements. Added and integrated an additional role/stage-based control flag across multiple services to maintain proper data visibility and processing permissions after modification of the approval workflow.
77 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 15/09/2026 | 15/09/2026 | GM Page Validation, Document Upload & Final Submission Enhancement | 16.00 | 8.00 | WIP | Yet To Update | Heading: GM Page UI and Functionality Enhancement Worked on the GM Page and analyzed multiple UI and functional issues reported during the workflow. Fixed the Hide/Show functionality of different sections and controls based on the selected input/options. Modified the Last Tab selection behavior to ensure that “No Selection” is displayed by default and dependent functionality works accordingly. Fixed the Scheme Trial Run related issue and verified the functionality with different selection scenarios. Implemented validation to block further processing/submission when the required input selection is not provided. Tested the updated UI functionality with different combinations of input values and selections.
78 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 15/09/2026 | 16/09/2026 | GM Page Validation, Document Upload & Final Submission Enhancement | 16.00 | 8.00 | Completed | Yet To Update | Heading: GM Page Validation, Document Upload & Final Submission Enhancement Fixed the Document Upload issue where the uploaded document was not being removed correctly from the document list. Updated the document list functionality to properly add, display and remove uploaded documents as required. Implemented the required default selection for “Water Supplied During Construction Phase?” as per the updated department requirement. Modified “Is Trial Run of Whole Scheme Given?” functionality to show “No” as the default selection during the initial load. Implemented dependent field functionality so that when “Yes” is selected for Trial Run, the related input fields/options are displayed for further data entry. Added Final Submit validation to check whether all previous tabs have been submitted/completed before allowing final submission. Added an appropriate validation message when any previous tab is incomplete and prevented the user from proceeding with Final Submit. Performed end-to-end testing of the GM Page after applying all UI, validation, document upload, dependency and submission-related changes.
79 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing Workflow b/w O&M GM & Higher officials | Worflow Functionality at each login for O&M Billing | 17/09/2026 | 17/09/2026 | Quarter Filter Enhancement in Approval Page | 8.00 | 8.00 | Completed | Yet To Update | Added Quarter filter along with PIU, Scheme, and Financial Year filters for bill search. Modified GetPendingApprovals() to support Quarter-wise filtering. Developed and integrated GetQuarterListForTracking() service for Quarter dropdown. Updated frontend and service-level changes for Quarter-based bill tracking. Heading: RA Bill Page Heading Modification Modified Frm_Bill_Tracking.aspx page heading to RA Bill Tracking. Modified Frm_ContractorBill_ForApproval.aspx page heading to Pending RA Bill For Approval. Heading: Master Page Menu Label Modification Updated JalRekhaMaster.Master menu labels for RA Bill Tracking and Pending RA Bill For Approval pages.
80 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Master Enhancements | Scheme Village OHT Mapping & Report Updations | 18/09/2026 | 18/09/2026 | Vistrit : Village Mapping – GM PIU Permission Workflow Modification | 8.00 | 8.00 | Completed | Yet To Update | Modified the Village Mapping form to update the GM PIU Permission and Water Supply Testing workflow as per the revised requirements. Implemented validation to ensure that Water Supply Testing Start Date is mandatory when “Is Water Supply Testing Started by Firm” is selected as Yes. Added dependency validation so that GM PIU Permission can be selected as Yes only after Water Supply Testing is marked Yes and its start date is entered. Modified the confirmation workflow by moving the “Are you sure? This will not change after that.” confirmation from radio button selection to the final Save/Update action. Updated the form behavior to allow users to change the GM PIU Permission selection before final submission. Restricted both Water Supply Testing Date and GM PIU Permission Date to the current month and previous month only. Added date validation to ensure that the GM PIU Permission Date cannot be earlier than the Water Supply Testing Start Date. Added additional validation at the Save/Update level as a safety check to prevent invalid GM PIU Permission and testing-date combinations. Updated the Edit Village Mapping workflow to load existing Scheme, District, Block, GP and Village data sequentially and preserve the existing mapped village details. Updated the confirmation and validation handling for both Insert and Update Village Mapping operations. Verified the dependent dropdown flow for PIU District → Scheme → District → Block → Gram Panchayat → Village after the workflow modifications. Tested the updated Village Mapping functionality for new mapping, existing record modification, date validation, permission validation, and final Save/Update confirmation.
81 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 22/09/2026 | 22/09/2026 | O&M Billing Addition & Deduction and Bill Tracking – Client Requirement Enhancement | 16.00 | 8.00 | WIP | Yet To Update | Implemented client requirement to extend Deduction Amount functionality from Contractor to TL SQC and GM (PIU) users. As per new requirement, added related document upload with Deduction submission and modified the service accordingly. Updated Addition flow to include related document upload during Addition submission as per client requirement. Implemented role-based functionality: Addition & Deduction disabled for Contractor and enabled for TL SQC and GM (PIU). Modified JS functions for Addition/Deduction access, data retrieval and submission with documents. Updated Service, DTO, Entity and DB Helper for the new document-related requirements. Tested the updated Addition/Deduction flow with Contractor, TL SQC and GM login roles.
82 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 22/09/2026 | 23/09/2026 | O&M Billing Addition & Deduction and Bill Tracking – Client Requirement Enhancement | 16.00 | 8.00 | Completed | Yet To Update | Enhanced Bill Tracking Consolidated Bill link and generation flow as per the updated contractor bill process. Modified Consolidated Bill PDF generation with the latest bill structure. Updated Final Bill to show Contractor and TL SQC/GM Addition-Deduction in separate blocks. Modified bill print layout to avoid confusion between Contractor and upper-level additions/deductions. Updated Bill_Tracking.js, Lodder.js and OMBillPrint.js for the new flow. Modified Frm_Bill_Tracking.aspx and OandMBillingPrint.aspx as per the updated requirements. Updated new-style-design.css for the revised bill layout.
83 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | O&M Billing Workflow b/w O&M GM & Higher officials | Worflow Functionality at each login for O&M Billing | 24/09/2026 | 24/09/2026 | Open Bill Access for Additional Authorities | 8.00 | 8.00 | Completed | Yet To Update | Modification: Updated OMBillPrint.js to allow additional authorities (TL-PMC, CGM, PD, CA, CFO, and MD) to view Open Bills as part of the bill approval workflow. Approval Flow: Modified bill viewing access according to the respective authority/stage in the approval process. JS Modification: Updated OMBillPrint.js to handle Open Bill visibility for the additional approval authorities.
84 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Anusharavan CR | Anusharavan Survey Bug fix and optimization | 01/09/2026 | 01/09/2026 | Work on Anusharavan Survey Bug fix and optimization | 8.00 | 8.00 | Completed | Yet To Update | Work on Anusharavan Survey Bug fix and optimization
85 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Anusharavan CR | Anusharavan Survey Bug fix and optimization | 02/09/2026 | 02/09/2026 | Anusharavan Survey Bug fix and optimization | 8.00 | 8.00 | Completed | Yet To Update | Work on Anusharavan Survey Bug fix and optimization
86 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | 2 Factor Authentication Implementation | 03/09/2026 | 03/09/2026 | work on 2 Factor Authentication Implementation | 8.00 | 8.00 | Completed | Yet To Update | work on 2 Factor Authentication Implementation Done
87 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Cube Testing CR | New Stage Changes - Mobile App, DB, API & Web level | 07/09/2026 | 07/09/2026 | work on New Stage Changes - DB, API & Web level | 8.00 | 8.00 | Completed | Yet To Update | work on Cube New Stage Changes - DB, API & Web level Done
88 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Material Testing Change Request | New Stage Changes - Mobile App, DB, API & Web level | 08/09/2026 | 09/09/2026 | work on Material New Stage Changes - DB, API & Web level | 8.00 | 8.00 | Completed | Yet To Update | work on Material New Stage Changes - DB, API & Web level
89 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Adhoc | 2 Factor Authentication Implementation | 10/09/2026 | 10/09/2026 | work on 2 Factor Authentication Implementation For Contractor | 8.00 | 8.00 | Completed | Yet To Update | work on 2 Factor Authentication Implementation For Contractor
90 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS Water Supply Monitoring | Database functionality to add specific fields into the required tables | 11/09/2026 | 11/09/2026 | Work on Database functionality to add specific fields into the required tables And Report Create | 8.00 | 8.00 | Completed | Yet To Update | Work on Database functionality to add specific fields into the required tables And Report Create
91 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Web Development, API & Database Functions | 15/09/2026 | 15/09/2026 | work on SVS - Anusharavan GP - create API for mobile app development and Web | 16.00 | 8.00 | WIP | Yet To Update | work on SVS - Anusharavan GP - create API for mobile app development
92 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Web Development, API & Database Functions | 15/09/2026 | 16/09/2026 | work on SVS - Anusharavan GP - create API for mobile app development and Web | 16.00 | 8.00 | Completed | Yet To Update | work on SVS - Anusharavan GP - create API for mobile app development and Web
93 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Web Development, API & Database Functions | 17/09/2026 | 17/09/2026 | SVS-Anushravan-Module-Work-On-Anushravan Reports | 8.00 | 8.00 | Completed | Yet To Update | SVS-Anushravan-Module-Work-On-Anushravan Reports
94 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 18/09/2026 | 18/09/2026 | Work on Dhara module -CR-update-sequence-name-of-columns | 8.00 | 8.00 | Completed | Yet To Update | Work on Dhara module -CR-update-sequence-name-of-columns
95 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Web Development, API & Database Functions | 21/09/2026 | 21/09/2026 | Work on SVS-Anushravan-Module-Work-On-Anushravan- URM | 16.00 | 8.00 | WIP | Yet To Update | Work on SVS-Anushravan-Module-Work-On-Anushravan- URM
96 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Web Development, API & Database Functions | 21/09/2026 | 22/09/2026 | Work on SVS-Anushravan-Module-Work-On-Anushravan- URM | 16.00 | 8.00 | Completed | Yet To Update | Work on SVS-Anushravan-Module-Work-On-Anushravan-URM
97 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Web Development, API & Database Functions | 23/09/2026 | 23/09/2026 | work on SVS-Anushravan Module Web Development, API & Database Functions | 16.00 | 8.00 | WIP | Yet To Update | work on SVS-Anushravan Module Web Development, API & Database Functions
98 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | SVS - Anusharavan GP | Web Development, API & Database Functions | 23/09/2026 | 24/09/2026 | work on SVS-Anushravan Module Web Development, API & Database Functions | 16.00 | 8.00 | Completed | Yet To Update | work on SVS-Anushravan Module Web Development, API & Database Functions
99 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Anusharavan | NEW Stage changes | 01/09/2026 | 01/09/2026 | Anusharavan - Bug fixing. | 4.00 | 4.00 | Completed | Yet To Update | Anusharavan - Bug fixing.
100 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Cube Testing CR | New Stage Changes - Mobile App, DB, API & Web level | 07/09/2026 | 07/09/2026 | Cube Testing Change Request-New Stage Changes - Mobile App. | 8.00 | 8.00 | Completed | Yet To Update | Cube Testing Change Request-New Stage Changes - Mobile App.
101 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Material Testing Change Request | New Stage Changes - Mobile App, DB, API & Web level | 08/09/2026 | 08/09/2026 | Material Testing Change Request-New Stage Changes - Mobile App. | 8.00 | 8.00 | Completed | Yet To Update | Material Testing Change Request-New Stage Changes - Mobile App.
102 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Cube Testing CR | New Stage Changes - Mobile App, DB, API & Web level | 09/09/2026 | 09/09/2026 | Cube Testing Change Request- Internal testing uat. | 4.00 | 4.00 | Completed | Yet To Update | Cube Testing Change Request- Internal testing uat.
103 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Material Testing Change Request | New Stage Changes - Mobile App, DB, API & Web level | 09/09/2026 | 09/09/2026 | Material Testing Change Request- Internal testing uat. | 4.00 | 4.00 | Completed | Yet To Update | Material Testing Change Request- Internal testing uat.
104 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Material Testing Change Request | New Stage Changes - Mobile App, DB, API & Web level | 23/09/2026 | 23/09/2026 | Material Testing Change Request- Bug fixing and ui enhancement. | 8.00 | 8.00 | Completed | Yet To Update | Material Testing Change Request- Bug fixing and ui enhancement.
105 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Department Meetings | Department meeting on All modules requirements and changes | 01/09/2026 | 02/09/2026 | Meeting with MD | 8.00 | 8.00 | Completed | Yet To Update | and discussed with internal team
106 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/20 | 01/09/2026 ¦ 30/09/2026 | Department Meetings | Department meeting on All modules requirements and changes | 07/09/2026 | 09/09/2026 | Department meeting with MD Sir & Internal Team meeting | 8.00 | 8.00 | Completed | Yet To Update | Completed meeting and updated team for the work , changes and enhancement and their issue to be resolved