## Version History
Date | Version | Description | Prepared by | Reviewed & approved by
2025-01-03 | 1 | Size base Estimation Model First baseline | SEPG Team | SEPG Head
2026-06-01 | 1.4 | Cycle 4 (Jan-May 2026) Size based Estimation - All modules updated | SEPG Team | SEPG Head
2026-06-17 | 2.0 | Cycle 4 Estimation corrected – All module Size and Effort values updated per CMMI L5 size-based estimation guidelines. Productivity=0.18 pt/hr; VAF=1.01; Risk=5%; PM=10%. Sizes: ANS=26, AST=9, BHR=23, CUBE=69, DHR=89, FHTC=53, MST=38, MAT=51, NRM=22, O&M=96, SAH=10, SVS=11. All hardcoded Size/TotalCount cells converted to Excel formulas. Complexity distributions recalibrated per Guidelines sheet. | SEPG Team | SEPG Head
2026-10-19 | 3.0 | Cycle 5 (Jun-Sep 2026) Size based Estimation - all modules. Productivity=0.19 pt/hr (1 point = ~5.26 hrs, revised from 0.179); VAF=1.01; Risk=5%; PM=10%. Sources: Jun-Sep MoMs, PSRs, Sprint 17-20 user stories, timesheet. Total size=475. Sizes: O&M=136, SAH=30, DHR=46, MST=22, FHTC=15, CUBE=9, MAT=10, NRM=16, SVS=20, SVS-GP=27, ANS=6, AST=7, BHR=5, AI=15, CMMI=15, ESIGN=21, BISAC/BISAG=21, OTH=54. | SEPG Team | SEPG Head

## Master
Estimation Elements
New Development | Enhancement and customization
Web Page / Screen with no of input fields | Web Page / Screen with no of input fields
Type of exit scenario | Type of exit scenario
No of Validation on the fields | No of Validation on the fields
No of Prefilled fields | No of Prefilled fields
No of API Integrations | No of API Integrations
No API integrations for saving the data | No API integrations for saving the data
Queries or Business rules for the application | Queries or Business rules for the application
No of Integration | No of Integration
mobile App-UI | mobile App-UI
Data Migration | Data Migration
Reports | Reports
Complexity | Type of work | VAF Rating
Low | New Development | 5 | 5 - Very Strong Influence
Medium | Enhancement and customization | 4 | 4 - Strong Influence
High |  | 3 | 3 - Average Influence
Complex |  | 2 | 2 - Moderate Influence
|  | 1 | 1- Slight Influence
|  | 0 | 0 - No Influence
Effort Distribution Guidelines
| Effort Distribution | Cost
|  | Min | Max
Business Analyst | 15% | 4000 | 6000
Solution Architecht | 10% | 6000 | 8000
Developer / Data Scientist | 40% | 3000 | 5000
Tester | 20% | 2500 | 5000
Project Manager | 10% | 8000 | 10000
Infrastructure Setup | 5% | 3000 | 5000
Business Analyst | 15%
Solution Architecht | 10%
Developer / Data Scientist | 40%
Tester | 20%
Project Manager | 10%
Infrastructure Setup | 5%

## Baseline Productivity
Type of work | Calculated Productivity | Targated Productivity | Unit
Development & Enhancement |  | 0.19 | Point / per hour
|  | 1 Point | 5.2632
~5.26 hours
Revision note (Cycle 5, Jun-Sep 2026)
Targeted productivity increased from 0.179 to 0.19 pt/hr: 1 story point = ~5.26 hours (was ~5.6 hours). All module sheets read the value in C4.
Complexity weights unchanged (Low = 1, Medium = 3, High = 5). VAF ratings, 5% risk contingency and 10% project management carried forward from Cycle 4 V2.0.

## Guidelines
| Complexity | 1 | 3 | 5
Work Type | Component | Low | Medium | High
Development | Web Page / Screen with no of input fields | 10 | 10-15 | > 15 | Elements Label Graph Tile Grid Pop-up Drop Down Data Entery Field Button Custom Built element |  |  | 1
| Type of exit scenario | 1 | 1 to 2 | >3 |  | label | text box
| No of Validation on the fields | 1 to 5 | 5 To 10 | >10 |  | button
| No of Prefilled fields | 10 to 30 | 30 to 50 | >50 |  | drop down
| No of API Integrations | 2 | 2 to 5 | > 5 |  | checkbox
| No API integrations for saving the data | 3 | 3 to 5 | >5 |  | aadhar
| Queries or Business rules for the application | No validation or business rules. One data store | No validation or business rules. Up to 3 data stores | Validation or business rules involved. Multiple data stores |  | samagra integration
| No of Integration | 2 | 2 to 5 | >5 |  | report
| mobile App-UI | Static screen | Screen with 2-4 internal components | Screen with external components |  | MObile app
| Data Migration | Master Table | Table with data errors and involves Data validation and cleansing | Table with relationship with data errors and requires data validation and cleansing |  | submit
| Reports | tabular report. <10 columns. 1 data source Elements( Table, PIE chart, Report count: 1-2 | 2-3 data source. Simple (Pie/Bar) chart Elements( Stack,Line etc.) Report type: 3-5 | >3 data source. Multiple complex graphs Elements( Doughnut, Trend analysis etc.) Report type: More than 5 |  | clear
reset
Code element Data Tranformation Data Pre-processing Custom Build element API creation for UI\UX API Integration

## Summary
Jal Rekha - Cycle 5 (Jun-Sep 2026) Size Based Estimation Summary
All figures link to the module estimation sheets. Productivity is read from Baseline Productivity!C4.
Estimation Sheet | Stories | Low | Medium | High | Size (Points) | Productivity (pt/hr) | Effort (Man hours) | VAF | Total Planned Effort (Man hours) | Range Low (-5%) | Range High (+5%) | Check vs Story Mapping
O&M Estimation | 46 | 11 | 25 | 10 | 136 | 0.19 | 715.7895 | 1.01 | 831.3895 | 789.82 | 872.9589 | OK
Sahbhagita Estimation | 12 | 4 | 7 | 1 | 30 | 0.19 | 157.8947 | 1.01 | 183.3947 | 174.225 | 192.5645 | OK
Dhara Estimation | 14 | 1 | 10 | 3 | 46 | 0.19 | 242.1053 | 1.01 | 281.2053 | 267.145 | 295.2655 | OK
Master Estimation | 10 | 4 | 6 | 0 | 22 | 0.19 | 115.7895 | 1.01 | 134.4895 | 127.765 | 141.2139 | OK
FHTC Estimation | 7 | 4 | 2 | 1 | 15 | 0.19 | 78.9474 | 1.01 | 91.6974 | 87.1125 | 96.2822 | OK
Cube Testing Estimation | 7 | 6 | 1 | 0 | 9 | 0.19 | 47.3684 | 1.01 | 55.0184 | 52.2675 | 57.7693 | OK
Material Testing Estimation | 4 | 2 | 1 | 1 | 10 | 0.19 | 52.6316 | 1.01 | 61.1316 | 58.075 | 64.1882 | OK
Nirmal Estimation | 6 | 2 | 3 | 1 | 16 | 0.19 | 84.2105 | 1.01 | 97.8105 | 92.92 | 102.7011 | OK
SVS Estimation | 8 | 4 | 2 | 2 | 20 | 0.19 | 105.2632 | 1.01 | 122.2632 | 116.15 | 128.3763 | OK
SVS Anusharavan GP Estimation | 7 | 0 | 4 | 3 | 27 | 0.19 | 142.1053 | 1.01 | 165.0553 | 156.8025 | 173.308 | OK
Anusharavan Estimation | 4 | 3 | 1 | 0 | 6 | 0.19 | 31.5789 | 1.01 | 36.6789 | 34.845 | 38.5129 | OK
Asset Mapping Estimation | 3 | 1 | 2 | 0 | 7 | 0.19 | 36.8421 | 1.01 | 42.7921 | 40.6525 | 44.9317 | OK
Bharosa CR Estimation | 3 | 2 | 1 | 0 | 5 | 0.19 | 26.3158 | 1.01 | 30.5658 | 29.0375 | 32.0941 | OK
AI Module Estimation | 3 | 0 | 0 | 3 | 15 | 0.19 | 78.9474 | 1.01 | 91.6974 | 87.1125 | 96.2822 | OK
CMMI Doc Estimation | 3 | 0 | 0 | 3 | 15 | 0.19 | 78.9474 | 1.01 | 91.6974 | 87.1125 | 96.2822 | OK
e-Sign CDAC Estimation | 5 | 0 | 2 | 3 | 21 | 0.19 | 110.5263 | 1.01 | 128.3763 | 121.9575 | 134.7951 | OK
BISAC-BISAG Estimation | 5 | 0 | 2 | 3 | 21 | 0.19 | 110.5263 | 1.01 | 128.3763 | 121.9575 | 134.7951 | OK
Other Modules Estimation | 16 | 2 | 9 | 5 | 54 | 0.19 | 284.2105 | 1.01 | 330.1105 | 313.605 | 346.6161 | OK
TOTAL - CYCLE 5 (JUN-SEP 2026) | 163 | 46 | 78 | 39 | 475 | 0.19 | 2500 |  | 2903.75 | 2758.5625 | 3048.9375 | OK
Reference - hours actually logged (Date-Wise Time Sheet, Jun-Sep 2026)
Jun 2026 (Sprint 17) | 889
Jul 2026 (Sprint 18) | 1133
Aug 2026 (Sprint 19) | 690
Sep 2026 (Sprint 20) | 730
Total hours logged (all activity incl. meetings, adhoc, CMMI) | 3442
Planned effort / hours logged | 84.36%
Source: Date_Wise_Time_Sheet (Jun-Sep 2026), hours by entry month. Blue = hardcoded input from the timesheet. The September PSR reports 706.0 hrs against 730.0 hrs in the timesheet file; August matches the PSR (690.0).

## O&M Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | O&M Billing Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
O&M Billing - Abstract, Bill PDF & Review | Abstract report, contractor-mistake correction, all-records view, merged bill PDF, landscape fix (Jun-Jul) | US-OM-C5-001 - O&M Billing – Abstract Report Generation [H] US-OM-C5-002 - O&M Billing – Contractor Mistake Correction by SQC/TL → GM [M] US-OM-C5-003 - O&M Billing – Show All Records on All IDs (GM, SQC) [M] US-OM-C5-004 - O&M Billing – Merge PDF of All O&M Bill Documents [M] US-OM-C5-011 - O&M Billing – GM (PIU) Login: Bill PDF (19–20 Docs) & 3-Month Consolidation [M] US-OM-C5-012 - O&M Billing – Sahbhagita Generate Abstract: Select RA Bill & Tag All [M] US-OM-C5-013 - O&M Billing – Landscape Issue Fix in O&M Bill Layout [L] Status: 7 Done | 1 | 5 | 1 | 21
O&M Billing - Power, Construction Bill & Complaints | Power consumption, construction-phase bill columns/villages, pump transformer deduction, residual pressure & complaint redressal (Jun-Jul) | US-OM-C5-005 - O&M Billing – Power Consumption: Contractor & GM Side Changes [H] US-OM-C5-006 - O&M Billing – Two New Columns in Water Supply During Construction Bill [M] US-OM-C5-007 - O&M Billing – O&M Villages: Construction Approval Status [M] US-OM-C5-009 - O&M Billing – GM: Pump Transformer 10% Deduction Logic [M] US-OM-C5-015 - O&M Billing - Residual Pressure & Complaint Redressal Report Format [M] US-OM-C5-016 - O&M Billing - Complaint Redressal: 48-Hour Flag & Penalty Relaxation [L] Status: 4 In Progress, 2 Done | 1 | 4 | 1 | 18
O&M Billing - Dispute, LGD & GST | Contractor dispute window on Dhara data, LGD code integration, GST number (Jun-Jul; also covers Aug restatements AUG-15/16/17) | US-OM-C5-008 - O&M Billing – Aaklan Contractor Dispute: Dhara Data Discrepancy Window [M] US-OM-C5-014 - O&M Billing – LGD Code Integration: LG Directory → MPSQC [M] US-OM-C5-017 - O&M Billing - GST Number Integration [M] Status: 2 In Progress, 1 Open | 0 | 3 | 0 | 9
O&M Billing - WSDCP Phase 1 | New WSDCP tab: payment details, banked-units power sheet, monthly bill sheet, UFW report, pilot UAT (Aug) | US-AUG-01 - O&M Billing — WSDCP - New WSDCP tab and Bill Generation status tracking [H] US-AUG-02 - O&M Billing — WSDCP - WSDCP Payment Details tab [H] US-AUG-03 - O&M Billing — WSDCP - WSDCP Power Consumption Sheet — Banked Units logic [H] US-AUG-04 - O&M Billing — WSDCP - WSDCP Monthly Bill Sheet — Functional HSC and deductions [H] US-AUG-05 - O&M Billing — WSDCP - WSDCP UFW Report (no penalty) [L] US-AUG-06 - O&M Billing — WSDCP - WSDCP User Acceptance Testing on pilot scheme [M] Status: 5 In Progress, 1 Done | 1 | 1 | 4 | 24
O&M Billing - Multi-role Workflow | Forward/backward routing, GM/SQC edit rights with remark, SQC-unavailable fallback, higher-officials chain (Aug) | US-AUG-07 - O&M Billing — Workflow - Full multi-role forward/backward billing workflow [H] US-AUG-08 - O&M Billing — Workflow - GM/SQC edit rights on bill data with mandatory remark [H] US-AUG-09 - O&M Billing — Workflow - SQC-not-available fallback — GM confirms directly [M] US-AUG-10 - O&M Billing — Workflow - Higher Officials approval chain (GM O&M → MD) [H] Status: 4 In Progress | 0 | 1 | 3 | 18
O&M Billing - Data Integrity & Adjustments | Census denominator fix, pending-bills UI, net payable add/deduct, complaint category coding, Aakalan add/deduct (Aug) | US-AUG-11 - O&M Billing — Data Integrity - Census Population / village denominator fix [M] US-AUG-12 - O&M Billing — UI/Workflow - 'Pending Bills for Review' rename and scheme filter [L] US-AUG-13 - O&M Billing — Net Payable - Net Payable Bill — Add More Deduction / Any Other Addition [M] US-AUG-14 - O&M Billing — Complaint Handling - Complaint category coding and extended deductions [M] US-AUG-18 - O&M Billing — Aakalan - Aakalan Addition/Deduction feature (TL SQC / GM PIU) [M] Status: 4 In Progress, 1 Done | 1 | 4 | 0 | 13
O&M Billing / Aaklan - Controls & Tracking | Withheld add/deduct, edit lock, TRP gate, phase tabs, audit trail, role-scoped visibility, validations, user management, complaint carry-forward (Sep) | US-SEP-02 - O&M Billing / Aaklan - Withheld Addition/Deduction amounts shown at End-of-Month [M] US-SEP-03 - O&M Billing / Aaklan - Fix: bill remains editable after Contractor submission [L] US-SEP-04 - O&M Billing / Aaklan - TRP gate controlling O&M Phase availability [L] US-SEP-05 - O&M Billing / Aaklan - Scheme-based SQC/TL list cleanup [L] US-SEP-06 - O&M Billing / Aaklan - WSDCP / TRP / O&M Phase tabs with staged Abstract pages [M] US-SEP-07 - O&M Billing / Aaklan - Full audit trail on Contractor Bill edits [M] US-SEP-08 - O&M Billing / Aaklan - PMC / Deputy O&M role-scoped scheme visibility [M] US-SEP-09 - O&M Billing / Aaklan - Gross Payable Bill — minimum value validation [L] US-SEP-10 - O&M Billing / Aaklan - Census Population verification before Generate Bill [L] US-SEP-11 - O&M Billing / Aaklan - User Management — PIU-wise ID search with Tenure and Agency columns [M] US-SEP-12 - O&M Billing / Aaklan - TL ID conflict resolution (Bhopal / Sehore) [L] US-SEP-13 - O&M Billing / Aaklan - Save-as-Draft confirmation popup on Bulk bill actions [L] US-SEP-14 - O&M Billing — Complaint Redressal - Carry-forward of unresolved complaints with 48-hour flag [M] Status: 6 In Progress, 2 Done, 5 Open | 7 | 6 | 0 | 25
O&M Billing - Contractor/GM UI | Bill Tracking page overhaul, Abstract Bill UI, responsive layout, GM Abstract PDF UI fixes (Sep, PSR/timesheet-sourced) | PSR-SEP-02 - O&M Billing Contractor - Bill Tracking page UI overhaul, Abstract Bill UI, responsive layout [H] PSR-SEP-03 - O&M Billing GM - Abstract Report PDF UI fixes [M] Status: 1 In Progress, 1 Done | 0 | 1 | 1 | 8
TOTAL O&M ESTIMATION (CYCLE 5) | [5 empty] | 136
Value added factors
| Total Count |  |  |  |  | 136 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 136 | Point
| Effort | 715.7895 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 831.3895 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 872.9589 | 789.82 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Sahbhagita Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Sahbhagita Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Sahbhagita - RA Bill, Abstract & Reports | RA Bill for ISA, village-wise/combined report, master activity list, RA(1)-RA(12) withhold bills, customised ISA report (Jun) | US-SAH-C5-001 - Sahbhagita – RA Bill for ISA (replacing CP Manager) [M] US-SAH-C5-002 - Sahbhagita – Village-wise & Combined Activity Report [M] US-SAH-C5-003 - Sahbhagita – Master Activity List Update (22 Combined + 32 Village-wise) [M] US-SAH-C5-006 - Sahbhagita – RA Bill: RA(1) till RA(12) Withhold Bills [M] US-SAH-C5-007 - Sahbhagita – Customised Report (ISA – Mainly Contractor Convention) [M] Status: 5 Done | 0 | 5 | 0 | 15
Sahbhagita - UI, Access & Mobile | Hyperlinked document preview, mobile save-as-draft, pagination, FE-to-ISA scoping, ISA password reset (Jun) | US-SAH-C5-005 - Sahbhagita – Hyperlink: Village Name → Village Activity → Document Preview [M] US-SAH-C5-008 - Sahbhagita – Save as Draft for Video, Image & Document (Mobile CR) [M] US-SAH-C5-009 - Sahbhagita - Pagination on Approval Pages [L] US-SAH-C5-010 - Sahbhagita - FE Visibility Scoped to Assigned ISA [L] US-SAH-C5-011 - Sahbhagita - Self-Service Password Reset for ISA Login [L] Status: 5 Done | 3 | 2 | 0 | 9
Sahbhagita - AI Photo Scan | AI face/background detection on activity photos for CP Manager (Jul) | US-SAH-C5-004 - Sahbhagita – Photo Scan AI: Face & Background Detection (CP Manager Review) [H] Status: 1 In Progress | 0 | 0 | 1 | 5
Sahbhagita - Abstract of RA Bill Release | UAT defects DEF-01 to DEF-04, PIU/scheme binding, production release (Aug) | US-AUG-26 - Sahbhagita - Sahbhagita Abstract of RA Bill — production release [L] Status: 1 In Progress | 1 | 0 | 0 | 1
TOTAL SAHBHAGITA ESTIMATION (CYCLE 5) | [5 empty] | 30
Value added factors
| Total Count |  |  |  |  | 30 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 30 | Point
| Effort | 157.8947 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 183.3947 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 192.5645 | 174.225 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Dhara Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Dhara Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Dhara - Reports & Approved Data | Report corrections, 27-May format, contractor dispute window, new reports on all logins, base-capacity columns, approved-data correction (Jun-Jul) | US-DHR-C5-001 - Dhara – Report Corrections (Approved Village MWSR, DWSR, OHT) [M] US-DHR-C5-002 - Dhara – Report Format Standardisation (27 May 2026 Format) [M] US-DHR-C5-003 - Dhara – Approved Reports & Contractor Dispute Window [M] US-DHR-C5-004 - Dhara – New Dhara Reports Visible on All Jal Rekha Logins [M] US-DHR-C5-006 - Dhara – OHT/WTP/Intake Base Capacity Column in Report [M] US-DHR-C5-007 - Dhara - Approved Report Data Correction (Agreed with Kapil Sir) [M] Status: 4 Done, 2 In Progress | 0 | 6 | 0 | 18
Dhara - Entry Lock & Optional Fields | Approved entry lock; non-mandatory remark/photo/forward/backward (Jun) | US-DHR-C5-005 - Dhara – Dhara Entry Lock (Approved Data Should Not Change) [M] US-DHR-C5-008 - Dhara - Non-Mandatory Remark, Photo Upload, Forward & Backward Options [L] Status: 2 Done | 1 | 1 | 0 | 4
Dhara - Meter Logic & Sequential Approval | FE/Dhara meter functional logic, sequential month-wise approval lock (Aug-Sep) | US-AUG-22 - SVS / Dhara Meter Logic - FE/Dhara Meter Functional logic and sequential approval [M] US-SEP-15 - Dhara - Dhara sequential reading approval lock [M] Status: 2 In Progress | 0 | 2 | 0 | 6
Dhara - Edit Rules, Survey Report & MPEB API | Reading edit rules by meter status, survey report column restructuring, MPEB smart-meter API (Sep) | US-SEP-16 - Dhara - Dhara reading edit rules by meter status (GM / SQC-TL login) [H] US-SEP-17 - Dhara - Dhara Survey Report column restructuring [M] US-SEP-18 - Dhara - Dhara Electricity Meter Bill — MPEB Smart Meter API integration [H] Status: 3 Open | 0 | 1 | 2 | 13
Dhara & Nirmal - Panchayat Monitoring | Panchayat-level dashboards for Dhara and Nirmal; 5-step MVS-to-local-body handover (Aug) | US-AUG-34 - Dhara & Nirmal Panchayat Monitoring - Panchayat-level dashboard and MVS-to-local-body handover [H] Status: 1 In Progress | 0 | 0 | 1 | 5
TOTAL DHARA ESTIMATION (CYCLE 5) | [5 empty] | 46
Value added factors
| Total Count |  |  |  |  | 46 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 46 | Point
| Effort | 242.1053 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 281.2053 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 295.2655 | 267.145 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Master Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Master / Vistrit Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Vistrit - Mapping, OTP & Validation | WTP meter mapping columns, OTP on GM edit/delete, field validation, OHT deactivate fix, meter naming, duplicate-village validation (Jun) | US-VST-C5-001 - Vistrit – WTP Meter Mapping: New Columns (Date, Scheme, PIU, Meter Name) [M] US-VST-C5-002 - Vistrit – OTP Verification for GM Edit/Delete on Scheme, OHT, Bulk Master [M] US-VST-C5-003 - Vistrit – Scheme Village Mapping: Testing/Permitted Field Validation & Census Population [L] US-VST-C5-004 - Vistrit – OHT Deactivate Bug Fix (OHT Not Visible in FE Login) [M] US-VST-C5-005 - Vistrit – WTP Meter Naming Convention Standardisation [L] US-VST-OTP-C5-002 - Vistrit – Scheme Village Mapping: Duplicate Village Validation [L] Status: 6 Done | 3 | 3 | 0 | 12
Master - Lock & Data Integrity | Lock Scheme/Village/OHT master on live link (CR MSTR-JUN-2026-006), Dhara mapped summary search fix, village deletion restriction (Jun-Jul) | US-MSTR-C5-001 - Master - Lock Scheme/Village/OHT Master Once Linked to Live Transactions [M] US-MSTR-C5-002 - Master - Dhara Mapped Summary Report Search Debugging & Enhancement [M] US-MSTR-C5-003 - Master - Village Deletion Restriction & Database Validation Message [L] Status: 1 Open, 2 Done | 1 | 2 | 0 | 7
Vistrit - Survey Intake/WTP/OHT Master | Three new master sub-modules with Add/Update action (Sep) | US-SEP-25 - Vistrit (Master) - Survey Intake, WTP and OHT Master sub-modules [M] Status: 1 In Progress | 0 | 1 | 0 | 3
TOTAL MASTER ESTIMATION (CYCLE 5) | [5 empty] | 22
Value added factors
| Total Count |  |  |  |  | 22 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 22 | Point
| Effort | 115.7895 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 134.4895 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 141.2139 | 127.765 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## FHTC Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | FHTC / Parinam Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
FHTC Parinam - Nasamajh, Samagra & Surveys | Nasamajh family head ID, Samagra API integration, multiple surveys per Samagra ID (Jun-Jul) | US-FHTC-C5-001 - FHTC Parinam – Nasamajh Family Head ID & Add Connection [M] US-FHTC-C5-004 - FHTC Parinam – Samagra API Integration for Household Data [H] US-FHTC-C5-005 - FHTC Parinam - Multiple Surveys per Samagra ID [M] Status: 2 In Progress, 1 Done | 0 | 2 | 1 | 11
FHTC Parinam - Reports & Search | FE name in reports, contractor search option (Jun) | US-FHTC-C5-002 - FHTC Parinam – FE Name Shown in Reports [L] US-FHTC-C5-003 - FHTC Parinam – Contractor Search Option [L] Status: 2 Done | 2 | 0 | 0 | 2
FHTC Parinam - Dashboard | Parinam Dashboard tab on HSC Survey screen; FE dashboard and FE-login reports in mobile APK (Aug-Sep) | US-AUG-27 - FHTC / Parinam - Parinam Dashboard tab on HSC Survey screen [L] US-SEP-26 - Parinam - FE dashboard, FE-login reports, and multi-survey support confirmed stable [L] Status: 2 Done | 2 | 0 | 0 | 2
TOTAL FHTC ESTIMATION (CYCLE 5) | [5 empty] | 15
Value added factors
| Total Count |  |  |  |  | 15 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 15 | Point
| Effort | 78.9474 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 91.6974 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 96.2822 | 87.1125 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Cube Testing Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Cube Testing Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Cube Testing - Contractor Visibility & ID | Rejected data to contractor, Cube ID before image upload, Filter Bed sub-component (Jun) | US-CUBE-C5-001 - Cube Testing – Show Rejected Data to Contractor [L] US-CUBE-C5-002 - Cube Testing – Cube ID Generated Before Image Upload [L] US-CUBE-C5-003 - Cube Testing – Filter Bed Sub-Component Under WTP [L] Status: 3 Done | 3 | 0 | 0 | 3
Cube Testing - Re-Inspection Loop | 2nd-loop re-inspection after GM rejection; optional image on 2nd RFI loop (Jul) | US-CUBE-C5-004 - Cube Testing - Re-Inspection Loop (2nd Loop after GM Rejection) [M] US-CUBE-C5-005 - Cube Testing - Optional Image Upload on Second RFI Loop [L] Status: 2 Done | 1 | 1 | 0 | 4
Cube Testing - Re-Inspection Status | Cube RFI Id display; colour flag and separate re-inspection status (Sep) | US-SEP-20 - Cube Testing - Cube RFI Id display [L] US-SEP-21 - Cube Testing - Cube Reinspection — colour flag and separate status [L] Status: 1 Open, 1 In Progress | 2 | 0 | 0 | 2
TOTAL CUBE TESTING ESTIMATION (CYCLE 5) | [5 empty] | 9
Value added factors
| Total Count |  |  |  |  | 9 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 9 | Point
| Effort | 47.3684 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 55.0184 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 57.7693 | 52.2675 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Material Testing Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Material Testing - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Material Testing - Re-Inspection Loop | 2nd-loop re-inspection and optional image on 2nd RFI loop (Jul-Aug; the AUG-25 production deployment is covered by these stories) | US-MAT-C5-001 - Material Testing - Re-Inspection Loop (2nd Loop after GM Rejection) [M] US-MAT-C5-002 - Material Testing - Optional Image Upload on Second RFI Loop [L] Status: 1 In Progress, 1 Open | 1 | 1 | 0 | 4
Material Testing - GM/Contractor DB & API | Database functions and API enhancements for re-inspection (Jul) | US-MAT-C5-003 - Material Testing - GM/Contractor Login Database & API Enhancements [H] Status: 1 In Progress | 0 | 0 | 1 | 5
Material Testing - Re-Inspection Id Flag | Separate flag status for Material Reinspection Id (Sep) | US-SEP-22 - Material Testing - Material Reinspection Id — separate flag status [L] Status: 1 In Progress | 1 | 0 | 0 | 1
TOTAL MATERIAL TESTING ESTIMATION (CYCLE 5) | [5 empty] | 10
Value added factors
| Total Count |  |  |  |  | 10 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 10 | Point
| Effort | 52.6316 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 61.1316 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 64.1882 | 58.075 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Nirmal Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Nirmal Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Nirmal - Reports & Bug Fixes | Beneficiary report fix, contractor counting bug, FE mobile reports, test scenarios/cases (Jun) | US-NRM-C5-001 - Nirmal - Beneficiary Report Issue Fix [M] US-NRM-C5-002 - Nirmal - Contractor Login Report Counting Bug Fix [L] US-NRM-C5-003 - Nirmal - FE Mobile Reports Validation & Bug Fixes [M] US-NRM-C5-004 - Nirmal - Test Scenario and Test Case Creation [L] Status: 4 Done | 2 | 2 | 0 | 8
Nirmal / SVS PHE - Water Testing | SVS PHE status labelling and approval lock; water-testing entry form with pass/fail logic (Aug) | US-AUG-23 - Nirmal / SVS PHE - Nirmal/SVS PHE integration logic and status labelling [M] US-AUG-24 - Nirmal / SVS PHE - Nirmal/SVS PHE water-testing entry form [H] Status: 2 In Progress | 0 | 1 | 1 | 8
TOTAL NIRMAL ESTIMATION (CYCLE 5) | [5 empty] | 16
Value added factors
| Total Count |  |  |  |  | 16 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 16 | Point
| Effort | 84.2105 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 97.8105 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 102.7011 | 92.92 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## SVS Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | SVS Water Supply Monitoring - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
SVS - Daily Water Supply Entry | Bilingual conversion, login-scoped District/Block/GP, additional No-Supply reason, JJM ID removal (Jun) | US-SVS-C5-001 - SVS – Bilingual Conversion (Hindi/English) for Water Supply Entry Page [M] US-SVS-C5-002 - SVS – Login-Specific District, Block, GP Auto-Selection [L] US-SVS-C5-003 - SVS – Additional Reason for NO Supply & Spelling Correction [L] US-SVS-C5-004 - SVS – Remove JJM ID and Village Status Fields [L] Status: 4 Done | 3 | 1 | 0 | 6
SVS - Dashboard V2 & Drill-down | KPI cards with colour coding; Gram Sachiv and CEO/CO Block drill-down (Aug) | US-AUG-19 - SVS Water Supply Dashboard - SVS Water Supply Status Dashboard V2 — KPI cards and colour coding [H] US-AUG-20 - SVS Water Supply Dashboard - SVS dashboard drill-down — Gram Sachiv and CEO/CO Block [H] Status: 2 In Progress | 0 | 0 | 2 | 10
SVS / MVS - Master | SVS master wireframe and MVS Master for 600+ schemes (Aug) | US-AUG-21 - SVS / MVS Master - SVS master wireframe and MVS Master (600+ entries) [M] Status: 1 In Progress | 0 | 1 | 0 | 3
SVS Nirmal - FTK Kit | FTK kit report and SVS Nirmal wireframe (Sep) | US-SEP-28 - SVS Nirmal - FTK kit report and SVS Nirmal wireframe [L] Status: 1 Done | 1 | 0 | 0 | 1
TOTAL SVS ESTIMATION (CYCLE 5) | [5 empty] | 20
Value added factors
| Total Count |  |  |  |  | 20 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 20 | Point
| Effort | 105.2632 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 122.2632 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 128.3763 | 116.15 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## SVS Anusharavan GP Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | SVS Anusharavan GP Module - Cycle 5 (Aug-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
SVS Anusharavan GP - Master & Wireframe | GP Master, Anusharavan GP wireframe, user management; funds-source and work-type masters (Sep) | US-SEP-29 - SVS Anusharavan GP - GP Master and Anusharavan GP wireframe and user management [M] US-SEP-34 - GP Master Data - Gram Panchayat Funds-Source and Nirman Karya work-type masters [M] Status: 1 Done, 1 Open | 0 | 2 | 0 | 6
SVS Anusharavan GP - Mobile & RFI Workflow | Simplified RFI, GP mobile screen for FE, GP RFI raise and Sub-Engineer review (Aug-Sep) | US-AUG-35 - RFI / Anusharavan (SVS-GP) - Simplified RFI system and GP–FE review workflow [H] US-SEP-30 - SVS Anusharavan GP - GP Anusharavan Mobile Screen for FE [M] US-SEP-31 - Anusharavan SVS — RFI - Gram Panchayat RFI raise and Sub-Engineer review workflow [H] Status: 1 Not Started, 1 In Progress, 1 Open | 0 | 1 | 2 | 13
SVS Anusharavan GP - SIPRI Integration | SIPRI/NREGA/Yuktdhara integration; AE block-wise login and Panchayat ID whitelisting (Sep) | US-SEP-32 - Anusharavan SVS — SIPRI Integration - SIPRI / NREGA / Yuktdhara integration for GP works planning [H] US-SEP-33 - Anusharavan SVS — SIPRI Integration - SIPRI AE block-wise login and Panchayat ID whitelisting [M] Status: 2 Open | 0 | 1 | 1 | 8
TOTAL SVS ANUSHARAVAN GP ESTIMATION (CYCLE 5) | [5 empty] | 27
Value added factors
| Total Count |  |  |  |  | 27 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 27 | Point
| Effort | 142.1053 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 165.0553 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 173.308 | 156.8025 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Anusharavan Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Anusharavan Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Anusharavan - RFI Reports & Search | Multi-date in report, OHT search during RFI, optional GPS/village for Intake/WTP/MBR/RWPM (Jun) | US-ANS-C5-001 - Anusharavan – Multi-Date in Report: FE RFI Submission Date & Block Name [M] US-ANS-C5-002 - Anusharavan – OHT Search Option During RFI [L] US-ANS-C5-003 - Anusharavan – Remove Mandatory GPS/Village for Intake, WTP, MBR, RWPM, CWPM [L] Status: 3 Done | 2 | 1 | 0 | 5
Anusharavan - Survey Fix | Fix multiple survey submission by SQC/TL (Sep) | US-SEP-24 - Anusharavan - Fix: multiple survey submission by SQC/TL [L] Status: 1 In Progress | 1 | 0 | 0 | 1
TOTAL ANUSHARAVAN ESTIMATION (CYCLE 5) | [5 empty] | 6
Value added factors
| Total Count |  |  |  |  | 6 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 6 | Point
| Effort | 31.5789 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 36.6789 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 38.5129 | 34.845 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Asset Mapping Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Asset Mapping Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Asset Mapping - SQC/TPIA/Contractor | SQC/TPIA/Contractor asset data and report on web; API integration and frontend fixes (Jun) | US-AST-C5-001 - Asset Mapping - SQC/TPIA Contractor Data & Report on Web [M] US-AST-C5-002 - Asset Mapping - API Integration & Frontend Bug Fixes [M] Status: 2 Done | 0 | 2 | 0 | 6
Asset Mapping - Report Cleanup | OHT Id cleanup in reports (Sep) | US-SEP-19 - Dhara / Asset Mapping - Asset Mapping — OHT Id cleanup in reports [L] Status: 1 Open | 1 | 0 | 0 | 1
TOTAL ASSET MAPPING ESTIMATION (CYCLE 5) | [5 empty] | 7
Value added factors
| Total Count |  |  |  |  | 7 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 7 | Point
| Effort | 36.8421 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 42.7921 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 44.9317 | 40.6525 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Bharosa CR Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Bharosa CR Module - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Bharosa - Factory Testing | Item master duplicate dropdown fix (web); factory testing mobile bug fixes (Jul) | US-BHR-C5-001 - Bharosa - Item Master Duplicate Dropdown Entry Fix [L] US-BHR-C5-002 - Bharosa - Factory Testing Mobile Bug Fixes [M] Status: 2 Done | 1 | 1 | 0 | 4
Bharosa - Inspection Reassignment | Inspection reassignment and photo-upload fix (Sep) | US-SEP-23 - Bharosa - Bharosa inspection reassignment and photo-upload fix [L] Status: 1 In Progress | 1 | 0 | 0 | 1
TOTAL BHAROSA CR ESTIMATION (CYCLE 5) | [5 empty] | 5
Value added factors
| Total Count |  |  |  |  | 5 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 5 | Point
| Effort | 26.3158 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 30.5658 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 32.0941 | 29.0375 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## AI Module Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | AI Module FHTC - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
AI Module - FHTC Tap Connection | YOLO tap/person detection model, buffer-region validation, data processing and training pipeline (Jun) | US-AI-C5-001 - AI Module - Tap & Person Detection Predictive Model [H] US-AI-C5-002 - AI Module - Tap Connection Buffer Region Validation (LLM/Pretrained Model Integration) [H] US-AI-C5-003 - AI Module - FHTC Data Processing & Model Training Pipeline [H] Status: 3 Done | 0 | 0 | 3 | 15
TOTAL AI MODULE ESTIMATION (CYCLE 5) | [5 empty] | 15
Value added factors
| Total Count |  |  |  |  | 15 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 15 | Point
| Effort | 78.9474 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 91.6974 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 96.2822 | 87.1125 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## CMMI Doc Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | CMMI Documentation - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
CMMI Doc - Cycle 5 Data & Documentation | Cycle 5 data collection; documentation streamlined for Cycle 5 modules (Jun-Jul) | US-CMMI-C5-001 - CMMI Doc – Cycle 5 Data Collection (June 2026) [H] US-CMMI-C5-002 - CMMI Doc – Streamline Documentation for Cycle 5 Modules [H] Status: 2 In Progress | 0 | 0 | 2 | 10
CMMI Doc - Cycle 4 Closure | Cycle 4 BRTM, release note, code review, SVN, Minitab analysis (Aug) | US-AUG-29 - CMMI L5 - Cycle 4 BRTM and Release Note closure [H] Status: 1 In Progress | 0 | 0 | 1 | 5
TOTAL CMMI DOC ESTIMATION (CYCLE 5) | [5 empty] | 15
Value added factors
| Total Count |  |  |  |  | 15 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 15 | Point
| Effort | 78.9474 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 91.6974 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 96.2822 | 87.1125 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## e-Sign CDAC Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | e-Sign via CDAC (Aadhaar) - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
e-Sign CDAC - FE & Contractor | FE e-Sign on all logins; Contractor/Firm e-Sign for bill documents; O&M Contractor & GM e-Sign (Jun-Jul) | US-ESIGN-C5-001 - e-Sign CDAC – FE e-Sign via Mobile/Web (All Logins) [H] US-ESIGN-C5-002 - e-Sign CDAC – Contractor/Firm e-Sign for O&M Bill Documents [H] US-OM-C5-010 - O&M Billing Workflow – e-Sign via CDAC (Contractor & GM) [H] Status: 3 In Progress | 0 | 0 | 3 | 15
e-Sign CDAC - TL Recommendation | TL (PMC) recommendation letter via E-Office; TL (SQC)/TL (PMC) account office integration (Jul) | US-ESIGN-C5-003 - e-Sign CDAC – TL (PMC) Recommendation Letter (E-Office Generated) [M] US-ESIGN-C5-004 - e-Sign CDAC – TL (SQC) & TL (PMC) Account Office Jal Rekha Integration [M] Status: 2 In Progress | 0 | 2 | 0 | 6
TOTAL E-SIGN CDAC ESTIMATION (CYCLE 5) | [5 empty] | 21
Value added factors
| Total Count |  |  |  |  | 21 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 21 | Point
| Effort | 110.5263 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 128.3763 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 134.7951 | 121.9575 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## BISAC-BISAG Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | BISAC / BISAG Integration - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
BISAC - NIC Asset & Pipeline Mapping | NIC Asset ID mapping, pipeline mapping with BISAC junction data, village LGD code logic (Jun-Jul) | US-BISAC-C5-001 - BISAC – NIC Asset ID Mapping (Asset & Junction Mapping) [H] US-BISAC-C5-002 - BISAC – Pipeline Mapping with BISAC Junction Data [H] US-BISAC-C5-003 - BISAC – Village LGD Code Integration (Village without LGD = Habitation) [M] Status: 2 In Progress, 1 Done | 0 | 1 | 2 | 13
BISAG - Delhi Data Integration | Asset & pipeline APIs, Annexure-C, shapefile API; scheme mapping and progress-reporting fix (Aug) | US-AUG-31 - BISAG / Delhi Data Integration - Asset & Pipeline API and Annexure-C data sharing [H] US-AUG-32 - BISAG / Delhi Data Integration - Scheme mapping and progress-reporting fix [M] Status: 2 In Progress | 0 | 1 | 1 | 8
TOTAL BISAC-BISAG ESTIMATION (CYCLE 5) | [5 empty] | 21
Value added factors
| Total Count |  |  |  |  | 21 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 21 | Point
| Effort | 110.5263 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 128.3763 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 134.7951 | 121.9575 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Other Modules Estimation
| Type Of work | Development | New Development
| Project Name | Jal Rekha
| Remark | Other Modules (Daily Inspection, Sopan, QA, Mobile, Dashboard, Admin, Jal Samadhan, Security) - Cycle 5 (Jun-Sep 2026)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | Low Complexity | Medium compexity | High Complexity
|  |  | 1 | 3 | 5
Daily Inspection | Role-based report modifications; mobile app bug fixes (Jun) | US-DIN-C5-001 - Daily Inspection - Role-Based Report Modifications [M] US-DIN-C5-002 - Daily Inspection - Mobile App Bug Fixes [L] Status: 2 Done | 1 | 1 | 0 | 4
Sopan - Contractor Calendar | Calendar functionality for 2026-27 on Contractor login, web and mobile (Jul) | US-SOP-C5-001 - Sopan - Calendar Functionality for 2026-27 [M] Status: 1 Open | 0 | 1 | 0 | 3
QA / User & Role Management Automation | Selenium (TestNG) scripts, automation review process, script extended through Assign Work (Jun, Sep) | US-QA-C5-001 - QA Automation - Selenium Scripts for User Login & Registration [M] US-QA-C5-002 - QA Automation - Internal Review Process for Automation Testing [L] PSR-SEP-04 - User & Role Management - Selenium automation extended through Assign Work [M] Status: 3 Done | 1 | 2 | 0 | 7
Mobile App - Fixes & Stability | UI/functional bug fixes (Aug); Play Console crash/ANR fixes (Sep); Azure DevOps Android CI/CD pipeline (Jun) | US-AUG-28 - Mobile App - Mobile app UI/functional bug fixes [M] US-SEP-37 - Mobile App Stability - Crash and ANR fixes from Play Console vitals [H] PSR-JUN-01 - CI/CD - Azure DevOps Android pipeline implementation [M] Status: 2 Done, 1 Open | 0 | 2 | 1 | 11
Dashboard & Public Reports | Redesign of all module inner pages, public reports on dashboard (Jul); login and forgot-password page UI (Sep) | PSR-JUL-01 - Dashboard - redesign of all module and inner pages of Jal Rekha [M] PSR-JUL-02 - All public reports on dashboard - sanity testing, bug fixes, report preparation [H] PSR-SEP-01 - Dashboard - login page and forgot-password page UI fixes [M] Status: 3 Done | 0 | 2 | 1 | 11
Admin / ID Management | PIU district-wise restructuring and TL-ID/PIU-ID linking (Aug) | US-AUG-36 - Admin / ID Management - PIU district-wise restructuring and TL-ID/PIU-ID linking [H] Status: 1 Not Started | 0 | 0 | 1 | 5
Jal Samadhan | Complaint queries module with SLA escalation (Aug); CM Helpline 181 integration (Sep) | US-AUG-37 - Jal Samadhan - Complaint Queries module [M] US-SEP-35 - Jal Samadhan - CM Helpline (181) integration for Jal Samadhan [H] Status: 1 Not Started, 1 Open | 0 | 1 | 1 | 8
Security - Two-Factor Authentication | 2FA implementation for GM login IDs (Sep) | US-SEP-36 - Jal Rekha — Security (2FA) - Two-Factor Authentication — current scope confirmed [H] Status: 1 Done | 0 | 0 | 1 | 5
TOTAL OTHER MODULES ESTIMATION (CYCLE 5) | [5 empty] | 54
Value added factors
| Total Count |  |  |  |  | 54 |  |  | Factor | Rating
[9 empty] | Data Communications | 0
| Productivity | 0.19 | [6 empty] | Distributed Data Processing | 0
| Size | 54 | Point
| Effort | 284.2105 | Man hours | [5 empty] | Performance | 0
| VAF | 1.01 | [6 empty] | Heavily used Configuration | 3
| Risk contingency | 0.05 | [6 empty] | Transaction Rate | 4
| Project Management | 0.1
| Total Planned effort | 330.1105 | Man hours | [5 empty] | Online Data Entry | 3
[9 empty] | End-User Efficiency | 2
| Permissible Range(Man hours) | 346.6161 | 313.605 | [5 empty] | Online Update | 1
[9 empty] | Complex Processing | 3
[9 empty] | Reusability | 4
[9 empty] | Installation Ease | 4
[9 empty] | Operational Ease | 4
[9 empty] | Multiple Sites | 4
[9 empty] | Facilitate Change | 4
[9 empty] | Total | 36

## Story Mapping
Jal Rekha - Cycle 5 (Jun-Sep 2026) Estimation: Story-to-Size Mapping (audit trail)
Complexity rule: weights Low=1, Medium=3, High=5 (as per Master / Guidelines sheets).
Jun-Jul stories (Consolidated Register): source effort <=6 hrs = Low, 7-19 hrs = Medium, >=20 hrs = High.
Aug-Sep stories (Sprint 19/20 documents carry no hours): acceptance-criteria count <=3 Low, 4-5 Medium, >=6 High; +1 level for external-system integration, multi-role workflow, KPI dashboards or complex multi-store business rules; -1 level for pure fix/rename/display scope. Overrides are stated in the Basis column.
PSR/timesheet-only items (no user story): level from timesheet hours with the same hours rule.
Excluded: duplicates of already-sized scope, confirmation-only stories, Cycle 4 scope and non-development activity (reason shown). The 41 stories in the Cycle 5 / CR Backlog document (US-C5-xx, US-CR-xx) restate register scope per the register CR Cross-Reference and are not counted again.
Sr. | Story ID | Source | Module / Title | Status | Period | Counted | Estimation Sheet | Sub-module Row | ACs | Source Effort (hrs) | Complexity | Points | Basis / Reason
1 | US-OM-C5-001 | Consolidated Register (Jun-Jul 2026) | O&M Billing – Abstract Report Generation | Done | Jun 2026 | Yes | O&M Estimation | O&M Billing - Abstract, Bill PDF & Review | 6 | 20 | High | 5 | Source effort 20 hrs: <=6 Low, 7-19 Medium, >=20 High
2 | US-OM-C5-002 | Consolidated Register (Jun-Jul 2026) | O&M Billing – Contractor Mistake Correction by SQC/TL → GM | Done | Jun 2026 | Yes | O&M Estimation | O&M Billing - Abstract, Bill PDF & Review | 5 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
3 | US-OM-C5-003 | Consolidated Register (Jun-Jul 2026) | O&M Billing – Show All Records on All IDs (GM, SQC) | Done | Jun 2026 | Yes | O&M Estimation | O&M Billing - Abstract, Bill PDF & Review | 6 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
4 | US-OM-C5-004 | Consolidated Register (Jun-Jul 2026) | O&M Billing – Merge PDF of All O&M Bill Documents | Done | Jun 2026 | Yes | O&M Estimation | O&M Billing - Abstract, Bill PDF & Review | 5 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
5 | US-OM-C5-005 | Consolidated Register (Jun-Jul 2026) | O&M Billing – Power Consumption: Contractor & GM Side Changes | In Progress | Jun-Jul 2026 | Yes | O&M Estimation | O&M Billing - Power, Construction Bill & Complaints | 5 | 24 | High | 5 | Source effort 24 hrs: <=6 Low, 7-19 Medium, >=20 High
6 | US-OM-C5-006 | Consolidated Register (Jun-Jul 2026) | O&M Billing – Two New Columns in Water Supply During Construction Bill | In Progress | Jun 2026 | Yes | O&M Estimation | O&M Billing - Power, Construction Bill & Complaints | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
7 | US-OM-C5-007 | Consolidated Register (Jun-Jul 2026) | O&M Billing – O&M Villages: Construction Approval Status | In Progress | Jul 2026 | Yes | O&M Estimation | O&M Billing - Power, Construction Bill & Complaints | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
8 | US-OM-C5-008 | Consolidated Register (Jun-Jul 2026) | O&M Billing – Aaklan Contractor Dispute: Dhara Data Discrepancy Window | In Progress | Jul 2026 | Yes | O&M Estimation | O&M Billing - Dispute, LGD & GST | 5 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
9 | US-OM-C5-009 | Consolidated Register (Jun-Jul 2026) | O&M Billing – GM: Pump Transformer 10% Deduction Logic | In Progress | Jul 2026 | Yes | O&M Estimation | O&M Billing - Power, Construction Bill & Complaints | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
10 | US-OM-C5-010 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – e-Sign via CDAC (Contractor & GM) | In Progress | Jun-Jul 2026 | Yes | e-Sign CDAC Estimation | e-Sign CDAC - FE & Contractor | 6 | 40 | High | 5 | Source effort 40 hrs: <=6 Low, 7-19 Medium, >=20 High
11 | US-OM-C5-011 | Consolidated Register (Jun-Jul 2026) | O&M Billing – GM (PIU) Login: Bill PDF (19–20 Docs) & 3-Month Consolidation | Done | Jun 2026 | Yes | O&M Estimation | O&M Billing - Abstract, Bill PDF & Review | 5 | 12 | Medium | 3 | Source effort 12 hrs: <=6 Low, 7-19 Medium, >=20 High
12 | US-OM-C5-012 | Consolidated Register (Jun-Jul 2026) | O&M Billing – Sahbhagita Generate Abstract: Select RA Bill & Tag All | Done | Jun 2026 | Yes | O&M Estimation | O&M Billing - Abstract, Bill PDF & Review | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
13 | US-OM-C5-013 | Consolidated Register (Jun-Jul 2026) | O&M Billing – Landscape Issue Fix in O&M Bill Layout | Done | Jun 2026 | Yes | O&M Estimation | O&M Billing - Abstract, Bill PDF & Review | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
14 | US-OM-C5-014 | Consolidated Register (Jun-Jul 2026) | O&M Billing – LGD Code Integration: LG Directory → MPSQC | In Progress | Jul 2026 | Yes | O&M Estimation | O&M Billing - Dispute, LGD & GST | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
15 | US-OM-C5-015 | Consolidated Register (Jun-Jul 2026) | O&M Billing - Residual Pressure & Complaint Redressal Report Format | Done | Jun 2026 | Yes | O&M Estimation | O&M Billing - Power, Construction Bill & Complaints | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
16 | US-OM-C5-016 | Consolidated Register (Jun-Jul 2026) | O&M Billing - Complaint Redressal: 48-Hour Flag & Penalty Relaxation | Done | Jun 2026 | Yes | O&M Estimation | O&M Billing - Power, Construction Bill & Complaints | 5 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
17 | US-OM-C5-017 | Consolidated Register (Jun-Jul 2026) | O&M Billing - GST Number Integration | Open | Jul 2026 | Yes | O&M Estimation | O&M Billing - Dispute, LGD & GST | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
18 | US-SAH-C5-001 | Consolidated Register (Jun-Jul 2026) | Sahbhagita – RA Bill for ISA (replacing CP Manager) | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - RA Bill, Abstract & Reports | 5 | 12 | Medium | 3 | Source effort 12 hrs: <=6 Low, 7-19 Medium, >=20 High
19 | US-SAH-C5-002 | Consolidated Register (Jun-Jul 2026) | Sahbhagita – Village-wise & Combined Activity Report | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - RA Bill, Abstract & Reports | 5 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
20 | US-SAH-C5-003 | Consolidated Register (Jun-Jul 2026) | Sahbhagita – Master Activity List Update (22 Combined + 32 Village-wise) | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - RA Bill, Abstract & Reports | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
21 | US-SAH-C5-004 | Consolidated Register (Jun-Jul 2026) | Sahbhagita – Photo Scan AI: Face & Background Detection (CP Manager Review) | In Progress | Jul 2026 | Yes | Sahbhagita Estimation | Sahbhagita - AI Photo Scan | 5 | 20 | High | 5 | Source effort 20 hrs: <=6 Low, 7-19 Medium, >=20 High
22 | US-SAH-C5-005 | Consolidated Register (Jun-Jul 2026) | Sahbhagita – Hyperlink: Village Name → Village Activity → Document Preview | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - UI, Access & Mobile | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
23 | US-SAH-C5-006 | Consolidated Register (Jun-Jul 2026) | Sahbhagita – RA Bill: RA(1) till RA(12) Withhold Bills | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - RA Bill, Abstract & Reports | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
24 | US-SAH-C5-007 | Consolidated Register (Jun-Jul 2026) | Sahbhagita – Customised Report (ISA – Mainly Contractor Convention) | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - RA Bill, Abstract & Reports | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
25 | US-SAH-C5-008 | Consolidated Register (Jun-Jul 2026) | Sahbhagita – Save as Draft for Video, Image & Document (Mobile CR) | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - UI, Access & Mobile | 6 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
26 | US-SAH-C5-009 | Consolidated Register (Jun-Jul 2026) | Sahbhagita - Pagination on Approval Pages | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - UI, Access & Mobile | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
27 | US-SAH-C5-010 | Consolidated Register (Jun-Jul 2026) | Sahbhagita - FE Visibility Scoped to Assigned ISA | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - UI, Access & Mobile | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
28 | US-SAH-C5-011 | Consolidated Register (Jun-Jul 2026) | Sahbhagita - Self-Service Password Reset for ISA Login | Done | Jun 2026 | Yes | Sahbhagita Estimation | Sahbhagita - UI, Access & Mobile | 4 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
29 | US-DHR-C5-001 | Consolidated Register (Jun-Jul 2026) | Dhara – Report Corrections (Approved Village MWSR, DWSR, OHT) | Done | Jun 2026 | Yes | Dhara Estimation | Dhara - Reports & Approved Data | 6 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
30 | US-DHR-C5-002 | Consolidated Register (Jun-Jul 2026) | Dhara – Report Format Standardisation (27 May 2026 Format) | Done | Jun 2026 | Yes | Dhara Estimation | Dhara - Reports & Approved Data | 6 | 12 | Medium | 3 | Source effort 12 hrs: <=6 Low, 7-19 Medium, >=20 High
31 | US-DHR-C5-003 | Consolidated Register (Jun-Jul 2026) | Dhara – Approved Reports & Contractor Dispute Window | In Progress | Jun-Jul 2026 | Yes | Dhara Estimation | Dhara - Reports & Approved Data | 6 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
32 | US-DHR-C5-004 | Consolidated Register (Jun-Jul 2026) | Dhara – New Dhara Reports Visible on All Jal Rekha Logins | Done | Jun 2026 | Yes | Dhara Estimation | Dhara - Reports & Approved Data | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
33 | US-DHR-C5-005 | Consolidated Register (Jun-Jul 2026) | Dhara – Dhara Entry Lock (Approved Data Should Not Change) | Done | Jun 2026 | Yes | Dhara Estimation | Dhara - Entry Lock & Optional Fields | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
34 | US-DHR-C5-006 | Consolidated Register (Jun-Jul 2026) | Dhara – OHT/WTP/Intake Base Capacity Column in Report | In Progress | Jul 2026 | Yes | Dhara Estimation | Dhara - Reports & Approved Data | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
35 | US-DHR-C5-007 | Consolidated Register (Jun-Jul 2026) | Dhara - Approved Report Data Correction (Agreed with Kapil Sir) | Done | Jul 2026 | Yes | Dhara Estimation | Dhara - Reports & Approved Data | 4 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
36 | US-DHR-C5-008 | Consolidated Register (Jun-Jul 2026) | Dhara - Non-Mandatory Remark, Photo Upload, Forward & Backward Options | Done | Jun 2026 | Yes | Dhara Estimation | Dhara - Entry Lock & Optional Fields | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
37 | US-VST-C5-001 | Consolidated Register (Jun-Jul 2026) | Vistrit – WTP Meter Mapping: New Columns (Date, Scheme, PIU, Meter Name) | Done | Jun 2026 | Yes | Master Estimation | Vistrit - Mapping, OTP & Validation | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
38 | US-VST-C5-002 | Consolidated Register (Jun-Jul 2026) | Vistrit – OTP Verification for GM Edit/Delete on Scheme, OHT, Bulk Master | Done | Jun 2026 | Yes | Master Estimation | Vistrit - Mapping, OTP & Validation | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
39 | US-VST-C5-003 | Consolidated Register (Jun-Jul 2026) | Vistrit – Scheme Village Mapping: Testing/Permitted Field Validation & Census Population | Done | Jun 2026 | Yes | Master Estimation | Vistrit - Mapping, OTP & Validation | 5 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
40 | US-VST-C5-004 | Consolidated Register (Jun-Jul 2026) | Vistrit – OHT Deactivate Bug Fix (OHT Not Visible in FE Login) | Done | Jun 2026 | Yes | Master Estimation | Vistrit - Mapping, OTP & Validation | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
41 | US-VST-C5-005 | Consolidated Register (Jun-Jul 2026) | Vistrit – WTP Meter Naming Convention Standardisation | Done | Jun 2026 | Yes | Master Estimation | Vistrit - Mapping, OTP & Validation | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
42 | US-FHTC-C5-001 | Consolidated Register (Jun-Jul 2026) | FHTC Parinam – Nasamajh Family Head ID & Add Connection | In Progress | Jun 2026 | Yes | FHTC Estimation | FHTC Parinam - Nasamajh, Samagra & Surveys | 5 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
43 | US-FHTC-C5-002 | Consolidated Register (Jun-Jul 2026) | FHTC Parinam – FE Name Shown in Reports | Done | Jun 2026 | Yes | FHTC Estimation | FHTC Parinam - Reports & Search | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
44 | US-FHTC-C5-003 | Consolidated Register (Jun-Jul 2026) | FHTC Parinam – Contractor Search Option | Done | Jun 2026 | Yes | FHTC Estimation | FHTC Parinam - Reports & Search | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
45 | US-FHTC-C5-004 | Consolidated Register (Jun-Jul 2026) | FHTC Parinam – Samagra API Integration for Household Data | In Progress | Jun-Jul 2026 | Yes | FHTC Estimation | FHTC Parinam - Nasamajh, Samagra & Surveys | 6 | 24 | High | 5 | Source effort 24 hrs: <=6 Low, 7-19 Medium, >=20 High
46 | US-FHTC-C5-005 | Consolidated Register (Jun-Jul 2026) | FHTC Parinam - Multiple Surveys per Samagra ID | UAT Done | Jul 2026 | Yes | FHTC Estimation | FHTC Parinam - Nasamajh, Samagra & Surveys | 4 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
47 | US-BISAC-C5-001 | Consolidated Register (Jun-Jul 2026) | BISAC – NIC Asset ID Mapping (Asset & Junction Mapping) | In Progress | Jul 2026 | Yes | BISAC-BISAG Estimation | BISAC - NIC Asset & Pipeline Mapping | 5 | 24 | High | 5 | Source effort 24 hrs: <=6 Low, 7-19 Medium, >=20 High
48 | US-BISAC-C5-002 | Consolidated Register (Jun-Jul 2026) | BISAC – Pipeline Mapping with BISAC Junction Data | In Progress | Jul 2026 | Yes | BISAC-BISAG Estimation | BISAC - NIC Asset & Pipeline Mapping | 5 | 20 | High | 5 | Source effort 20 hrs: <=6 Low, 7-19 Medium, >=20 High
49 | US-BISAC-C5-003 | Consolidated Register (Jun-Jul 2026) | BISAC – Village LGD Code Integration (Village without LGD = Habitation) | Done | Jun 2026 | Yes | BISAC-BISAG Estimation | BISAC - NIC Asset & Pipeline Mapping | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
50 | US-ESIGN-C5-001 | Consolidated Register (Jun-Jul 2026) | e-Sign CDAC – FE e-Sign via Mobile/Web (All Logins) | In Progress | Jun-Jul 2026 | Yes | e-Sign CDAC Estimation | e-Sign CDAC - FE & Contractor | 5 | 30 | High | 5 | Source effort 30 hrs: <=6 Low, 7-19 Medium, >=20 High
51 | US-ESIGN-C5-002 | Consolidated Register (Jun-Jul 2026) | e-Sign CDAC – Contractor/Firm e-Sign for O&M Bill Documents | In Progress | Jun-Jul 2026 | Yes | e-Sign CDAC Estimation | e-Sign CDAC - FE & Contractor | 5 | 20 | High | 5 | Source effort 20 hrs: <=6 Low, 7-19 Medium, >=20 High
52 | US-ESIGN-C5-003 | Consolidated Register (Jun-Jul 2026) | e-Sign CDAC – TL (PMC) Recommendation Letter (E-Office Generated) | In Progress | Jul 2026 | Yes | e-Sign CDAC Estimation | e-Sign CDAC - TL Recommendation | 5 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
53 | US-ESIGN-C5-004 | Consolidated Register (Jun-Jul 2026) | e-Sign CDAC – TL (SQC) & TL (PMC) Account Office Jal Rekha Integration | In Progress | Jul 2026 | Yes | e-Sign CDAC Estimation | e-Sign CDAC - TL Recommendation | 5 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
54 | US-ANS-C5-001 | Consolidated Register (Jun-Jul 2026) | Anusharavan – Multi-Date in Report: FE RFI Submission Date & Block Name | Done | Jun 2026 | Yes | Anusharavan Estimation | Anusharavan - RFI Reports & Search | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
55 | US-ANS-C5-002 | Consolidated Register (Jun-Jul 2026) | Anusharavan – OHT Search Option During RFI | Done | Jun 2026 | Yes | Anusharavan Estimation | Anusharavan - RFI Reports & Search | 5 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
56 | US-ANS-C5-003 | Consolidated Register (Jun-Jul 2026) | Anusharavan – Remove Mandatory GPS/Village for Intake, WTP, MBR, RWPM, CWPM | Done | Jun 2026 | Yes | Anusharavan Estimation | Anusharavan - RFI Reports & Search | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
57 | US-CUBE-C5-001 | Consolidated Register (Jun-Jul 2026) | Cube Testing – Show Rejected Data to Contractor | Done | Jun 2026 | Yes | Cube Testing Estimation | Cube Testing - Contractor Visibility & ID | 5 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
58 | US-CUBE-C5-002 | Consolidated Register (Jun-Jul 2026) | Cube Testing – Cube ID Generated Before Image Upload | Done | Jun 2026 | Yes | Cube Testing Estimation | Cube Testing - Contractor Visibility & ID | 5 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
59 | US-CUBE-C5-003 | Consolidated Register (Jun-Jul 2026) | Cube Testing – Filter Bed Sub-Component Under WTP | Done | Jun 2026 | Yes | Cube Testing Estimation | Cube Testing - Contractor Visibility & ID | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
60 | US-CUBE-C5-004 | Consolidated Register (Jun-Jul 2026) | Cube Testing - Re-Inspection Loop (2nd Loop after GM Rejection) | Done | Jul 2026 | Yes | Cube Testing Estimation | Cube Testing - Re-Inspection Loop | 5 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
61 | US-CUBE-C5-005 | Consolidated Register (Jun-Jul 2026) | Cube Testing - Optional Image Upload on Second RFI Loop | Done | Jul 2026 | Yes | Cube Testing Estimation | Cube Testing - Re-Inspection Loop | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
62 | US-SVS-C5-001 | Consolidated Register (Jun-Jul 2026) | SVS – Bilingual Conversion (Hindi/English) for Water Supply Entry Page | Done | Jun 2026 | Yes | SVS Estimation | SVS - Daily Water Supply Entry | 5 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
63 | US-SVS-C5-002 | Consolidated Register (Jun-Jul 2026) | SVS – Login-Specific District, Block, GP Auto-Selection | Done | Jun 2026 | Yes | SVS Estimation | SVS - Daily Water Supply Entry | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
64 | US-SVS-C5-003 | Consolidated Register (Jun-Jul 2026) | SVS – Additional Reason for NO Supply & Spelling Correction | Done | Jun 2026 | Yes | SVS Estimation | SVS - Daily Water Supply Entry | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
65 | US-SVS-C5-004 | Consolidated Register (Jun-Jul 2026) | SVS – Remove JJM ID and Village Status Fields | Done | Jun 2026 | Yes | SVS Estimation | SVS - Daily Water Supply Entry | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
66 | US-VST-OTP-C5-001 | Consolidated Register (Jun-Jul 2026) | Vistrit – OTP Verification on Scheme/OHT/Bulk Master (GM Edit/Delete) | Done | Jun 2026 | No |  |  | 5 | 8 |  | 0 | Excluded: Duplicate of US-VST-C5-002 (OTP on GM edit/delete)
67 | US-VST-OTP-C5-002 | Consolidated Register (Jun-Jul 2026) | Vistrit – Scheme Village Mapping: Duplicate Village Validation | Done | Jun 2026 | Yes | Master Estimation | Vistrit - Mapping, OTP & Validation | 5 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
68 | US-CMMI-C5-001 | Consolidated Register (Jun-Jul 2026) | CMMI Doc – Cycle 5 Data Collection (June 2026) | In Progress | Jun-Jul 2026 | Yes | CMMI Doc Estimation | CMMI Doc - Cycle 5 Data & Documentation | 5 | 40 | High | 5 | Source effort 40 hrs: <=6 Low, 7-19 Medium, >=20 High
69 | US-CMMI-C5-002 | Consolidated Register (Jun-Jul 2026) | CMMI Doc – Streamline Documentation for Cycle 5 Modules | In Progress | Jun-Jul 2026 | Yes | CMMI Doc Estimation | CMMI Doc - Cycle 5 Data & Documentation | 5 | 60 | High | 5 | Source effort 60 hrs: <=6 Low, 7-19 Medium, >=20 High
70 | US-OMWF-C4-001 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – Firm Bill Submission | Done | Cycle 4 | No |  |  | 6 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
71 | US-OMWF-C4-002 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – GM (PIU) Forward to TL (CSC) | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
72 | US-OMWF-C4-003 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – TL (CSC) Review & Recommendation | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
73 | US-OMWF-C4-004 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – GM (PIU) Final Data Entry & Signed Document Upload | Done | Cycle 4 | No |  |  | 6 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
74 | US-OMWF-C4-005 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – GM (O&M) to TL (PMC) Routing | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
75 | US-OMWF-C4-006 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – DGM (O&M) Review | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
76 | US-OMWF-C4-007 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – GM (O&M) Pass Order & HO Letter Upload | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
77 | US-OMWF-C4-008 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – CGM Regional Office Routing | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
78 | US-OMWF-C4-009 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – CA Financial Review | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
79 | US-OMWF-C4-010 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – CFO Sign-off | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
80 | US-OMWF-C4-011 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – P.D. Review | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
81 | US-OMWF-C4-012 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – MD Final Approval | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
82 | US-OMWF-C4-013 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – Manage Bill (View Pending Bills) | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
83 | US-OMWF-C4-014 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – Document Upload Hub (Multi-Document Per Bill) | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
84 | US-OMWF-C4-015 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – GM (PIU) Login Screen Structure | Done | Cycle 4 | No |  |  | 5 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
85 | US-OMWF-C4-016 | Consolidated Register (Jun-Jul 2026) | O&M Billing Workflow – End-to-End Workflow Testing | WIP | Cycle 4 | No |  |  | 6 |  |  | 0 | Excluded: Cycle 4 scope (Sprint 12-16, delivered Jan-May 2026) - already estimated in Cycle 4 O&M Billing Workflow row
86 | US-MAT-C5-001 | Consolidated Register (Jun-Jul 2026) | Material Testing - Re-Inspection Loop (2nd Loop after GM Rejection) | In Progress | Jul 2026 | Yes | Material Testing Estimation | Material Testing - Re-Inspection Loop | 5 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
87 | US-MAT-C5-002 | Consolidated Register (Jun-Jul 2026) | Material Testing - Optional Image Upload on Second RFI Loop | Open | Jul 2026 | Yes | Material Testing Estimation | Material Testing - Re-Inspection Loop | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
88 | US-MAT-C5-003 | Consolidated Register (Jun-Jul 2026) | Material Testing - GM/Contractor Login Database & API Enhancements | In Progress | Jul 2026 | Yes | Material Testing Estimation | Material Testing - GM/Contractor DB & API | 4 | 20 | High | 5 | Source effort 20 hrs: <=6 Low, 7-19 Medium, >=20 High
89 | US-NRM-C5-001 | Consolidated Register (Jun-Jul 2026) | Nirmal - Beneficiary Report Issue Fix | Done | Jun 2026 | Yes | Nirmal Estimation | Nirmal - Reports & Bug Fixes | 4 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
90 | US-NRM-C5-002 | Consolidated Register (Jun-Jul 2026) | Nirmal - Contractor Login Report Counting Bug Fix | Done | Jun 2026 | Yes | Nirmal Estimation | Nirmal - Reports & Bug Fixes | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
91 | US-NRM-C5-003 | Consolidated Register (Jun-Jul 2026) | Nirmal - FE Mobile Reports Validation & Bug Fixes | Done | Jun 2026 | Yes | Nirmal Estimation | Nirmal - Reports & Bug Fixes | 4 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
92 | US-NRM-C5-004 | Consolidated Register (Jun-Jul 2026) | Nirmal - Test Scenario and Test Case Creation | Done | Jun 2026 | Yes | Nirmal Estimation | Nirmal - Reports & Bug Fixes | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
93 | US-AI-C5-001 | Consolidated Register (Jun-Jul 2026) | AI Module - Tap & Person Detection Predictive Model | Done | Jun 2026 | Yes | AI Module Estimation | AI Module - FHTC Tap Connection | 4 | 40 | High | 5 | Source effort 40 hrs: <=6 Low, 7-19 Medium, >=20 High
94 | US-AI-C5-002 | Consolidated Register (Jun-Jul 2026) | AI Module - Tap Connection Buffer Region Validation (LLM/Pretrained Model Integration) | Done | Jun 2026 | Yes | AI Module Estimation | AI Module - FHTC Tap Connection | 4 | 32 | High | 5 | Source effort 32 hrs: <=6 Low, 7-19 Medium, >=20 High
95 | US-AI-C5-003 | Consolidated Register (Jun-Jul 2026) | AI Module - FHTC Data Processing & Model Training Pipeline | Done | Jun 2026 | Yes | AI Module Estimation | AI Module - FHTC Tap Connection | 4 | 32 | High | 5 | Source effort 32 hrs: <=6 Low, 7-19 Medium, >=20 High
96 | US-MSTR-C5-001 | Consolidated Register (Jun-Jul 2026) | Master - Lock Scheme/Village/OHT Master Once Linked to Live Transactions | Open | Jul 2026 | Yes | Master Estimation | Master - Lock & Data Integrity | 4 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
97 | US-MSTR-C5-002 | Consolidated Register (Jun-Jul 2026) | Master - Dhara Mapped Summary Report Search Debugging & Enhancement | Done | Jun 2026 | Yes | Master Estimation | Master - Lock & Data Integrity | 4 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
98 | US-MSTR-C5-003 | Consolidated Register (Jun-Jul 2026) | Master - Village Deletion Restriction & Database Validation Message | Done | Jun 2026 | Yes | Master Estimation | Master - Lock & Data Integrity | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
99 | US-AST-C5-001 | Consolidated Register (Jun-Jul 2026) | Asset Mapping - SQC/TPIA Contractor Data & Report on Web | Done | Jun 2026 | Yes | Asset Mapping Estimation | Asset Mapping - SQC/TPIA/Contractor | 4 | 12 | Medium | 3 | Source effort 12 hrs: <=6 Low, 7-19 Medium, >=20 High
100 | US-AST-C5-002 | Consolidated Register (Jun-Jul 2026) | Asset Mapping - API Integration & Frontend Bug Fixes | Done | Jun 2026 | Yes | Asset Mapping Estimation | Asset Mapping - SQC/TPIA/Contractor | 4 | 10 | Medium | 3 | Source effort 10 hrs: <=6 Low, 7-19 Medium, >=20 High
101 | US-BHR-C5-001 | Consolidated Register (Jun-Jul 2026) | Bharosa - Item Master Duplicate Dropdown Entry Fix | Done | Jul 2026 | Yes | Bharosa CR Estimation | Bharosa - Factory Testing | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
102 | US-BHR-C5-002 | Consolidated Register (Jun-Jul 2026) | Bharosa - Factory Testing Mobile Bug Fixes | Done | Jul 2026 | Yes | Bharosa CR Estimation | Bharosa - Factory Testing | 4 | 8 | Medium | 3 | Source effort 8 hrs: <=6 Low, 7-19 Medium, >=20 High
103 | US-DIN-C5-001 | Consolidated Register (Jun-Jul 2026) | Daily Inspection - Role-Based Report Modifications | Done | Jun 2026 | Yes | Other Modules Estimation | Daily Inspection | 4 | 12 | Medium | 3 | Source effort 12 hrs: <=6 Low, 7-19 Medium, >=20 High
104 | US-DIN-C5-002 | Consolidated Register (Jun-Jul 2026) | Daily Inspection - Mobile App Bug Fixes | Done | Jun 2026 | Yes | Other Modules Estimation | Daily Inspection | 4 | 6 | Low | 1 | Source effort 6 hrs: <=6 Low, 7-19 Medium, >=20 High
105 | US-SOP-C5-001 | Consolidated Register (Jun-Jul 2026) | Sopan - Calendar Functionality for 2026-27 | Open | Jul 2026 | Yes | Other Modules Estimation | Sopan - Contractor Calendar | 4 | 10 | Medium | 3 | Source effort 10 hrs: <=6 Low, 7-19 Medium, >=20 High
106 | US-QA-C5-001 | Consolidated Register (Jun-Jul 2026) | QA Automation - Selenium Scripts for User Login & Registration | Done | Jun 2026 | Yes | Other Modules Estimation | QA / User & Role Management Automation | 4 | 16 | Medium | 3 | Source effort 16 hrs: <=6 Low, 7-19 Medium, >=20 High
107 | US-QA-C5-002 | Consolidated Register (Jun-Jul 2026) | QA Automation - Internal Review Process for Automation Testing | Done | Jun-Jul 2026 | Yes | Other Modules Estimation | QA / User & Role Management Automation | 4 | 4 | Low | 1 | Source effort 4 hrs: <=6 Low, 7-19 Medium, >=20 High
108 | US-AUG-01 | Sprint 19 User Stories (Aug 2026) | O&M Billing — WSDCP - New WSDCP tab and Bill Generation status tracking | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - WSDCP Phase 1 | 5 |  | High | 5 | AC=5 (Medium) +1: new workflow-stage tracking and bill history across multiple data stores
109 | US-AUG-02 | Sprint 19 User Stories (Aug 2026) | O&M Billing — WSDCP - WSDCP Payment Details tab | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - WSDCP Phase 1 | 7 |  | High | 5 | AC=7 (High): agreement fetch, variation orders, multi-field computation
110 | US-AUG-03 | Sprint 19 User Stories (Aug 2026) | O&M Billing — WSDCP - WSDCP Power Consumption Sheet — Banked Units logic | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - WSDCP Phase 1 | 5 |  | High | 5 | AC=5 (Medium) +1: banked-units business rules validated against sample scheme formula
111 | US-AUG-04 | Sprint 19 User Stories (Aug 2026) | O&M Billing — WSDCP - WSDCP Monthly Bill Sheet — Functional HSC and deductions | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - WSDCP Phase 1 | 6 |  | High | 5 | AC=6 (High): gross-amount formula, deductions table, net payable and GST
112 | US-AUG-05 | Sprint 19 User Stories (Aug 2026) | O&M Billing — WSDCP - WSDCP UFW Report (no penalty) | Done | Aug 2026 | Yes | O&M Estimation | O&M Billing - WSDCP Phase 1 | 3 |  | Low | 1 | AC=3 (Low): report display, no penalty logic
113 | US-AUG-06 | Sprint 19 User Stories (Aug 2026) | O&M Billing — WSDCP - WSDCP User Acceptance Testing on pilot scheme | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - WSDCP Phase 1 | 4 |  | Medium | 3 | AC=4 (Medium): UAT across four screen sets on one pilot scheme
114 | US-AUG-07 | Sprint 19 User Stories (Aug 2026) | O&M Billing — Workflow - Full multi-role forward/backward billing workflow | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - Multi-role Workflow | 5 |  | High | 5 | AC=5 (Medium) +1: multi-role forward/backward routing
115 | US-AUG-08 | Sprint 19 User Stories (Aug 2026) | O&M Billing — Workflow - GM/SQC edit rights on bill data with mandatory remark | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - Multi-role Workflow | 6 |  | High | 5 | AC=6 (High): edit rights with mandatory remark across four sheets
116 | US-AUG-09 | Sprint 19 User Stories (Aug 2026) | O&M Billing — Workflow - SQC-not-available fallback — GM confirms directly | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - Multi-role Workflow | 5 |  | Medium | 3 | AC=5 (Medium): single-SQC fallback routing
117 | US-AUG-10 | Sprint 19 User Stories (Aug 2026) | O&M Billing — Workflow - Higher Officials approval chain (GM O&M → MD) | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - Multi-role Workflow | 5 |  | High | 5 | AC=5 (Medium) +1: seven-role higher-officials chain
118 | US-AUG-11 | Sprint 19 User Stories (Aug 2026) | O&M Billing — Data Integrity - Census Population / village denominator fix | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - Data Integrity & Adjustments | 4 |  | Medium | 3 | AC=4 (Medium): denominator rule and sequence-date enforcement
119 | US-AUG-12 | Sprint 19 User Stories (Aug 2026) | O&M Billing — UI/Workflow - 'Pending Bills for Review' rename and scheme filter | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - Data Integrity & Adjustments | 5 |  | Low | 1 | AC=5 (Medium) -1: rename, filter option, date columns (UI/labels)
120 | US-AUG-13 | Sprint 19 User Stories (Aug 2026) | O&M Billing — Net Payable - Net Payable Bill — Add More Deduction / Any Other Addition | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - Data Integrity & Adjustments | 4 |  | Medium | 3 | AC=4 (Medium): multi-entry deduction/addition with document
121 | US-AUG-14 | Sprint 19 User Stories (Aug 2026) | O&M Billing — Complaint Handling - Complaint category coding and extended deductions | In Progress | Aug 2026 | Yes | O&M Estimation | O&M Billing - Data Integrity & Adjustments | 4 |  | Medium | 3 | AC=4 (Medium): five complaint categories with reason and document
122 | US-AUG-15 | Sprint 19 User Stories (Aug 2026) | O&M Billing — GST - GST Number on Bill and Abstract | Open | Aug 2026 | No |  |  | 4 |  |  | 0 | Excluded: Duplicate of US-OM-C5-017 (GST Number, same CR OMB-MAY-2026-003)
123 | US-AUG-16 | Sprint 19 User Stories (Aug 2026) | O&M Billing — LGD Integration - LGD Code integration (LG Directory → MPSQC) | In Progress | Aug 2026 | No |  |  | 4 |  |  | 0 | Excluded: Duplicate of US-OM-C5-014 (LGD code integration)
124 | US-AUG-17 | Sprint 19 User Stories (Aug 2026) | O&M Billing — Contractor Discrepancy - Contractor discrepancy time-window on Dhara data | In Progress | Aug 2026 | No |  |  | 4 |  |  | 0 | Excluded: Duplicate of US-OM-C5-008 (Contractor dispute window on Dhara data)
125 | US-AUG-18 | Sprint 19 User Stories (Aug 2026) | O&M Billing — Aakalan - Aakalan Addition/Deduction feature (TL SQC / GM PIU) | Done | Aug 2026 | Yes | O&M Estimation | O&M Billing - Data Integrity & Adjustments | 5 |  | Medium | 3 | AC=5 (Medium): role-restricted adjustment with audit in consolidated abstract
126 | US-AUG-19 | Sprint 19 User Stories (Aug 2026) | SVS Water Supply Dashboard - SVS Water Supply Status Dashboard V2 — KPI cards and colour coding | In Progress | Aug 2026 | Yes | SVS Estimation | SVS - Dashboard V2 & Drill-down | 5 |  | High | 5 | AC=5 (Medium) +1: dashboard with KPI cards, colour rules and workflow
127 | US-AUG-20 | Sprint 19 User Stories (Aug 2026) | SVS Water Supply Dashboard - SVS dashboard drill-down — Gram Sachiv and CEO/CO Block | In Progress | Aug 2026 | Yes | SVS Estimation | SVS - Dashboard V2 & Drill-down | 4 |  | High | 5 | AC=4 (Medium) +1: role-specific drill-down with approve/reject
128 | US-AUG-21 | Sprint 19 User Stories (Aug 2026) | SVS / MVS Master - SVS master wireframe and MVS Master (600+ entries) | In Progress | Aug 2026 | Yes | SVS Estimation | SVS / MVS - Master | 4 |  | Medium | 3 | AC=4 (Medium): master wireframe and 600+ entry master mirroring Vistrit
129 | US-AUG-22 | Sprint 19 User Stories (Aug 2026) | SVS / Dhara Meter Logic - FE/Dhara Meter Functional logic and sequential approval | In Progress | Aug 2026 | Yes | Dhara Estimation | Dhara - Meter Logic & Sequential Approval | 4 |  | Medium | 3 | AC=4 (Medium): meter functional/absent logic and sequential approval
130 | US-AUG-23 | Sprint 19 User Stories (Aug 2026) | Nirmal / SVS PHE - Nirmal/SVS PHE integration logic and status labelling | In Progress | Aug 2026 | Yes | Nirmal Estimation | Nirmal / SVS PHE - Water Testing | 5 |  | Medium | 3 | AC=5 (Medium): status labelling, colour coding, drill-down, approval lock
131 | US-AUG-24 | Sprint 19 User Stories (Aug 2026) | Nirmal / SVS PHE - Nirmal/SVS PHE water-testing entry form | In Progress | Aug 2026 | Yes | Nirmal Estimation | Nirmal / SVS PHE - Water Testing | 6 |  | High | 5 | AC=6 (High): multi-field water-testing form with pass/fail logic and photos
132 | US-AUG-25 | Sprint 19 User Stories (Aug 2026) | Material Testing - Material Testing 2nd-loop re-inspection — production deployment | In Progress | Aug 2026 | No |  |  | 5 |  |  | 0 | Excluded: Production deployment of scope already sized in US-MAT-C5-001/002/003
133 | US-AUG-26 | Sprint 19 User Stories (Aug 2026) | Sahbhagita - Sahbhagita Abstract of RA Bill — production release | In Progress | Aug 2026 | Yes | Sahbhagita Estimation | Sahbhagita - Abstract of RA Bill Release | 5 |  | Low | 1 | AC=5 (Medium) -1: UAT defect fixes and release of work sized in Jun (SAH-C5-002/006)
134 | US-AUG-27 | Sprint 19 User Stories (Aug 2026) | FHTC / Parinam - Parinam Dashboard tab on HSC Survey screen | Done | Aug 2026 | Yes | FHTC Estimation | FHTC Parinam - Dashboard | 4 |  | Low | 1 | AC=4 (Medium) -1: display-only dashboard tab
135 | US-AUG-28 | Sprint 19 User Stories (Aug 2026) | Mobile App - Mobile app UI/functional bug fixes | Done | Aug 2026 | Yes | Other Modules Estimation | Mobile App - Fixes & Stability | 6 |  | Medium | 3 | AC=6 (High) -1: mobile navigation and duplicate-control fixes
136 | US-AUG-29 | Sprint 19 User Stories (Aug 2026) | CMMI L5 - Cycle 4 BRTM and Release Note closure | In Progress | Aug 2026 | Yes | CMMI Doc Estimation | CMMI Doc - Cycle 4 Closure | 6 |  | High | 5 | AC=6 (High): BRTM, release note, code review, SVN, Minitab
137 | US-AUG-30 | Sprint 19 User Stories (Aug 2026) | Master Data - Master Data Lock scope finalisation | Open | Aug 2026 | No |  |  | 4 |  |  | 0 | Excluded: Duplicate of US-MSTR-C5-001 (Master lock, CR MSTR-JUN-2026-006)
138 | US-AUG-31 | Sprint 19 User Stories (Aug 2026) | BISAG / Delhi Data Integration - Asset & Pipeline API and Annexure-C data sharing | In Progress | Aug 2026 | Yes | BISAC-BISAG Estimation | BISAG - Delhi Data Integration | 5 |  | High | 5 | AC=5 (Medium) +1: external BISAG API and Annexure-C data sharing
139 | US-AUG-32 | Sprint 19 User Stories (Aug 2026) | BISAG / Delhi Data Integration - Scheme mapping and progress-reporting fix | In Progress | Aug 2026 | Yes | BISAC-BISAG Estimation | BISAG - Delhi Data Integration | 5 |  | Medium | 3 | AC=5 (Medium): integration (+1) offset by fix scope (-1)
140 | US-AUG-33 | Sprint 19 User Stories (Aug 2026) | Contractor Billing Acceleration - Hands-on training for non-submitting agencies | Done | Aug 2026 | No |  |  | 5 |  |  | 0 | Excluded: Hands-on training for agencies - operational activity, not development scope
141 | US-AUG-34 | Sprint 19 User Stories (Aug 2026) | Dhara & Nirmal Panchayat Monitoring - Panchayat-level dashboard and MVS-to-local-body handover | In Progress | Aug 2026 | Yes | Dhara Estimation | Dhara & Nirmal - Panchayat Monitoring | 6 |  | High | 5 | AC=6 (High): panchayat dashboards for two modules plus 5-step handover
142 | US-AUG-35 | Sprint 19 User Stories (Aug 2026) | RFI / Anusharavan (SVS-GP) - Simplified RFI system and GP–FE review workflow | Not Started | Aug 2026 | Yes | SVS Anusharavan GP Estimation | SVS Anusharavan GP - Mobile & RFI Workflow | 9 |  | High | 5 | AC=9 (High): simplified RFI with geotag, classification and review workflow
143 | US-AUG-36 | Sprint 19 User Stories (Aug 2026) | Admin / ID Management - PIU district-wise restructuring and TL-ID/PIU-ID linking | Not Started | Aug 2026 | Yes | Other Modules Estimation | Admin / ID Management | 6 |  | High | 5 | AC=6 (High): PIU restructuring, ID linking, agency re-mapping protocol
144 | US-AUG-37 | Sprint 19 User Stories (Aug 2026) | Jal Samadhan - Complaint Queries module | Not Started | Aug 2026 | Yes | Other Modules Estimation | Jal Samadhan | 4 |  | Medium | 3 | AC=4 (Medium): complaint queries page with SLA escalation
145 | US-SEP-01 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - O&M Billing workflow confirmed stable in production | Done | Sep 2026 | No |  |  | 4 |  |  | 0 | Excluded: Production confirmation of workflow scope already sized (US-AUG-01/07/08/12/18)
146 | US-SEP-02 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - Withheld Addition/Deduction amounts shown at End-of-Month | In Progress | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 4 |  | Medium | 3 | AC=4 (Medium)
147 | US-SEP-03 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - Fix: bill remains editable after Contractor submission | Done | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 3 |  | Low | 1 | AC=3 (Low): client-side lock fix
148 | US-SEP-04 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - TRP gate controlling O&M Phase availability | In Progress | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 3 |  | Low | 1 | AC=3 (Low): phase-availability gate
149 | US-SEP-05 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - Scheme-based SQC/TL list cleanup | In Progress | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 4 |  | Low | 1 | AC=4 (Medium) -1: list cleanup
150 | US-SEP-06 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - WSDCP / TRP / O&M Phase tabs with staged Abstract pages | In Progress | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 3 |  | Medium | 3 | AC=3 (Low) +1: three phase tabs with staged abstract pages
151 | US-SEP-07 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - Full audit trail on Contractor Bill edits | Open | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 4 |  | Medium | 3 | AC=4 (Medium): audit trail on contractor bill edits
152 | US-SEP-08 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - PMC / Deputy O&M role-scoped scheme visibility | Open | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 4 |  | Medium | 3 | AC=4 (Medium): role-scoped visibility
153 | US-SEP-09 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - Gross Payable Bill — minimum value validation | Open | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 3 |  | Low | 1 | AC=3 (Low): minimum-value validation
154 | US-SEP-10 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - Census Population verification before Generate Bill | Done | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 3 |  | Low | 1 | AC=3 (Low): pre-generation census check
155 | US-SEP-11 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - User Management — PIU-wise ID search with Tenure and Agency columns | In Progress | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 4 |  | Medium | 3 | AC=4 (Medium): PIU-wise ID search with tenure/agency columns
156 | US-SEP-12 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - TL ID conflict resolution (Bhopal / Sehore) | Open | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 3 |  | Low | 1 | AC=3 (Low): TL ID conflict resolution
157 | US-SEP-13 | Sprint 20 User Stories (Sep 2026) | O&M Billing / Aaklan - Save-as-Draft confirmation popup on Bulk bill actions | Open | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 3 |  | Low | 1 | AC=3 (Low) -1: confirmation popup
158 | US-SEP-14 | Sprint 20 User Stories (Sep 2026) | O&M Billing — Complaint Redressal - Carry-forward of unresolved complaints with 48-hour flag | In Progress | Sep 2026 | Yes | O&M Estimation | O&M Billing / Aaklan - Controls & Tracking | 5 |  | Medium | 3 | AC=5 (Medium): complaint carry-forward with 48-hour flag
159 | US-SEP-15 | Sprint 20 User Stories (Sep 2026) | Dhara - Dhara sequential reading approval lock | In Progress | Sep 2026 | Yes | Dhara Estimation | Dhara - Meter Logic & Sequential Approval | 4 |  | Medium | 3 | AC=4 (Medium): sequential approval lock
160 | US-SEP-16 | Sprint 20 User Stories (Sep 2026) | Dhara - Dhara reading edit rules by meter status (GM / SQC-TL login) | Open | Sep 2026 | Yes | Dhara Estimation | Dhara - Edit Rules, Survey Report & MPEB API | 5 |  | High | 5 | AC=5 (Medium) +1: edit-rules matrix by meter status and login role
161 | US-SEP-17 | Sprint 20 User Stories (Sep 2026) | Dhara - Dhara Survey Report column restructuring | Open | Sep 2026 | Yes | Dhara Estimation | Dhara - Edit Rules, Survey Report & MPEB API | 5 |  | Medium | 3 | AC=5 (Medium): survey report column restructuring
162 | US-SEP-18 | Sprint 20 User Stories (Sep 2026) | Dhara - Dhara Electricity Meter Bill — MPEB Smart Meter API integration | Open | Sep 2026 | Yes | Dhara Estimation | Dhara - Edit Rules, Survey Report & MPEB API | 4 |  | High | 5 | AC=4 (Medium) +1: external MPEB smart-meter API
163 | US-SEP-19 | Sprint 20 User Stories (Sep 2026) | Dhara / Asset Mapping - Asset Mapping — OHT Id cleanup in reports | Open | Sep 2026 | Yes | Asset Mapping Estimation | Asset Mapping - Report Cleanup | 3 |  | Low | 1 | AC=3 (Low): report cleanup
164 | US-SEP-20 | Sprint 20 User Stories (Sep 2026) | Cube Testing - Cube RFI Id display | Open | Sep 2026 | Yes | Cube Testing Estimation | Cube Testing - Re-Inspection Status | 3 |  | Low | 1 | AC=3 (Low): id display
165 | US-SEP-21 | Sprint 20 User Stories (Sep 2026) | Cube Testing - Cube Reinspection — colour flag and separate status | In Progress | Sep 2026 | Yes | Cube Testing Estimation | Cube Testing - Re-Inspection Status | 3 |  | Low | 1 | AC=3 (Low): colour flag and status
166 | US-SEP-22 | Sprint 20 User Stories (Sep 2026) | Material Testing - Material Reinspection Id — separate flag status | In Progress | Sep 2026 | Yes | Material Testing Estimation | Material Testing - Re-Inspection Id Flag | 3 |  | Low | 1 | AC=3 (Low): flag status
167 | US-SEP-23 | Sprint 20 User Stories (Sep 2026) | Bharosa - Bharosa inspection reassignment and photo-upload fix | In Progress | Sep 2026 | Yes | Bharosa CR Estimation | Bharosa - Inspection Reassignment | 4 |  | Low | 1 | AC=4 (Medium) -1: reassignment and photo-upload fix
168 | US-SEP-24 | Sprint 20 User Stories (Sep 2026) | Anusharavan - Fix: multiple survey submission by SQC/TL | In Progress | Sep 2026 | Yes | Anusharavan Estimation | Anusharavan - Survey Fix | 3 |  | Low | 1 | AC=3 (Low): bug fix
169 | US-SEP-25 | Sprint 20 User Stories (Sep 2026) | Vistrit (Master) - Survey Intake, WTP and OHT Master sub-modules | In Progress | Sep 2026 | Yes | Master Estimation | Vistrit - Survey Intake/WTP/OHT Master | 4 |  | Medium | 3 | AC=4 (Medium): three master sub-modules, web page and API
170 | US-SEP-26 | Sprint 20 User Stories (Sep 2026) | Parinam - FE dashboard, FE-login reports, and multi-survey support confirmed stable | Done | Sep 2026 | Yes | FHTC Estimation | FHTC Parinam - Dashboard | 4 |  | Low | 1 | AC=4 (Medium) -1: only the new FE dashboard/FE-login reports sized; FE name and multi-survey already sized in FHTC-C5-002/005
171 | US-SEP-27 | Sprint 20 User Stories (Sep 2026) | SVS Water Supply Monitoring - SVS Water Supply Dashboard and SVS Nirmal module completed | Done | Sep 2026 | No |  |  | 3 |  |  | 0 | Excluded: Completion confirmation of SVS dashboard/Nirmal scope already sized (US-AUG-19/20/23/24, US-SVS-C5-001..004)
172 | US-SEP-28 | Sprint 20 User Stories (Sep 2026) | SVS Nirmal - FTK kit report and SVS Nirmal wireframe | Done | Sep 2026 | Yes | SVS Estimation | SVS Nirmal - FTK Kit | 3 |  | Low | 1 | AC=3 (Low): FTK report and wireframe
173 | US-SEP-29 | Sprint 20 User Stories (Sep 2026) | SVS Anusharavan GP - GP Master and Anusharavan GP wireframe and user management | Done | Sep 2026 | Yes | SVS Anusharavan GP Estimation | SVS Anusharavan GP - Master & Wireframe | 3 |  | Medium | 3 | AC=3 (Low) override +1: wireframe plus GP Master development and user management
174 | US-SEP-30 | Sprint 20 User Stories (Sep 2026) | SVS Anusharavan GP - GP Anusharavan Mobile Screen for FE | In Progress | Sep 2026 | Yes | SVS Anusharavan GP Estimation | SVS Anusharavan GP - Mobile & RFI Workflow | 3 |  | Medium | 3 | AC=3 (Low) override +1: new mobile screen for FE login
175 | US-SEP-31 | Sprint 20 User Stories (Sep 2026) | Anusharavan SVS — RFI - Gram Panchayat RFI raise and Sub-Engineer review workflow | Open | Sep 2026 | Yes | SVS Anusharavan GP Estimation | SVS Anusharavan GP - Mobile & RFI Workflow | 5 |  | High | 5 | AC=5 (Medium) +1: GP RFI raise and Sub-Engineer review workflow
176 | US-SEP-32 | Sprint 20 User Stories (Sep 2026) | Anusharavan SVS — SIPRI Integration - SIPRI / NREGA / Yuktdhara integration for GP works planning | Open | Sep 2026 | Yes | SVS Anusharavan GP Estimation | SVS Anusharavan GP - SIPRI Integration | 5 |  | High | 5 | AC=5 (Medium) +1: SIPRI/NREGA/Yuktdhara external integration
177 | US-SEP-33 | Sprint 20 User Stories (Sep 2026) | Anusharavan SVS — SIPRI Integration - SIPRI AE block-wise login and Panchayat ID whitelisting | Open | Sep 2026 | Yes | SVS Anusharavan GP Estimation | SVS Anusharavan GP - SIPRI Integration | 4 |  | Medium | 3 | AC=4 (Medium): block-wise login and ID whitelisting
178 | US-SEP-34 | Sprint 20 User Stories (Sep 2026) | GP Master Data - Gram Panchayat Funds-Source and Nirman Karya work-type masters | Open | Sep 2026 | Yes | SVS Anusharavan GP Estimation | SVS Anusharavan GP - Master & Wireframe | 5 |  | Medium | 3 | AC=5 (Medium): two new masters
179 | US-SEP-35 | Sprint 20 User Stories (Sep 2026) | Jal Samadhan - CM Helpline (181) integration for Jal Samadhan | Open | Sep 2026 | Yes | Other Modules Estimation | Jal Samadhan | 4 |  | High | 5 | AC=4 (Medium) +1: external CM Helpline 181 integration
180 | US-SEP-36 | Sprint 20 User Stories (Sep 2026) | Jal Rekha — Security (2FA) - Two-Factor Authentication — current scope confirmed | Done | Sep 2026 | Yes | Other Modules Estimation | Security - Two-Factor Authentication | 3 |  | High | 5 | 2FA implementation: 24 hrs logged in Sep timesheet (Adhoc) - hours rule (>=20 hrs = High)
181 | US-SEP-37 | Sprint 20 User Stories (Sep 2026) | Mobile App Stability - Crash and ANR fixes from Play Console vitals | Open | Sep 2026 | Yes | Other Modules Estimation | Mobile App - Fixes & Stability | 8 |  | High | 5 | AC=8 (High): eight independent crash/ANR root causes
182 | PSR-JUN-01 | June 2026 PSR / timesheet | CI/CD - Azure DevOps Android pipeline implementation | Completed | Jun 2026 | Yes | Other Modules Estimation | Mobile App - Fixes & Stability |  | 16 | Medium | 3 | Timesheet: AzureDevOps 16 hrs (Sprint 17): <=6 Low, 7-19 Medium, >=20 High
183 | PSR-JUL-01 | July 2026 PSR / timesheet | Dashboard - redesign of all module and inner pages of Jal Rekha | Completed | Jul 2026 | Yes | Other Modules Estimation | Dashboard & Public Reports |  | 16 | Medium | 3 | Timesheet: Dashboard 16 hrs (Sprint 18): <=6 Low, 7-19 Medium, >=20 High
184 | PSR-JUL-02 | July 2026 PSR / timesheet | All public reports on dashboard - sanity testing, bug fixes, report preparation | Completed | Jul 2026 | Yes | Other Modules Estimation | Dashboard & Public Reports |  | 26 | High | 5 | Timesheet: All Public Reports on Dashboard 26 hrs (Sprint 18): <=6 Low, 7-19 Medium, >=20 High
185 | PSR-SEP-01 | September 2026 PSR / timesheet | Dashboard - login page and forgot-password page UI fixes | Completed | Sep 2026 | Yes | Other Modules Estimation | Dashboard & Public Reports |  | 16 | Medium | 3 | Timesheet: Dashboard 16 hrs (Sprint 20): <=6 Low, 7-19 Medium, >=20 High
186 | PSR-SEP-02 | September 2026 PSR / timesheet | O&M Billing Contractor - Bill Tracking page UI overhaul, Abstract Bill UI, responsive layout | In Progress | Sep 2026 | Yes | O&M Estimation | O&M Billing - Contractor/GM UI |  | 48 | High | 5 | Timesheet: O&M Billing - Change Request Contractor 48 hrs (Sprint 20): <=6 Low, 7-19 Medium, >=20 High
187 | PSR-SEP-03 | September 2026 PSR / timesheet | O&M Billing GM - Abstract Report PDF UI fixes | Completed | Sep 2026 | Yes | O&M Estimation | O&M Billing - Contractor/GM UI |  | 8 | Medium | 3 | Timesheet: O&M Billing GM 8 hrs (Sprint 20): <=6 Low, 7-19 Medium, >=20 High
188 | PSR-SEP-04 | September 2026 PSR / timesheet | User & Role Management - Selenium automation extended through Assign Work | Completed | Sep 2026 | Yes | Other Modules Estimation | QA / User & Role Management Automation |  | 12 | Medium | 3 | Timesheet: User & Role Management 12 hrs (Sprint 20): <=6 Low, 7-19 Medium, >=20 High