## INDEX
JAL REKHA – Monthly MoM Points ¦ August 2026 ¦ MD Sir Meeting ¦ MPSEDC / MPSSDI
Sheet | Tab Name | Coverage | No. of Items | Meeting Date
1 | 03 Aug MoM | 03rd August 2026 – MD Sir Meeting Action Items | 13 | 03 Aug 2026
2 | 19 Aug MoM | 19th August 2026 – MD Sir Meeting Action Items | 12 | 19 Aug 2026
3 | O&M Billing Status | O&M Billing Module – Consolidated Sub-Feature Status | 21 | Aug 2026
4 | All Modules Status | All Jal Rekha Modules – Post-July MoM Consolidated Status | 22 | Aug 2026

## 03 Aug MoM
Jal Rekha – MoM Action Items ¦ 03rd August 2026 ¦ MD Sir Meeting
S.No. | Module / Activity | Tasks / Changes / Enhancements | Owner | Status
1 | SVS Water Supply Status Dashboard | SVS PME Dashboard: • KPI Cards: Total Villages, Dhara Entry (Yes/No), Dhara Partial Entry, Water Supply (Yes/No) • Colour coding: Dark Blue = Dhara Entry + Water Supply; Light Blue = Partial Dhara Entry + Water Supply; Red = No Dhara Entry + No Water Supply • Workflow 'Remove' option on dashboard • Drill-down from KPI card to village-level detail • 2nd level: Gram Sachiv login → source of water, cost, document upload, Infra work completed Yes/No • CEO / COBlock → Block level table shown with Approve/Reject • SVS (master) wireframe and workflow (19 Aug 2026 target) • MV Master with 600+ entries – Contractor MV structure like Vistrit GM table (Scheme Master) • FE Meter Functional: If FE absent → next day Start & End Reading open; GM approval condition → cannot change start reading of next day • Dhara Meter Functional (MF) logic: handle meter-functional/non-functional/absent scenarios • Sequential Approval of months; Last Approval Date → scheme-wise • Remark column: Remove from dashboard | Dev Team / BA | ⟳ In Progress
2 | O&M Billing – WSDCP (Water Supply During Construction Phase) – Phase 1 | New tab 'W.S.D.C.P.' / 'Water Supply During Const.' added to O&M Billing module alongside existing O&M Billing phase: • Page of WSDCP, TRP, O&M Phase tabs • Tabs available: Payment Details, Residual Pressure Sheet, Complaint Redressal Sheet, Additional Facilities, Power Consumption Sheet, UFW Report, Monthly Bill Sheet • Bill No prefix: WSDCP-…, Current TRP prefix: TRP-… • Additional Facilities Tab: Disable • Residual Same; Complaint Same • Power Consumption Sheet: On Contract Details → Under Power Consumption Details → Approved Banked Units (Numeric, can be zero) • UFW Report: Show it (but No penalty) • Monthly Bill Sheet: Present HSC (NOT), Functional HSC (Editable: 80); V₁ = 100000; * Days → Gross Amount = 25 × 80500 / 1.0 | Dev Team | ⟳ In Progress
3 | O&M Billing – WSDCP – Payment Details Tab | Payment Details screen for WSDCP: (A) Contract Amount (in Rs.) – from Agreement Auto-fetch, Non-Editable (B) Upto Date Cumulative Variation (in Rs. amount) – can be Positive or Negative; Cumulative Amount; Upload Variation Order Copy (Multiple Copies Allowed, Descending Order) (C) Final Payment Done (under retrofitting scheme) – cross-field (nothing in C section); Total Amount (A+B) in Rs. • Last Paid RA Bill No • Bill No: WSDCP prefix • Yearly Factor = 1 (always) No Increment Allowed; O&M Amount of 1st Year (from Pro-Rata Date); O&M Amount for Present Billing Year (same value, No Increment = All Same) • Monthly O&M Amount (in Rs.) ¦ Per KL O&M Amount (disabled) • All 12+ fields disabled on Payment Details for WSDCP (No Increment) | Dev Team | ⟳ In Progress
4 | O&M Billing – WSDCP – Power Consumption Sheet | Power Consumption Sheet for WSDCP billing (Barwani / Talunkhurd example): • Month & Year: Apr-2026; Intermediate Raw Water Demand (MLD): 5.8500 • Approved Power Guarantee Variable for Intermediate Raw Water Demand: 3837.1300 • Power Consumption Per Day Per MLD for Variable Components (Y): 655.9197 • Number of Days WTP is Functional: 30 • Actual Monthly Raw Water Drawn (in ML): 135.3000 • Actual Water Supplied Including Allowable Losses S (in ML): 37.7624 • Monthly KWH For Variable Components (As Per Present Supply): 24769.10 • Total Monthly KWH: 24769.10 • Approved Banked Units: Auto-fetch + Disabled • Balance Banked Units: Numeric (editable) • Excess Consumption (KWH) field • Consumed Banked Units: Numeric; (i) Not greater than Balance Banked Units; (ii) Not greater than Excess Consumption • Balance Banked Units after adjusting this month excess consumption • Upload Supporting Document (As Per Submeter Reading); Upload Supporting Documents (Electricity Bills – Intake, IPS, WTP) | Dev Team | ⟳ In Progress
5 | O&M Billing – WSDCP – Monthly Bill Sheet | Monthly Bill Sheet for WSDCP (27 June 2026 discussion): • Present HSC: crossed/NOT shown • Functional HSC: Editable (e.g. 80) • V₁ = 100000; * Days • Gross Amount = Days × Functional HSC × Per KL Rate → e.g. 25 × 80500 / 1.0 • Bill Details: RA Bill No format; WSDCP Start Date field • Month; No. of Days in the Month • O&M Start Date; Capacity of WTP (MLD) • Firm Name (from Agreement) • Upto Date Payment Done (Execution Phase) A; Final Payment Done (Under Retrofitting Scheme) C; Upto Date Payment Done (Under Clause Extension of New Pipeline During O&M Phase) B • Total Expenditure Done (A+B+C); Yearly Factor; O&M Amount of 1st Year; O&M Amount of the Year Considered in This Bill • Monthly O&M Amount; Per KL O&M Amount W.R.T. Capacity of WTP • Gross Amount; Deductions table: Quality/Quantity/Pressure/Complaint, UFW, Power Consumption, Manpower & Mobile, Vehicle, Landline, Additional Bulk Supply • Net Payable Amount; Add GST; Total Payable Amount | Dev Team | ⟳ In Progress
6 | O&M Billing – Bill Generation Column & Current Status/Stage | Bill Generation tracking column and stage display: • Tab 5 – W.S.D.C.P. (Water Supply During Construction) tab added to O&M Billing generate bill flow • Three phases visible: (1) Trial Run Phase, (2) O&M Billing Phase, (3) O&M Billing Phase check (√) • Bill Generation Column showing current status and stage • Generate Bill button under each phase tab • Bill History Timeline → sequence dates • Current Status → Pending with GM (PIU) → shown in 'Review Bills for Approval' section | Dev Team | ⟳ In Progress
7 | O&M Billing – Workflow: Forward/Backward Multi-Role | O&M Billing workflow forward/backward mechanism from handwritten notes: Contractor: • Forward to GM PIU (Dropdown) SQC Firm: • Forward to: Firm / GM (PIU) / GM (HO) / Deputy GM GM (PIU): • Forward to: TL(PMC) / Deputy GM / GM(O&M) / CA / CFO / PD / MD TL(PMC) → Dy.M.O&M → CA, CFO, PD, MD TL(PMC) → Dy.M.O&M → GM & O&M, GM & PIU, GM(HO) – Adding GM(HO) Dropdown Button: Forward to Role → Options: Contractor, GM (PIU), SQC/TL, GM(O&M), GM(HO), Deputy GM • GM(PIU) – can check back with GM (PIU) • External roles: GM (PIU), GM (HO), Deputy GM | Dev Team / BA | ⟳ In Progress
8 | O&M Billing – GM/SQC Edit Rights on Bill | GM/SQC Edit permissions on bill data: (i) Payment Details → Primary Details (to be changed) – Add Remark (ii) Residual / Complaints → Additional Facilities – Add/Edit – Issues by SQC & GM (iii) Power Consumption → Editable by GM/W (iv) No change in UFW (v) Monthly Bill Sheet → Apply Deductions; Remark; Editable by GM/SQC; Deduction as per Norms also (vi) Keep One Copy – Contractor Bill (vii) Net Payable Bill → Add More Deduction; Amount Deducted (Menu) → Any Other Addition GM/SQC Edit/Add/Delete on bill: • GM (CRU) → GM(SQC) Edit/Add/Delete • GM (MQ) → GM (PIU) → Stay + Observation • Backward by GM (PIU) – now open for Contractor to Edit + Save as Draft • Bill Status of TL/TMC after TL/SQC confirm and check to any Draft | Dev Team | ⟳ In Progress
9 | O&M Billing – SQC Not Available → GM Confirms | SQC availability handling in workflow: • SQC not available → GM then confirms (if SQC 1 = available, show GM only; → show 2nd SQC if GM selects forward) • GM (Usage) → save as Draft and forward to GM only • Bill goes again into Draft and GM opens Bill only • Backward by GM (PIU) – now open for Contractor to Edit/Save as Draft | Dev Team | ⟳ In Progress
10 | O&M Billing – O&M Census Population & Village Denominator Fix | O&M calculation fixes: • Census Population cannot be zero in O&M billing denominator • Village in denominator: all Villages should be there according to Census • Sequence dates for sequential approval of months • Monthly Bill Sheet → Pending with < GM (PIU)> shown in Review Bills for Approval | Dev Team | ⟳ In Progress
11 | Nirmal / SVS PHE – Water Testing Module | New Nirmal / SVS PHE integration (1st July 2026 logic): • Lock Approval on Bill • SVS PHE: Yes/Partial/No → colour: Blue/Light Blue/Red • Dhara 2: 'No Data Entry' → Dhara 3: 'Date Entry Done' • Total Villages (Drill Down) • Nirmal Entry: 'No Nirmal Entry' → 'Nirmal Entry Done' • Source of Sample: (1) Dugwell, Tubewell, Borewell OHT, Handpump; (2) Beneficiary Name; (3) Details (in the form) • 3) Fill Details: Date of Testing, Photo (Max 2), Remarks • Location Sample Tested; Sample Passed; Sample Failed • Place of Testing: School, Anganwadi, Health Centre, Any Other | Dev Team | ⟳ In Progress
12 | O&M Billing – 'Pending Bills for Review' Rename & Scheme Dropdown | Left Menu Changes: • Rename 'Pending Bills for Review' (name change on left menu) • Scheme → Add 'All' in dropdown (for Pending Bills for Review page) • Generation Date and Forwarded Date columns added to bill list • GM/SQC Edit button on Manage Bill page | Dev Team | ⟳ In Progress
13 | O&M Billing – Net Payable Bill: Any Other Addition | Net Payable Bill section: • Add More Deduction option • Amount Deducted field • (Menu) → Any Other Addition • Action: (+) Multiple Entries allowed for deductions • Amount, Reason, Document per deduction entry | Dev Team | ⟳ In Progress

## 19 Aug MoM
Jal Rekha – MoM Action Items ¦ 19th August 2026 ¦ MD Sir Meeting
S.No. | Module / Activity | Tasks / Changes / Enhancements | Owner | Status
1 | SVS Water Supply Status Dashboard – Wireframe & Workflow (19 Aug Target) | SVS Dashboard V2 wireframe finalised: • KPI cards: Total Villages; Dhara Entry done; Dhara Partial Entry; No Dhara Entry / No Water Supply • Colour scheme confirmed: Dark Blue (Dhara + WS), Light Blue (Partial), Red (No WS) • Workflow button 'Remove' implemented on dashboard • Gram Sachiv login: Source of Water, Cost, Document upload, Infra Work Completed (Yes/No) shown against their village • CEO/CO Block level: table shown with Approve/Reject • Remark Column removed from dashboard view • SVS (master) target date confirmed 19 Aug 2026 • MVS Master: 600+ entries, Contractor MVS structure like Vistrit GM Scheme Master table | Dev Team | ⟳ In Progress
2 | SVS PHE Nirmal Integration – Water Testing Logic | SVS PHE and Nirmal integration points (discussed 29–30 June, 1–2 July 2026): • Accept ranges: Nirmal 6.5–8.5; SVS PHE 6.5–8.5; 2→ 6; 6.6→ 1→ 3; 8.6→ 0.5+−5 • Test Result A → Photolysis formula • Bypass in Emergency: Accept in Emergency (Byp) → Same plotting • 829 / 592 / 600 → 350 entries range • Sample counts: 200–600 = 6; 200+600 = 600 • 6+5→ 8.5; 6 ranges confirmed • Source of Sample: Dugwell, Tubewell, Borewell OHT, Handpump • Remark Column: Remove from water testing form | Dev Team | ⟳ In Progress
3 | O&M Billing – WSDCP Phase 1: Production Deployment | WSDCP Phase 1 (Water Supply During Construction Phase) deployment status: • Tab W.S.D.C.P. added to Generate Bill page • Payment Details: Auto-fetched Contract Amount, Variation Order (positive/negative), Final Payment Done • Power Consumption: Approved Banked Units, Balance Banked Units, Consumed Banked Units logic • UFW Report: Show but No Penalty • Monthly Bill Sheet: Present HSC removed, Functional HSC (editable), Gross Amount formula active • Yearly Factor = 1 always (No Increment) • Bill No prefix: WSDCP-…; TRP prefix: TRP-… • Additional Facilities tab: Disabled for WSDCP • UAT testing of WSDCP screens in progress for Barwani / Talunkhurd scheme • RA Bill No: RA/8/140/2026-27/Q1/25 | Dev Team | ⟳ In Progress
4 | O&M Billing – Multi-Role Workflow (Full Chain Implementation) | Full multi-role billing workflow implementation: Firm → Forward to GM PIU (Dropdown) SQC/Firm → Forward to: Firm / GM(PIU) / GM(HO) / Deputy GM GM(PIU) → Forward to: TL(PMC) / Deputy GM / GM(O&M) / CA / CFO / PD / MD TL(PMC) → Dy.M.O&M → CA, CFO, PD, MD TL(PMC) → Dy.M.O&M → GM & O&M, GM & PIU, GM(HO) Dropdown Forward-to Button: • Internal roles: Contractor, GM(PIU), SQC/TL • External roles: GM(O&M), GM(HO), Deputy GM • GM(PIU) check-back option • Backward/Forward fully implemented per role chain • Bill History Timeline → sequence dates • Current Status: Pending with GM(PIU) visible in 'Review Bills for Approval' | Dev Team | ⟳ In Progress
5 | O&M Billing – SQC/GM Edit Rights & Backward Flow | SQC and GM edit rights on forwarded bill: • GM/SQC can Add/Edit: Payment Details Remark; Residual Pressure/Complaint Additional Facilities; Power Consumption • Monthly Bill Sheet: Apply Deductions + Remark – editable by GM/SQC; Deductions per norms shown • Net Payable Bill: Add More Deduction; Amount Deducted; Any Other Addition • Keep One Copy – Contractor Bill • SQC not available → GM Confirms; if SQC=1 available → show GM only; SQC 2 on GM forward • GM(PIU) Backward → now open for Contractor to Edit and Save as Draft • Bill status of TL/TMC after TL/SQC confirm → check to any Draft | Dev Team | ⟳ In Progress
6 | O&M Billing – Pending Bills Rename, Scheme Dropdown & Date Columns | Left-menu and page-level changes: • Rename left-menu item 'Pending Bills for Review' (name change) • Scheme dropdown: Add 'All' option • Add 'Generation Date' and 'Forwarded Date' columns to Pending Bills list • GM/SQC Edit button on Manage Bill page • Census Population: Cannot be zero in O&M bill denominator • All villages should be in denominator per Census data • Sequential approval of months; Last Approval Date → scheme-wise • Bill History Timeline → sequenced dates | Dev Team | ⟳ In Progress
7 | O&M Billing – O&M Module Workflow Bill Tracker | O&M Workflow Bill Tracking: • Dashboard of SVS PHE (point 1 of 3 Aug MoM) • O&M Billing Changes • O&M Workflow ← Bill Tracking • HSC Functional: 8 Portable • Bill Generation Column & Current Status & Stage • Tabs: W.S.D.C.P. / Trial Run Phase / O&M Billing Phase • Bill tracking integration with workflow stages • Generate Bill button under each phase with status indicator | Dev Team | ⟳ In Progress
8 | Material Testing – Re-Inspection Loop (Production Deployment) | Material Testing 2nd loop re-inspection (In Progress from July MoM): • API for Contractor re-inspection insert loop: Done • API for Web multi-login re-inspection loop: Done • FE login API: Done • DB changes: Done • Mobile and Web changes: Done • UAT in local and UAT environment: Done • Production deployment: In Progress (target 19 Aug 2026) • Optional image upload on 2nd loop: Implemented | Dev Team | ⟳ In Progress
9 | Sahbhagita – Abstract of RA Bill Production Release | Sahbhagita Abstract of RA Bill final UAT and production: • All DEF-01 to DEF-04 defects fixed and validated in UAT • PIU/Scheme binding on page load: resolved • Village/Combined dropdown: confirmed working • Pagination: confirmed working • Production release: target 19 Aug 2026 • RA Bill No multi-select RA(1)–RA(12): implemented • Drill-down 'No. of Activities' hyperlink: functional | Dev Team | ⟳ In Progress
10 | CMMI L5 – Cycle 4 BRTM & Release Note Closure | Remaining CMMI L5 Cycle 4 documentation: • BRTM (Baseline Requirements Traceability Matrix): In progress • Release Note: In progress • Cycle 5 CR Log: Updated up to August 2026 • Code Review documents: All modules complete • SVN repository: Updated • Statistical analysis Minitab: Complete • Target: Both BRTM and Release Note to be submitted before next MQAS appraisal | SEPG Team | ⟳ In Progress
11 | Master Data Lock – Scheme/Village/OHT (CR MSTR-JUN-2026-006) | Master data entry lock design discussion: • Design/impact discussion still ongoing per July MoM • OTP verification for GM Login Edit/Delete on Scheme, OHT, Bulk Master: Pending development • Interim control: GM PIU all details locked once bill submitted • Target: Sprint 19 planning session to define scope | Dev Team / BA | ⚠ Open
12 | O&M Billing – Higher Officials Chain (GM O&M → MD) | Higher official approval chain development (carry-forward from Sprint 18): • GM O&M → DGM → TL PMC → CFO → CA → P.D. → MD • Firm → GM PIU → TL SQC → GM O&M chain: Implemented • Higher official chain: In Progress • Bill PDF consolidation (19–20 documents): In Progress • Document Upload Hub for all roles: In Progress • Target: Sprint 19 | Dev Team | ⟳ In Progress

## O&M Billing Status
Jal Rekha – O&M Billing Module Consolidated Status ¦ August 2026
S.No. | Sub-Module / Feature | Description / Details | Status
1 | O&M Billing – WSDCP Tab (Phase 1) | Water Supply During Construction Phase (WSDCP) billing module – Phase 1: New tab added to O&M Billing. Payment Details (auto-fetched Contract Amount, Variation), Power Consumption (Banked Units logic), UFW (show/no penalty), Monthly Bill Sheet (Functional HSC editable, Gross Amount formula). Bill No prefix WSDCP-…; Yearly Factor = 1 always. | ⟳ In Progress
2 | O&M Billing – WSDCP Payment Details | Contract Amount auto-fetched; Variation Order (positive/negative) upload with multiple copies; Final Payment Done (Retrofitting); Total = A+B; All 12 payment fields disabled (No Increment). Yearly Factor = 1 always; O&M Amount of 1st Year from Pro-Rata Date. | ⟳ In Progress
3 | O&M Billing – WSDCP Power Consumption | Approved Banked Units (auto-fetch, disabled); Balance Banked Units (editable numeric, can be zero); Consumed Banked Units: not > Balance Banked Units AND not > Excess Consumption; Balance Banked Units after adjustment. Upload: Sub-meter & Electricity Bills (Intake, IPS, WTP). | ⟳ In Progress
4 | O&M Billing – WSDCP Monthly Bill Sheet | Present HSC removed; Functional HSC editable; V₁ census data; Days × Functional HSC × Rate = Gross Amount. WSDCP Start Date field. RA Bill No prefix WSDCP-…; Contract Amount, Variation, Expenditure Done (A+B+C). Monthly O&M Amount; Per KL O&M Amount W.R.T. WTP Capacity. | ⟳ In Progress
5 | O&M Billing – UFW Report (WSDCP) | UFW Report shown on WSDCP tab but No penalty applied. UFW data sourced from Dhara approved readings. OHT+Village-WTP+Bulk Consumer meters summation formula corrected. | ✓ Done
6 | O&M Billing – Abstract Bill (Landscape) | Abstract Bill PDF changed from portrait to landscape orientation (CR OMB-JUN-2026-004). Auto-generated on Contractor Save & Submit. Linked to selected RA Bill. Included in merged PDF package. | ✓ Done
7 | O&M Billing – Residual Pressure Sheet | Screen columns updated per OM_RA_Bill_Report.pdf: S.No, District, Block, GP, Village, Consumer Name, Mobile, Measured Pressure (meters), Remark, No. Affected HSCs, No. Days, Penalty calculation. Tested with Barwani/Talunkhurd sample data (RA/8/140/2026-27/Q1/25). | ✓ Done
8 | O&M Billing – Complaint Redressal Sheet | Page renamed 'Complaint Redressal Sheet'. New fields: Date complaint received, Date resolved, Total days. 48-hour flag auto-derived. Penalty Relaxation (Yes/No). Front-end date validation. Submeter upload. Is complaint resolved flag. | ✓ Done
9 | O&M Billing – Mandatory Document Upload Gate (Contractor) | Firm Submission Letter and Tax Invoice mandatory before Draft bill can be forwarded to GM PIU (CR OMB-JUN-2026-001). Additional mandatory docs on 'View Bills' page: Firm Letter, Tax Invoice, Any Other (with Remark) (CR OMB-JULY-2026-007). | ✓ Done
10 | O&M Billing – Gross O&M Bill & Net Payable Calculation | Formula: Gross Village Amount = (V₁ Census / Σ Village Census) × (Monthly O&M – Bulk Supply); Net Payable = Gross – UFW Deduction; UFW Deduction = (UFW% – Allowable UFW%) × Gross; Allowable UFW% from Abstract Contract Details. Stored procedures corrected. | ✓ Done
11 | O&M Billing – Bill PDF Merge (19–20 Documents) | Static docs (GM, SQC, Firm, Form 27A, MB, Abstract) × 1 for 3-month bill. Monthly docs (Residual, Complaint, Power, Electricity, Manpower, Bill Sheet) × 3 months. Total ≈ 19–20 docs merged into single PDF. Landscape issue fixed. | ⟳ In Progress
12 | O&M Billing – Multi-Role Workflow (Firm → GM O&M) | Firm → GM PIU → TL(SQC) → GM PIU → GM(O&M) flow: Implemented. Document Upload Hub: Firm docs★, SQC docs★, PIU docs★ all functional. Backward flow from GM PIU → Contractor edit: implemented. | ⟳ In Progress
13 | O&M Billing – Higher Officials Chain (GM O&M → MD) | GM O&M → DGM → TL PMC → CFO → CA → P.D. → MD chain: In Progress. Dropdown Forward-to button with internal/external roles. GM(PIU) check-back. Bill History Timeline sequenced dates. | ⟳ In Progress
14 | O&M Billing – GM/SQC Edit Rights on Bill Data | GM/SQC can Add Remark on Payment Details. Residual/Complaint: Add/Edit by SQC & GM. Power Consumption: Editable by GM/W. Monthly Bill Sheet: Editable Deductions + Remark by GM/SQC. Net Payable: Add More Deduction (Amount + Reason + Document). | ⟳ In Progress
15 | O&M Billing – 'Pending Bills for Review' Rename & UI Changes | Left menu item renamed 'Pending Bills for Review'. Scheme dropdown: 'All' option added. Generation Date + Forwarded Date columns added. GM/SQC Edit button on Manage Bill. Census Population cannot be zero. All villages per Census in denominator. | ⟳ In Progress
16 | O&M Billing – WSDCP Bill Generation Tabs & Current Status | Three tabs on Generate Bill: (1) WSDCP, (2) Trial Run Phase, (3) O&M Billing Phase. Bill Generation Column + Current Status + Stage column. Bill History Timeline (sequence dates). Current Status → Pending with GM(PIU) in 'Review Bills for Approval'. | ⟳ In Progress
17 | O&M Billing – UFW Report on Contractor Login (CR OMB-JULY-2026-006) | UFW Report from Dhara shown on O&M Billing Contractor login page attached with bill. Dhara approved readings integrated. OHT + Village-WTP + Bulk Consumer meters summation formula corrected. | ✓ Done
18 | O&M Billing – Power Consumption: Contract Details + Formula (CR OMB-JULY-2026-008) | Power Consumption tab: Contract Details (Basic Detail + Intermediate Raw Water Demand sections). Formula corrected. Two new columns in Water Supply During Construction Bill. UFW formula update done. | ✓ Done
19 | O&M Billing – GST Number on Bill & Abstract | GST Number field added to Contractor/Firm master profile. GST No. appears on all bill PDFs and Abstract headers. Mandatory before bill finalisation. | ⚠ Open
20 | O&M Billing – Contractor Discrepancy Time-Window (Dhara Data) | Time-bound window for Contractor to review Dhara approved data linked to RA Bill and raise discrepancy before bill finalisation. Dispute raise: remark + optional document. Window expiry locks data. GM resolution logged. | ⟳ In Progress
21 | O&M Billing – LGD Code Integration (LG Directory → MPSQC) | LGD Code fetch from LG Directory for each O&M village. LGD Code column in O&M Village listing and reports. Revenue Portal LGD integration tested. Mismatched LGD codes flagged. | ⟳ In Progress

## All Modules Status
Jal Rekha – All Modules Consolidated Status ¦ August 2026 (Post July MoM Review)
S.No. | Module / Activity | Tasks / Changes / Enhancements | Status
1 | Sahbhagita | Pagination on Sahbhagita approval pages; RA bill routing to ISA; FE scoped to mapped ISA; ISA password reset; Village/Combined Activity abstract with Category filter and RA(1)–RA(12) (CR OMB-JUN-2026-003 / SHB-JUN-2026-004); Abstract of RA Bill UAT defects DEF-01 to DEF-04 fixed; PIU/Scheme binding resolved; Production deployment target 19 Aug 2026 | ⟳ In Progress
2 | Cube Testing | Cube ID before image upload; Rejected data shown to Contractor; Re-inspection Loop (2nd cycle) confirmed stable in production. All June action items Done. | ✓ Prod Stable
3 | Material Testing – Re-Inspection Loop | 2nd cycle loop: API (Contractor, FE, Web multi-login) done; DB changes done; Mobile & Web done; UAT done in local+UAT environment. Production deployment: In Progress (target Aug 2026). Optional image upload on 2nd loop: implemented. | ⟳ In Progress
4 | O&M Billing – June CRs (OMB-JUN-2026-001 to 004) | CR-001: Mandatory doc gate (Submission Letter + Tax Invoice) before forward to GM PIU – Done. CR-002: Complaint Redressal (Received Date, 48-hr flag, Penalty Relaxation) – Done. CR-004: Abstract landscape orientation – Done. All June O&M Billing CRs confirmed stable in production. | ✓ Prod Stable
5 | O&M Billing – July CRs (OMB-JULY-2026-005 to 008) | CR-005: Naming/formatting on all Contractor login pages – Done. CR-006: UFW Report from Dhara on Contractor login – Done. CR-007: Additional mandatory doc upload on 'View Bills' page – Done. CR-008: FHTC & Sahbhagita bug fixes and API updates – Mostly Done; Landscape fix & API updates: In Progress. | ⟳ In Progress
6 | O&M Billing – WSDCP Phase 1 (New Module) | Water Supply During Construction Phase billing (Phase 1): Payment Details, Power Consumption (Banked Units), UFW (no penalty), Monthly Bill Sheet (Functional HSC, Gross Amount formula). UAT in progress – Barwani/Talunkhurd scheme. | ⟳ In Progress
7 | O&M Billing – Workflow (Multi-Role 13-chain) | Firm → GM PIU → TL SQC → GM O&M: implemented. Higher official chain (GM O&M → MD): In Progress. Backward flow: done. GM/SQC edit rights: In Progress. | ⟳ In Progress
8 | Parinam (FHTC) | FE name in Parinam reports: Done (June). Samagra ID multiple survey: UAT Done (July). FHTC API/external API updates (CR OMB-JULY-2026-008): Mostly Done. FamilyMember tap connection changes (20-21 Jul): Done. Color-coded status tags (Accepted/Pending/Rejected): In Progress. | ⟳ In Progress
9 | Vistrit / Dhara | Approved Report data corrected per Kapil Sir review (July): Done. Dhara Meter Survey logic (Functional/Non-Functional/No WS): In Progress. UFW Summation fix (OHT+Village-WTP+Bulk-WTP): Done. Master data entry lock (CR MSTR-JUN-2026-006): Open (design discussion ongoing). | ⟳ In Progress
10 | SVS Water Supply Monitoring | SVS Dashboard V2 wireframe prepared (23 Jul); Department review & suggestions incorporated (29-30 Jul); Har Ghar Jal Yojana DB function developed (31 Jul); Bilingual form complete; NO reason updated; JJM ID removed. Dashboard KPI cards + colour coding + Gram Sachiv + CEO/CO Block login: In Progress (target 19 Aug). | ⟳ In Progress
11 | Nirmal | Beneficiary Report bug: Done. Contractor login counting bug: Done. FE Mobile Nirmal Reports: Done. No new issues in July/August. | ✓ Prod Stable
12 | Sopan | Calendar functionality for 2026-27 on Contractor login (Web & Mobile): UAT Done (July). | ✓ UAT Done
13 | Bharosa Factory Testing | Item Master dropdown duplicate data-entry bug fixed (Web). Factory Testing mobile flow bugs fixed. Production stable. | ✓ Prod Stable
14 | AI Module – FHTC Tap Connection | Initial YOLO model in production. Further FHTC bug-fix and API/external API updates (CR OMB-JULY-2026-008): Mostly Done. Color-coded status tags for Parinam reports: In Progress. | ⟳ In Progress
15 | Anusharavan | 2 new columns in Customised Report and Summary Report (API + Web): Done (22 Jul). UI redesign: Done. Stage updation flow: Done. | ✓ Prod Stable
16 | CMMI L5 – Cycle 4 Closure | Code Review docs (all modules): Done. RCA + Action Plan: Done. SVN updated: Done. Cycle 5 CR Log created: Done. BRTM: In Progress. Release Note: In Progress. Target: Before next MQAS appraisal. | ⟳ In Progress
17 | UI/UX – Full Portal Redesign | Table alignment (39+ files): Done. Print/PDF alignment: Done. Modal popups/button colours/tab navigation/mobile responsiveness across all modules: Done. | ✓ Prod Stable
18 | Dashboard – Public Reports | Main Dashboard redesign: Done. Approved_Village_MWSR.js, Abstract_RA_Bill.js, Abstract_Of_Agreement_Report.js: Done. Public DWSR bug fixes: Done. | ✓ Prod Stable
19 | Daily Inspection | Role-specific report views (SQC/TPIA/Contractor, GM/CGM/TL): Done. Mobile app bug fixes: Done. No new issues in July/August. | ✓ Prod Stable
20 | QA / User & Role Management | Selenium automation scripts (User Login, Registration, TestNG): Done. Automation suite in regular use. Automation review ongoing. | ✓ Prod Stable
21 | Master Data Lock (CR MSTR-JUN-2026-006) | Scheme/Village/OHT Master lock once linked to live transactions: Design discussion ongoing. OTP verification for GM Login Edit/Delete: Pending development. Interim: GM PIU details locked post bill submission. | ⚠ Open
22 | Jal Samadhan – Complaint Queries Module | Complaint queries page for Jal Samadhan: Not started. Timelines and notification design not yet defined. Carry-forward from June/July MoM. Escalated for Sprint 19 planning. | ○ Not Started