Minutes of Meeting

Jal Rekha PREPARED BY — Mr. Dheeraj Motiyani Dated — 16th June 2026

| Date | Version | Description | Prepared by | Reviewed by | Approved By |
| --- | --- | --- | --- | --- | --- |
| 16th June 2026 | 1.0 | Monthly Meeting with MD Sir | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal | Dr. Rakesh Dubey |

| Agenda | Monthly Meeting – June 2026 ¦ Project Status Review |  |  |
| --- | --- | --- | --- |
| Presided By | Mr. Tapan Khandelwal | Start Time | 03:30 PM |
| Location | Jal Nigam, Bhopal | End Time | 06:00 PM |

| Participants | Designation |
| --- | --- |
| Mr. KVS Choudary | MD, Jal Nigam |
| Dr. Rakesh Dubey | Head, MPSSDI |
| Mr. Tapan Khandelwal | Project Manager |
| Mr. Dheeraj Motiyani | Sr. Business Analyst |

SECTION 1 — May 2026 Action Items: Status Review as on 16th June 2026

| S.No. | Module / Activity | Task (May 2026 Discussion Points) | Status as on 16th June 2026 |
| --- | --- | --- | --- |
| 1 | SVS – Har Ghar Jal (GP / PHE Jal Rekha) | - New SVS Water Supply Monitoring module – Gram Panchayat/PHE daily water supply entry (District, Block, GP, Village, No. of Connections, Date of Supply). - Water Supply Status: Yes / No / Partial, with Reason dropdown for 'No' and Partial-supply connection count + remarks. - MP Shashan (Hindi) interface for GP-level users; District/Block/GP pre-filled from user profile. - Remove JJM, village status, and 'hand over to community' fields – not required. | - ✓ Done – Module released; JJM Id & Village status fields removed. - ✓ Done – Login-scoped District/Block/GP auto-populate confirmed. - ✓ Done – Additional 'No Supply' reason option added and spelling corrected. - ✓ Done – Bilingual (Hindi/English) conversion completed for entry page & report column headers. |
| 2 | Dhara – Meter Reading Workflow | - Intake / WTP / OHT–WTP Village Meter Survey re-sequencing (GM Login), aligned with O&M Billing. - Contractor KL Remark/Objection on meter reading – GM Approve/Reject with 3-day auto-approve. - Mohkhed scheme – meter reading replication bug (multiple tapping points, single reading captured). - New Dhara Report shown on all Jal Rekha logins; GM Approved Reports & Contractor Dispute workflow. | - ✓ Done – Meter survey re-sequencing released, aligned with O&M Billing sequence. - ○ In Progress – Approve/Reject routing implemented; auto-approve timer under Approved Report Lock CR (DHARA-MAY-2026-009). - ✓ Done – Mohkhed tapping-point replication bug fixed on priority. - ✓ Done – New Dhara Report live on all logins; GM Approved Reports & Contractor Dispute tracking released. |
| 3 | O&M Billing – Meter Survey Alignment | - O&M Billing GM – Intake/WTP/OHT–WTP Meter Survey aligned with Dhara re-sequencing. - Power Consumption module – Contractor & GM side Generate Bill with Contract Details (Basic, Raw Water, Intermediate demand). - Scheme Status – 2 new columns in Water Supply During Construction Bill. - O&M Villages list finalisation; Contractor discrepancy-raising window; Pump Transformer 10% deduction logic. | - ✓ Done – Meter survey alignment released. - ✓ Done – Power Consumption Contract Details fields live for Contractor & GM. - ✓ Done – 2 new Scheme Status columns added. - ✓ Done – O&M Villages list finalised; discrepancy window and 10% Pump Transformer deduction logic released. |
| 4 | Vistrit / Master | - WTP Meter Mapping – new columns: Date, Scheme, PIU; Meter Name, No. of OHT connections, District, Block, GP. - WTP Meter Name naming convention (e.g. Narela-WTP-01) enforced platform-wide. - SMS integration & OTP authentication on GM Login ID for Vistrit Reports (Scheme/OHT/Bulk Master Edit-Delete). - Scheme Village Mapping – validation on Testing/Permitted fields; Census Population open at all levels. Pipeline Master details & report pages. | - ✓ Done – All new columns added to WTP Meter Mapping & Intake Mapping. - ✓ Done – Naming convention enforced across the platform. - ○ Pending – Re-raised in the 16-Jun review (OTP verification for GM Login on Scheme/OHT/Bulk Master Edit-Delete); not yet delivered. - ✓ Done (validation) – Testing/Permitted field validation live, Census Population open at all levels. Pipeline Master – ○ Pending, not yet released. |
| 5 | Sahbhagita | - Save as Draft for video, images and documents on Sahbhagita Mobile. - Village-wise activity bill linkage with payment system – confirm full end-to-end flow. - RA Bill on CP Manager – post-approval activity billing to be validated with finance team. | - ✓ Done – Save as Draft (video/image/document) live on Sahbhagita Mobile. - ○ In Progress – End-to-end payment linkage validation ongoing. - ✓ Done – RA Bill functionality delivered; subsequently reassigned from CP Manager to ISA Manager login per 16-Jun review to align with the correct approval role. |
| 6 | UI/UX & Portal | - Change Module sequence on portal – finalise new navigation order and deploy. - Grouping and Colour Coding of Left Menu on Jal Rekha portal. - Public Report DWSR – open to public without login. - Material, Cube & Bharosa Reports on web (CGM, PMU user IDs) – post-enablement validation. | - ✓ Done – Module sequence change released. - ○ Pending – Grouping/colour-coding of left menu not yet released. - ✓ Done – Public DWSR report opened to public access. - ✓ Done – Material, Cube & Bharosa reports enabled on Jal Rekha web for CGM/PMU IDs. |
| 7 | Jal Samadhan | - Complaint related queries page for Jal Samadhan – development and UAT. - Complaint tracking with status view for public users and GM login. - SLA-based escalation workflow to PIU. | - □ Not Done – No progress reported this cycle; follow-up required with the Jal Samadhan team. - □ Not Done – Pending. - □ Not Done – Pending; timelines and notification design yet to be defined. |
| 8 | Issues / Cross-Module | - Sujalam Bharat App (BISAG/Gati Shakti) – Master data still pending from Jal Nigam. - Anusharavan RFI Pull Back & Reassign Option for GM PIU. - Abstract of Anusharavan at Contractor mobile login. - No Water Supply = 0 KL & Meter Not Functional = 'X KL' – display consistency across all logins. | - □ Not Done – Still awaiting master data from Jal Nigam; escalation ongoing. - ○ Pending – Not yet taken up; to be prioritised. - ○ Pending – Design not yet finalised. - ○ Pending – Consistency check not yet completed across all login types. |

SECTION 2 — June 2026 New Discussion Points & Action Items

| S.No. | Module / Activity | Details / Discussion Points | Status |
| --- | --- | --- | --- |
| 1 | Sahbhagita | - Pagination introduced on Sahbhagita approval pages for easier review. - RA bill routing changed – now goes to ISA (Implementation Support Agency) instead of CP Manager. - Field Executives (FE) now scoped and visible only to their specifically mapped ISA. - Self-service password reset option added for ISA login. - Village-wise / Combined Activity abstract report with Category filter (Village / Combined / All) and quarterly RA Bill numbering RA(1)–RA(12) on the abstract header (CR OMB-JUN-2026-003 / SHB-JUN-2026-004). | ✓ Done (Cat. filter report – ○ In Progress) |
| 2 | Cube Testing | - Cube ID now generated before image upload, so a failed/slow upload no longer blocks record creation. - Rejected inspection data is now shown back to the Contractor login for correction and resubmission (CR CUBE-JUN-2026-005). | ✓ Done |
| 3 | O&M Billing | - Mandatory document upload (Firm Submission Letter, Tax Invoice) gate added before a bill can move out of Draft and be forwarded to GM PIU (CR OMB-JUN-2026-001). - Residual Pressure report reformatted to the OM_RA_Bill_Report.pdf column layout; Complaint Redressal screen relabeled with resolution status (CR OMB-MAY-2026-020). - Complaint Redressal – Complaint Received Date, auto Event-above-48-hours flag, and Penalty Relaxation (Yes/No) field with document upload added (CR OMB-JUN-2026-002). | ✓ Done |
| 4 | Master Data | - Proposal to lock Scheme Master, Village Master and OHT Master entries once linked to live Dhara/O&M Billing/Asset Mapping transactions, to protect billing data integrity (CR MSTR-JUN-2026-006). - Master Change Requests and enhancements reviewed on 9-Jun and 11-Jun – search/debug fixes on the Dhara Mapped Summary report used in Abstract generation. | ○ Open / In Progress |
| 5 | Parinam (HSC / FHTC) | - Field Executive (FE) name now shown against records in Parinam reports for attribution and follow-up. | ✓ Done |
| 6 | Nirmal (New Module Discussion) | - Beneficiary Report data issue identified and fixed. - Contractor Login report-counting bug fixed in production. - FE Mobile Nirmal Reports validated and related bugs fixed. - Test scenarios and test cases documented for the Nirmal Change Request for future regression coverage. | ✓ Done |
| 7 | AI Module – FHTC Tap Connection Detection | - Machine-learning predictive model (YOLO-based) built for tap and person detection on FHTC connection photos, with blur-robust fine-tuning for field-quality images. - Buffer-region validation implemented using an LLM-assisted identification approach with an integrated pretrained human-detection model; model retrained iteratively. - Data processing and model training pipeline (YOLOv8-based tap identification) established for ongoing retraining cycles. | ✓ Done (initial model) |
| 8 | Daily Inspection | - Daily Inspection Report module modified for role-specific views: SQC/TPIA/Contractor and GM/CGM/TL. - Identified bugs in the Daily Inspection mobile app fixed. | ✓ Done |
| 9 | QA / User & Role Management | - Automated Selenium scripts developed for User Login and User Registration flows (TestNG framework) to support faster regression testing. - Recurring internal review process established for automation-testing coverage and defect tracking. | ✓ Done |

| Prepared by: Mr. Dheeraj Motiyani, Sr. BA | Reviewed by: Mr. Tapan Khandelwal, PM ¦ Approved by: Dr. Rakesh Dubey |
| --- | --- |