## Cycle 1
Requirement Review
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
S.no. | Requirement Review | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Requirement Review Defects | Recommendation of Review | Compliance Status | Date
1 | Yes | Jal Rekha | Dhara | Admin | BA Team | Development Team | 1 | Refine meter registration and bulk upload validations; update error messages. | Complied
2 | Yes | Jal Rekha | Dhara | GM PIU User | BA Team | Development Team | 1 | Clarify GM responsibilities for mapping, approval, and delete rights in use‑case flows. | Complied
3 | Yes | Jal Rekha | Dhara | Change Request – GM PIU | BA Team | Development Team | 1 | Freeze drill‑down hierarchy and reading‑change rules; update CR specification. | Complied
4 | Yes | Jal Rekha | Dhara | TL | BA Team | Development Team | 1 | Distinguish TL edit vs. approve behaviour and escalation scenarios. | Complied
5 | No | Jal Rekha | Dhara | Change Request – TL | BA Team | Development Team | 0 | Existing description adequate; no change required. | Not Applicable
6 | Yes | Jal Rekha | Dhara | FE / Mobile User | BA Team | Development Team | 1 | Detail offline sync rules and mandatory photo capture conditions. | Complied
7 | Yes | Jal Rekha | Dhara | Contractor Report View | BA Team | Development Team | 1 | Align contractor report filters with GM reports; document access control. | Complied
8 | No | Jal Rekha | Master | GM | BA Team | Development Team | 0 | Master‑data responsibilities already clearly defined. | Not Applicable
9 | Yes | Jal Rekha | Master | All Web Reports | BA Team | Development Team | 1 | Specify refresh frequency and drill‑down navigation for CWGM/CWPM/RWPM. | Complied
10 | No | Jal Rekha | Master | Contractor | BA Team | Development Team | 0 | No ambiguity found in pipeline master RFI flow. | Not Applicable
11 | No | Jal Rekha | Master | FE Mobile | BA Team | Development Team | 0 | Existing FE mobile RFI requirement accepted as‑is. | Not Applicable
12 | No | Jal Rekha | Master | Change Request – Master | BA Team | Development Team | 0 | Schema/mobile anusharan CR description sufficient. | Not Applicable
13 | Yes | Jal Rekha | Nirmal | FE Mobile | BA Team | Development Team | 1 | Clarify geofence rules, offline submission, and sample‑type tagging. | Complied
14 | Yes | Jal Rekha | Nirmal | Contractor Login | BA Team | Development Team | 1 | Define status transitions from “Sample Collected” to “Report Submitted”. | Complied
15 | No | Jal Rekha | Nirmal | GM | BA Team | Development Team | 0 | GM view‑only defect dashboard already clear. | Not Applicable
16 | Yes | Jal Rekha | Nirmal | Change Request – Nirmal | BA Team | Development Team | 1 | Tighten parameter list and mobile change scope; add impact note for Dhara linkages. | Complied
17 | Yes | Jal Rekha | Sahbhagita | GM | BA Team | Development Team | 1 | Specify mapping constraints for PM–scheme relationships. | Complied
18 | No | Jal Rekha | Sahbhagita | PM | BA Team | Development Team | 0 | Report view requirement is straightforward; no action. | Not Applicable
19 | No | Jal Rekha | Sahbhagita | FE | BA Team | Development Team | 0 | Activity capture flow already detailed in BRD. | Not Applicable
20 | Yes | Jal Rekha | Sopan | Contractor | BA Team | Development Team | 1 | Clarify stage definitions and dependencies for plan start/end dates. | Complied
21 | No | Jal Rekha | Sopan | GM | BA Team | Development Team | 0 | GM freeze and actual‑date responsibilities already clear. | Not Applicable
22 | Yes | Jal Rekha | Sopan | Sopan Document Upload & Chat | BA Team | Development Team | 1 | Add limits for document size/types and chat retention policy. | Complied
23 | Yes | Jal Rekha | Sopan | All Web User | BA Team | Development Team | 1 | Clarify which roles can see OHT/WTP/Intake monitoring dashboards. | Complied

## Cycle 2
Requirement Review
Project Name:
Date Updated On:
Manager | Ensure the Work to be done
S.no. | Requirement Review | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Requirement Review Defects | Recommendation of Review | Compliance Status | Date
1 | Yes | Jal Rekha | FHTC | FE / Reports | BA Team | Development Team | 1 | Clarify FE report filters, pagination, and export behaviour; update SRS. | Complied | 05-11-2025 ​
2 | Yes | Jal Rekha | FHTC | Change Request FHTC | BA Team | Development Team | 1 | Document impact of GM/Contractor report changes and SQL fixes; add regression scope. | Complied | 07-11-2025 ​
3 | Yes | Jal Rekha | O&M Billing | GM | BA Team | Development Team | 1 | Refine GM access rules for PIU/contractor mapping and agreement value fields. | Complied | 10-11-2025 ​
4 | Yes | Jal Rekha | O&M Billing | Contractor | BA Team | Development Team | 1 | Specify contractor billing validations, mandatory documents, and CPI calculation cases. | Complied | 12-11-2025 ​
5 | Yes | Jal Rekha | O&M Billing | Workflow b/w O&M GM & Higher officials | BA Team | Development Team | 1 | Add swim‑lane description for approval workflow and notification triggers. | Complied | 14-11-2025 ​
6 | No | Jal Rekha | O&M Billing | Change Request O&M Billing | BA Team | Development Team | 0 | CR text already clear for scope and reports; no change required. | Not Applicable | 14-11-2025 ​
7 | Yes | Jal Rekha | Bharosa | Factory Testing Web | BA Team | Development Team | 1 | Detail negative scenarios for failed tests and partial lot approvals. | Complied | 18-11-2025 ​
8 | No | Jal Rekha | Bharosa | Factory Testing Mobile | BA Team | Development Team | 0 | Mobile scope matches web flows; no additional clarification needed. | Not Applicable | 18-11-2025 ​
9 | Yes | Jal Rekha | Dhara Rework | Change Request – GM PIU User / TL | BA Team | Development Team | 1 | Separate GM vs TL permissions on reading change and drill‑down actions. | Complied | 22-11-2025 ​
10 | Yes | Jal Rekha | Dhara Rework | Change Request – FE / Mobile User | BA Team | Development Team | 2 | Tighten offline‑sync rules and image handling; describe meter‑status transitions. | Complied | 24-11-2025 ​
11 | Yes | Jal Rekha | Dhara Rework | Change Request – Admin / Contractor Report View | BA Team | Development Team | 1 | Align contractor report access with admin dashboards and security roles. | Complied | 26-11-2025 ​
12 | No | Jal Rekha | Master | Change Request – GM / Contractor | BA Team | Development Team | 0 | Master CR description is sufficient for scheme–component changes. | Not Applicable | 26-11-2025 ​
13 | Yes | Jal Rekha | Master | Change Request – FE Pipeline Mater | BA Team | Development Team | 1 | Clarify FE responsibilities for pipeline data capture and error correction. | Complied | 28-11-2025 ​
14 | No | Jal Rekha | Nirmal | Change request – WTP, OHT Report | BA Team | Development Team | 0 | WTP/OHT report parameters already well detailed. | Not Applicable | 30-11-2025 ​
15 | Yes | Jal Rekha | Nirmal | Change Request – Beneficiary Report | BA Team | Development Team | 1 | Document mapping between lab parameters and beneficiary‑level drill‑downs. | Complied | 02-12-2025 ​
16 | Yes | Jal Rekha | Sahbhagita | Sahbhagita Reports | BA Team | Development Team | 1 | Clarify video size/format constraints and survey‑status counters. | Complied | 05-12-2025 ​
17 | No | Jal Rekha | Sahbhagita | Change Request – GM / PM | BA Team | Development Team | 0 | GM/PM report view requirement accepted as‑is. | Not Applicable | 05-12-2025 ​
18 | Yes | Jal Rekha | Sopan | Change Request – Contractor (Web / Mobile) | BA Team | Development Team | 1 | Define stage list, dependencies, and mandatory plan dates per asset type. | Complied | 08-12-2025 ​
19 | Yes | Jal Rekha | Sopan | Change Request – GM Document Upload & Reports | BA Team | Development Team | 1 | Add document type/size rules and clarify GM review/approval flow for uploads. | Complied | 10-12-2025 ​

## Cycle 3
Requirement Review
Project Name: | [8 empty] | 24 total
Date Updated On:
Manager | Ensure the Work to be done
S.no. | Requirement Review | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Requirement Review Defects | Recommendation of Review | Compliance Status | Date
1 | Yes | Jal Rekha | Anusharavaan | RFI Stage Updations and Reports Modifications | BA Team | Development Team | 1 | Refine RFI stage definitions, status transitions, and report filters; update workflow diagrams. | Complied | 05-01-2026 ​
2 | Yes | Jal Rekha | Bharosa CR | Factory Testing Web | BA Team | Development Team | 2 | Detail multi‑sample handling, retest logic, and negative test‑case coverage for web screens. | Complied | 06-01-2026 ​
3 | Yes | Jal Rekha | Bharosa CR | Factory Testing Mobile | BA Team | Development Team | 1 | Clarify offline capture, photo attachment, and sync behaviour for mobile testing. | Complied | 07-01-2026 ​
4 | Yes | Jal Rekha | Bharosa CR | CR – Report View | BA Team | Development Team | 1 | Specify factory‑testing summary/report drill‑downs and role‑based visibility. | Complied | 08-01-2026 ​
5 | Yes | Jal Rekha | Material Testing | GM/Contractor Login | BA Team | Development Team | 2 | Distinguish GM vs Contractor permissions for sample approval, rejection, and comments. | Complied | 09-01-2026 ​
6 | Yes | Jal Rekha | Material Testing | FE Login | BA Team | Development Team | 1 | Detail FE responsibilities for capturing lab results and attaching certificates. | Complied | 10-01-2026 ​
7 | Yes | Jal Rekha | FHTC | GM / Contractor Reports | BA Team | Development Team | 1 | Align report fields with latest CR (Samagra, scheme mapping) and clarify filters. | Complied | 11-01-2026 ​
8 | No | Jal Rekha | FHTC | CR – FE / Reports | BA Team | Development Team | 0 | FE report CR already precise; no additional clarification needed. | Not Applicable | 11-01-2026 ​
9 | Yes | Jal Rekha | O&M Billing | Change Request GM | BA Team | Development Team | 1 | Reconfirm GM edit rights, scheme change behaviour, and SLA constraints. | Complied | 12-01-2026 ​
10 | Yes | Jal Rekha | O&M Billing | Change Request Contractor | BA Team | Development Team | 1 | Tighten description of CPI base year logic, penalty relaxation, and document uploads. | Complied | 13-01-2026 ​
11 | Yes | Jal Rekha | O&M Billing | Security Vulnerability – Sonarcube & SVN | BA Team | Development Team | 1 | Map each security finding to specific modules and confirm sanitization approach. | Complied | 14-01-2026 ​
12 | Yes | Jal Rekha | Dhara CR | Change Request – Dhara Reports | BA Team | Development Team | 1 | Clarify scope for redesigned Dhara reports (DWSR, MWSR, village‑wise, bulk, UFW). | Complied | 15-01-2026 ​
13 | Yes | Jal Rekha | Dhara CR | Security Vulnerability – Sonarcube & SVN | BA Team | Development Team | 2 | Document JS/SQL hardening for Dhara pages and regression testing approach. | Complied | 16-01-2026 ​
14 | Yes | Jal Rekha | Nirmal | Change request – WTP, OHT, Beneficiary Report | BA Team | Development Team | 2 | Expand parameter list, drill‑down behaviour, and inline‑query migration notes. | Complied | 17-01-2026 ​
15 | Yes | Jal Rekha | Nirmal | Change Request – Raw water Report | BA Team | Development Team | 1 | Define date‑range, sample‑ID search, and pass/fail drill‑down criteria. | Complied | 18-01-2026 ​
16 | Yes | Jal Rekha | Sahbhagita | Sahbhagita Reports | BA Team | Development Team | 1 | Reconfirm NGO summary KPIs, video handling, and district/village dropdown logic. | Complied | 19-01-2026 ​
17 | Yes | Jal Rekha | Sahbhagita | Change Request – GM / PM | BA Team | Development Team | 1 | Clarify PIU → Scheme → ISA → Village dependency and PM dashboard expectations. | Complied | 20-01-2026 ​
18 | Yes | Jal Rekha | CMMI Doc | Documentation | QA Lead | BA Team | 2 | Ensure CR lifecycle, review checklists, and traceability matrices meet CMMI L5 expectations. | Complied | 22-01-2026 ​
19 | Yes | Jal Rekha | Bharosa / Anusharavan RFI – Cube Testing | Cube Testing Requirement & Sanitization | QA Lead | Development Team | 2 | Detail cube‑testing data sets, XSS/SQL‑injection checks, and acceptance criteria. | Complied | 24-01-2026 ​

## Cycle 4
Requirement Review
Project Name: |  | Jal Rekha | [6 empty] | 22 total
Date Updated On: |  | 30-05-2026
Manager | Ensure the Work to be done
S.no. | Requirement Review | Project Name | Module | Name of Sub Modules | Reviewer Name | Name of Developer | Requirement Review Defects | Recommendation of Review | Compliance Status | Date
1 | Yes | Jal Rekha | Anusharavaan | RFI New Stages & Reports | BA Team | Development Team | 1 | Refine new RFI stage sequence, status labels, and notification triggers; update stage-transition diagram. | Complied | 02-02-2026
2 | No | Jal Rekha | Anusharavaan | CR - RFI Stage Updations and Reports Modifications | BA Team | Development Team | 0 | CR description and report-modification scope already clear; no change required. | Not Applicable | 03-02-2026
3 | No | Jal Rekha | Asset Mapping | Asset data Map | BA Team | Development Team | 0 | Asset mapping data model and field-survey correction flow already well documented. | Not Applicable | 04-02-2026
4 | No | Jal Rekha | Bharosa CR | Factory Testing Web | BA Team | Development Team | 0 | Multi-document upload and inner-page redesign scope already adequately specified. | Not Applicable | 05-02-2026
5 | No | Jal Rekha | Bharosa CR | CR - Factory Testing Mobile | BA Team | Development Team | 0 | QAP download and contractor mobile login requirement accepted as-is; no further clarification needed. | Not Applicable | 06-02-2026
6 | Yes | Jal Rekha | Cube Testing | Contractor Login | BA Team | Development Team | 1 | Clarify Contractor inspection-creation flow, RFI sample-day logic (7-day/28-day), and submission validations. | Complied | 09-02-2026
7 | Yes | Jal Rekha | Cube Testing | FE Login | BA Team | Development Team | 2 | Detail FE wireframe screens, cube sample data capture rules, and mandatory photo/document attachment; expand mobile sync scope. | Complied | 10-02-2026
8 | Yes | Jal Rekha | Cube Testing | GM - SQC - TPIA - CR | BA Team | Development Team | 1 | Specify GM RFI status update flow, SQC/TPIA read-only access scope, and database schema/Master design dependencies for the new module. | Complied | 11-02-2026
9 | No | Jal Rekha | Dhara | Dhara Change Request - GM PIU User/TL | BA Team | Development Team | 0 | Intake/WTP/OHT meter survey re-sequencing and GM PIU freeze logic already clear; no additional clarification needed. | Not Applicable | 12-02-2026
10 | No | Jal Rekha | Dhara | Dhara CR - Reports (MWSR,DWSR,UFW) | BA Team | Development Team | 0 | Report redesign scope (DWSR, MWSR, Bulk Consumer, UFW) already adequately defined from Cycle 3 carry-forward. | Not Applicable | 13-02-2026
11 | No | Jal Rekha | Dhara | CR - All Reports Public / Site Security Audit | BA Team | Development Team | 0 | Public report exposure rules and security-audit remediation scope already documented and verified. | Not Applicable | 14-02-2026
12 | Yes | Jal Rekha | FHTC | Change Request FHTC | BA Team | Development Team | 1 | Clarify FHTC Loop (re-inspection) functionality, geo-fencing buffer parameters, and AI/ML validation acceptance criteria. | Complied | 17-05-2026
13 | Yes | Jal Rekha | FHTC | GM - Contractor - Reports | BA Team | Development Team | 1 | Define GM/Contractor report drill-down fields and Connection/Work-Done/Payment stage-linkage rules. | Complied | 18-02-2026
14 | No | Jal Rekha | Master | Change Request | BA Team | Development Team | 0 | Scheme Village/OHT Master validation rules and Bulk Consumer CRUD scope already sufficiently detailed. | Not Applicable | 19-02-2026
15 | Yes | Jal Rekha | Material | FE Login | BA Team | Development Team | 1 | Clarify FE mobile API integration, OHT search behaviour, and Save-as-Draft photo-upload sequencing. | Complied | 20-03-2026
16 | Yes | Jal Rekha | Material | GM login | BA Team | Development Team | 1 | Detail GM/Contractor sample approval-rejection flow, SQC/TPIA routing, and customised report drill-down scope. | Complied | 23-03-2026
17 | No | Jal Rekha | Nirmal | CR | BA Team | Development Team | 0 | FE mobile report and water-quality test changes already clearly specified; no additional clarification needed. | Not Applicable | 24-03-2026
18 | Yes | Jal Rekha | O&M | CR - GM | BA Team | Development Team | 1 | Clarify Intake/WTP/OHT meter survey re-sequencing alignment with Dhara and Power Consumption bill calculation logic. | Complied | 25-04-2026
19 | Yes | Jal Rekha | O&M | CR - Contractor | BA Team | Development Team | 1 | Define contractor-side Summary Page, Net Payable Bill calculation, and Final Bill Submission validation rules. | Complied | 26-04-2026
20 | Yes | Jal Rekha | O&M | Workflow | BA Team | Development Team | 1 | Add swim-lane description for O&M GM → Higher Officials escalation workflow and SLA-based auto-routing triggers. | Complied | 27-05-2026
21 | No | Jal Rekha | Sahbhagita | Change Request -GM PM Reports | BA Team | Development Team | 0 | ISA payment tracking and CR Manager approval-step scope already adequately documented. | Not Applicable | 02-03-2026
22 | No | Jal Rekha | SVS | Water Supply Monitoring | BA Team | Development Team | 0 | GP/PHE daily water-supply form fields, Yes/No/Partial status logic, and reason-code dropdown already clearly specified. | Not Applicable | 19-05-2026