## Sheet1
Problem Statement | Source of Problem | Why 1 | Why 2 | Why 3 | Why 4 | Why 5 | Correction (immidiate Fix) | Corrective Action (Preventive actions) | Responsibility | Action Items | Target Date | Actual Status | Closure Date | Remarks
Code rate for the Water Supply Monitoring module is below the planned target, resulting in an outlier in PPM productivity. | Requirement discussions, external data dependency, and additional non-development activities | Why was the code rate lower than planned? → Because a significant amount of effort was spent on requirement discussions, meetings, API finalization, documentation, and data validation activities instead of coding. | Why was additional effort required for discussions and validation? → Because the Water Supply Monitoring module was a new module involving multiple stakeholders and external integrations with NIC and Village Master data. | Why did external integration consume additional effort? → Because GP Codes and master data shared by NIC did not match the Jal Rekha Master data, requiring analysis and repeated validations. | Why were repeated validations required? → Because there was no predefined data mapping and reconciliation process between NIC data and Jal Rekha master data. | Why was the reconciliation process not available? → Because data governance and master data synchronization mechanisms were not established during the initial project planning phase. | Prioritized GP code mapping activity, coordinated with NIC for data clarification, and completed required validations before proceeding with development. | Establish a standard data reconciliation process, finalize master data before development, and allocate separate effort for requirement discussions, security activities, and external dependency management in project estimation. | Project Manager / Development Team / NIC Team / BA Team | 1. Define data reconciliation process with NIC. 2. Freeze master data before development starts. 3. Maintain a dependency tracker for external APIs and data. 4. Include meeting and security activities in effort estimation. 5. Create a standard data mapping document. |  |  |  | Lower code rate was primarily due to requirement discussions, external data dependencies, and additional non-coding activities rather than development inefficiency.
Test Cycle Time exceeded the planned timeline for the Material Testing FE Login module. | Multiple testing cycles, real-time change requests from field surveys, production issues, and mobile app deployment activities. | Why did the Test Cycle Time exceed the planned timeline? → Because multiple rounds of testing, regression testing, production validation, and Play Store deployment activities were required. | Why were multiple testing rounds required? → Because defects and new requirements were identified during production validation and actual field surveys conducted by Fes | Why did new requirements emerge during field surveys? → Because certain business scenarios and practical field conditions were not identified during the initial requirement gathering and design phase. | Why were all field scenarios not identified initially? → Because the actual survey process and ground-level challenges became evident only when FEs started conducting inspections in real environments | Why were ground-level scenarios not considered during planning and estimation? → Because field validation and pilot testing with end users were not performed before finalizing requirements and test scenarios. | Prioritized change requests and defect fixes, completed regression testing, and validated all new scenarios identified during field surveys before deployment. | Conduct field validation and pilot testing before finalizing requirements, include production-like scenarios in test planning, prepare detailed end-to-end test cases, and allocate buffer for change requests and regression activities in estimation | QA Team / Development Team / Business Analyst / Release Team | 1. Conduct pilot testing with FE before finalizing requirements. 2. Include field survey scenarios in requirement documents and test cases. 3. Maintain a regression checklist for mobile releases. 4. Conduct integration testing before Play Store deployment. 5. Allocate contingency effort for field-driven change requests and production validation. |  |  |  | Increased Test Cycle Time was primarily due to real-time requirement changes identified during field surveys, multiple testing cycles, production validation, and regression activities after implementing change requests and defect fixes..
Code Review Defect identified in the Anushravan module, impacting the DRE (Code Review per Size) metric. | Requirement Change and Incomplete Analysis of Ground-Level Scenarios During Development | Why was the defect identified during code review? → Because two RFI IDs were generated for the same village when multiple OHTs existed in a single village. | Why were two RFI IDs generated? → Because the application was designed considering that one village would have only one OHT, as per the initial requirement received from Jal Nigam. | Why did the application design not support multiple OHTs in the same village? → Because the scenario of having more than one OHT in a village was not identified during requirement gathering and design discussions. | Why was this scenario not identified earlier? → Because actual field configurations and exceptions were not validated with ground data before implementation. | Why was ground-level validation not performed? → Because there was no process to verify business assumptions and field scenarios before finalizing the design and unique identification logic. | Modified the application logic to use OHT UID as the unique identifier instead of the village, and performed regression testing for all RFI creation scenarios. | Conduct field validation before finalizing requirements, document exceptional scenarios, and perform impact analysis whenever master data assumptions change. | Development Team / Business Analyst / QA Team | 1. Validate business assumptions with field data before development. 2. Document exceptional scenarios such as multiple OHTs in a village. 3. Include field configuration scenarios in design and code review checklists. 4. Perform impact analysis for requirement changes. 5. Add regression test cases for multi-OHT scenarios. |  |  |  | The defect occurred due to an incorrect business assumption that one village would always have one OHT. The identification logic has been revised to use OHT UID to support multiple OHTs within the same village.