## Sheet1
Problem Statement | Source of Problem | Why 1 | Why 2 | Why 3 | Why 4 | Why 5 | Correction (immidiate Fix) | Corrective Action (Preventive actions) | Responsibility | Action Items | Target Date | Actual Status | Closure Date | Remarks
The document uploaded by the FE is not visible to the GM on the web. The FE Survey Report column appears blank when an image is uploaded; however, if the FE uploads a PDF document, it is visible. | Validation mismatch between Mobile and Web document handling. | Uploaded files are not displayed on the GM web portal | The web application only supports predefined image formats (JPG, PNG) and PDF documents for display. | The mobile application allows uploading additional file formats that are not supported by the web application. | File validation rules were implemented separately in Mobile and Web without a common validation standard. | Cross-platform file compatibility requirements and test scenarios were not defined during design, development, and UAT phases. | Restrict unsupported file types in the mobile application and update the web application to handle approved file formats consistently | Define a common file upload specification for all platforms; implement API-level validation as a single source of truth; add cross-platform upload/download test cases to SIT, UAT, and regression suites. | Mobile Team, Web Team, Backend/API Team, QA Team | 1. Publish supported file format matrix. 2. Implement centralized API validation. 3. Synchronize Mobile and Web validation rules. 4. Add production readiness checklist for file upload features. 5. Add cross-platform compatibility test cases.
Cube Testing (Web): After FE survey, the RFI sequence is not displayed correctly on the UI. Once the 7-day RFI is completed, RFIs with images are displayed below the 28-day RFI instead of following the expected sequence. | RFI workflow enhancement (7-day & 28-day survey flow). | The UI displayed RFIs in an incorrect sequence after completion of the 7-day survey | The sequence logic was not updated to handle the newly introduced 7-day and 28-day survey workflow. | Existing UI logic was designed for a single RFI flow and did not consider multiple survey stages. | The workflow enhancement introduced additional survey stages but corresponding display rules were not updated. | End-to-end workflow impact analysis and regression testing were not performed for the new 7-day and 28-day survey process. | Update UI sequence logic to display RFIs according to workflow stage order (Initial → 7-day → 28-day). | Perform workflow impact assessment for all future enhancements; add UI sequence validation scenarios in SIT/UAT and regression testing. | Frontend Developer, QA Team, Business Analyst | Update sequence logic, verify workflow ordering, execute regression testing for all RFI stages.
Web GM Login →After GM adds remarks and accepts the RFI, the status still shows as "Pending" instead of being frozen after both 7-day and 28-day remarks are added and accepted. | RFI workflow enhancement (7-day & 28-day survey flow). | The RFI status remained "Pending" even after GM completed the approval process. | The workflow status flag was not updated after acceptance of 7-day and 28-day reviews. | Status transition logic was not modified to support the newly introduced survey workflow stages. | Existing workflow was designed for a simpler approval process and did not account for additional review stages. | End-to-end workflow impact analysis and regression testing were not performed for the new 7-day and 28-day survey process. | Update status flag logic to freeze RFIs and change status after final approval/rejection action. | Maintain workflow transition matrix; validate all status transitions during SIT/UAT; include complete approval lifecycle scenarios in regression suite. | Backend Developer, QA Team, Business Analyst | Fix status flag update logic, verify freeze functionality, execute workflow regression testing, update requirement traceability matrix.