## Sheet1
Total Bugs Reported
Date & Time: June 8, 2026 at 02:16:56 PM
Sr No | Project | Bug Id | Bug Type | Entry Date | Bug Title | Status | Severity | Priority | Assignee | Reporter | Sprint | Module Name | Activity Name | Phase Detected | Defect Type | Phase Injected
1 | Jal Rekha | 19770 | Bug | 22/01/2026 | Tap Photo Upload Not Persisted / Corrupt on Server | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | FHTC (Functional Household Tap Connection) FE Reports | SIT Testing | Testing | Functional | Development
2 | Jal Rekha | 19785 | Bug | 22/01/2026 | Reject Routing Not Delivered to Contractor | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | FHTC (Functional Household Tap Connection) FE Reports | SIT Testing | UAT | Functional | UAT
3 | Jal Rekha | 19787 | Bug | 22/01/2026 | Accept Routing Misrouted / Duplicate Notifications | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | FHTC (Functional Household Tap Connection) FE Reports | UAT/Prod/CR Testing | UAT | Functional | UAT
4 | Jal Rekha | 19789 | Bug | 22/01/2026 | HSC Report Missing Mandatory Photo Flag / Export Incomplete | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | FHTC (Functional Household Tap Connection) FE Reports | UAT/Prod/CR Testing | Production | Functional | Production
5 | Jal Rekha | 19791 | Bug | 22/01/2026 | O&M Billing>GM>Contract details>Advance details | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | O&M Billing GM | SIT Testing | Testing | Cosmetic | Testing
6 | Jal Rekha | 19792 | Bug | 22/01/2026 | O&M Billing >GM Login >Contract Details | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | O&M Billing GM | SIT Testing | Testing | Functional | Testing
7 | Jal Rekha | 19793 | Bug | 22/01/2026 | O&M Billing>Contractor Login > Generate Bill > Residual Pressure > Measured Pressure | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | O&M Billing GM | SIT Testing | Testing | Functional | Testing
8 | Jal Rekha | 19794 | Bug | 22/01/2026 | O&M Billing>Contractor Login > Generate Bill > O&M Bill | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | O&M Billing GM | SIT Testing | Testing | Functional | Testing
9 | Jal Rekha | 19796 | Bug | 22/01/2026 | In correct pop-up message is displaying after adding Census population data. | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | O&M Billing GM | UAT/Prod/CR Testing | UAT | Functional | UAT
10 | Jal Rekha | 19797 | Bug | 22/01/2026 | User is able to delete census population record even after save and next | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | O&M Billing GM | UAT/Prod/CR Testing | UAT | Functional | UAT
11 | Jal Rekha | 19798 | Bug | 22/01/2026 | Pop-up message displaying after clicking on save and next from basic details, needs to be changed | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | O&M Billing GM | UAT/Prod/CR Testing | UAT | Functional | UAT
12 | Jal Rekha | 19800 | Bug | 22/01/2026 | New Vendor Not Appearing After Addition | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Bharosa Factory Testing - Web | SIT Testing | Testing | Functional | Testing
13 | Jal Rekha | 19801 | Bug | 22/01/2026 | Sub-Component Dropdown Not Filtering After Component Selection | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Bharosa Factory Testing - Web | SIT Testing | Testing | Functional | Testing
14 | Jal Rekha | 19804 | Bug | 22/01/2026 | Video File Upload Not Supported Though Spec Allows It | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Bharosa Factory Testing - Web | UAT/Prod/CR Testing | UAT | Functional | UAT
15 | Jal Rekha | 19806 | Bug | 22/01/2026 | Report Export Missing Newly Added Fields | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Bharosa Factory Testing - Web | UAT/Prod/CR Testing | UAT | Functional | UAT
16 | Jal Rekha | 19813 | Bug | 22/01/2026 | Habitation-to-OHT Mapping Not Being Saved | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | SIT Testing | Testing | Functional | Testing
17 | Jal Rekha | 19815 | Bug | 22/01/2026 | FE Mobile App Not Receiving Assigned Habitations | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | SIT Testing | Testing | Functional | Testing
18 | Jal Rekha | 19816 | Bug | 22/01/2026 | Intake Meter Survey Update Not Saving | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | SIT Testing | Testing | Functional | Testing
19 | Jal Rekha | 19817 | Bug | 22/01/2026 | Updated OHT Readings Not Reflected in Reports | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | SIT Testing | Testing | Functional | Testing
20 | Jal Rekha | 19818 | Bug | 22/01/2026 | Intake Reading Modification Not Saving Changes | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | UAT/Prod/CR Testing | UAT | Functional | UAT
21 | Jal Rekha | 19819 | Bug | 22/01/2026 | OHT Count in Drill-Down Does Not Match Actual Data | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | UAT/Prod/CR Testing | UAT | Functional | UAT
22 | Jal Rekha | 19820 | Bug | 22/01/2026 | WTP Reading Modification Incorrectly Fails Validation | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | UAT/Prod/CR Testing | UAT | Functional | UAT
23 | Jal Rekha | 19821 | Bug | 22/01/2026 | FE Not Receiving Assigned Habitation Tasks | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | UAT/Prod/CR Testing | Production | Functional | Production
24 | Jal Rekha | 19822 | Bug | 22/01/2026 | Full Village List Not Loading for OHT Mapping | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | UAT/Prod/CR Testing | Production | Functional | Production
25 | Jal Rekha | 19823 | Bug | 22/01/2026 | Meter Status Update (Functional / Not Functional / Replace) Not Saving | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | UAT/Prod/CR Testing | Production | Functional | Production
26 | Jal Rekha | 19824 | Bug | 22/01/2026 | Bulk Meter PDF/Document Upload Not Working | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | UAT/Prod/CR Testing | Production | Functional | Production
27 | Jal Rekha | 19830 | Bug | 22/01/2026 | Habitation Not Opening in OHT Mapping Screen | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Master GM | SIT Testing | Testing | Functional | Testing
28 | Jal Rekha | 19832 | Bug | 22/01/2026 | RFI Stage Status Not Updating in Pipeline Master | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Master GM | SIT Testing | Testing | Functional | Testing
29 | Jal Rekha | 19833 | Bug | 22/01/2026 | WTP–Intake Relationship Mapping Creates Duplicate Links | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Master GM | UAT/Prod/CR Testing | UAT | Functional | UAT
30 | Jal Rekha | 19835 | Bug | 22/01/2026 | WTP Daily Reading Not Syncing to Monthly Summary | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Dhara | UAT/Prod/CR Testing | Production | Functional | Production
31 | Jal Rekha | 19844 | Bug | 23/01/2026 | Raw Water Sample Collection Still Restricted to Old Buffer (Not 200m) | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Nirmal FE Mobile | SIT Testing | Testing | Functional | Testing
32 | Jal Rekha | 19847 | Bug | 23/01/2026 | FE Offline Reading Submission Not Syncing After Network Restored | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Nirmal FE Mobile | UAT/Prod/CR Testing | UAT | Functional | UAT
33 | Jal Rekha | 19850 | Bug | 23/01/2026 | Contractor and GM Unable to View Remark Comments on Web | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Nirmal FE Mobile | UAT/Prod/CR Testing | Production | Functional | Production
34 | Jal Rekha | 19851 | Bug | 23/01/2026 | Contractor and GM Unable to View Remark Comments on Web | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Nirmal FE Mobile | UAT/Prod/CR Testing | Production | Functional | Production
35 | Jal Rekha | 19852 | Bug | 23/01/2026 | Contractor and GM Unable to View Remark Comments on Web | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Nirmal FE Mobile | UAT/Prod/CR Testing | Production | Functional | Production
36 | Jal Rekha | 19855 | Bug | 23/01/2026 | Unsupported File Types Not Blocked | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Sahbhagita GM |  | Testing | Functional | Testing
37 | Jal Rekha | 19858 | Bug | 23/01/2026 | FE Activity Upload Not Syncing to GM Dashboard | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Sahbhagita GM | SIT Testing | Testing | Functional | Testing
38 | Jal Rekha | 19859 | Bug | 23/01/2026 | Gram Sabha Photo Upload Not Validated | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Sahbhagita GM | SIT Testing | Testing | Functional | Testing
39 | Jal Rekha | 19861 | Bug | 23/01/2026 | Village Filter Not Showing All Villages | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Sahbhagita GM | UAT/Prod/CR Testing | Production | Functional | Production
40 | Jal Rekha | 19862 | Bug | 23/01/2026 | Report Export Missing FE Name and Timestamp | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Sahbhagita GM | UAT/Prod/CR Testing | Production | Functional | Production
41 | Jal Rekha | 19864 | Bug | 23/01/2026 | Panchanama PDF Upload Not Working | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Sopan Contractor | SIT Testing | Testing | Functional | Testing
42 | Jal Rekha | 19865 | Bug | 23/01/2026 | GM Edit of Actual Dates Not Updating RFI Records | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Sopan Contractor | SIT Testing | Testing | Functional | Testing
43 | Jal Rekha | 19869 | Bug | 23/01/2026 | Duplicate Stage Records on Page Refresh | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/12 | Sopan Contractor | UAT/Prod/CR Testing | Production | Functional | Production
44 | Jal Rekha | 21607 | Bug | 17/02/2026 | WTP Report Parameter Change--WTP report shows incorrect parameter mapping after CR deployment | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | UAT/Prod/CR Testing | Production | Functional | Production
45 | Jal Rekha | 21610 | Bug | 17/02/2026 | RFI Approval Status Not Synced Between Contractor and GM | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Material Testing - GM/Contractor Login | Internal Testing | Testing | Functional | Testing
46 | Jal Rekha | 21613 | Bug | 17/02/2026 | FE Receives RFI Without Complete Assignment Chain | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Material Testing - GM/Contractor Login | Internal Testing | Testing | Functional | Testing
47 | Jal Rekha | 21614 | Bug | 17/02/2026 | Pending at PIU Report Shows Incorrect Records | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Material Testing - GM/Contractor Login | Internal Testing | Testing | Functional | Testing
48 | Jal Rekha | 21616 | Bug | 17/02/2026 | Material Testing Insert API allows saving records even when some mandatory fields are missing, resulting in incomplete data in database tables. | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Material Testing - GM/Contractor Login | UAT/PROD/CR Testing | UAT | Functional | UAT
49 | Jal Rekha | 21620 | Bug | 17/02/2026 | FE Geofencing Validation Missing at API Leve | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Material Testing - GM/Contractor Login | UAT/PROD/CR Testing | Production | Functional | Production
50 | Jal Rekha | 21621 | Bug | 17/02/2026 | Photo Mandatory but Generated PDF/Excel Shows Blank Image Placeholders and Does Not Validate Missing Photos | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | FHTC (Functional Household Tap Connection) FE Reports | SIT Testing | Testing | Functional | Testing
51 | Jal Rekha | 21622 | Bug | 17/02/2026 | Data Mismatch After NIC to Samagra API Replacement | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | FHTC (Functional Household Tap Connection) FE Reports | SIT Testing | Testing | Functional | Requirement Analysis
52 | Jal Rekha | 21623 | Bug | 17/02/2026 | GM PIU Data Not Visible to Admin After Save and Submit | Closed |  |  | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | O&M Billing GM | SIT Testing | Testing
53 | Jal Rekha | 21624 | Bug | 17/02/2026 | Incorrect Data Refresh | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | O&M Billing GM | SIT Testing | Testing | Functional | Testing
54 | Jal Rekha | 21625 | Bug | 17/02/2026 | Incorrect Mapping and Display of GM PIU and Contractor Names in Reports | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | O&M Billing GM | SIT Testing | Testing | Functional | Testing
55 | Jal Rekha | 21626 | Bug | 17/02/2026 | Incorrect Field Labels and Data Representation in Contractor Billing Reports- | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | O&M Billing GM | SIT Testing | Testing | Functional | Testing
56 | Jal Rekha | 21627 | Bug | 17/02/2026 | Bulk Upload and New Functionality Pages Not Integrated with Database- | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | O&M Billing GM | SIT Testing | UAT | Functional | UAT
57 | Jal Rekha | 21628 | Bug | 17/02/2026 | Duplicate Village Displayed During Meter Reading Entry in Mobile App: | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Dhara | SIT Testing | Testing | Functional | Requirement Analysis
58 | Jal Rekha | 21630 | Bug | 17/02/2026 | Meter Mapping Between WTP and Village Not Reflected Correctly- | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Dhara | SIT Testing | Testing | Functional | Testing
59 | Jal Rekha | 21634 | Bug | 17/02/2026 | WTP Report Not Showing Updated Parameters- | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | SIT Testing | Testing | Functional | Testing
60 | Jal Rekha | 21635 | Bug | 17/02/2026 | WTP Raw Water Quality Parameters Not Displaying Correct Units | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | SIT Testing | Testing | Functional | Testing
61 | Jal Rekha | 21637 | Bug | 17/02/2026 | OHT-Date Range Filter Not Working in Web Report | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | SIT Testing | Testing | Functional | Testing
62 | Jal Rekha | 21640 | Bug | 17/02/2026 | Drill Down & New Query Mapping Issue- | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | UAT/Prod/CR Testing | UAT | Functional | UAT
63 | Jal Rekha | 21641 | Bug | 17/02/2026 | Raw Water Data Mapping and Drill-Down Records Incorrect or Incomplete- | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | UAT/Prod/CR Testing | UAT | Functional | UAT
64 | Jal Rekha | 21644 | Bug | 17/02/2026 | UI Enhancements and 200m Buffer Rule Not Applied Consistently Across NIRMAL Reports and FE Login- | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | UAT/Prod/CR Testing | Production | Functional | Production
65 | Jal Rekha | 21645 | Bug | 17/02/2026 | GM Report Export Not Matching On-Screen Village Data | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sahbhagita GM | SIT Testing | Testing | Functional | Testing
66 | Jal Rekha | 21647 | Bug | 17/02/2026 | Village-wise Approval and ISA Dependency Not Functioning Correctly in Sahbhagita Module | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sahbhagita GM | SIT Testing | Testing | Functional | Testing
67 | Jal Rekha | 21781 | Bug | 18/02/2026 | MBR Check Option Removed from CWGM Dropdown and Also Missing in Stages | Closed | Critical | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Anusharavan | Testing | Testing | Functional | Testing
68 | Jal Rekha | 21783 | Bug | 18/02/2026 | Range Filter Not Working for Few Schemes in Anushravan Report | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Anusharavan | Testing | Production | Validation | Production
69 | Jal Rekha | 21901 | Bug | 20/02/2026 | Issue while adding meter reading | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Dhara | SIT Testing | Testing | Functional | Testing
70 | Jal Rekha | 21902 | Bug | 20/02/2026 | Login Page-->Forgot Password--> Mobile field-->Enter unregistered mobile Number-->Send OTP-->Enter here OTP -->Enter OTP-->Password-->Enter new password-->Update password-->Page disappears after clic | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Dhara | SIT Testing | Testing | UI/UX | Testing
71 | Jal Rekha | 21903 | Bug | 20/02/2026 | DHARA → Meter Registration | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Dhara | UAT/Prod/CR Testing | UAT | Data | UAT
72 | Jal Rekha | 21904 | Bug | 20/02/2026 | DHARA → Bulk Meter Upload | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Dhara | UAT/Prod/CR Testing | Production | Data | Production
73 | Jal Rekha | 21905 | Bug | 20/02/2026 | OHT not appearing in 'Select OHT' dropdown on first attempt; appears only after revisiting and updating mapping screen | Closed | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Master GM | SIT Testing | Testing | Functional | Testing
74 | Jal Rekha | 21906 | Bug | 20/02/2026 | OHT Name is not reflecting on OHT Village mapping screen | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Master GM | SIT Testing | Testing | Functional | Testing
75 | Jal Rekha | 21907 | Bug | 20/02/2026 | Deactivated village still appearing in OHT village mapping | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Master GM | UAT/Prod/CR Testing | UAT | Data | UAT
76 | Jal Rekha | 21908 | Bug | 20/02/2026 | Bulk Meter village mapping saved but not reflected in DHARA | Closed | Critical | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Master GM | UAT/Prod/CR Testing | Production | Functional | Production
77 | Jal Rekha | 21909 | Bug | 20/02/2026 | Nirmal-FE- Field Engineer is not able to submit the FRC Test | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | SIT Testing | Testing | Validation | Testing
78 | Jal Rekha | 21910 | Bug | 20/02/2026 | Nirmal-FE- Field Engineer is not able to submit photo | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | SIT Testing | Testing | Functional | Testing
79 | Jal Rekha | 21912 | Bug | 20/02/2026 | Nirmal-FE- Field Engineer is not able to submit the sample report from field | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | UAT/Prod/CR Testing | UAT | Functional | UAT
80 | Jal Rekha | 21913 | Bug | 20/02/2026 | Nirmal-FE – Geofence validation not working correctly for sample collection | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Nirmal FE Mobile | UAT/Prod/CR Testing | UAT | Functional | UAT
81 | Jal Rekha | 21914 | Bug | 20/02/2026 | ISA list is not visible as per scheme-wise | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sahbhagita GM | SIT Testing | Testing | Functional | Testing
82 | Jal Rekha | 21915 | Bug | 20/02/2026 | FE→Data Submission Fails Intermittently | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sahbhagita GM | SIT Testing | Testing | Functional | Testing
83 | Jal Rekha | 21916 | Bug | 20/02/2026 | PM → Sahbhagita Activity Report is not displaying to PM | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sahbhagita GM | UAT/Prod/CR Testing | UAT | Data | Testing
84 | Jal Rekha | 21917 | Bug | 20/02/2026 | FE →Unable to Upload PDF | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sahbhagita GM | UAT/Prod/CR Testing | Production | Functional | Production
85 | Jal Rekha | 21918 | Bug | 20/02/2026 | SOPAN INTAKE-System allows the GM to submit the Work Monitoring form without entering the Actual End Date | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sopan Contractor | SIT Testing | Testing | Functional | Testing
86 | Jal Rekha | 21919 | Bug | 20/02/2026 | SOPAN OHT-While submitting the Work Monitoring form an error pop-up is displaying with a message "Please select Status" | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sopan Contractor | SIT Testing | Testing | Functional | Testing
87 | Jal Rekha | 21920 | Bug | 20/02/2026 | Old chat history not loading completely | Closed | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sopan Contractor | UAT/Prod/CR Testing | UAT | Validation | UAT
88 | Jal Rekha | 21921 | Bug | 20/02/2026 | OHT mapping changes not reflected in Monitoring screen | Closed | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/13 | Sopan Contractor | UAT/Prod/CR Testing | Production | Data | Production
89 | Jal Rekha | 24354 | Bug | 09/04/2026 | Re-Inspection Button Visible in History Tab Instead of Showing “In Progress” Status After Re-Inspection | Ready For Testing | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
90 | Jal Rekha | 24356 | Bug | 09/04/2026 | Re-Inspection Request Not Visible to PIU Under “Pending (With PIU)” Tab on Web App | Ready For Testing | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
91 | Jal Rekha | 24357 | Bug | 09/04/2026 | Error While Submitting Re-Inspection Request – Data Type Mismatch for “properly_Installed” Column | Ready For Testing | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
92 | Jal Rekha | 24361 | Bug | 09/04/2026 | RFI Not Visible on Web When Assigned Only to SQC or TPIA; Visible Only When Assigned to Both | Ready For Testing | Critical | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
93 | Jal Rekha | 24362 | Bug | 09/04/2026 | PIU Action Status Incorrect – Showing Accepted/Rejected Instead of Pending for Final GM Decision | Ready For Testing | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Requirement Analysis
94 | Jal Rekha | 24363 | Bug | 09/04/2026 | Re-Inspection Record Not Removed from Rejected Tab After Upload | Ready For Testing | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
95 | Jal Rekha | 24364 | Bug | 09/04/2026 | Incorrect Mapping of “Connection Installed” Value to “Installed Location” Column on Web | Ready For Testing | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
96 | Jal Rekha | 24365 | Bug | 09/04/2026 | Re-Inspection Record Not Visible on First Login; Appears After Second Login for FE | Ready For Testing | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
97 | Jal Rekha | 24367 | Bug | 09/04/2026 | Re-Inspection Updates Not Reflected – Old Images and Remarks Displayed in History Tab | Ready For Testing | Medium | Normal | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
98 | Jal Rekha | 24369 | Bug | 09/04/2026 | When the FE performs rejection during the re-inspection for the second time, It is visible to both Contractor and PIU both. | Ready For Testing | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
99 | Jal Rekha | 24370 | Bug | 09/04/2026 | Unable to find the image captured by FE. When GM clicks on eye button image is not displaying | Ready For Testing | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
100 | Jal Rekha | 24431 | Bug | 10/04/2026 | Rejected Survey Not Visible in History Tab and Remains Missing After Re-Inspection in Contractor Login | Ready For Testing | High | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
101 | Jal Rekha | 24433 | Bug | 10/04/2026 | PIU Login – Only One Image Displayed in Log Details After Re-Inspection Despite Multiple Images Captured | Ready For Testing | Medium | High | Ranjana Yadav | Ranjana Yadav | Jal Rekha/15 | FHTC Change request FHTC | FHTC Loop functionality implementation | Testing | Functional | Development
102 | Jal Rekha | 24435 | Bug | 10/04/2026 | Cube Image Capture Field Becomes Non-Mandatory on Save as Draft: | New | High | High | Anand Gour | Ranjana Yadav | Jal Rekha/15 | Cube Testing - Contractor | Internal Testing | Testing | Functional | Development
103 | Jal Rekha | 24437 | Bug | 10/04/2026 | Incorrect Time Display in Survey Details | New | Medium | Normal | Anand Gour | Ranjana Yadav | Jal Rekha/15 | Cube Testing - Contractor | Internal Testing | Testing | Functional | Development
104 | Jal Rekha | 24439 | Bug | 10/04/2026 | Contractor Unable to Generate RFI for CWPM, CWGM, RWPM, and Distribution Pipe | New | High | High | Anand Gour | Ranjana Yadav | Jal Rekha/15 | Cube Testing - Contractor | Internal Testing | Testing | Validation | Requirement Analysis
105 | Jal Rekha | 24441 | Bug | 10/04/2026 | Web PIU Login – Application Crash on “Pending with PIU” Tab: | New | Critical | High | Neha Soni | Ranjana Yadav | Jal Rekha/15 | Cube Testing - GM | Internal Testing | Testing | Functional | Development
106 | Jal Rekha | 24445 | Bug | 10/04/2026 | Structural Component Field Displayed for Non-Applicable Components | New | High | High | Anand Gour | Ranjana Yadav | Jal Rekha/15 | Cube Testing - Contractor | Internal Testing | Testing | Validation | Requirement Analysis
107 | Jal Rekha | 24447 | Bug | 10/04/2026 | SQC/TPIA Login – View Cube Details (Eye Icon) Not Working in Pending RFI: | New | High | High | Neha Soni | Ranjana Yadav | Jal Rekha/15 | Cube Testing - SQC/TPIA | Internal Testing | Testing | Functional | Development
108 | Jal Rekha | 24453 | Bug | 10/04/2026 | RFI Not Visible to SQC/TPIA and Disappears When Assigned to Both | New | High | High | Neha Soni | Ranjana Yadav | Jal Rekha/15 | Cube Testing - SQC/TPIA | Internal Testing | Testing | Functional | Development
109 | Jal Rekha | 24456 | Bug | 10/04/2026 | Location/Address Field Displayed as Blank in Cube Testing List and Logs: | New | Medium | High | Neha Soni | Ranjana Yadav | Jal Rekha/15 | Cube Testing - GM | Internal Testing | Testing | Functional | Requirement Analysis
110 | Jal Rekha | 27181 | Bug | 26/05/2026 | The RFI Submitted Date is displayed incorrectly. Currently, the system is picking the Inspection Date as the RFI Submitted Date. | New | High | High | Anand Gour | Ranjana Yadav | Jal Rekha/16 | Cube Testing - FE | Internal Testing | Testing | Functional | Development
111 | Jal Rekha | 27187 | Bug | 26/05/2026 | The date format Issue | New | Low | Normal | Anand Gour | Ranjana Yadav | Jal Rekha/16 | Cube Testing - Contractor | Internal Testing | Testing | Cosmetic | Development
112 | Jal Rekha | 27192 | Bug | 26/05/2026 | For the same RFI, dates are passed incorrectly in View Cube Details and View RFI Log Details. | New | High | High | Anand Gour | Ranjana Yadav | Jal Rekha/16 | Cube Testing - Contractor | Internal Testing | Testing | Functional | Development
113 | Jal Rekha | 27195 | Bug | 26/05/2026 | Cube Testing(Web)SQC/TPIA Login – View Cube Details (Eye Icon) Not Working in In Progress tab: | New | Medium | High | Neha Soni | Ranjana Yadav | Jal Rekha/16 | Cube Testing - SQC/TPIA | Internal Testing | Testing | Functional | Development
114 | Jal Rekha | 27197 | Bug | 26/05/2026 | Even when the Date of Casting is selected as a past date, the day difference is being calculated based on today’s date, which is incorrect. | New | High | High | Susheel Kumar Patel | Ranjana Yadav | Jal Rekha/16 | Cube Testing - Contractor | Internal Testing | Testing | Functional | Development
115 | Jal Rekha | 27200 | Bug | 26/05/2026 | The “Inspection Date” placeholder is still visible. | New |  | High | Susheel Kumar Patel | Ranjana Yadav | Jal Rekha/16 | Cube Testing - Contractor | Internal Testing | Testing | UI/UX | Development
116 | Jal Rekha | 27202 | Bug | 26/05/2026 | The time should either be removed from the UI or corrected. | New | Medium | Normal | Susheel Kumar Patel | Ranjana Yadav | Jal Rekha/16 | Cube Testing - FE | Internal Testing | Testing | Cosmetic | Development
117 | Jal Rekha | 27203 | Bug | 26/05/2026 | The “Submitted On” date is missing. | New | High | High | Susheel Kumar Patel | Ranjana Yadav | Jal Rekha/16 | Cube Testing - FE | Internal Testing | Testing | Functional | Development
118 | Jal Rekha | 27206 | Bug | 26/05/2026 | Inspection Date column should be removed from the table in each sub-module under Cube Testing. | New | Medium | Normal | Neha Soni | Ranjana Yadav | Jal Rekha/16 | Cube Testing - GM | Internal Testing | Testing | Functional | Requirement Analysis
119 | Jal Rekha | 27237 | Bug | 26/05/2026 | Cube Testing (Web) | New | High | High | Neha Soni | Ranjana Yadav | Jal Rekha/16 | Cube Testing - GM | Internal Testing | Testing | Functional | Requirement Analysis
120 | Jal Rekha | 27238 | Bug | 26/05/2026 | Images captured by FE during the survey is not getting saved in History | New | High | High | Susheel Kumar Patel | Ranjana Yadav | Jal Rekha/16 | Cube Testing - FE | Internal Testing | Testing | Functional | Development
121 | Jal Rekha | 27728 | Bug | 2026-06-08 | Unable to view uploaded document properly | New | Medium | Normal | Susheel Kumar Patel | Ranjana Yadav | Jal Rekha/17 | Factory Testing | Internal Testing | Testing | UI/UX | Development
122 | Jal Rekha | 27729 | Bug | 2026-06-08 | After uploading the video and saving it as draft, system allows the user to submit the survey even though the video was removed | New | High | High | Susheel Kumar Patel | Ranjana Yadav | Jal Rekha/17 | Factory Testing | Internal Testing | Testing | Functional | Development
123 | Jal Rekha | 27733 | Bug | 2026-06-08 | Factory Testing: Incorrect Document Deleted When Removing the Last Uploaded File | New | Medium | High | Neha Soni | Ranjana Yadav | Jal Rekha/17 | Factory Testing | SIT Testing | Testing | Functional | Production
124 | Jal Rekha | 27735 | Bug | 2026-06-08 | Web – Factory Testing: Same Document Displayed in All Document Folders After Uploading Multiple Files | New | High | High | Neha Soni | Ranjana Yadav | Jal Rekha/17 | Factory Testing | SIT Testing | Testing | Functional | Production