Madhya Pradesh Electronics Development Corporation (MPSEDC)

State IT Centre, 47-A, Arera Hills, Bhopal, M.P. – 462011,

Phone: +91-755-2518300, Fax: +91-755-2579824

URL: www.mapit.gov.in, Email: info@mapit.gov.in

Parakh – Impact Analysis

Document Version History

| Version | Date | Author | Comments |
| --- | --- | --- | --- |
| 1.0 | 26/06/2024 | Dikshant Gitey | Initial draft |
| 1.1 | 26/09/2024 | Dikshant Gitey | Added CMS |
| 1.2 | 31/07/2025 | Tanu jha | Updated SRS |

Contents

1. Overview	4

2. Change Requests and Impact Summary	4

3. Key Observations	7

4. Key CMMI Level 5 Practices Applied & Reflected	7

4.1 Quantitative Process Management	7

4.2 Integrated Change Management	7

4.3 Data & Process Traceability	8

4.4 Continuous Improvement	8

5. Conclusion	8

Impact Analysis

# 1. Overview

The Impact Analysis for Parakh Project Change Requests, following CMMI Level 5 standards, involves systematic assessment of each proposed change across cost, schedule, quality, risk, and process implications. Below is a detailed report based on the analysis of "Parakh_Change_Request_Log.xlsx" file, strictly mapped to CMMI5 requirements and change management best practices.

Change requests are reviewed for their technical, operational, schedule, quality, and risk implications. Each CR is assessed on the basis of expected outcomes, required resources, dependencies, and process alignment. Only changes with full traceability, measurable metrics, and mitigation plans are approved for implementation. This aligns with CMMI Level 5 practices by ensuring traceability, quantitative metrics, risk/mitigation, and compliance mapping.

Per CMMI Level 5, all requests must:

- Have measurable impacts (time, resources, quality metrics).

- Be linked to process governance and compliance.

- Undergo systematic review before approval.

# 2. Change Requests and Impact Summary

| CR ID | Description | Cost Impact | Schedule Impact | Quality Impact | Risk & Mitigation | Process/Compliance | Approval Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CR-001 | Hostel Inspection: add student capacity fields | Minor DB update, +2 days dev | No delay; one sprint | Improved inspection detail | Low (minor DB update) | Fully compliant | Approved |
| CR-002 | Enable bilingual forms | +5 days dev, UI redesign | Extra dev/test effort, 1 sprint | Accessibility, usability | Medium (UI/UX redesign, translation testing needs) | Needs documentation review | Pending Review |
| CR-003 | Offline sync for video uploads | +10 days dev, +3 days test | Major storage & sync testing, +2 sprints | Enhances field usability | High (Storage increase, sync integrity, connectivity) | Compliance checks for mobile sync | Approved |
| CR-004 | Enforce 2FA for admin logins | +7 days dev, +2 days test | Dependent on deployment window | Security hardening, audit | Low (standard, widely used security practice) | Process aligns with ISO/SOC2 | Approved |
| CR-005 | Drone imagery in GIS dashboard | +20 days dev, vendor needed | Major dependency: external vendor | Data depth, field coverage | High (vendor dependency, integration issues) | To be reviewed under data governance | Proposed |
| CR-006 | Automated regression in form validation | +6 days dev, 2 days QA | No delay; supplements QA | Release quality, error reduction | Low (standard test automation risk) | Follows QA automation policies | Approved |
| CR-007 | Compliance tracking report | +8 days dev, +2 days test | Slight extension, 1 sprint | Transparency, auditing | Low (mainly reporting logic) | Reporting standards met | Approved |
| CR-008 | Data retention for citizen forms | +5 days dev, data migration | Minor DB ops, 1 sprint | Regulatory/data compliance | Medium (legal, data archival risks) | Needs InfoSec review | Pending Review |
| CR-009 | Helpdesk feedback module (mobile) | +4 days dev | No impact, minor feature | Engagement, support | Low (mobile UI feature) | Follows mobile feedback process | Approved |
| CR-010 | Enable single sign-on (state portal) | +12 days dev, +3 days test | Major dependency: External SSO integration | Security, seamless access | High (integration risk, external systems) | Identity management alignment | Proposed |
| CR-011 | Dark Mode in Mobile App | +3 days UI dev | No major delay | Improves usability | Low (UI-only) | UX standards | Proposed |
| CR-012 | Advanced MIS export (Excel/PDF) | +5 days dev/test | Minor schedule extension | Enhances reporting & traceability | Low (reporting module only) | Reporting policies | Approved |
| CR-013 | Real-time anomaly alerts in inspections | +15 days dev +10 days test | +2 sprints delay | Early detection of fraud/errors | High (algorithm accuracy) | Risk mgmt guidelines | Pending Review |
| CR-014 | Multi-lingual interface (Hindi/English) | +20 days dev, +10 days testing | +3 sprints | Improves accessibility & adoption | Medium (translation QA risk) | Accessibility policy | Approved |
| CR-015 | Dashboard performance optimization | +8 days dev | No delay (parallel sprint) | Faster analytics, better UX | Low (query tuning) | Performance benchmarks | Approved |
| CR-016 | API integration with State HRMS | +25 days dev, +15 test | +4 weeks | Improves user sync accuracy | High (external dependency) | Data governance | Proposed |
| CR-017 | Geo-fencing alerts for field inspections | +12 days dev/test | +1 sprint | Improves monitoring reliability | Medium (location accuracy risk) | GIS standards | In Review |
| CR-018 | Auto archival of old inspection data | +7 days dev | No delay | Compliance with data retention rules | Medium (storage risks) | Legal & archival policy | Approved |
| CR-019 | Enhanced role-based dashboards (Dept-wise) | +10 days dev/test | +2 weeks | Improves departmental oversight | Low (role config risk) | Access control | Approved |
| CR-020 | Integration of drone imagery in dashboard | +30 days dev/test | +6 weeks delay | Improves field coverage, richer insights | High (vendor dependency) | Data governance, procurement rules | Proposed |

# 3. Key Observations

- High Priority CRs: Multi-lingual interface (CR-014), Anomaly Alerts (CR-013), HRMS Integration (CR-016).

- Major Risks Identified: Vendor dependency (CR-020), external system dependency (CR-016), algorithm integrity (CR-013).

- Compliance Alignment:

  - Accessibility standards → CR-014

  - GIS/data governance → CR-017, CR-020

  - Archival/legal compliance → CR-018

# 4. Key CMMI Level 5 Practices Applied & Reflected

## 4.1 Quantitative Process Management

- Changes are estimated with clear resource allocation (dev/test days) for cost and schedule reliability.

- Metrics for quality improvement are built into each request, including increased security, data accuracy, and compliance.

- Each CR is estimated with resource impacts (developer/tester days).

## 4.2 Integrated Change Management

- Approval workflow ensures all changes go through documented review (Pending, Proposed, Approved).

- Risk assessment and mitigation (vendor dependencies, legal compliance, external system integration) are explicit per change request.

- Every CR passes through documented status (Proposed → Review → Approved → Completed).

## 4.3 Data & Process Traceability

- Each change links to specific modules and teams (owner) for accountability.

- Implementation and actual completion dates are tracked for post-change audit and lessons learned.

- CRs linked to impacted modules, teams, and policies.

## 4.4 Continuous Improvement

- Feedback, reporting, and automation requests directly address process maturity, release efficacy, and user experience, embodying CMMI5's focus on measurable improvement.

- Requests (e.g., MIS export, auto archival, anomaly alerts) drive maturity of the system.

# 5. Conclusion

All listed change requests are assessed and actioned per CMMI Level 5 guidelines. Risks, dependencies, and improvement opportunities are logged and tracked for every CR, supporting mature, scalable process control and delivery.

Report ensures Parakh Project maintains process maturity, compliance, and risk governance while implementing critical features. CRs are prioritized based on business value, compliance urgency, and operational risks, supporting scalable and controlled delivery.