## Sheet1
CR ID | Date Raised | Raised By | Description of Change | Priority | Impacted Modules | Impact Analysis (Cost/Schedule/Quality) | Approval Status | Owner | Target Completion | Actual Completion | Remarks
CR-001 | 2025-07-15 | Nodal Officer – Tribal Dept | Add new form fields for hostel inspection (student capacity, food quality rating) | High | Forms Module, Reporting | +2 days dev, minor DB schema update, no infra impact | Approved | Dev Lead | 2025-07-20 | 2025-07-19 | Deployed successfully
CR-002 | 2025-07-18 | Citizen Services | Enable bilingual forms (Hindi + English) | Medium | Forms Module, Mobile App | +5 days dev, UI redesign, moderate testing | Pending Review | BA Team | 2025-07-25 | - | Requires UI/UX approval
CR-003 | 2025-07-22 | Field Officer | Offline sync enhancement to support video uploads | High | Mobile App, Sync Engine | +10 days dev, +3 days test, storage increase | Approved | Mobile Dev Lead | 2025-08-05 | - | In progress
CR-004 | 2025-07-25 | Security Audit | Enforce 2FA for admin logins | High | Auth Service, Web Portal | +7 days dev, +2 days test, no infra cost | Approved | Security Lead | 2025-07-31 | - | Pending deployment
CR-005 | 2025-07-28 | GIS Admin | Integrate drone imagery with GIS dashboard | Low | GIS Engine, Dashboard | +20 days dev, external vendor support needed | Proposed | GIS Lead | TBD | - | To be discussed in Steering Committee
CR-006 | 2025-08-01 | QA Specialist | Add automated regression test cases for form validation | Medium | Forms Module, Test Suite | +6 days dev, 2 days QA, improved release quality | Approved | QA Lead | 2025-08-10 | - | Awaiting final regression pass
CR-007 | 2025-08-02 | Reporting Officer | Add compliance tracking report for submitted inspections | High | Reporting Portal, Database | +8 days dev, +2 days test, increases transparency | Approved | Backend Team | 2025-08-12 | - | Draft report format under review
CR-008 | 2025-08-04 | Data Governance Team | Implement data retention policy for citizen-submitted forms | Medium | Database, Policy Engine | +5 days dev, minor data migration, aligns with compliance | Pending Review | Policy Lead | 2025-08-15 | - | Legal review underway
CR-009 | 2025-08-06 | Support Desk | Add helpdesk feedback module to mobile interface | Low | Mobile App, Helpdesk | +4 days dev, improves user engagement | Approved | Mobile UX Team | 2025-08-13 | - | Deployment scheduled
CR-010 | 2025-08-08 | Integration Lead | Enable single sign-on with state government services portal | High | Auth Service, Portal Integration | +12 days dev, +3 days test, minimal infra changes | Proposed | Integration Team | 2025-08-20 | - | Coordination with external team
1011 | 2025-07-10 | Field Officer | Add offline draft saving of inspection forms | High | Mobile App, Sync Services | Medium cost, schedule extension 1 week, improved data quality | Approved | Dev Team Lead | 2025-07-25 | Pending | Needed for low-connectivity areas
1012 | 2025-07-12 | Nodal Officer | Enhance GIS map layer filters for inspections | Medium | Web Portal, GIS DB | Low cost, no schedule impact, quality improvement | Approved | GIS Specialist | 2025-07-20 | 2025-07-18 | Completed ahead of time
1013 | 2025-07-15 | Admin | Role-based dashboard views by department | High | Web Portal, Analytics | Medium cost, 2 weeks schedule, improved usability | In Review | UI/UX Lead | 2025-08-05 | Pending | Awaiting UAT feedback
1014 | 2025-07-16 | Citizen Feedback | OTP login via email in addition to SMS | Medium | Auth Service | Low cost, minor schedule impact, security improvement | Approved | Security Lead | 2025-07-28 | Pending | Suggested during user survey
1015 | 2025-07-18 | QA Team | Auto regression suite for mobile sync | High | Mobile App, API | Medium cost, 1 week schedule, major quality boost | Approved | QA Manager | 2025-08-01 | Pending | Linked with release 3.2
1016 | 2025-07-20 | Project Manager | Enable multi-lingual forms (Hindi/English) | High | Form Builder, DB | High cost, 3 weeks schedule, quality + accessibility | Approved | Localization Lead | 2025-08-15 | Pending | Strategic priority
1017 | 2025-07-22 | State Admin | Add advanced MIS report export (Excel/PDF) | Medium | Reporting, ETL | Low cost, 1 week schedule, usability improvement | Approved | Reporting Team | 2025-08-05 | Pending | Required by stakeholders
1018 | 2025-07-25 | DevOps Team | CI/CD pipeline integration for Parakh app | High | DevOps, Release Mgmt | Medium cost, schedule +1 week, major quality gain | Approved | DevOps Lead | 2025-08-10 | Pending | Aligns with CMMI-5 governance
1019 | 2025-07-27 | Citizen Helpdesk | Dark mode support in mobile app | Low | Mobile UI | Low cost, no major schedule impact, UX improvement | In Review | UI Team | 2025-08-15 | Pending | Nice-to-have feature
1020 | 2025-07-30 | Monitoring Team | Real-time anomaly alerts in inspections | High | Analytics Engine, Alert Module | High cost, +2 weeks schedule, strong quality + compliance | Proposed | Data Science Lead | 2025-08-25 | Pending | To improve monitoring effectiveness

## Sheet2
CR log as a living document to track all future changes, link it to BRTM and UAT results, ensuring full CMMI L5 compliance.
this aligns with CMMI Level 5:
1. Traceability – Each CR links to impacted modules and quality outcomes.
2. Impact Analysis – Cost, schedule, quality are explicitly assessed.
3. Governance – Status flows through Proposed → Review → Approved → Completed.
4. Metrics – Target vs. Actual completion dates tracked for process maturity.