## Project Status Review Process Document

### 1. Purpose

The purpose of this document is to define a standard process for conducting Project Status Reviews to ensure regular, consistent, and effective communication regarding project progress, issues, and risks among stakeholders.

### 2. Scope

This process is applicable to all project stakeholders including the project team, project manager, and client representatives.

### 3. Objectives

- Monitor and track project progress against planned schedules and milestones.

- Identify and address issues, risks, or delays in a timely manner.

- Ensure alignment between the project team and client stakeholders.

- Facilitate informed decision-making and corrective actions when required.

### 4. Frequency

- Internal Reviews: As per project need

- Client Reviews: Bi-weekly or monthly (as agreed with the client)

### 5. Participants

- Project Manager

- Business Analyst

- Client Representative(s)

- Other relevant stakeholders (as required)

### 6. Inputs to the Review

- Updated Project Plan / Timeline

- Status Update Sheet

- List of completed, ongoing, and upcoming tasks

- Action Item Log from previous reviews

### 7. Review Process Steps

- Preparation

  - Project Manager consolidates updates.

  - Status document is shared.

- Conducting the Review

  - Walkthrough of project progress

  - Highlight completed tasks and progress on ongoing work.

  - Discuss blockers/issues

- Post-Review Activities

  - Meeting minutes (MoM) are documented.

  - Action Item Log is updated.

  - Tasks from the review are followed up in the next cycle.

### 8. Output/Deliverables

- Updated Status Report

- Minutes of Meeting (MoM)

### 9. Tools Used

- Google Docs/Sheets (Status Template)

- Email / Shared Drive for document sharing

### 10. Responsibilities

- Project Manager: Oversees and coordinates project status reviews and follow-ups.

- Business Analyst: Provides business insights and updates on requirements and changes.

- Project Executive: Supports documentation, meeting notes, and communication for status review tasks.