# Project Status Report

Project: Parakh

Madhya Pradesh State Electronic Department,

Govt. of Madhya Pradesh

Revision History

| Version | Date | Description | Prepared by | Reviewed by |
| --- | --- | --- | --- | --- |
| 1.0 | 28/07/2025 | Status report including completed activities, delays, and next steps | Business Analyst |  |

M.P. STATE ELECTRONICS DEVELOPMENT CORPORATION LTD.

State IT Centre, 47-A, Arera Hills, Bhopal-462011 (M.P.)

www.mpsedc.mp.gov.in

# Project Status Report

| Project Code: MPSEDC/MPSSDI (GIS)/2024/00388 |  |  |  | Project Name: Parakh 2.0 |
| --- | --- | --- | --- | --- |
| Client: State Electronic Department, Govt. of MP |  |  |  |  |
| Business account Manager: |  |  |  | Service Project Manager: Kundan Singh Rathore |
| Planned Activities; Activities Completed; Scheduled Variance; Effort Variance; DRE (Defect removal effectiveness). Liquor Rate QR Code Module; Live with shop-wise QR, search feature, and report generation; On Schedule; None; 85.71. Shop Wise Default Amount Report; District filter and Excel export added and live; On Schedule; None; N/A. Mfg. Unit to Warehouse Vehicle Receive; Live with validation and trigger system; On Schedule; None; 88.88. Security Audit; All levels complete, reports shared; On Schedule; None; N/A. e-Aabkari Connect Mobile App; Live on Play Store; under review; Minor Delay; Slight Overrun; 86.95. FL-5 License Module; In Progress – App/API/procedure under development; Delayed; Moderate Overrun; N/A. ECCMS; In Progress – Aadhaar login, API, SMS integration; Delayed; Moderate Overrun; N/A. Country Liquor Supply Module; In Progress – Retailer to warehouse workflow setup; On Track; Slight Overrun; 81.82. Manual Penalty Entry; In Progress – Demand/penalty creation page being developed; On Track; None; 66.67. Vehicle Breakdown System; Documentation submitted; under department verification; Slight Delay; None; N/A. Add Log Manager; Demo implemented, waiting for infra update approval; Pending Approval; None; 77.77. User Support & Maintenance; Ongoing; On Track; N/A; N/A. Liquor Rate QR Code Module; Live with shop-wise QR, search feature, and report generation; On Schedule; None; 83.33. |
| Reason for Variance (Scheduled/Effort) – Milestone wise (more than target as per QA Plan) 1. Delay in receiving department feedback for mobile app (FL-5, ECCMS). 2. MFA infra update pending departmental approval affecting log manager deployment. |  |  |  |  |
| Activities Planned for the next Reporting Period: 1. Complete and test FL-5 mobile app. 2. Finish Aadhaar-based login and communications APIs for ECCMS. |  |  |  |  |
| Decisions taken in Project Review Meeting 1. Move forward with ECCMS user dashboard integration by 18.07.2025. 2. Prioritize infra update request for MFA implementation. |  |  |  |  |
| Issues for Management: |  |  |  |  |
| Issues |  |  |  | Impact |
| MFA server infra upgrade pending |  |  |  | Delays log manager production deployment |
| App review delays on Play Store |  |  |  | Risk of extended go-live timeline for FL-5 |
| Risk Management: |  |  |  |  |
| Risk Description |  | Risk Mitigation Plan |  | Status |
| Infra update not approved on time |  | Follow up with dept. for official letter |  | Open |
| ECCMS complexity & user integration delays |  | Allocate extra dev/ testing bandwidth |  | Mitigated |
| Quantitative Information: |  |  |  |  |
| Metric | Planned Value |  | Actual Value | Remarks |
| Completed Modules | 5 |  | 5 | All listed live modules delivered |
| In-Progress Tasks | 5 |  | 5 | Targeted for completion by 18.07.2025 |
| Prepared by: Rahul Pragalbh, Sr. Business Analyst, MPSeDC |  |  |  | Date: |
| Reviewed by: Project Manager, Kundan Singh Rathore |  |  |  | Date: |
| Review Comments: Project is progressing steadily. Some modules are delayed due to external dependencies (Play Store, infra approval). Timely follow-up advised. |  |  |  |  |