## District Initiatives
District Level Initiatives
S. No | District | Initiative | Request Received on (Letter / Verbal) | Lettes | District Level SPOC | Status | Current Status | Project Manager | Vertical | OIC | DeGM Name | DeGM Contact Number
1 | Alirajpur | Hostel Survey (Parakh) | Letter | LetterFromCollector-Alirajpur.pdf | Virendra Singh Baghel (Joint Collector) | The department was onboarded to UAT, and the inspection form was created and shared with them on 17-01-2025 for review. | UAT Completed & Went Live (In use by Dept) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Vineet Vishwkarma | 6260437738
2 | Chhindwara | Wash on wheel (Parakh) | Letter | LetterToOnboardParakh-Chindwara.pdf | Agrim (CEO Jila Panchayat) | Work Complete & submiited to Dept. (Go Live) | UAT Completed & Went Live (In use by Dept) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Atul Kumar Sharma | 7898452023
3 | Chhindwara | School Survey (Parakh) | Letter | LetterToOnboardParakh-Chindwara.pdf | Agrim (CEO Jila Panchayat) | Work Complete & submiited to Dept. for (UAT) | UAT completed. Awaiting approval from the Collectorate to Go Live | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Atul Kumar Sharma | 7898452023
4 | Bhopal commissioner office | General Inspection on (Parakh) | Letter | Comm. bpl letter for Parakh login.pdf | Alok (Consultant) MPSEDC |  | UAT completed. Awaiting approval from the Collectorate to Go Live | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Vikas Gupta | 7000180080/ 8305303857
5 | Damoh | School & Hostel Survey (Parath) | Letter | Parakh Letter Damoh.pdf | No Name in Letter | Work Complete & submitted to Dept. for (UAT) on 16-01-2025 | UAT Completed & Went Live (In use by Dept) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Mahesh Agrawal | 9893691611
6 | Zila Punchayat , Anuppur | Anuppur Works Management System (Mobile wire frames for WMS) | With COE | - | - |  | Work In Progress | Dr.Rakesh Sir | GIS | Dr. Sandeep Goyal | Vikas Singh | 7697869606
7 | Tikamgarh , Collectorate | Inspection Mobile App on (Parakh) | Letter | parakh portal letter tikamgarh.pdf | - | In Tikamgarh Collectorate, forms are being prepared but have already taken considerable time. | UAT completed. Awaiting approval from the Collectorate to Go Live | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Pushpendra Tiwari | 7415360791
8 | Dindori , Collectorate | School Survey, Hostel, Anganbadi, PDS Center Extra Inspection App (Parakh) | Letter | Parakh App dindori.pdf | - |  | UAT Completed & Went Live (In use by Dept) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Deepak Sahu | 9179173987
9 | Vidisha | Hostel Survey (Parakh) | Direction by MD / APD Sir | विदिशा जिले में स्_कूलों के निरीक्षण संबंधी APP उपलब्_ध कराने बाबत् तथा तकनीकी सहयोग.pdf | - | The department was onboarded to UAT, and the inspection form was created and shared with them on 17-01-2025 for review. | UAT Completed & Went Live (In use by Dept) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | AMIT AGARWAL | 9893276222
10 | Bhind | Drone Survey | Letter | Bhind E Khaniz Letter.pdf | - | Survey completed. Finalization of the data is in process | UAT Completed & Went Live (In use by Dept) | Anoop Patel | GIS | Dr. Sandeep Goyal | Saurbabh Upadhyay | 9893310941
11 | Khandwa | Drone Urban Survey | Direction by ACS Sir | - | - | Drone survey is in process. | Drone survey is in process. | Anoop Patel | GIS | Dr. Sandeep Goyal | Anil Chandel | 7089189689/ 9926575646 | Need to confirm on Report
12 | Rewa | Scanning of (Old Revenue / Naksha Record of Rewa (14399 Sheets) | Letter | Scanning Old Revenue Naksha of Land Records Rewa.pdf | - | Till now 6 sheets received from district and completed. Reamining sheets are awaited from district. | Work in Progress (Till Date 2793 sheets done) | Anoop Patel | GIS | Dr. Sandeep Goyal | Ashish Dubey | 9424468702
13 | Patan | Satellite data based maps for Urban Local Body boundary extension | Letter | Jabalpur Satellite data Urban Local Body boundary Letter From Dept.pdf | - | Survey completed. Data Shared with Department | Survey completed. Data Shared with Department | Anoop Patel | GIS | Dr. Sandeep Goyal | - | -
14 | Sidhi | Satellite data based maps for Urban Local Body boundary extension | Letter | Sidhi Satellite data Urban Local Body boundary.pdf | - | Survey completed. Data Shared with Department | Survey completed. Data Shared with Department | Anoop Patel | GIS | Dr. Sandeep Goyal | Manish Kumar Singh | 8120699041/ 7582074124
15 | Sagar | Satellite data based maps for Urban Local Body boundary extension | Letter | Bina ULB letter for satellte image.pdf | - | Survey completed. Data Shared with Department | Survey completed. Data Shared with Department | Anoop Patel | GIS | Dr. Sandeep Goyal | Rahul Sharma | 7987851221
16 | Narsinghpur | Satellite data based maps for Urban Local Body boundary extension | Letter | Narsinghpur Satellite data Urban Local Body boundary.pdf | - | Survey completed. Data Shared with Department | Survey completed. Data Shared with Department | Anoop Patel | GIS | Dr. Sandeep Goyal | Ms Kripa Singh | 9131374712
17 | Bhind | Hostel Survey (Parakh) | Letter | PARAKH Hostel Survey Bhind 15.01.2025.pdf | - | In Bhind District, the forms are being finalized. | Bhind Collectorate is onboarded. Development work completed. Awaiting list of Hostels from the Collectorate office, so to initiate UAT. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Saurabh Upadhyay | 9893310941
18 | Chhatarpur Dist | Creation Google form , Login ID Password | Letter | Creation Google form for Chattarpur DIst login id 15 01 2025.pdf | - | Request received on 20-01-2025. Department onboarded. A meeting will be scheduled to discuss and finalize the details of the form creation | UAT In-Progress. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Tiwari | 9993551020
19 | Narmadapuram | Sarthak _Attendance / Parakh | Letter | Letter to MD_MPSeDC_15_01_2025_Narmadapuram.pdf | - | Work In Progress | UAT Completed & Went Live (In use by Dept) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Sandeep Chaurasia | 9425966696
20 |  | Hostel Inpection , Adharcard Inpection , aganwadi Inpection, Goverment School Inpection | Letter | Inspection Form Letter_Narmadapuram.pdf
21 | Bhopal Tribal Department | lnspection Module (Parakh App) | Letter | Tribal_Letter_FRS_2842_01.02.2025.pdf | - | Work In Progress | Required Master data is pending at Department's end. (Meeting held on 10th Feb) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
22 | SAPS | lnspection Module (Parakh App) | Letter | SAPS Letter from Dept to MPSEDC_Parakh Inspection.pdf | - | Work In Progress | UAT Completed & Went Live (In use by Dept) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Nitin Tiwari | 8894278707
22 | Satna District | Parakh _Survey Form Adhar Kendra Inspection/Data Collection | Letter | Parakh_Portal_Suggestions_District Satna.pdf Collector E governence District Satna.pdf | - | Work In Progress | Work completed. Issued for UAT on 13/02/25 | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Yogesh Tiwari | 8085144449
23 | Seoni District | Parakh _Survey Form ST/SC hostel | Letter | Prakhar letter Seoni District.pdf | - | Work In Progress | UAT Completed & Went Live (In use by Dept) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Shivhare | 9302469983
23 | कार्यालय कलेक्टर भोपाल म.प्र | Parakh _App_Hostel Survey | Letter | कार्यालय कलेक्टर भोपाल म.प्र.pdf | - |  | Work In Progress_ Hostel Survey on Parakh App | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | VIKAS GUPTA | 8305303857
24 | कार्यालय कलेक्टर (अनुसूचित जाति एवं जनजातीय कार्य विभाग ) भोपाल | Parakh _App_Hostel Survey | Letter | अनुसूचित जाति एवं जनजातीय कार्य विभाग_Hostel Survey.pdf | - |  | Work In Progress_ Hostel Survey on Parakh App | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | VIKAS GUPTA | 8305303857
24 | कार्यालय कलेक्टर (पिछड़ा वर्ग तथा अल्पसंख्यक कल्याण ) भोपाल | Parakh _App_Hostel Survey | Letter | पिछड़ा वर्ग तथा अल्पसंख्यक कल्याण_Hostel Survey.pdf | - |  | Work In Progress_ Hostel Survey on Parakh App | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | VIKAS GUPTA | 8305303857
25 | Ashoknagar Distrct | Sarthak App_Attendance Marking | Letter | Sarthak _Attendance Marking_Dist_AshokNagar.pdf | - |  | Work In Progress_ Sarthak App_Attendance Marking | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
25 | Rajgarh | lnspection Module (Parakh App) | Letter |  | - | Work In Progress | UAT Completed & Went Live (In use by Dept) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
26 | PNRD RES | MP MLA CM A CM A+ & Ghoshna Form | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Veertika
26 | Jabalpur | Hospital Inspection form | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Sandeep Chaurasia
27 | Jabalpur | Grameen Vikas Panchyat Grading live | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Sandeep Chaurasia
27 | Chhattarpur | Grocery, Hostel , & General Inspection form | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
28 | MGNREGA Dynamic Form Creation | lnspection Module (Parakh App) | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Kratika Avi sir
| UADD SQM Inspection Form | lnspection Module (Parakh App) | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Uday Dharmendra sir
| Narmadapuram | Health Inspection Form | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
| Vidisha | Hostel Inspection Form
| Vidisha | NRC Inspection Form, Primary middle school Inspection Form, Anganwadi inspection form

## MeiTY District
S. No | District | Initiative | Request Received on (Letter / Verbal) | Lettes | District Level SPOC | Current Status | Project Manager | Vertical | OIC | DeGM Name | DeGM Contact Number
1 | Harda | Inspection_Parakh | - | single window 2-1 Harda Parakh.pdf | - | Work in Progress | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
2 | Seoni District | Parakh _Survey Form ST/SC hostel | Letter | Prakhar letter Seoni District.pdf | - | UAT is In-Progress for 1st Inspection form. Development for 2nd Form is in progress. Target 17/02/2025 | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Shivhare | 9302469983
3 | Rajgarh District | Hostel Inspection (Parakh) | Letter | Rajgarh District Hostel Inspection Letter.pdf | - | UAT In-Progress. Work completed on 05-02-2025. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
4 | Ujjain | उज्जैनी विक्रन, व्यापार मेला 2025 हेतु Geo-tracking software _ Parakh | Letter | उज्जैनी विक्रन, व्यापार मेला 2025 हेतु Geo-tracking software बनाये जाने के संबध मे।.pdf | - | Work in Progress | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
5 | Seoni District | जिला सिवनी ड्रोन सर्वे कराये जाने के संबंध | Letter | Collector Seoni letter for Drone Survey.pdf |  | Work Done, Data Submited to Department, Also Data Upload in District GIS Portal | Anoop Patel | GIS | Dr. Sandeep Goyal