## Parakh
Sr.No | Module Name | Added Dated | Last Modified Dated | Status | Work Status | Uploaded Document | SRS Plan Start Date ¦ End Date | SRS Actual Start Date ¦ End Date | Development Plan Start Date ¦ End Date | Development Actual Start Date ¦ End Date | Testing Plan Start Date ¦ End Date | Testing Actual Start Date ¦ End Date | UAT Plan Start Date ¦ End Date | UAT Actual Start Date ¦ End Date | Go Live Plan Date | Go Live Actual Date | Design Plan Start Date ¦ End Date | Design Actual Start Date ¦ End Date | Action
Sandeep Narmadapuram - Hospital Spelling correction, Survey date
Veerthika MP MLA BRD Doc creation
Jabalpur update - UAT testing Remark Feature added
Adarsh Training on Tribal
Veerthika MP MLA flow
| Jabalpur requirement | 10 page form
1 | Mandla - Wash on Wheels |  |  |  | InProgress
2 | Dhar Mandir Survey | will go into GAM |  |  | InProgress
3 | Chattarpur - Grocery, Hostel & General Form | 19/08/2025 | 19/08/2025 | Active | Is Live Completed |  | 07/08/2025 ¦ 07/08/2025 | 07/08/2025 ¦ 07/08/2025 | 12/08/2025 ¦ 13/08/2025 | 13/08/2025 ¦ 13/08/2025 | 14/08/2025 ¦ 14/08/2025 | 14/08/2025 ¦ 14/08/2025 | 14/08/2025 ¦ 14/08/2025 | 14/08/2025 ¦ 14/08/2025 | 14/08/2025 | 14/08/2025 | 08/08/2025 ¦ 11/08/2025 | 11/08/2025 ¦ 11/08/2025
4 | P&RD Department | 14/07/2025 | 25/07/2025 | Active | Completed |  | 14/07/2025 ¦ 16/07/2025 | 14/07/2025 ¦ 16/07/2025 | 14/07/2025 ¦ 20/07/2025 | 14/07/2025 ¦ 20/07/2025 | 16/07/2025 ¦ 20/07/2025 | 16/07/2025 ¦ 18/07/2025 | 16/07/2025 ¦ 16/07/2025 | 16/07/2025 ¦ 18/07/2025 | 16/07/2025 | 21/07/2025
5 | Agar Malwa - स्वस्थ यकृत मिशन inspection form | 2025-01-07 | 2025-03-07 | Active | Completed |  | 30/06/2025 ¦ 30/07/2025 | 30/06/2025 ¦ 30/06/2025 | 30/06/2025 ¦ 30/06/2025 | 30/06/2025 | 30/06/2025 ¦ 30/06/2025 | 30/06/2025 ¦ 30/06/2025 | 30/06/2025 | 30/06/2025 | 2025-02-07 | 2025-02-07
6 | Agar Malwa | 30/06/2025 | 25/07/2025 | Active |  |  | 30/06/2025 ¦ 01/07/2025 | 30/06/2025 ¦ 01/07/2025 | 01/07/2025 ¦ 06/07/2025 | 01/07/2025 ¦ 06/07/2025 | 03/07/2025 ¦ 07/07/2025 | 03/07/2025 ¦ 07/07/2025 | 07/07/2025 ¦ 08/07/2025 | 07/07/2025 ¦ 08/07/2025 | 2025-09-07 | 2025-09-07
7 | Parakh Enhancement | 16/06/2025 | 25/07/2025 | Active |  |  | 16/06/2025 ¦ 24/06/2025 | 16/06/2025 ¦ 24/06/2025 | 24/06/2025 ¦ 03/08/2025 | 24/06/2025 | [5 empty] | 31/08/2025
8 | Assets Survey | 2025-10-06 | 25/07/2025 | Active |  |  | 10/06/2025 ¦ 10/06/2025 | 10/06/2025 ¦ 10/06/2025 | 10/06/2025 ¦ 10/06/2025 | 10/06/2025 ¦ 10/06/2025 | 10/06/2025 ¦ 11/06/2025 | 10/06/2025 ¦ 11/06/2025 | 11/06/2025 ¦ 11/06/2025 | 11/06/2025 ¦ 11/06/2025 | 2025-12-06 | 2025-12-06
9 | धरती आबा | 2025-03-06 | 25/07/2025 | Active |  |  | 20/05/2025 ¦ 23/05/2025 | 20/05/2025 ¦ 23/05/2025 | 22/05/2025 ¦ 02/06/2025 | 22/05/2025 ¦ 02/06/2025 | 28/05/2025 ¦ 05/06/2025 | 28/05/2025 ¦ 05/06/2025 | 06/06/2025 ¦ 11/06/2025 | 06/06/2025 ¦ 11/06/2025 | 2025-12-06 | 2025-12-06
10 | assets mapping- Dis.GIS | 22/05/2025 | 17/06/2025 | Inactive | [8 empty] | 13/06/2025 |  | 16/06/2025
11 | Commissioner Office | 22/05/2025 | 25/07/2025 | Active |  |  | 06/11/2024 ¦ 08/11/2024 | 06/11/2024 ¦ 08/11/2024 | 08/11/2024 ¦ 15/11/2024 | 08/11/2024 ¦ 15/11/2024 | 11/11/2024 ¦ 15/11/2024 | 11/11/2024 ¦ 15/11/2024 | 18/11/2024 ¦ 22/11/2024 | 18/11/2024 ¦ 30/11/2024 | 31/07/2025
12 | Bhopal Collected Office | 22/05/2025 | 25/07/2025 | Active |  |  | 06/11/2024 ¦ 08/11/2024 | 06/11/2024 ¦ 08/11/2024 | 08/11/2024 ¦ 15/11/2024 | 08/11/2024 ¦ 15/11/2024 | 11/11/2024 ¦ 15/11/2024 | 11/11/2024 ¦ 15/11/2024 | 18/11/2024 ¦ 20/12/2025 | 18/11/2024 ¦ 04/06/2025 | 2025-05-06 | 2025-05-06
13 | अशोकनगर जिले में मैटरनल हेल्थ कैंप के निरीक्षण हेत | 22/05/2025 | 25/07/2025 | Active |  |  | 24/02/2025 ¦ 02/03/2025 | 24/02/2025 ¦ 02/03/2025 | 02/03/2025 ¦ 21/04/2025 | 02/03/2025 ¦ 21/04/2025 | 18/04/2025 ¦ 03/05/2025 | 18/04/2025 ¦ 03/05/2025 | 04/05/2025 ¦ 13/05/2025 | 04/05/2025 ¦ 13/05/2025 | 14/05/2025 | 14/05/2025
14 | Districts reports - 3 | 29/04/2025 | 20/06/2025 | Active | [11 empty] | 15/05/2025
15 | Districts reports - 2 | 2025-08-04 | 20/06/2025 | Active | [11 empty] | 30/04/2025
16 | Districts Reports - 1 | 18/03/2025 | 20/06/2025 | Active | [11 empty] | 31/03/2025
17 | Tribal Affairs Department | 17/03/2025 | 25/07/2025 | Active |  |  | 25/02/2025 ¦ 10/03/2025 | 25/02/2025 ¦ 10/03/2025 | 11/03/2025 ¦ 10/05/2025 | 11/03/2025 ¦ 10/05/2025 | 27/04/2025 ¦ 29/05/2025 | 27/04/2025 ¦ 29/05/2025 | 30/05/2025 ¦ 14/06/2025 | 30/05/2025 ¦ 14/06/2025 | 15/06/2025 | 15/06/2025
18 | Tribal Department | 2025-10-03 | 20/06/2025 | Inactive
19 | Dindori Collectorate Forms (Parakh) | 2025-04-03 | 25/07/2025 | Active |  |  | 07/01/2025 ¦ 13/01/2025 | 07/01/2025 ¦ 13/01/2025 | 14/01/2025 ¦ 26/02/2025 | 14/01/2025 ¦ 26/02/2025 | 05/02/2025 ¦ 03/03/2025 | 05/02/2025 ¦ 03/03/2025 | 04/03/2025 ¦ 10/03/2025 | 04/03/2025 ¦ 10/03/2025 | 2025-11-03 | 2025-11-03
20 | Rajgarh Collector Office's- Hostel Inspection Form | 2025-04-03 | 25/07/2025 | Active |  |  | 31/01/2025 ¦ 31/01/2025 | 31/01/2025 ¦ 31/01/2025 | 01/02/2025 ¦ 04/02/2025 | 01/02/2025 ¦ 04/02/2025 | 02/02/2025 ¦ 05/02/2025 | 02/02/2025 ¦ 05/02/2025 | 05/02/2025 ¦ 23/04/2025 | 05/02/2025 ¦ 23/04/2025 | 24/04/2025 | 24/04/2025
21 | Narwadapuram Collector Office | 2025-04-03 | 25/07/2025 | Active |  |  | 19/02/2025 ¦ 22/02/2025 | 19/02/2025 ¦ 22/02/2025 | 21/07/2025 ¦ 02/03/2025 | 21/07/2025 ¦ 02/03/2025 | 26/02/2025 ¦ 04/03/2025 | 26/02/2025 ¦ 04/03/2025 | 04/03/2025 ¦ 06/03/2025 | 04/03/2025 ¦ 06/03/2025 | 2025-07-03 | 2025-07-03
22 | SAps for LKS Inspection Form | 2025-04-03 | 25/07/2025 | Active |  |  | 31/01/2025 ¦ 02/02/2025 | 31/01/2025 ¦ 02/02/2025 | 01/02/2025 ¦ 12/02/2025 | 01/02/2025 ¦ 12/02/2025 | 07/02/2025 ¦ 14/02/2025 | 07/02/2025 ¦ 14/02/2025 | 15/02/2025 ¦ 17/02/2025 | 15/02/2025 ¦ 17/02/2025 | 18/02/2025 | 18/02/2025
23 | Seoni- Hostel Inspection Form & Hostel Food Qualit | 2025-04-03 | 25/07/2025 | Active |  |  | 24/01/2025 ¦ 27/01/2025 | 24/01/2025 ¦ 27/01/2025 | 27/01/2025 ¦ 03/02/2025 | 27/01/2025 ¦ 03/02/2025 | 03/02/2025 ¦ 07/02/2025 | 03/02/2025 ¦ 07/02/2025 | 10/02/2025 ¦ 14/02/2025 | 10/02/2025 ¦ 24/07/2025 | 21/02/2025 | 25/02/2025
24 | Bhind- Hostel Survey | 2025-04-03 | 25/07/2025 | Active |  |  | 05/02/2025 ¦ 18/02/2025 | 05/02/2025 ¦ 18/02/2025 | 18/02/2025 ¦ 19/03/2025 | 18/02/2025 ¦ 19/03/2025 | 10/03/2025 ¦ 24/03/2025 | 10/03/2025 ¦ 24/03/2025 | 25/03/2025 ¦ 29/03/2025 | 25/03/2025 ¦ 29/03/2025 | 30/03/2025 | 30/03/2025
25 | Vidisha-Hostel survey | 2025-04-03 | 25/07/2025 | Active |  |  | 10/01/2025 ¦ 14/01/2025 | 10/01/2025 ¦ 14/01/2025 | 14/01/2025 ¦ 15/01/2025 | 14/01/2025 ¦ 15/01/2025 | 16/01/2025 ¦ 17/01/2025 | 16/01/2025 ¦ 17/01/2025 | 17/01/2025 ¦ 20/01/2025 | 17/01/2025 ¦ 13/02/2025 | 28/02/2025 | 21/02/2025
26 | Damoh-School & Hostel Survey | 2025-04-03 | 25/07/2025 | Active |  |  | 01/01/2025 ¦ 04/07/2025 | 10/01/2025 ¦ 04/07/2025 | 03/07/2025 ¦ 14/01/2025 | 03/07/2025 ¦ 14/01/2025 | 14/01/2025 ¦ 16/01/2025 | 14/01/2025 ¦ 16/01/2025 | 16/01/2025 ¦ 28/02/2025 | 16/01/2025 ¦ 24/02/2025 | 24/02/2025 | 24/02/2025
27 | Chhindwara-Wash on wheel & School Survey | 2025-04-03 | 25/07/2025 | Active |  |  | 20/09/2024 ¦ 04/10/2024 | 20/09/2024 ¦ 04/10/2024 | 02/10/2024 ¦ 22/12/2024 | 02/10/2024 ¦ 22/12/2024 | 06/12/2024 ¦ 03/01/2025 | 06/12/2024 ¦ 03/01/2025 | 03/01/2025 ¦ 21/01/2025 | 03/01/2025 ¦ 21/01/2025 | 22/01/2025 | 22/01/2025
28 | Alirajpur Collector Office | 2025-04-03 | 25/07/2025 | Active |  |  | 02/09/2024 ¦ 10/09/2024 | 02/09/2024 ¦ 10/09/2024 | 10/09/2024 ¦ 20/10/2024 | 10/09/2024 ¦ 20/10/2024 | 14/10/2024 ¦ 25/10/2024 | 14/10/2024 ¦ 25/10/2024 | 25/10/2024 ¦ 03/11/2024 | 25/10/2024 ¦ 03/11/2024 | 2024-04-11 | 2024-04-11

## GIS Web
Sr.No | Module Name | Added Dated | Last Modified Dated | Status | Work Status | Uploaded Document | SRS Plan Start Date ¦ End Date | SRS Actual Start Date ¦ End Date | Development Plan Start Date ¦ End Date | Development Actual Start Date ¦ End Date | Testing Plan Start Date ¦ End Date | Testing Actual Start Date ¦ End Date | UAT Plan Start Date ¦ End Date | UAT Actual Start Date ¦ End Date | Go Live Plan Date | Go Live Actual Date | Design Plan Start Date ¦ End Date | Design Actual Start Date ¦ End Date | Action

## E-Khanij
Sr.No | Module Name | Added Dated | Last Modified Dated | Status | Work Status | Uploaded Document | SRS Plan Start Date ¦ End Date | SRS Actual Start Date ¦ End Date | Development Plan Start Date ¦ End Date | Development Actual Start Date ¦ End Date | Testing Plan Start Date ¦ End Date | Testing Actual Start Date ¦ End Date | UAT Plan Start Date ¦ End Date | UAT Actual Start Date ¦ End Date | Go Live Plan Date | Go Live Actual Date | Design Plan Start Date ¦ End Date | Design Actual Start Date ¦ End Date | Action