## Cover Note
District GIS Parakh Project — Consolidated User Stories Register
Period Covered: 30-Jun-2026 to 18-Aug-2026
Prepared for: MPSSDI / MPSeDC — District GIS Parakh Project
Total User Stories: 140
Districts / Departments Covered: 76
Scope
This register consolidates user stories for the District GIS Parakh platform covering:
• District & department-specific inspection form onboarding across districts (per the PSR District Initiatives log)
• Betul district — 8-form rollout (KGBV, PM Poshan, WCD Anganwadi, School Monitoring, Health, Mining, Aadhaar Centre, Tribal Hostel), including field-level changes (Q16/17, Sector->Gram conditional master data)
• Damoh district — 13-form rollout (BBGRAMJI, PMAY, Gram Nal Jal Praday, School/Institute, Anganwadi, Jan Vishwas Health, Fair Price Shop, Petrol Pump, LPG Dealer, Farm & Dairy, Liquor, Hostel/Ashram, Krishi Saakh/Cooperative)
• Indore district — 17-form multi-department rollout (Phase 1 & 2), Property Inspection, Sugamya Abhiyaan, Jan Vishwas
• Workflow Management: Action Taken Report (ATR) for Tribal Department; Roster of Nirikshan Karta for MP Cooperative
• CTA Treasury & JD Inspection forms
• Asset Survey module (User Creation -> Asset Creation -> Assignment -> Survey)
• PM Poshan Social Audit inspection form and training
• State-level master form standardization (Aadhar Centre form) and platform enhancements (report sync, dynamic reports)
Sources
• Parakh – District Level Initiatives GIS (PSR2) workbook — District Initiatives & Parakh Internal Work sheets
• WhatsApp project coordination thread, 30-Jun-2026 to 03-Jul-2026 (Dheeraj, Madhur Nema, Manisha, Ajeet Singh)
• Asset Survey User Manual v1.2 (24-Jul-2026); MP Cooperative Nirikshan BRD (modified 29-Jul-2026)
• District GIS Parakh Consolidated Bilingual User Manual v2.0, Sudden Inspection Manual, User Manual v1.2 (13-Aug-2026)
• Indore Inspection Spec Overview (8-Aug-2026); Indore User Manual (12–15-Aug-2026)
Note: Dates shown in individual stories reflect the source document/message date where available; items
sourced only from the cumulative PSR status log are marked 'PSR Log' without a specific date.

## User Stories
S.No | User Story ID | District / Department | Module / Initiative | Epic / Category | User Story | Acceptance Criteria | Priority | Status | Source / Reference | Remarks / Pending Items
1 | US-PARAKH-001 | Alirajpur | Hostel Survey (Parakh) | District/Department Form Onboarding | As a Field Surveyor in Alirajpur, I want the 'Hostel Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Medium | Completed | Letter
2 | US-PARAKH-002 | Chhindwara | Wash on wheel (Parakh) | District/Department Form Onboarding | As a District Nodal Officer in Chhindwara, I want the 'Wash on wheel (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Medium | Completed | Letter
3 | US-PARAKH-003 | Chhindwara | School Survey (Parakh) | District/Department Form Onboarding | As a Field Surveyor in Chhindwara, I want the 'School Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT completed. Go Live | Medium | Pending Department Action | Letter
4 | US-PARAKH-004 | Khargone | Inspection Mobile App on (Parakh) | District/Department Form Onboarding | As a Inspecting Officer in Khargone, I want the 'Inspection Mobile App on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | The current collector of Khargone has changed. The new collector will decide whether this project will proceed or not, and if it does, how the work will be carried forward. | High | In Progress | Direction by MD / APD Sir
5 | US-PARAKH-005 | Damoh | School & Hostel Survey (Parakha) | District/Department Form Onboarding | As a Field Surveyor in Damoh, I want the 'School & Hostel Survey (Parakha)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Go-live | Medium | Completed | Letter
6 | US-PARAKH-006 | Burhanpur | Inspection Mobile App on (Parakh) | District/Department Form Onboarding | As a Inspecting Officer in Burhanpur, I want the 'Inspection Mobile App on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Medium | Completed | Letter
7 | US-PARAKH-007 | Zila Punchayat , Anuppur | Anuppur Works Management System (Mobile wire frames for WMS) | District/Department Form Onboarding | As a District Nodal Officer in Zila Punchayat , Anuppur, I want the 'Anuppur Works Management System (Mobile wire frames for WMS)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress | High | In Progress | With COE
8 | US-PARAKH-008 | Tikamgarh , Collectorate | Inspection Mobile App on (Parakh) | District/Department Form Onboarding | As a Inspecting Officer in Tikamgarh , Collectorate, I want the 'Inspection Mobile App on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT completed. Awaiting approval from the Collectorate to Go Live | Medium | Pending Department Action | Letter
9 | US-PARAKH-009 | Dindori , Collectorate | School Survey, Hostel, Anganbadi, PDS Center Extra Inspection App (Parakh) | District/Department Form Onboarding | As a Field Surveyor in Dindori , Collectorate, I want the 'School Survey, Hostel, Anganbadi, PDS Center Extra Inspection App (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Medium | Completed | Letter
10 | US-PARAKH-010 | Vidisha | Hostel Survey (Parakh) | District/Department Form Onboarding | As a Field Surveyor in Vidisha, I want the 'Hostel Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Medium | Completed | Direction by MD / APD Sir
11 | US-PARAKH-011 | Bhind | Drone Survey | District/Department Form Onboarding | As a Field Surveyor in Bhind, I want the 'Drone Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Medium | Completed | Letter
12 | US-PARAKH-012 | Chhatarpur Dist | Creation Google form , Login ID Password | District/Department Form Onboarding | As a District Nodal Officer in Chhatarpur Dist, I want the 'Creation Google form , Login ID Password' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | they will preparing our form and sending it from the Tikamgarh department, but they have also requested Alirajgarh's Parhak credentials for review. | High | In Progress | Letter
13 | US-PARAKH-013 | Khandwa | Drone Urban Survey | District/Department Form Onboarding | As a Field Surveyor in Khandwa, I want the 'Drone Urban Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Drone survey is in process. | High | In Progress | Direction by ACS Sir
14 | US-PARAKH-014 | Rewa | Scanning of (Old Revenue / Naksha Record of Rewa (14399 Sheets) | District/Department Form Onboarding | As a District Nodal Officer in Rewa, I want the 'Scanning of (Old Revenue / Naksha Record of Rewa (14399 Sheets)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work in Progress (Till Date 2793 sheets done) | Medium | Completed | Letter
15 | US-PARAKH-015 | Bhopal commissioner office | General Inspection on (Parakh) | District/Department Form Onboarding | As a Inspecting Officer in Bhopal commissioner office, I want the 'General Inspection on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Live | Medium | Completed | Letter
16 | US-PARAKH-016 | Patan | Satellite data based maps for Urban Local Body boundary extension | District/Department Form Onboarding | As a District Nodal Officer in Patan, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Medium | Completed | Letter
17 | US-PARAKH-017 | Sidhi | Satellite data based maps for Urban Local Body boundary extension | District/Department Form Onboarding | As a District Nodal Officer in Sidhi, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Medium | Completed | Letter
18 | US-PARAKH-018 | Sagar | Satellite data based maps for Urban Local Body boundary extension | District/Department Form Onboarding | As a District Nodal Officer in Sagar, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Medium | Completed | Letter
19 | US-PARAKH-019 | Narsinghpur | Satellite data based maps for Urban Local Body boundary extension | District/Department Form Onboarding | As a District Nodal Officer in Narsinghpur, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Medium | Completed | Letter
20 | US-PARAKH-020 | Bhind | Hostel Survey (Parakh) | District/Department Form Onboarding | As a Field Surveyor in Bhind, I want the 'Hostel Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Bhind Collectorate is onboarded. Development work completed. Awaiting list of Hostels from the Collectorate office, so to initiate UAT. | Medium | Pending Department Action | Letter
21 | US-PARAKH-021 | Chhatarpur Dist | Creation Google form , Login ID Password | District/Department Form Onboarding | As a District Nodal Officer in Chhatarpur Dist, I want the 'Creation Google form , Login ID Password' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Live | High | In Progress | Letter
22 | US-PARAKH-022 | Narmadapuram | Sarthak _Attendance / Parakh | District/Department Form Onboarding | As a Nodal Attendance Officer in Narmadapuram, I want the 'Sarthak _Attendance / Parakh' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Medium | Completed | Letter
23 | US-PARAKH-023 | Narmadapuram | Hostel Inpection , Adharcard Inpection , aganwadi Inpection, Goverment School Inpection | District/Department Form Onboarding | As a Hostel Inspecting Officer in Narmadapuram, I want the 'Hostel Inpection , Adharcard Inpection , aganwadi Inpection, Goverment School Inpection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Medium | Proposed | Letter
24 | US-PARAKH-024 | Narmadapuram | Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म | District/Department Form Onboarding | As a Inspecting Officer in Narmadapuram, I want the 'Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | The form has arrived, UAT has been sent, and testing has started. | Medium | Completed | Letter
25 | US-PARAKH-025 | rajgarh | छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey | District/Department Form Onboarding | As a Field Surveyor in rajgarh, I want the 'छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | The form has arrived, UAT has been sent, and testing has started. | Medium | Completed | Letter
26 | US-PARAKH-026 | seoni | छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म | District/Department Form Onboarding | As a District Nodal Officer in seoni, I want the 'छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Medium | Completed | Letter
27 | US-PARAKH-027 | Saps | LKS Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in Saps, I want the 'LKS Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Go-live | Medium | Completed | PSR Log
28 | US-PARAKH-028 | Tribale department | जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र | District/Department Form Onboarding | As a District Nodal Officer in Tribale department, I want the 'जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work complete | Medium | Completed | PSR Log
29 | US-PARAKH-029 | SAPS | lnspection Module (Parakh App) | District/Department Form Onboarding | As a District Nodal Officer in SAPS, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Medium | Completed | Letter
30 | US-PARAKH-030 | Satna District | Parakh _Survey Form Adhar Kendra Inspection/Data Collection | District/Department Form Onboarding | As a Field Surveyor in Satna District, I want the 'Parakh _Survey Form Adhar Kendra Inspection/Data Collection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work completed. Issued for UAT on 13/02/25 | High | In Progress | Letter
31 | US-PARAKH-031 | Seoni District | Parakh _Survey Form ST/SC hostel | District/Department Form Onboarding | As a Field Surveyor in Seoni District, I want the 'Parakh _Survey Form ST/SC hostel' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Medium | Completed | Letter
32 | US-PARAKH-032 | कार्यालय कलेक्टर भोपाल म.प्र | Parakh _App_Hostel Survey | District/Department Form Onboarding | As a Field Surveyor in कार्यालय कलेक्टर भोपाल म.प्र, I want the 'Parakh _App_Hostel Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Hostel Survey on Parakh App | High | In Progress | Letter
33 | US-PARAKH-033 | कार्यालय कलेक्टर (अनुसूचित जाति एवं जनजातीय कार्य विभाग ) भोपाल | Parakh _App_Hostel Survey | District/Department Form Onboarding | As a Field Surveyor in कार्यालय कलेक्टर (अनुसूचित जाति एवं जनजातीय कार्य विभाग ) भोपाल, I want the 'Parakh _App_Hostel Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Hostel Survey on Parakh App | High | In Progress | Letter
34 | US-PARAKH-034 | कार्यालय कलेक्टर (पिछड़ा वर्ग तथा अल्पसंख्यक कल्याण ) भोपाल | Parakh _App_Hostel Survey | District/Department Form Onboarding | As a Field Surveyor in कार्यालय कलेक्टर (पिछड़ा वर्ग तथा अल्पसंख्यक कल्याण ) भोपाल, I want the 'Parakh _App_Hostel Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Hostel Survey on Parakh App | High | In Progress | Letter
35 | US-PARAKH-035 | Ashoknagar Distrct | Sarthak App_Attendance Marking | District/Department Form Onboarding | As a Nodal Attendance Officer in Ashoknagar Distrct, I want the 'Sarthak App_Attendance Marking' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Sarthak App_Attendance Marking | High | In Progress | Letter
36 | US-PARAKH-036 | Rajgarh | lnspection Module (Parakh App) | District/Department Form Onboarding | As a District Nodal Officer in Rajgarh, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Medium | Completed | Letter
37 | US-PARAKH-037 | PNRD RES | MP MLA CM A CM A+ & Ghoshna Form | District/Department Form Onboarding | As a District Nodal Officer in PNRD RES, I want the 'MP MLA CM A CM A+ & Ghoshna Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Medium | Proposed | PSR Log
38 | US-PARAKH-038 | Jabalpur | Hospital Inspection form | District/Department Form Onboarding | As a Inspecting Officer in Jabalpur, I want the 'Hospital Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Medium | Proposed | PSR Log
39 | US-PARAKH-039 | Jabalpur | Grameen Vikas Panchyat Grading live | District/Department Form Onboarding | As a District Nodal Officer in Jabalpur, I want the 'Grameen Vikas Panchyat Grading live' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed and went live | Medium | Completed | PSR Log
40 | US-PARAKH-040 | Chhattarpur | Grocery, Hostel , & General Inspection form | District/Department Form Onboarding | As a Inspecting Officer in Chhattarpur, I want the 'Grocery, Hostel , & General Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Medium | Proposed | PSR Log
41 | US-PARAKH-041 | MGNREGA Dynamic Form Creation | lnspection Module (Parakh App) | District/Department Form Onboarding | As a District Nodal Officer in MGNREGA Dynamic Form Creation, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Dynamic Form - Meeting Video Link Meeting Recording Notes | Medium | Proposed | PSR Log
42 | US-PARAKH-042 | Bhopal - UADD Department SQM Inspection Form | lnspection Module (Parakh App) | District/Department Form Onboarding | As a District Nodal Officer in Bhopal - UADD Department SQM Inspection Form, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form in UAT. But no call back from the department. Waiting for their confirmation. | Medium | Proposed | PSR Log
43 | US-PARAKH-043 | Narmadapuram | Health Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in Narmadapuram, I want the 'Health Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Medium | Completed | PSR Log
44 | US-PARAKH-044 | Vidisha | Hostel Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in Vidisha, I want the 'Hostel Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Medium | Completed | PSR Log
45 | US-PARAKH-045 | Vidisha | NRC Inspection Form, Primary middle school Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in Vidisha, I want the 'NRC Inspection Form, Primary middle school Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Medium | Completed | PSR Log
46 | US-PARAKH-046 | Vidisha | Pharmacist Medical Drug store form, Anganwadi inspection form | District/Department Form Onboarding | As a Inspecting Officer in Vidisha, I want the 'Pharmacist Medical Drug store form, Anganwadi inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Need Clarifications form department on few questions ¦ Pending with: District Collectorate | Medium | Proposed | PSR Log
47 | US-PARAKH-047 | Bhind | Mgnrega work related inspection form | District/Department Form Onboarding | As a Inspecting Officer in Bhind, I want the 'Mgnrega work related inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Completed | Medium | Completed | PSR Log
48 | US-PARAKH-048 | Mandla | PM School, Awas and AAdhar center | District/Department Form Onboarding | As a School Inspecting Officer in Mandla, I want the 'PM School, Awas and AAdhar center' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form and report Deployed ¦ Pending with: Distrcit collectorate - GIS executive - Ankita Soni 1) to clarify on pm poshan form to incorporate same like mgnrega one | Medium | Completed | PSR Log
49 | US-PARAKH-049 | Sehore | School Inspection FOrm | District/Department Form Onboarding | As a Inspecting Officer in Sehore, I want the 'School Inspection FOrm' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in UAT. Email sent to District collectorate & GIS executive ¦ Pending with: District Collectorate | Medium | Completed | PSR Log
50 | US-PARAKH-050 | Ayush Department | Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in Ayush Department, I want the 'Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Departement onboarded on uat. department to share survey form ¦ Pending with: Subhee Nema | Medium | Proposed | PSR Log
51 | US-PARAKH-051 | Guna | Anganwadi | District/Department Form Onboarding | As a Anganwadi Inspecting Officer in Guna, I want the 'Anganwadi' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created in Uat, Email sent to District collectorate & GIS executive, confirmation required from the District Collectorate & GIS executive ¦ Pending with: Manisha | Medium | Completed | PSR Log
52 | US-PARAKH-052 | Health Department | 1. DISTRICT / CIVIL / SUPER SPECIALITY HOSPITAL (जिला / सिविल / सुपर स्पेशियलिटी अस्पताल) 2. COMMUNITY HEALTH CENTRE (सामुदायिक स्वास्थ्य केंद्र (सीएच | District/Department Form Onboarding | As a Health Inspecting Officer in Health Department, I want the '1. DISTRICT / CIVIL / SUPER SPECIALITY HOSPITAL (जिला / सिविल / सुपर स्पेशियलिटी अस्पताल) 2. COMMUNITY HEALTH CENTRE (सा' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in prod . chase department for progress ¦ Pending with: Ajeet | Medium | Pending Department Action | PSR Log
53 | US-PARAKH-053 | School Education Department | form is live but awaiting for autopopulation | District/Department Form Onboarding | As a District Nodal Officer in School Education Department, I want the 'form is live but awaiting for autopopulation' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in prod . chase department for autopopulation of School list ¦ Pending with: Madhur/ Dheeraj and Altamsah | Medium | Pending Department Action | PSR Log
54 | US-PARAKH-054 | Labour Department | Intergration with CIS system for user onboarding , establishment, and form to establishment mapping | District/Department Form Onboarding | As a District Nodal Officer in Labour Department, I want the 'Intergration with CIS system for user onboarding , establishment, and form to establishment mapping' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Completed ¦ Pending with: Madhur | Medium | Completed | PSR Log
55 | US-PARAKH-055 | MGNREGA PM Poshan Department | This form comes Under Sate coordinator PM Poshan Department Social Audit of schools Scheme | District/Department Form Onboarding | As a School Inspecting Officer in MGNREGA PM Poshan Department, I want the 'This form comes Under Sate coordinator PM Poshan Department Social Audit of schools Scheme' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Deployed to Prod ¦ Pending with: Department | Medium | Completed | PSR Log
56 | US-PARAKH-056 | PNRD NRM PMKSY | Inspection on Watershed projects ( project name and related work cost ) | District/Department Form Onboarding | As a Inspecting Officer in PNRD NRM PMKSY, I want the 'Inspection on Watershed projects ( project name and related work cost )' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in UAT. Email sent to department, ¦ Pending with: Department | Medium | Proposed | PSR Log
57 | US-PARAKH-057 | MP Cooperative | Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in MP Cooperative, I want the 'Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | 1) Department Creating the structure of complete document 2) Updating sections and subsections into the format ¦ Pending with: Department Souresh Kulshetra | Medium | Proposed | PSR Log
58 | US-PARAKH-058 | Agar Malwa | Narcotics Drug Form | District/Department Form Onboarding | As a District Nodal Officer in Agar Malwa, I want the 'Narcotics Drug Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Deployed to Prod, email need to be sent ¦ Pending with: Development team/ Dheeraj | Medium | Completed | PSR Log
59 | US-PARAKH-059 | MPHIDB | Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in MPHIDB, I want the 'Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created on UAT ¦ Pending with: Ajeet | Medium | Proposed | PSR Log
60 | US-PARAKH-060 | Chhindwara | Feedback form | District/Department Form Onboarding | As a Department Feedback Coordinator in Chhindwara, I want the 'Feedback form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | deployed to Prod , email sent ¦ Pending with: Manisha | Medium | Completed | PSR Log
61 | US-PARAKH-061 | Ashoknagar Distrct | Hostel Inspection | District/Department Form Onboarding | As a Inspecting Officer in Ashoknagar Distrct, I want the 'Hostel Inspection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | adopted tribal department form | Medium | Proposed | PSR Log
62 | US-PARAKH-062 | Gwalior | School, Hostel, Anganwadi, Health Center | District/Department Form Onboarding | As a Hostel Inspecting Officer in Gwalior, I want the 'School, Hostel, Anganwadi, Health Center' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form/report created and deployed,email sent ¦ Pending with: Waiting for mail confirmation | Medium | Completed | PSR Log
63 | US-PARAKH-063 | Gwalior | Aadhar account verification form | District/Department Form Onboarding | As a District Nodal Officer in Gwalior, I want the 'Aadhar account verification form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form/report created and deployed,email sent ¦ Pending with: Waiting for mail confirmation | Medium | Completed | PSR Log
64 | US-PARAKH-064 | Burhanpur | Health Inspection form ,निरीक्षण प्रतिवेदन,गोदाम निरीक्षण | District/Department Form Onboarding | As a Inspecting Officer in Burhanpur, I want the 'Health Inspection form ,निरीक्षण प्रतिवेदन,गोदाम निरीक्षण' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form is live,report is created ¦ Pending with: Department | High | In Progress | Letter
65 | US-PARAKH-065 | Mandla (On Hold) | मनरेगा (MGNREGA) योजनांतगत नमाण काय के नर ण | District/Department Form Onboarding | As a District Nodal Officer in Mandla (On Hold), I want the 'मनरेगा (MGNREGA) योजनांतगत नमाण काय के नर ण' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Mandla district specific Department is not clear on requirement as conveyed by Ankita ¦ Pending with: Ankita Soni GIS Executive | Medium | Pending Department Action | Letter
66 | US-PARAKH-066 | Bhind | 75 वर्ष या उससे अधिक आयुके बिना सन्त लाभार्थियो हेतु मासिक सुविधा मॉनिटरिंग करने के लिए | District/Department Form Onboarding | As a District Nodal Officer in Bhind, I want the '75 वर्ष या उससे अधिक आयुके बिना सन्त लाभार्थियो हेतु मासिक सुविधा मॉनिटरिंग करने के लिए' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form and report is deployed on production, ¦ Pending with: Sakshi | Medium | Completed | Letter
67 | US-PARAKH-067 | PNRD-MGNREGA | SNA Sparsh अंतर्गत प्रशासकीय मद के भुगतान की जानकारी | District/Department Form Onboarding | As a District Nodal Officer in PNRD-MGNREGA, I want the 'SNA Sparsh अंतर्गत प्रशासकीय मद के भुगतान की जानकारी' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live ¦ Pending with: Dheeraj,Aman | Medium | Completed | PSR Log
68 | US-PARAKH-068 | Rajgarh | School Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in Rajgarh, I want the 'School Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created, awaiting for confirmation | Medium | Pending Department Action | Letter
69 | US-PARAKH-069 | Ashoknagar Distrct | Aganwadi | District/Department Form Onboarding | As a District Nodal Officer in Ashoknagar Distrct, I want the 'Aganwadi' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created ¦ Pending with: Madhur and arindham | Medium | Completed | Letter
70 | US-PARAKH-070 | Chhindwara | Adhar inspection | District/Department Form Onboarding | As a Inspecting Officer in Chhindwara, I want the 'Adhar inspection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created,email sent confirmed | Medium | Completed | Letter
71 | US-PARAKH-071 | Ujjain Mela | Ujjain Mela | District/Department Form Onboarding | As a District Nodal Officer in Ujjain Mela, I want the 'Ujjain Mela' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created and live | Medium | Completed | Letter
72 | US-PARAKH-072 | Bhopal commissioner office | Hostel Inspection Form(SC/ST category) | District/Department Form Onboarding | As a Inspecting Officer in Bhopal commissioner office, I want the 'Hostel Inspection Form(SC/ST category)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form is same as tribal department. Bhopal Commissioner Office has raised request for creation of the Tribal Inspection Form. This form is same as of the Tribal Hostel Inspection Forms launched by the Tribal Department. T | High | In Progress | Letter
73 | US-PARAKH-073 | PNRD-SRLM | Baseline Survey Form | District/Department Form Onboarding | As a Field Surveyor in PNRD-SRLM, I want the 'Baseline Survey Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created,email sent and waiting for department confirmation ¦ Pending with: Department | Medium | Completed | Letter
74 | US-PARAKH-074 | Ujjain | सरकारी स्कूल में शौचालय | District/Department Form Onboarding | As a District Nodal Officer in Ujjain, I want the 'सरकारी स्कूल में शौचालय' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is still not finalized from CEO ZP ¦ Pending with: Sakshi / ON Hold | High | In Progress | Letter
75 | US-PARAKH-075 | Indore | Sugamya Abhiyaan | District/Department Form Onboarding | As a District Nodal Officer in Indore, I want the 'Sugamya Abhiyaan' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created and live on production, report is created | Medium | Completed | PSR Log
76 | US-PARAKH-076 | Directorate Public Instructions | Hostel Inspection form | District/Department Form Onboarding | As a Inspecting Officer in Directorate Public Instructions, I want the 'Hostel Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created ¦ Pending with: Madhur | Medium | Proposed | PSR Log
77 | US-PARAKH-077 | Religious and Trust Endowment | Temple and Temple Land Details Form | District/Department Form Onboarding | As a District Nodal Officer in Religious and Trust Endowment, I want the 'Temple and Temple Land Details Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created on UAT ¦ Pending with: Bharat/Aman | High | In Progress | PSR Log
78 | US-PARAKH-078 | Bhopal - Food Department | Kharidi Kendra | District/Department Form Onboarding | As a District Nodal Officer in Bhopal - Food Department, I want the 'Kharidi Kendra' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form received from bhopal collectorate ¦ Pending with: Sakshi / Madhur | Medium | Proposed | PSR Log
79 | US-PARAKH-079 | Indore Collectorate | Property Inspection | District/Department Form Onboarding | As a Inspecting Officer in Indore Collectorate, I want the 'Property Inspection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created and Tested | High | In Progress | PSR Log
80 | US-PARAKH-080 | Rajgarh Collectorate | Hand-Pump Inspection form | District/Department Form Onboarding | As a Inspecting Officer in Rajgarh Collectorate, I want the 'Hand-Pump Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form Created & live | Medium | Completed | PSR Log
81 | US-PARAKH-081 | Guna & Gwalior | Patient Feedback Form | District/Department Form Onboarding | As a Department Feedback Coordinator in Guna & Gwalior, I want the 'Patient Feedback Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | HTML Form and QR Code Created | Medium | Completed | PSR Log
82 | US-PARAKH-082 | Betul | 6 forms - KGBV , PMPoshan, WCD Anganwadi, School Monitoring, Health form , Mining Form, AAdhar Center form, Tribal Hostel form | District/Department Form Onboarding | As a Hostel Inspecting Officer in Betul, I want the '6 forms - KGBV , PMPoshan, WCD Anganwadi, School Monitoring, Health form , Mining Form, AAdhar Center form, Tribal Hoste' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | 1) KGBV Form: Verified and approved by the DEO. 2) PM Poshan (PNRD) Form: Department Form verification is completed. Nodal assignment is pending. 3) WCD Form: Currently with the developer team, as modifications are requi ¦ Pending with: Pending items: 1) WCD form update from the developer team. 2) Update on the Mining form from the developer team. 3) Conf | Medium | Pending Department Action | 1st Letter Parakh Mining E-Governance letter
83 | US-PARAKH-083 | CTA | JD Inspection form and Treasury Inspection form | District/Department Form Onboarding | As a Inspecting Officer in CTA, I want the 'JD Inspection form and Treasury Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form Created ¦ Pending with: Pending from CTA Department | High | In Progress | PSR Log
84 | US-PARAKH-084 | Chhindwara | 5 forms - Anganwadi, PMPoshan, Godown, Hostel Monitoring, Health Form, | District/Department Form Onboarding | As a Hostel Inspecting Officer in Chhindwara, I want the '5 forms - Anganwadi, PMPoshan, Godown, Hostel Monitoring, Health Form,' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Forms are created and Live in Production. Report work is going on ¦ Pending with: Pending from Chhindwara Collectorate Department & Development team for Report | High | In Progress | Letter
85 | US-PARAKH-085 | Jabalpur | Building Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in Jabalpur, I want the 'Building Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Forms are created and Testing needs to be done ¦ Pending with: Pending from Jabalpur Collectorate Department | High | In Progress | Letter
86 | US-PARAKH-086 | MPRRD | Road Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in MPRRD, I want the 'Road Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | In UAT ¦ Pending with: Dev Team | High | In Progress | PSR Log
87 | US-PARAKH-087 | Mining Department | Mining Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in Mining Department, I want the 'Mining Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Forms created and Live in Production | Medium | Completed | PSR Log
88 | US-PARAKH-088 | MP Cooperative (Changes) | Inspection Form | District/Department Form Onboarding | As a Inspecting Officer in MP Cooperative (Changes), I want the 'Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | 1) Department Recreating the structure of complete document 2) Updating sections and subsections into the format 3) Revamping Inspection and including Rooster of Nirikshan karta Summary Change request document and BRD do ¦ Pending with: Department ICMIS - Devendra, Priya and Jyoti Ma'am. They have to review CRs and BRD dcoument | High | In Progress | PSR Log
89 | US-PARAKH-089 | Indore Inspection forms | Indore 17 forms | District/Department Form Onboarding | As a District Nodal Officer in Indore Inspection forms, I want the 'Indore 17 forms' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | 1) Phase 1 developed 2) Phase 2 Action taken and Divisional level work under progress ¦ Pending with: Department to finalize 17 forms | High | In Progress | PSR Log
90 | US-PARAKH-090 | Rajgarh | OBC Triabl Hostel form | District/Department Form Onboarding | As a Hostel Inspecting Officer in Rajgarh, I want the 'OBC Triabl Hostel form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created in UAT ¦ Pending with: Department to verify | High | In Progress | PSR Log
91 | US-PARAKH-091 | Damoh | BBGRAMJI Form Pradhan Mantri Awas Yojana Inspection Form Gram Nal Jal Praday Yojana Inspection Form School/Institute Inspection Form Anganwadi Inspect | District/Department Form Onboarding | As a Inspecting Officer in Damoh, I want the 'BBGRAMJI Form Pradhan Mantri Awas Yojana Inspection Form Gram Nal Jal Praday Yojana Inspection Form School/Institute Ins' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | ZIla Panchayat form created and live in Prod ¦ Pending with: Department sharing master data of other forms and parallely checking if any CR required from department end | High | In Progress | PSR Log
92 | US-PARAKH-092 | Guna | Ayush Department | District/Department Form Onboarding | As a District Nodal Officer in Guna, I want the 'Ayush Department' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form | High | In Progress | PSR Log
93 | US-PARAKH-093 | MP Metro | Plantation Form | District/Department Form Onboarding | As a District Nodal Officer in MP Metro, I want the 'Plantation Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | QR Code based functionality . Form created | High | In Progress | PSR Log
94 | US-PARAKH-094 | CTA - CRs Updates from Department | JD Inspection form and Treasury Inspection form | District/Department Form Onboarding | As a Inspecting Officer in CTA - CRs Updates from Department, I want the 'JD Inspection form and Treasury Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form Created ¦ Pending with: Pending from CTA Department | High | In Progress | PSR Log
95 | US-PARAKH-095 | Bhind | Patient Feedback form OPD/IPD Patient Satisfaction Survey Forms | District/Department Form Onboarding | As a Field Surveyor in Bhind, I want the 'Patient Feedback form OPD/IPD Patient Satisfaction Survey Forms' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form copied from Guna form format and new questions to be added for Bhind requirement | High | In Progress | PSR Log
96 | US-PARAKH-096 | Indore | Jan Vishwas forms like Damoh | District/Department Form Onboarding | As a District Nodal Officer in Indore, I want the 'Jan Vishwas forms like Damoh' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | High | In Progress | PSR Log
97 | US-PARAKH-097 | Betul | WCD Anganwadi Inspection Form | Betul Multi-Form Rollout (8 forms) | As the Betul WCD (Women & Child Development) nodal team, we want Questions 16 and 17 added to the Anganwadi inspection form, so that the form captures the two additional data points requested by the department. | Questions 16 & 17 added and confirmed by Manisha (MPSeDC Testing) on 30-Jun-2026. | High | Completed | WhatsApp - Dheeraj/Madhur/Manisha, 30-Jun-2026 | Confirmed: Question 16 & 17 Added.
98 | US-PARAKH-098 | Betul | WCD Anganwadi Inspection Form - Conditional Master Fields | Betul Multi-Form Rollout (8 forms) | As an Inspector filling the Betul Anganwadi form, I want the 'Gram Name' field to be conditionally filtered by the selected 'Sector Name' (Sector -> Gram cascading dropdown) sourced from master data, so that I only see relevant villages and avoid data entry errors. | Of the 5 master-linked fields, only Gram Name and Sector Name are conditional; Sector Name is selected first and Gram Name list populates accordingly. Updated Betul master (with Sector and Gram) received and applied. | High | Completed | WhatsApp - Dheeraj/Madhur, 30-Jun to 2-Jul-2026 | Master data review requested by Ajeet Singh; Manisha confirmed.
99 | US-PARAKH-099 | Betul | KGBV Hostel Monitoring Form | Betul Multi-Form Rollout (8 forms) | As the Betul District GIS Admin, I want the KGBV (Kasturba Gandhi Balika Vidyalaya) Hostel Monitoring form cloned from the Directorate of Public Instruction (DPI) department's existing form on Parakh, so that Betul can use a standardized, already-verified format. | DPI form copied to Betul Collectorate account by Madhur (2-Jul-2026). KGBV Form verified and approved by the DEO. Betul KGBV master list shared/uploaded (1-Jul-2026). | Medium | Completed | WhatsApp / PSR Log (row: Betul) | DEO approval received; nodal assignment pending for PM Poshan sub-form.
100 | US-PARAKH-100 | Betul | Mine Inspection Form Update | Betul Multi-Form Rollout (8 forms) | As a Mining Department Officer in Betul, I want the Mine Inspection form updated per the revised questions and master data shared by the department on 30-Jun-2026, so that inspections reflect the correct field requirements. | Updated 'mine inspection_30-06-2026' form shared by Dheeraj; Madhur flagged the update needs clarification before implementation. | High | Pending Department Action | WhatsApp - Dheeraj/Madhur, 30-Jun-2026 | Awaiting clarification discussion between Dheeraj and Madhur.
101 | US-PARAKH-101 | Betul | Mine Inspection Form - Mineral Stock/Quality/Sand Master List | Betul Multi-Form Rollout (8 forms) | As a Mining Department Officer in Betul, I want the Betul Mineral List (Stock, Quality Level (QL) and Sand list) loaded as master data in the Mine Inspection form, so that inspectors select accurate, pre-approved mineral references during inspection instead of free-text entry. | Mineral list (Stock, QL & Sand) shared with Manisha and Madhur on 3-Jul-2026; questions and master data formatted per department discussion. | Medium | In Progress | WhatsApp - Dheeraj, 3-Jul-2026 | Awaiting update from developer team per PSR log.
102 | US-PARAKH-102 | Betul | School Nirikshan (Sehore format) merge into Betul School Monitoring Form | Betul Multi-Form Rollout (8 forms) | As the Betul Education Department, we want the Sehore 'School Nirikshan Prapatra - Part 1' questions merged into our School Monitoring form (after our department's own requested questions are added first), so that Betul's school inspections follow a combined, standardized format aligned with the state model. | Madhur copied both the DPI hostel form and the Sehore school form templates to the Betul Collectorate account (2-Jul-2026). Betul department instructed: add their own questions first, then merge in Sehore Part 1. | Medium | In Progress | WhatsApp - Madhur/Dheeraj, 2-Jul-2026 | Sequencing: Betul dept questions first, then Sehore merge.
103 | US-PARAKH-103 | Betul | Aadhar Center Inspection Form - State-Level Adoption | State-Level Master Form Standardization | As the State Parakh Admin, I want the Narmadapuram district's Aadhar Center Inspection form adopted as the common state-level template, so that all districts (including Betul) use one consistent Aadhar verification form instead of building district-specific versions. | Confirmed by Dheeraj (1-Jul-2026): 'Narmadapuram Aadhar form can be used at the state level.' Referenced in Betul PSR row as 'Aadhar form taken at the state level - Common form for all districts.' | Medium | Completed | WhatsApp - Dheeraj, 1-Jul-2026 / PSR Log | Betul Aadhaar Centre form confirmation still awaited from department per PSR log.
104 | US-PARAKH-104 | Betul | Tribal Hostel Inspection Form - Access Credentials | Betul Multi-Form Rollout (8 forms) | As the Betul Collectorate Tribal Department, we want login credentials issued for the Tribal Hostel Inspection form (mirrored from the Tribal Department's launched form), so that our officials can begin conducting hostel inspections on Parakh. | Awaiting login credentials for Betul Collectorate Tribal Department per PSR log; Bhopal Commissioner Office granted similar access as reference precedent. | Medium | Pending Department Action | PSR Log - Betul row | Blocking item for Tribal Hostel form go-live in Betul.
105 | US-PARAKH-105 | State-wide (PM Poshan / SNC PNRD) | PM Poshan Social Audit Inspection Form | PM Poshan Social Audit Program | As the State Coordinator for the PM Poshan (Social Audit of Schools) Scheme, I want the PM Poshan Social Audit inspection form deployed on Parakh, so that field auditors can capture school meal-scheme compliance data digitally across all onboarded districts. | Form completed and deployed to Production (per PSR Log, PM Poshan/MGNREGA row). Mandla district requested one question be aligned with the MGNREGA form format and a correction to the '270 sq ft' related question. | High | Completed | PSR Log / WhatsApp - Dheeraj, 1-Jul-2026 | Mandla-specific clarification pending with GIS Executive Ankita Soni.
106 | US-PARAKH-106 | State-wide (PM Poshan) | PM Poshan Social Audit Training | PM Poshan Social Audit Program | As a PM Poshan Program Coordinator, I want the Social Audit training session conducted and photo evidence of the training uploaded/tracked, so that we have documented proof that field auditors were trained on the inspection form and process before rollout. | Training conducted; photo documentation shared by Dheeraj on 1-Jul-2026 and again on 3-Jul-2026. | Medium | Completed | WhatsApp - Dheeraj, 1-Jul & 3-Jul-2026
107 | US-PARAKH-107 | Tribal Department (State) | Action Taken Report (ATR) Workflow | Workflow Management System | As a Tribal Department reviewing officer, I want an Action Taken Report (ATR) workflow implemented within Parakh, so that follow-up/corrective actions raised against an inspection finding can be logged, assigned, and tracked through to closure instead of being tracked manually outside the system. | Item logged in Parakh Internal Work Enhancement log ('ATR Report for Tribal'). Requires: ATR entry against inspection record, action-owner assignment, status tracking (Open/In Progress/Closed), and closure report. | High | In Progress | Parakh Internal Work Log | Scope currently limited to Tribal Department; evaluate extension to other departments.
108 | US-PARAKH-108 | MP Cooperative Society | Roster of Nirikshan Karta (Inspector Roster/Assignment) | Workflow Management System | As an MP Cooperative Department Nodal Officer, I want a 'Rooster of Nirikshan Karta' (inspector roster/assignment list) feature added to the Nirikshan module, so that inspectors can be formally rostered and assigned to specific societies/units for inspection, with visibility into who is assigned where. | Referenced in PSR log under MP Cooperative (Changes): 'Revamping Inspection and including Rooster of Nirikshan karta.' Summary CR and BRD document shared with department (ICMIS - Devendra, Priya, Jyoti) for review. | High | In Progress | PSR Log / BRD Specification - MP Cooperative Nirikshan Module (modified 29-Jul-2026) | Awaiting department review of CRs and BRD document.
109 | US-PARAKH-109 | State-wide | Blank Form Download (Offline Reference) | Platform Enhancement | As a District Nodal Officer (e.g. Narsinghpur), I want to download a blank copy of any onboarded form as a PDF/template, so that I do not have to manually screenshot every page to share the form structure with field staff. | Feature requested by Narsinghpur; logged in Parakh Internal Work Enhancement log. | Low | Proposed | Parakh Internal Work Log
110 | US-PARAKH-110 | State-wide | Dynamic Reports - Phase 1 | Platform Enhancement | As a State Admin, I want inspection reports to be generated dynamically and linked with the dashboard, so that report structures automatically reflect form changes without manual report redevelopment. | Phase 1 marked 'Done' in Parakh Internal Work Enhancement log. | Medium | Completed | Parakh Internal Work Log | Further phases to be scoped.
111 | US-PARAKH-111 | State-wide | Report Sync for Department Forms | Platform Enhancement | As a State Admin, I want a 'Sync Data' action available from the Tabular View of Inspection screen, so that the latest submitted inspection data is pulled into reports on demand. | Functionality documented: Login as State Admin -> Tabular View of Inspection -> Sync Data -> Data Synced. | Medium | Completed | District GIS Parakh New Sync Functionality for Reports v1.0
112 | US-PARAKH-112 | CTA (Commissioner Treasury & Accounts) | Treasury Inspection Form | CTA Treasury & JD Inspection | As a Treasury Officer under CTA, I want a Treasury Accounts inspection form implemented on Parakh, so that treasury account inspections/audits can be digitally recorded, submitted, and reported instead of paper-based inspection registers. | Form created; awaiting Change Requests (CRs) and confirmation from CTA Department (per PSR log, rows: 'CTA' and 'CTA - CRs Updates from Department'). | High | Pending Department Action | PSR Log - CTA rows | Two related entries in PSR log indicate iterative CR cycles with CTA.
113 | US-PARAKH-113 | CTA (Commissioner Treasury & Accounts) | JD (Joint Director) Inspection Form | CTA Treasury & JD Inspection | As a Joint Director (JD) at CTA, I want a JD-level inspection form implemented on Parakh, so that JD-level treasury inspections are captured with the appropriate authority and reporting level distinct from the base Treasury Officer form. | Form created; pending CRs and confirmation from CTA Department. | High | Pending Department Action | PSR Log - CTA rows
114 | US-PARAKH-114 | PHED / MPSSDI Departments | Asset Survey Module - End-to-End Workflow | Asset Survey Module | As a Department using District GIS Parakh (Mobile & Web), I want an end-to-end Asset Survey workflow covering User Creation & Approval -> Asset Creation -> Asset Assignment to Department User -> Asset Survey, so that government assets can be inventoried, assigned, and periodically surveyed digitally. | Bilingual (English/Hindi) Asset Survey User Manual v1.2 produced, dated 24-Jul-2026, covering Introduction, Roles & Responsibilities, Pre-Requisites, 4-step Process Overview, Validation & Exception Handling, and Reports. | High | Completed | Asset Survey User Manual v1.2 (dated 24-Jul-2026) | Manual covers single-entry and bulk-upload asset creation.
115 | US-PARAKH-115 | State-wide | Asset Survey - Bulk Asset Upload | Asset Survey Module | As a Department Admin, I want to bulk-upload assets (instead of single entry only), so that large asset inventories can be onboarded quickly ahead of survey assignment. | Documented as part of Asset Creation scope in the Asset Survey User Manual (Section 6/1.2 Scope). | Medium | Completed | Asset Survey User Manual v1.2
116 | US-PARAKH-116 | Indore | Indore 17 Department Inspection Forms - Phase 1 & 2 | Indore Multi-Department Rollout | As the Indore Collectorate GIS Cell, I want all 17 department-specific inspection forms configured on Parakh in phases, so that Indore's district and divisional-level departments can move from paper-based to digital inspection reporting. | Phase 1 developed; Phase 2 (Action Taken workflow and divisional-level work) under progress. Department to finalize remaining forms. Indore Inspection Spec Overview deck created 8-Aug-2026 documenting the specification. | High | In Progress | PSR Log - Indore Inspection forms / Indore Inspection Spec Overview.pptx (8-Aug-2026)
117 | US-PARAKH-117 | Indore | Property Inspection Form | Indore Multi-Department Rollout | As an Indore Collectorate Property Inspector, I want a Property Inspection form on Parakh, so that property inspections are digitally recorded and tested ahead of go-live. | Form created and tested (per PSR log). | Medium | In Progress | PSR Log - Indore Collectorate row
118 | US-PARAKH-118 | Indore | Sugamya Abhiyaan (Accessibility Survey) Form | Indore Multi-Department Rollout | As an Indore District Officer running the Sugamya Abhiyaan (Accessibility Campaign), I want a dedicated inspection form and report on Parakh, so that accessibility compliance surveys across the district are tracked centrally. | Form created and live on production; report created (per PSR log). | Medium | Completed | PSR Log - Indore row
119 | US-PARAKH-119 | Indore | Jan Vishwas Abhiyaan Forms (modelled on Damoh) | Indore Multi-Department Rollout | As an Indore District Officer, I want Jan Vishwas Abhiyaan inspection forms (Health & Farm/Dairy Department variants) replicated from the Damoh district template, so that Indore can launch the same statewide campaign inspections without rebuilding the form from scratch. | Referenced in PSR log ('Jan Vishwas forms like Damoh') as work-in-progress with no further detail logged yet. | Medium | Proposed | PSR Log - Indore row | Depends on finalized Damoh Jan Vishwas form set.
120 | US-PARAKH-120 | Damoh | BBGRAMJI Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'BBGRAMJI Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
121 | US-PARAKH-121 | Damoh | Pradhan Mantri Awas Yojana (PMAY) Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'Pradhan Mantri Awas Yojana (PMAY) Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
122 | US-PARAKH-122 | Damoh | Gram Nal Jal Praday Yojana Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'Gram Nal Jal Praday Yojana Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
123 | US-PARAKH-123 | Damoh | School/Institute Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'School/Institute Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
124 | US-PARAKH-124 | Damoh | Anganwadi Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'Anganwadi Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
125 | US-PARAKH-125 | Damoh | Jan Vishwas Abhiyaan - Health Department Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'Jan Vishwas Abhiyaan - Health Department Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
126 | US-PARAKH-126 | Damoh | Govt. Uchit Mulya Ki Dukan (Fair Price Shop) Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'Govt. Uchit Mulya Ki Dukan (Fair Price Shop) Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
127 | US-PARAKH-127 | Damoh | Petrol Pump Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'Petrol Pump Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
128 | US-PARAKH-128 | Damoh | LPG Dealer Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'LPG Dealer Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
129 | US-PARAKH-129 | Damoh | CM Jan Vishwas Abhiyaan - Farm & Dairy Department Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'CM Jan Vishwas Abhiyaan - Farm & Dairy Department Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
130 | US-PARAKH-130 | Damoh | Liquor Department Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'Liquor Department Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
131 | US-PARAKH-131 | Damoh | Hostel/Ashram Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'Hostel/Ashram Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
132 | US-PARAKH-132 | Damoh | Krishi Saakh and Sahkari Samiti (Agri Credit & Cooperative Society) Inspection Form | Damoh Multi-Form Rollout (13 forms) | As a Damoh Zila Panchayat / District Officer, I want the 'Krishi Saakh and Sahkari Samiti (Agri Credit & Cooperative Society) Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Medium | In Progress | PSR Log - Damoh row | Master data collection ongoing across all 13 forms.
133 | US-PARAKH-133 | Betul | KGBV Hostel Form | Betul Multi-Form Rollout (8 forms) | As the Betul District GIS Cell, I want the 'KGBV Hostel Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Verified and approved by the DEO. | Medium | Completed | PSR Log - Betul consolidated row
134 | US-PARAKH-134 | Betul | PM Poshan (PNRD) Form | Betul Multi-Form Rollout (8 forms) | As the Betul District GIS Cell, I want the 'PM Poshan (PNRD) Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Department Form verification completed; nodal assignment pending. | High | In Progress | PSR Log - Betul consolidated row
135 | US-PARAKH-135 | Betul | WCD Anganwadi Form | Betul Multi-Form Rollout (8 forms) | As the Betul District GIS Cell, I want the 'WCD Anganwadi Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | With developer team for Questions 16 & 17 modification. | Medium | Completed | PSR Log - Betul consolidated row
136 | US-PARAKH-136 | Betul | School Monitoring Patra Form | Betul Multi-Form Rollout (8 forms) | As the Betul District GIS Cell, I want the 'School Monitoring Patra Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Decided to proceed with a single form format; department to raise official request if a separate form is needed. | Medium | Completed | PSR Log - Betul consolidated row
137 | US-PARAKH-137 | Betul | Health Inspection Form | Betul Multi-Form Rollout (8 forms) | As the Betul District GIS Cell, I want the 'Health Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Development and deployment completed; form is live. | Medium | Completed | PSR Log - Betul consolidated row
138 | US-PARAKH-138 | Betul | Mining Inspection Form | Betul Multi-Form Rollout (8 forms) | As the Betul District GIS Cell, I want the 'Mining Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Questions and master data formatted and shared; awaiting developer team update. | High | In Progress | PSR Log - Betul consolidated row
139 | US-PARAKH-139 | Betul | Aadhaar Centre Inspection Form | Betul Multi-Form Rollout (8 forms) | As the Betul District GIS Cell, I want the 'Aadhaar Centre Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Email shared with department; awaiting confirmation. | Medium | Pending Department Action | PSR Log - Betul consolidated row
140 | US-PARAKH-140 | Betul | Tribal Hostel Inspection Form | Betul Multi-Form Rollout (8 forms) | As the Betul District GIS Cell, I want the 'Tribal Hostel Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Awaiting login credentials for Betul Collectorate Tribal Department. | Medium | Pending Department Action | PSR Log - Betul consolidated row

## Module Summary
Epic / Category | Total Stories | Completed | In Progress | Pending Department Action | On Hold | Proposed
District/Department Form Onboarding | 96 | 46 | 28 | 8 | 0 | 14
Betul Multi-Form Rollout (8 forms) | 15 | 7 | 4 | 4 | 0 | 0
Damoh Multi-Form Rollout (13 forms) | 13 | 0 | 13 | 0 | 0 | 0
Indore Multi-Department Rollout | 4 | 1 | 2 | 0 | 0 | 1
Platform Enhancement | 3 | 2 | 0 | 0 | 0 | 1
PM Poshan Social Audit Program | 2 | 2 | 0 | 0 | 0 | 0
Workflow Management System | 2 | 0 | 2 | 0 | 0 | 0
CTA Treasury & JD Inspection | 2 | 0 | 0 | 2 | 0 | 0
Asset Survey Module | 2 | 2 | 0 | 0 | 0 | 0
State-Level Master Form Standardization | 1 | 1 | 0 | 0 | 0 | 0
TOTAL | 140 | 61 | 49 | 14 | 0 | 16
Districts / Departments Covered in this Register
Total distinct districts / departments: 76
# | District / Department
1 | Agar Malwa
2 | Alirajpur
3 | Ashoknagar Distrct
4 | Ayush Department
5 | Betul
6 | Bhind
7 | Bhopal - Food Department
8 | Bhopal - UADD Department SQM Inspection Form
9 | Bhopal commissioner office
10 | Burhanpur
11 | CTA
12 | CTA - CRs Updates from Department
13 | CTA (Commissioner Treasury & Accounts)
14 | Chhatarpur Dist
15 | Chhattarpur
16 | Chhindwara
17 | Damoh
18 | Dindori , Collectorate
19 | Directorate Public Instructions
20 | Guna
21 | Guna & Gwalior
22 | Gwalior
23 | Health Department
24 | Indore
25 | Indore Collectorate
26 | Indore Inspection forms
27 | Jabalpur
28 | Khandwa
29 | Khargone
30 | Labour Department
31 | MGNREGA PM Poshan Department
32 | MGNREGA Dynamic Form Creation
33 | MP Cooperative
34 | MP Cooperative (Changes)
35 | MP Cooperative Society
36 | MP Metro
37 | MPHIDB
38 | MPRRD
39 | Mandla
40 | Mandla (On Hold)
41 | Mining Department
42 | Narmadapuram
43 | Narsinghpur
44 | PHED / MPSSDI Departments
45 | PNRD NRM PMKSY
46 | PNRD RES
47 | PNRD-MGNREGA
48 | PNRD-SRLM
49 | Patan
50 | Rajgarh
51 | Rajgarh Collectorate
52 | Religious and Trust Endowment
53 | Rewa
54 | SAPS
55 | Sagar
56 | Saps
57 | Satna District
58 | School Education Department
59 | Sehore
60 | Seoni District
61 | Sidhi
62 | State-wide
63 | State-wide (PM Poshan / SNC PNRD)
64 | State-wide (PM Poshan)
65 | Tikamgarh , Collectorate
66 | Tribal Department (State)
67 | Tribale department
68 | Ujjain
69 | Ujjain Mela
70 | Vidisha
71 | Zila Punchayat , Anuppur
72 | rajgarh
73 | seoni
74 | कार्यालय कलेक्टर (अनुसूचित जाति एवं जनजातीय कार्य विभाग ) भोपाल
75 | कार्यालय कलेक्टर (पिछड़ा वर्ग तथा अल्पसंख्यक कल्याण ) भोपाल
76 | कार्यालय कलेक्टर भोपाल म.प्र