## INDEX
DISTRICT GIS PARAKH - CONSOLIDATED USER STORY REGISTER ¦ 30-Jun to 18-Aug 2026 ¦ MPSSDI / MPSeDC
Prepared by: Dheeraj, Senior Business Analyst, MPSeDC (MPSSDI) ¦ Consolidated: 18-Aug-2026
Sr. No. | Sheet Name | Module / Area | No. of User Stories | Coverage
1 | Betul US | Betul District – 8-Form Rollout | 15 | 30-Jun to 18-Aug 2026 consolidated
2 | Damoh US | Damoh District – 13-Form Rollout | 13 | 30-Jun to 18-Aug 2026 consolidated
3 | Indore US | Indore District – 17-Form Rollout | 4 | 30-Jun to 18-Aug 2026 consolidated
4 | Hostel-School-AWW US | Hostel, School & Anganwadi Inspection | 31 | 30-Jun to 18-Aug 2026 consolidated
5 | Health Facility US | Health & Medical Facility Inspection | 7 | 30-Jun to 18-Aug 2026 consolidated
6 | GIS Survey-Land US | GIS Survey, Land & Property Inspection | 10 | 30-Jun to 18-Aug 2026 consolidated
7 | Rural Dev-MGNREGA US | Rural Development & MGNREGA Inspection | 8 | 30-Jun to 18-Aug 2026 consolidated
8 | Govt Scheme-Welfare US | Govt. Scheme & Welfare Verification Forms | 11 | 30-Jun to 18-Aug 2026 consolidated
9 | Institutional Dept US Eg: Chhindwara,Guna, Rajgarh | Institutional & Departmental Inspection Forms | 14 | 30-Jun to 18-Aug 2026 consolidated
10 | Other District US | Other District Inspection Forms | 7 | 30-Jun to 18-Aug 2026 consolidated
11 | PM Poshan US | PM Poshan Social Audit Program | 2 | 30-Jun to 18-Aug 2026 consolidated
12 | Asset Survey US | Asset Survey Module | 2 | 30-Jun to 18-Aug 2026 consolidated
13 | CTA Treasury-JD US | CTA – Treasury & JD Inspection | 2 | 30-Jun to 18-Aug 2026 consolidated
14 | Workflow Mgmt US | Workflow Management (ATR & Roster) | 2 | 30-Jun to 18-Aug 2026 consolidated
15 | Platform Enhance US | Platform Enhancement | 3 | 30-Jun to 18-Aug 2026 consolidated
16 | Master Form Std US | State-Level Master Form Standardization | 1 | 30-Jun to 18-Aug 2026 consolidated
| TOTAL USER STORIES (30-Jun to 18-Aug 2026) |  | 132
Notes:
1. Format mirrors the Jal Rekha Consolidated User Story Register (one sheet per module/theme, INDEX front sheet, same header/column structure).
2. Sources: PSR2 'District Level Initiatives GIS' workbook (District Initiatives + Parakh Internal Work sheets), WhatsApp coordination thread (30-Jun to 03-Jul-2026), Asset Survey User Manual v1.2 (24-Jul-2026), MP Cooperative Nirikshan BRD (modified 29-Jul-2026), Indore Inspection Spec Overview (8-Aug-2026), and the Consolidated Bilingual/Sudden Inspection/User Manual v1.2 (13-Aug-2026).
3. 'Sprint' is shown as a single consolidated cycle ('Cycle 1, Jun-Aug 2026') because Parakh's sprint-level tracking was not available in the source files (unlike Jal Rekha, which had per-sprint MoM/timesheet data).
4. 'Effort (hrs)' is marked 'Not tracked' rather than an estimated number, since no effort-hour data exists in the PSR log or chat threads for this project; fabricating hours would misrepresent actual tracking.
5. Generic per-district PSR log rows for Betul, Damoh, Indore Inspection Forms, MP Cooperative, and CTA were folded into their dedicated module sheets instead of also appearing in the thematic sheets, to avoid duplicate stories.
6. Status colour key: Green = Completed, Yellow = In Progress, Orange = Pending Department Action, Grey = Proposed (not yet started).

## Betul US
District GIS Parakh – Consolidated User Stories ¦ Betul District – 8-Form Rollout ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs) | Month
WCD Anganwadi Inspection Form | US-BETUL-001 | High | As the Betul WCD (Women & Child Development) nodal team, we want Questions 16 and 17 added to the Anganwadi inspection form, so that the form captures the two additional data points requested by the department. | Questions 16 & 17 added and confirmed by Manisha (MPSeDC Testing) on 30-Jun-2026. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked | July
WCD Anganwadi Inspection Form - Conditional Master Fields | US-BETUL-002 | High | As an Inspector filling the Betul Anganwadi form, I want the 'Gram Name' field to be conditionally filtered by the selected 'Sector Name' (Sector -> Gram cascading dropdown) sourced from master data, so that I only see relevant villages and avoid data entry errors. | Of the 5 master-linked fields, only Gram Name and Sector Name are conditional; Sector Name is selected first and Gram Name list populates accordingly. Updated Betul master (with Sector and Gram) received and applied. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked | July
KGBV Hostel Monitoring Form | US-BETUL-003 | Medium | As the Betul District GIS Admin, I want the KGBV (Kasturba Gandhi Balika Vidyalaya) Hostel Monitoring form cloned from the Directorate of Public Instruction (DPI) department's existing form on Parakh, so that Betul can use a standardized, already-verified format. | DPI form copied to Betul Collectorate account by Madhur (2-Jul-2026). KGBV Form verified and approved by the DEO. Betul KGBV master list shared/uploaded (1-Jul-2026). | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked | July
Mine Inspection Form Update | US-BETUL-004 | High | As a Mining Department Officer in Betul, I want the Mine Inspection form updated per the revised questions and master data shared by the department on 30-Jun-2026, so that inspections reflect the correct field requirements. | Updated 'mine inspection_30-06-2026' form shared by Dheeraj; Madhur flagged the update needs clarification before implementation. | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked | July
Mine Inspection Form - Mineral Stock/Quality/Sand Master List | US-BETUL-005 | Medium | As a Mining Department Officer in Betul, I want the Betul Mineral List (Stock, Quality Level (QL) and Sand list) loaded as master data in the Mine Inspection form, so that inspectors select accurate, pre-approved mineral references during inspection instead of free-text entry. | Mineral list (Stock, QL & Sand) shared with Manisha and Madhur on 3-Jul-2026; questions and master data formatted per department discussion. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | July
School Nirikshan (Sehore format) merge into Betul School Monitoring Form | US-BETUL-006 | Medium | As the Betul Education Department, we want the Sehore 'School Nirikshan Prapatra - Part 1' questions merged into our School Monitoring form (after our department's own requested questions are added first), so that Betul's school inspections follow a combined, standardized format aligned with the state model. | Madhur copied both the DPI hostel form and the Sehore school form templates to the Betul Collectorate account (2-Jul-2026). Betul department instructed: add their own questions first, then merge in Sehore Part 1. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | July
Tribal Hostel Inspection Form - Access Credentials | US-BETUL-007 | Medium | As the Betul Collectorate Tribal Department, we want login credentials issued for the Tribal Hostel Inspection form (mirrored from the Tribal Department's launched form), so that our officials can begin conducting hostel inspections on Parakh. | Awaiting login credentials for Betul Collectorate Tribal Department per PSR log; Bhopal Commissioner Office granted similar access as reference precedent. | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked | July
KGBV Hostel Form | US-BETUL-008 | Medium | As the Betul District GIS Cell, I want the 'KGBV Hostel Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Verified and approved by the DEO. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked | July
PM Poshan (PNRD) Form | US-BETUL-009 | High | As the Betul District GIS Cell, I want the 'PM Poshan (PNRD) Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Department Form verification completed; nodal assignment pending. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | July
WCD Anganwadi Form | US-BETUL-010 | Medium | As the Betul District GIS Cell, I want the 'WCD Anganwadi Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | With developer team for Questions 16 & 17 modification. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked | July
School Monitoring Patra Form | US-BETUL-011 | Medium | As the Betul District GIS Cell, I want the 'School Monitoring Patra Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Decided to proceed with a single form format; department to raise official request if a separate form is needed. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked | July
Health Inspection Form | US-BETUL-012 | Medium | As the Betul District GIS Cell, I want the 'Health Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Development and deployment completed; form is live. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked | July
Mining Inspection Form | US-BETUL-013 | High | As the Betul District GIS Cell, I want the 'Mining Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Questions and master data formatted and shared; awaiting developer team update. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | July
Aadhaar Centre Inspection Form | US-BETUL-014 | Medium | As the Betul District GIS Cell, I want the 'Aadhaar Centre Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Email shared with department; awaiting confirmation. | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked | July
Tribal Hostel Inspection Form | US-BETUL-015 | Medium | As the Betul District GIS Cell, I want the 'Tribal Hostel Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Awaiting login credentials for Betul Collectorate Tribal Department. | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked | July

## Damoh US
District GIS Parakh – Consolidated User Stories ¦ Damoh District – 13-Form Rollout ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs) | Month
BBGRAMJI Form | US-DAMOH-001 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'BBGRAMJI Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Pradhan Mantri Awas Yojana (PMAY) Inspection Form | US-DAMOH-002 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Pradhan Mantri Awas Yojana (PMAY) Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Gram Nal Jal Praday Yojana Inspection Form | US-DAMOH-003 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Gram Nal Jal Praday Yojana Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
School/Institute Inspection Form | US-DAMOH-004 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'School/Institute Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Anganwadi Inspection Form | US-DAMOH-005 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Anganwadi Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Jan Vishwas Abhiyaan - Health Department Form | US-DAMOH-006 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Jan Vishwas Abhiyaan - Health Department Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Govt. Uchit Mulya Ki Dukan (Fair Price Shop) Inspection Form | US-DAMOH-007 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Govt. Uchit Mulya Ki Dukan (Fair Price Shop) Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Petrol Pump Inspection Form | US-DAMOH-008 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Petrol Pump Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
LPG Dealer Inspection Form | US-DAMOH-009 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'LPG Dealer Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
CM Jan Vishwas Abhiyaan - Farm & Dairy Department Inspection Form | US-DAMOH-010 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'CM Jan Vishwas Abhiyaan - Farm & Dairy Department Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Liquor Department Inspection Form | US-DAMOH-011 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Liquor Department Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Hostel/Ashram Inspection Form | US-DAMOH-012 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Hostel/Ashram Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Krishi Saakh and Sahkari Samiti (Agri Credit & Cooperative Society) Inspection Form | US-DAMOH-013 | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Krishi Saakh and Sahkari Samiti (Agri Credit & Cooperative Society) Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug

## Indore US
District GIS Parakh – Consolidated User Stories ¦ Indore District – 17-Form Rollout ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs) | Month
Indore 17 Department Inspection Forms - Phase 1 & 2 | US-INDORE-001 | High | As the Indore Collectorate GIS Cell, I want all 17 department-specific inspection forms configured on Parakh in phases, so that Indore's district and divisional-level departments can move from paper-based to digital inspection reporting. | Phase 1 developed; Phase 2 (Action Taken workflow and divisional-level work) under progress. Department to finalize remaining forms. Indore Inspection Spec Overview deck created 8-Aug-2026 documenting the specification. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug
Property Inspection Form | US-INDORE-002 | Medium | As an Indore Collectorate Property Inspector, I want a Property Inspection form on Parakh, so that property inspections are digitally recorded and tested ahead of go-live. | Form created and tested (per PSR log). | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked | July
Sugamya Abhiyaan (Accessibility Survey) Form | US-INDORE-003 | Medium | As an Indore District Officer running the Sugamya Abhiyaan (Accessibility Campaign), I want a dedicated inspection form and report on Parakh, so that accessibility compliance surveys across the district are tracked centrally. | Form created and live on production; report created (per PSR log). | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked | July
Jan Vishwas Abhiyaan Forms (modelled on Damoh) | US-INDORE-004 | Medium | As an Indore District Officer, I want Jan Vishwas Abhiyaan inspection forms (Health & Farm/Dairy Department variants) replicated from the Damoh district template, so that Indore can launch the same statewide campaign inspections without rebuilding the form from scratch. | Referenced in PSR log ('Jan Vishwas forms like Damoh') as work-in-progress with no further detail logged yet. | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked | Aug

## Hostel-School-AWW US
District GIS Parakh – Consolidated User Stories ¦ Hostel, School & Anganwadi Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Hostel Survey (Parakh) | US-HSA-001 | Medium | As a Field Surveyor in Alirajpur, I want the 'Hostel Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
School Survey (Parakh) | US-HSA-002 | Medium | As a Field Surveyor in Chhindwara, I want the 'School Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT completed. Go Live | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked
School Survey, Hostel, Anganbadi, PDS Center Extra Inspection App (Parakh) | US-HSA-003 | Medium | As a Field Surveyor in Dindori , Collectorate, I want the 'School Survey, Hostel, Anganbadi, PDS Center Extra Inspection App (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Hostel Survey (Parakh) | US-HSA-004 | Medium | As a Field Surveyor in Vidisha, I want the 'Hostel Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Hostel Survey (Parakh) | US-HSA-005 | Medium | As a Field Surveyor in Bhind, I want the 'Hostel Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Bhind Collectorate is onboarded. Development work completed. Awaiting list of Hostels from the Collectorate office, so to initiate UAT. | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked
Hostel Inpection , Adharcard Inpection , aganwadi Inpection, Goverment School Inpection | US-HSA-006 | Medium | As a Hostel Inspecting Officer in Narmadapuram, I want the 'Hostel Inpection , Adharcard Inpection , aganwadi Inpection, Goverment School Inpection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म | US-HSA-007 | Medium | As a Inspecting Officer in Narmadapuram, I want the 'Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | The form has arrived, UAT has been sent, and testing has started. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey | US-HSA-008 | Medium | As a Field Surveyor in rajgarh, I want the 'छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | The form has arrived, UAT has been sent, and testing has started. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म | US-HSA-009 | Medium | As a District Nodal Officer in seoni, I want the 'छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र | US-HSA-010 | Medium | As a District Nodal Officer in Tribale department, I want the 'जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work complete | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Parakh _Survey Form ST/SC hostel | US-HSA-011 | Medium | As a Field Surveyor in Seoni District, I want the 'Parakh _Survey Form ST/SC hostel' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Parakh _App_Hostel Survey | US-HSA-012 | High | As a Field Surveyor in कार्यालय कलेक्टर भोपाल म.प्र, I want the 'Parakh _App_Hostel Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Hostel Survey on Parakh App | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Parakh _App_Hostel Survey | US-HSA-013 | High | As a Field Surveyor in कार्यालय कलेक्टर (अनुसूचित जाति एवं जनजातीय कार्य विभाग ) भोपाल, I want the 'Parakh _App_Hostel Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Hostel Survey on Parakh App | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Parakh _App_Hostel Survey | US-HSA-014 | High | As a Field Surveyor in कार्यालय कलेक्टर (पिछड़ा वर्ग तथा अल्पसंख्यक कल्याण ) भोपाल, I want the 'Parakh _App_Hostel Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Hostel Survey on Parakh App | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Grocery, Hostel , & General Inspection form | US-HSA-015 | Medium | As a Inspecting Officer in Chhattarpur, I want the 'Grocery, Hostel , & General Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
Hostel Inspection Form | US-HSA-016 | Medium | As a Inspecting Officer in Vidisha, I want the 'Hostel Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
NRC Inspection Form, Primary middle school Inspection Form | US-HSA-017 | Medium | As a Inspecting Officer in Vidisha, I want the 'NRC Inspection Form, Primary middle school Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Pharmacist Medical Drug store form, Anganwadi inspection form | US-HSA-018 | Medium | As a Inspecting Officer in Vidisha, I want the 'Pharmacist Medical Drug store form, Anganwadi inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Need Clarifications form department on few questions ¦ Pending with: District Collectorate | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
PM School, Awas and AAdhar center | US-HSA-019 | Medium | As a School Inspecting Officer in Mandla, I want the 'PM School, Awas and AAdhar center' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form and report Deployed ¦ Pending with: Distrcit collectorate - GIS executive - Ankita Soni 1) to clarify on pm poshan form to incorporate same like mgnrega one | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
School Inspection FOrm | US-HSA-020 | Medium | As a Inspecting Officer in Sehore, I want the 'School Inspection FOrm' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in UAT. Email sent to District collectorate & GIS executive ¦ Pending with: District Collectorate | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Anganwadi | US-HSA-021 | Medium | As a Anganwadi Inspecting Officer in Guna, I want the 'Anganwadi' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created in Uat, Email sent to District collectorate & GIS executive, confirmation required from the District Collectorate & GIS executive ¦ Pending with: Manisha | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
This form comes Under Sate coordinator PM Poshan Department Social Audit of schools Scheme | US-HSA-022 | Medium | As a School Inspecting Officer in MGNREGA PM Poshan Department, I want the 'This form comes Under Sate coordinator PM Poshan Department Social Audit of schools Scheme' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Deployed to Prod ¦ Pending with: Department | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Hostel Inspection | US-HSA-023 | Medium | As a Inspecting Officer in Ashoknagar Distrct, I want the 'Hostel Inspection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | adopted tribal department form | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
School, Hostel, Anganwadi, Health Center | US-HSA-024 | Medium | As a Hostel Inspecting Officer in Gwalior, I want the 'School, Hostel, Anganwadi, Health Center' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form/report created and deployed,email sent ¦ Pending with: Waiting for mail confirmation | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
School Inspection Form | US-HSA-025 | Medium | As a Inspecting Officer in Rajgarh, I want the 'School Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created, awaiting for confirmation | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked
Aganwadi | US-HSA-026 | Medium | As a District Nodal Officer in Ashoknagar Distrct, I want the 'Aganwadi' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created ¦ Pending with: Madhur and arindham | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Hostel Inspection Form(SC/ST category) | US-HSA-027 | High | As a Inspecting Officer in Bhopal commissioner office, I want the 'Hostel Inspection Form(SC/ST category)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form is same as tribal department. Bhopal Commissioner Office has raised request for creation of the Tribal Inspection Form. This form is same as of the Tribal Hostel Inspection Forms launched by the Tribal Department. T | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
सरकारी स्कूल में शौचालय | US-HSA-028 | High | As a District Nodal Officer in Ujjain, I want the 'सरकारी स्कूल में शौचालय' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is still not finalized from CEO ZP ¦ Pending with: Sakshi / ON Hold | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Hostel Inspection form | US-HSA-029 | Medium | As a Inspecting Officer in Directorate Public Instructions, I want the 'Hostel Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created ¦ Pending with: Madhur | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
5 forms - Anganwadi, PMPoshan, Godown, Hostel Monitoring, Health Form, | US-HSA-030 | High | As a Hostel Inspecting Officer in Chhindwara, I want the '5 forms - Anganwadi, PMPoshan, Godown, Hostel Monitoring, Health Form,' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Forms are created and Live in Production. Report work is going on ¦ Pending with: Pending from Chhindwara Collectorate Department & Development team for Report | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
OBC Triabl Hostel form | US-HSA-031 | High | As a Hostel Inspecting Officer in Rajgarh, I want the 'OBC Triabl Hostel form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created in UAT ¦ Pending with: Department to verify | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked

## Health Facility US
District GIS Parakh – Consolidated User Stories ¦ Health & Medical Facility Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Hospital Inspection form | US-HMF-001 | Medium | As a Inspecting Officer in Jabalpur, I want the 'Hospital Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
Health Inspection Form | US-HMF-002 | Medium | As a Inspecting Officer in Narmadapuram, I want the 'Health Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
1. DISTRICT / CIVIL / SUPER SPECIALITY HOSPITAL (जिला / सिविल / सुपर स्पेशियलिटी अस्पताल) 2. COMMUNITY HEALTH CENTRE (सामुदायिक स्वास्थ्य केंद्र (सीएच | US-HMF-003 | Medium | As a Health Inspecting Officer in Health Department, I want the '1. DISTRICT / CIVIL / SUPER SPECIALITY HOSPITAL (जिला / सिविल / सुपर स्पेशियलिटी अस्पताल) 2. COMMUNITY HEALTH CENTRE (सा' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in prod . chase department for progress ¦ Pending with: Ajeet | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked
Health Inspection form ,निरीक्षण प्रतिवेदन,गोदाम निरीक्षण | US-HMF-004 | High | As a Inspecting Officer in Burhanpur, I want the 'Health Inspection form ,निरीक्षण प्रतिवेदन,गोदाम निरीक्षण' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form is live,report is created ¦ Pending with: Department | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Patient Feedback Form | US-HMF-005 | Medium | As a Department Feedback Coordinator in Guna & Gwalior, I want the 'Patient Feedback Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | HTML Form and QR Code Created | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Ayush Department | US-HMF-006 | High | As a District Nodal Officer in Guna, I want the 'Ayush Department' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Patient Feedback form OPD/IPD Patient Satisfaction Survey Forms | US-HMF-007 | High | As a Field Surveyor in Bhind, I want the 'Patient Feedback form OPD/IPD Patient Satisfaction Survey Forms' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form copied from Guna form format and new questions to be added for Bhind requirement | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked

## GIS Survey-Land US
District GIS Parakh – Consolidated User Stories ¦ GIS Survey, Land & Property Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Drone Survey | US-GSL-001 | Medium | As a Field Surveyor in Bhind, I want the 'Drone Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Drone Urban Survey | US-GSL-002 | High | As a Field Surveyor in Khandwa, I want the 'Drone Urban Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Drone survey is in process. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Scanning of (Old Revenue / Naksha Record of Rewa (14399 Sheets) | US-GSL-003 | Medium | As a District Nodal Officer in Rewa, I want the 'Scanning of (Old Revenue / Naksha Record of Rewa (14399 Sheets)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work in Progress (Till Date 2793 sheets done) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Satellite data based maps for Urban Local Body boundary extension | US-GSL-004 | Medium | As a District Nodal Officer in Patan, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Satellite data based maps for Urban Local Body boundary extension | US-GSL-005 | Medium | As a District Nodal Officer in Sidhi, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Satellite data based maps for Urban Local Body boundary extension | US-GSL-006 | Medium | As a District Nodal Officer in Sagar, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Satellite data based maps for Urban Local Body boundary extension | US-GSL-007 | Medium | As a District Nodal Officer in Narsinghpur, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Sugamya Abhiyaan | US-GSL-008 | Medium | As a District Nodal Officer in Indore, I want the 'Sugamya Abhiyaan' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created and live on production, report is created | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Property Inspection | US-GSL-009 | High | As a Inspecting Officer in Indore Collectorate, I want the 'Property Inspection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created and Tested | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Building Inspection Form | US-GSL-010 | High | As a Inspecting Officer in Jabalpur, I want the 'Building Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Forms are created and Testing needs to be done ¦ Pending with: Pending from Jabalpur Collectorate Department | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked

## Rural Dev-MGNREGA US
District GIS Parakh – Consolidated User Stories ¦ Rural Development & MGNREGA Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Anuppur Works Management System (Mobile wire frames for WMS) | US-RDM-001 | High | As a District Nodal Officer in Zila Punchayat , Anuppur, I want the 'Anuppur Works Management System (Mobile wire frames for WMS)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Grameen Vikas Panchyat Grading live | US-RDM-002 | Medium | As a District Nodal Officer in Jabalpur, I want the 'Grameen Vikas Panchyat Grading live' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed and went live | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Mgnrega work related inspection form | US-RDM-003 | Medium | As a Inspecting Officer in Bhind, I want the 'Mgnrega work related inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Completed | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Inspection on Watershed projects ( project name and related work cost ) | US-RDM-004 | Medium | As a Inspecting Officer in PNRD NRM PMKSY, I want the 'Inspection on Watershed projects ( project name and related work cost )' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in UAT. Email sent to department, ¦ Pending with: Department | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
मनरेगा (MGNREGA) योजनांतगत नमाण काय के नर ण | US-RDM-005 | Medium | As a District Nodal Officer in Mandla (On Hold), I want the 'मनरेगा (MGNREGA) योजनांतगत नमाण काय के नर ण' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Mandla district specific Department is not clear on requirement as conveyed by Ankita ¦ Pending with: Ankita Soni GIS Executive | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked
SNA Sparsh अंतर्गत प्रशासकीय मद के भुगतान की जानकारी | US-RDM-006 | Medium | As a District Nodal Officer in PNRD-MGNREGA, I want the 'SNA Sparsh अंतर्गत प्रशासकीय मद के भुगतान की जानकारी' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live ¦ Pending with: Dheeraj,Aman | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Baseline Survey Form | US-RDM-007 | Medium | As a Field Surveyor in PNRD-SRLM, I want the 'Baseline Survey Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created,email sent and waiting for department confirmation ¦ Pending with: Department | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Road Inspection Form | US-RDM-008 | High | As a Inspecting Officer in MPRRD, I want the 'Road Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | In UAT ¦ Pending with: Dev Team | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked

## Govt Scheme-Welfare US
District GIS Parakh – Consolidated User Stories ¦ Govt. Scheme & Welfare Verification Forms ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Sarthak _Attendance / Parakh | US-GSW-001 | Medium | As a Nodal Attendance Officer in Narmadapuram, I want the 'Sarthak _Attendance / Parakh' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Parakh _Survey Form Adhar Kendra Inspection/Data Collection | US-GSW-002 | High | As a Field Surveyor in Satna District, I want the 'Parakh _Survey Form Adhar Kendra Inspection/Data Collection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work completed. Issued for UAT on 13/02/25 | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Sarthak App_Attendance Marking | US-GSW-003 | High | As a Nodal Attendance Officer in Ashoknagar Distrct, I want the 'Sarthak App_Attendance Marking' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Sarthak App_Attendance Marking | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
MP MLA CM A CM A+ & Ghoshna Form | US-GSW-004 | Medium | As a District Nodal Officer in PNRD RES, I want the 'MP MLA CM A CM A+ & Ghoshna Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
Narcotics Drug Form | US-GSW-005 | Medium | As a District Nodal Officer in Agar Malwa, I want the 'Narcotics Drug Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Deployed to Prod, email need to be sent ¦ Pending with: Development team/ Dheeraj | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Feedback form | US-GSW-006 | Medium | As a Department Feedback Coordinator in Chhindwara, I want the 'Feedback form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | deployed to Prod , email sent ¦ Pending with: Manisha | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Aadhar account verification form | US-GSW-007 | Medium | As a District Nodal Officer in Gwalior, I want the 'Aadhar account verification form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form/report created and deployed,email sent ¦ Pending with: Waiting for mail confirmation | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
75 वर्ष या उससे अधिक आयुके बिना सन्त लाभार्थियो हेतु मासिक सुविधा मॉनिटरिंग करने के लिए | US-GSW-008 | Medium | As a District Nodal Officer in Bhind, I want the '75 वर्ष या उससे अधिक आयुके बिना सन्त लाभार्थियो हेतु मासिक सुविधा मॉनिटरिंग करने के लिए' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form and report is deployed on production, ¦ Pending with: Sakshi | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Adhar inspection | US-GSW-009 | Medium | As a Inspecting Officer in Chhindwara, I want the 'Adhar inspection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created,email sent confirmed | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Ujjain Mela | US-GSW-010 | Medium | As a District Nodal Officer in Ujjain Mela, I want the 'Ujjain Mela' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created and live | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Jan Vishwas forms like Damoh | US-GSW-011 | High | As a District Nodal Officer in Indore, I want the 'Jan Vishwas forms like Damoh' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked

## Institutional Dept US
District GIS Parakh – Consolidated User Stories ¦ Institutional & Departmental Inspection Forms ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Inspection Mobile App on (Parakh) | US-IDI-001 | High | As a Inspecting Officer in Khargone, I want the 'Inspection Mobile App on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | The current collector of Khargone has changed. The new collector will decide whether this project will proceed or not, and if it does, how the work will be carried forward. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Inspection Mobile App on (Parakh) | US-IDI-002 | Medium | As a Inspecting Officer in Burhanpur, I want the 'Inspection Mobile App on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Inspection Mobile App on (Parakh) | US-IDI-003 | Medium | As a Inspecting Officer in Tikamgarh , Collectorate, I want the 'Inspection Mobile App on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT completed. Awaiting approval from the Collectorate to Go Live | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked
Creation Google form , Login ID Password | US-IDI-004 | High | As a District Nodal Officer in Chhatarpur Dist, I want the 'Creation Google form , Login ID Password' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | they will preparing our form and sending it from the Tikamgarh department, but they have also requested Alirajgarh's Parhak credentials for review. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
General Inspection on (Parakh) | US-IDI-005 | Medium | As a Inspecting Officer in Bhopal commissioner office, I want the 'General Inspection on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Live | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Creation Google form , Login ID Password | US-IDI-006 | High | As a District Nodal Officer in Chhatarpur Dist, I want the 'Creation Google form , Login ID Password' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Live | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
LKS Inspection Form | US-IDI-007 | Medium | As a Inspecting Officer in Saps, I want the 'LKS Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Go-live | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Inspection Form | US-IDI-008 | Medium | As a Inspecting Officer in Ayush Department, I want the 'Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Departement onboarded on uat. department to share survey form ¦ Pending with: Subhee Nema | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
Inspection Form | US-IDI-009 | Medium | As a Inspecting Officer in MPHIDB, I want the 'Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created on UAT ¦ Pending with: Ajeet | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
Temple and Temple Land Details Form | US-IDI-010 | High | As a District Nodal Officer in Religious and Trust Endowment, I want the 'Temple and Temple Land Details Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created on UAT ¦ Pending with: Bharat/Aman | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Kharidi Kendra | US-IDI-011 | Medium | As a District Nodal Officer in Bhopal - Food Department, I want the 'Kharidi Kendra' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form received from bhopal collectorate ¦ Pending with: Sakshi / Madhur | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
Hand-Pump Inspection form | US-IDI-012 | Medium | As a Inspecting Officer in Rajgarh Collectorate, I want the 'Hand-Pump Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form Created & live | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Mining Inspection Form | US-IDI-013 | Medium | As a Inspecting Officer in Mining Department, I want the 'Mining Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Forms created and Live in Production | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Plantation Form | US-IDI-014 | High | As a District Nodal Officer in MP Metro, I want the 'Plantation Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | QR Code based functionality . Form created | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked

## Other District US
District GIS Parakh – Consolidated User Stories ¦ Other District Inspection Forms ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Wash on wheel (Parakh) | US-ODF-001 | Medium | As a District Nodal Officer in Chhindwara, I want the 'Wash on wheel (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
lnspection Module (Parakh App) | US-ODF-002 | Medium | As a District Nodal Officer in SAPS, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
lnspection Module (Parakh App) | US-ODF-003 | Medium | As a District Nodal Officer in Rajgarh, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
lnspection Module (Parakh App) | US-ODF-004 | Medium | As a District Nodal Officer in MGNREGA Dynamic Form Creation, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Dynamic Form - Meeting Video Link Meeting Recording Notes | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
lnspection Module (Parakh App) | US-ODF-005 | Medium | As a District Nodal Officer in Bhopal - UADD Department SQM Inspection Form, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form in UAT. But no call back from the department. Waiting for their confirmation. | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
form is live but awaiting for autopopulation | US-ODF-006 | Medium | As a District Nodal Officer in School Education Department, I want the 'form is live but awaiting for autopopulation' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in prod . chase department for autopopulation of School list ¦ Pending with: Madhur/ Dheeraj and Altamsah | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked
Intergration with CIS system for user onboarding , establishment, and form to establishment mapping | US-ODF-007 | Medium | As a District Nodal Officer in Labour Department, I want the 'Intergration with CIS system for user onboarding , establishment, and form to establishment mapping' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Completed ¦ Pending with: Madhur | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked

## PM Poshan US
District GIS Parakh – Consolidated User Stories ¦ PM Poshan Social Audit Program ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
PM Poshan Social Audit Inspection Form | US-PMP-001 | High | As the State Coordinator for the PM Poshan (Social Audit of Schools) Scheme, I want the PM Poshan Social Audit inspection form deployed on Parakh, so that field auditors can capture school meal-scheme compliance data digitally across all onboarded districts. | Form completed and deployed to Production (per PSR Log, PM Poshan/MGNREGA row). Mandla district requested one question be aligned with the MGNREGA form format and a correction to the '270 sq ft' related question. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
PM Poshan Social Audit Training | US-PMP-002 | Medium | As a PM Poshan Program Coordinator, I want the Social Audit training session conducted and photo evidence of the training uploaded/tracked, so that we have documented proof that field auditors were trained on the inspection form and process before rollout. | Training conducted; photo documentation shared by Dheeraj on 1-Jul-2026 and again on 3-Jul-2026. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked

## Asset Survey US
District GIS Parakh – Consolidated User Stories ¦ Asset Survey Module ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Asset Survey Module - End-to-End Workflow | US-ASM-001 | High | As a Department using District GIS Parakh (Mobile & Web), I want an end-to-end Asset Survey workflow covering User Creation & Approval -> Asset Creation -> Asset Assignment to Department User -> Asset Survey, so that government assets can be inventoried, assigned, and periodically surveyed digitally. | Bilingual (English/Hindi) Asset Survey User Manual v1.2 produced, dated 24-Jul-2026, covering Introduction, Roles & Responsibilities, Pre-Requisites, 4-step Process Overview, Validation & Exception Handling, and Reports. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Asset Survey - Bulk Asset Upload | US-ASM-002 | Medium | As a Department Admin, I want to bulk-upload assets (instead of single entry only), so that large asset inventories can be onboarded quickly ahead of survey assignment. | Documented as part of Asset Creation scope in the Asset Survey User Manual (Section 6/1.2 Scope). | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked

## CTA Treasury-JD US
District GIS Parakh – Consolidated User Stories ¦ CTA – Treasury & JD Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Treasury Inspection Form | US-CTA-001 | High | As a Treasury Officer under CTA, I want a Treasury Accounts inspection form implemented on Parakh, so that treasury account inspections/audits can be digitally recorded, submitted, and reported instead of paper-based inspection registers. | Form created; awaiting Change Requests (CRs) and confirmation from CTA Department (per PSR log, rows: 'CTA' and 'CTA - CRs Updates from Department'). | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked
JD (Joint Director) Inspection Form | US-CTA-002 | High | As a Joint Director (JD) at CTA, I want a JD-level inspection form implemented on Parakh, so that JD-level treasury inspections are captured with the appropriate authority and reporting level distinct from the base Treasury Officer form. | Form created; pending CRs and confirmation from CTA Department. | Pending Department Action | Cycle 1 (Jun-Aug 2026) | Not tracked

## Workflow Mgmt US
District GIS Parakh – Consolidated User Stories ¦ Workflow Management (ATR & Roster) ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Action Taken Report (ATR) Workflow | US-WFM-001 | High | As a Tribal Department reviewing officer, I want an Action Taken Report (ATR) workflow implemented within Parakh, so that follow-up/corrective actions raised against an inspection finding can be logged, assigned, and tracked through to closure instead of being tracked manually outside the system. | Item logged in Parakh Internal Work Enhancement log ('ATR Report for Tribal'). Requires: ATR entry against inspection record, action-owner assignment, status tracking (Open/In Progress/Closed), and closure report. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked
Roster of Nirikshan Karta (Inspector Roster/Assignment) | US-WFM-002 | High | As an MP Cooperative Department Nodal Officer, I want a 'Rooster of Nirikshan Karta' (inspector roster/assignment list) feature added to the Nirikshan module, so that inspectors can be formally rostered and assigned to specific societies/units for inspection, with visibility into who is assigned where. | Referenced in PSR log under MP Cooperative (Changes): 'Revamping Inspection and including Rooster of Nirikshan karta.' Summary CR and BRD document shared with department (ICMIS - Devendra, Priya, Jyoti) for review. | In Progress | Cycle 1 (Jun-Aug 2026) | Not tracked

## Platform Enhance US
District GIS Parakh – Consolidated User Stories ¦ Platform Enhancement ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Blank Form Download (Offline Reference) | US-PLAT-001 | Low | As a District Nodal Officer (e.g. Narsinghpur), I want to download a blank copy of any onboarded form as a PDF/template, so that I do not have to manually screenshot every page to share the form structure with field staff. | Feature requested by Narsinghpur; logged in Parakh Internal Work Enhancement log. | Proposed | Cycle 1 (Jun-Aug 2026) | Not tracked
Dynamic Reports - Phase 1 | US-PLAT-002 | Medium | As a State Admin, I want inspection reports to be generated dynamically and linked with the dashboard, so that report structures automatically reflect form changes without manual report redevelopment. | Phase 1 marked 'Done' in Parakh Internal Work Enhancement log. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked
Report Sync for Department Forms | US-PLAT-003 | Medium | As a State Admin, I want a 'Sync Data' action available from the Tabular View of Inspection screen, so that the latest submitted inspection data is pulled into reports on demand. | Functionality documented: Login as State Admin -> Tabular View of Inspection -> Sync Data -> Data Synced. | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked

## Master Form Std US
District GIS Parakh – Consolidated User Stories ¦ State-Level Master Form Standardization ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Aadhar Center Inspection Form - State-Level Adoption | US-MSTR-001 | Medium | As the State Parakh Admin, I want the Narmadapuram district's Aadhar Center Inspection form adopted as the common state-level template, so that all districts (including Betul) use one consistent Aadhar verification form instead of building district-specific versions. | Confirmed by Dheeraj (1-Jul-2026): 'Narmadapuram Aadhar form can be used at the state level.' Referenced in Betul PSR row as 'Aadhar form taken at the state level - Common form for all districts.' | Completed | Cycle 1 (Jun-Aug 2026) | Not tracked