## INDEX
DISTRICT GIS PARAKH - CONSOLIDATED USER STORY REGISTER (v2) ¦ 30-Jun to 18-Aug 2026 ¦ MPSSDI / MPSeDC
Prepared by: Dheeraj, Senior Business Analyst, MPSeDC (MPSSDI) ¦ v2 Consolidated: 18-Aug-2026 ¦ Adds: Category, Use Case Type, FR/NFR classification, Estimation (Jal Rekha guideline format), and Activity-Hours task breakdown
Sr. No. | Sheet Name | Module / Area | No. of User Stories | Coverage
1 | Betul US | Betul District – 8-Form Rollout | 15 | 30-Jun to 18-Aug 2026 consolidated
2 | Damoh US | Damoh District – 13-Form Rollout | 13 | 30-Jun to 18-Aug 2026 consolidated
3 | Indore US | Indore Division – 17-Department / 58-Type Rollout | 29 | 30-Jun to 18-Aug 2026 consolidated
4 | Hostel-School-AWW US | Hostel, School & Anganwadi Inspection | 31 | 30-Jun to 18-Aug 2026 consolidated
5 | Health Facility US | Health & Medical Facility Inspection | 7 | 30-Jun to 18-Aug 2026 consolidated
6 | GIS Survey-Land US | GIS Survey, Land & Property Inspection | 10 | 30-Jun to 18-Aug 2026 consolidated
7 | Rural Dev-MGNREGA US | Rural Development & MGNREGA Inspection | 8 | 30-Jun to 18-Aug 2026 consolidated
8 | Govt Scheme-Welfare US | Govt. Scheme & Welfare Verification Forms | 11 | 30-Jun to 18-Aug 2026 consolidated
9 | Institutional Dept US | Institutional & Departmental Inspection Forms | 14 | 30-Jun to 18-Aug 2026 consolidated
10 | Other District US | Other District Inspection Forms | 7 | 30-Jun to 18-Aug 2026 consolidated
11 | PM Poshan US | PM Poshan Social Audit Program | 2 | 30-Jun to 18-Aug 2026 consolidated
12 | Asset Survey US | Asset Survey Module | 2 | 30-Jun to 18-Aug 2026 consolidated
13 | CTA Treasury-JD US | CTA – Treasury & JD Inspection | 2 | 30-Jun to 18-Aug 2026 consolidated
14 | Workflow Mgmt US | Workflow Management (ATR & Roster) | 2 | 30-Jun to 18-Aug 2026 consolidated
15 | Platform Enhance US | Platform Enhancement | 3 | 30-Jun to 18-Aug 2026 consolidated
16 | Master Form Std US | State-Level Master Form Standardization | 1 | 30-Jun to 18-Aug 2026 consolidated
| TOTAL USER STORIES |  | 157
What's new in v2 vs the previous register:
1. Category column: classifies every story as Implementation (new form/feature), Enhancement (platform capability upgrade), CR / Change Request (a modification to something already built/deployed), or Defect (a flagged issue/gap awaiting a fix).
2. Type of Use Case: functional grouping (Form Data Entry, Master Data Management, Workflow & Approval, Reporting & Analytics, Dashboard & Monitoring, Mobile Offline Capture, Data Sync & Integration, User/Role & Access Management, Training & Capacity Building).
3. Requirement Type: each story is tagged Functional or Non-Functional Requirement, with a one-line description of why.
4. Estimation column: follows the Jal Rekha Modules Estimation workbook's own Guidelines/Master sheets — Complexity (Low/Medium/High, using the 1/3/5-point scale), Work Type (New Development vs Enhancement and customization), and Component Category (Web Page/Screen, Reports, Mobile App-UI, API Integration, Data Migration, or Business Rules/Workflow) as defined there.
5. Activity Hours Consumed: each story's total estimated hours is split across 9 tasks (Requirement Gathering, Meetings, Form Development, Coding Development, Testing, Verifying, Monitoring, Deployment, Training to Department) using percentage weights derived from the Jal Rekha estimation workbook's own role-based Effort Distribution Guidelines (BA 15%, Architect 10%, Developer 40%, Tester 20%, PM 10%, Infra 5%), remapped to these 9 task types.
6. IMPORTANT — these are PLANNING ESTIMATES, not logged actuals. Parakh has no per-story timesheet data (unlike Jal Rekha's Sprint MoMs), so a base-hours figure was assigned per complexity tier (Low=8h, Medium=18h, High=36h, mirroring Jal Rekha's own point-to-hour productivity ratio) and then split by the percentages above. Treat these hours as indicative effort sizing for planning/budgeting, not as billed or actual time. Full methodology is documented in the accompanying Document of Understanding (DOU).
7. Indore worksheet: expanded from 4 to 29 stories — one per department (17 depts / 58 institution types) plus 12 platform/workflow stories (Divisional Commissioner dashboard, Collector monitoring, RO/HOD setup, User-Department assignment, offline mobile sync, access control, master data versioning, filtered reporting, auto-assignment, and the deferred Phase-2 SLA/escalation workflow), sourced from Indore_Inspection_Spec_Overview.pptx (Aug-2026).

## Betul US
District GIS Parakh – Consolidated User Stories ¦ Betul District – 8-Form Rollout ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
WCD Anganwadi Inspection Form | US-BETUL-001 | CR / Change Request | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As the Betul WCD (Women & Child Development) nodal team, we want Questions 16 and 17 added to the Anganwadi inspection form, so that the form captures the two additional data points requested by the department. | Questions 16 & 17 added and confirmed by Manisha (MPSeDC Testing) on 30-Jun-2026. | Complexity: Low ¦ Work Type: Enhancement and customization ¦ Component Category: Web Page / Screen with no of input fields | 1 | 0.5 | 1.5 | 1.5 | 1 | 0.5 | 0.5 | 0.5 | 1 | 8 | Completed | Cycle 1 (Jun-Aug 2026)
WCD Anganwadi Inspection Form - Conditional Master Fields | US-BETUL-002 | Defect | Master Data Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As an Inspector filling the Betul Anganwadi form, I want the 'Gram Name' field to be conditionally filtered by the selected 'Sector Name' (Sector -> Gram cascading dropdown) sourced from master data, so that I only see relevant villages and avoid data entry errors. | Of the 5 master-linked fields, only Gram Name and Sector Name are conditional; Sector Name is selected first and Gram Name list populates accordingly. Updated Betul master (with Sector and Gram) received and applied. | Complexity: Medium ¦ Work Type: Enhancement and customization ¦ Component Category: Data Migration | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
KGBV Hostel Monitoring Form | US-BETUL-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As the Betul District GIS Admin, I want the KGBV (Kasturba Gandhi Balika Vidyalaya) Hostel Monitoring form cloned from the Directorate of Public Instruction (DPI) department's existing form on Parakh, so that Betul can use a standardized, already-verified format. | DPI form copied to Betul Collectorate account by Madhur (2-Jul-2026). KGBV Form verified and approved by the DEO. Betul KGBV master list shared/uploaded (1-Jul-2026). | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Mine Inspection Form Update | US-BETUL-004 | CR / Change Request | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Mining Department Officer in Betul, I want the Mine Inspection form updated per the revised questions and master data shared by the department on 30-Jun-2026, so that inspections reflect the correct field requirements. | Updated 'mine inspection_30-06-2026' form shared by Dheeraj; Madhur flagged the update needs clarification before implementation. | Complexity: Medium ¦ Work Type: Enhancement and customization ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
Mine Inspection Form - Mineral Stock/Quality/Sand Master List | US-BETUL-005 | CR / Change Request | Master Data Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Mining Department Officer in Betul, I want the Betul Mineral List (Stock, Quality Level (QL) and Sand list) loaded as master data in the Mine Inspection form, so that inspectors select accurate, pre-approved mineral references during inspection instead of free-text entry. | Mineral list (Stock, QL & Sand) shared with Manisha and Madhur on 3-Jul-2026; questions and master data formatted per department discussion. | Complexity: Medium ¦ Work Type: Enhancement and customization ¦ Component Category: Data Migration | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
School Nirikshan (Sehore format) merge into Betul School Monitoring Form | US-BETUL-006 | CR / Change Request | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As the Betul Education Department, we want the Sehore 'School Nirikshan Prapatra - Part 1' questions merged into our School Monitoring form (after our department's own requested questions are added first), so that Betul's school inspections follow a combined, standardized format aligned with the state model. | Madhur copied both the DPI hostel form and the Sehore school form templates to the Betul Collectorate account (2-Jul-2026). Betul department instructed: add their own questions first, then merge in Sehore Part 1. | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Web Page / Screen with no of input fields | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | In Progress | Cycle 1 (Jun-Aug 2026)
Tribal Hostel Inspection Form - Access Credentials | US-BETUL-007 | Implementation | User, Role & Access Management | Non-Functional Requirement | Non-Functional — an access-control/security constraint governing who may see or act on data, rather than a feature the end user directly invokes. | Medium | As the Betul Collectorate Tribal Department, we want login credentials issued for the Tribal Hostel Inspection form (mirrored from the Tribal Department's launched form), so that our officials can begin conducting hostel inspections on Parakh. | Awaiting login credentials for Betul Collectorate Tribal Department per PSR log; Bhopal Commissioner Office granted similar access as reference precedent. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
KGBV Hostel Form | US-BETUL-008 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As the Betul District GIS Cell, I want the 'KGBV Hostel Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Verified and approved by the DEO. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
PM Poshan (PNRD) Form | US-BETUL-009 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As the Betul District GIS Cell, I want the 'PM Poshan (PNRD) Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Department Form verification completed; nodal assignment pending. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
WCD Anganwadi Form | US-BETUL-010 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As the Betul District GIS Cell, I want the 'WCD Anganwadi Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | With developer team for Questions 16 & 17 modification. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
School Monitoring Patra Form | US-BETUL-011 | Enhancement | Workflow & Approval Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As the Betul District GIS Cell, I want the 'School Monitoring Patra Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Decided to proceed with a single form format; department to raise official request if a separate form is needed. | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Queries or Business rules for the application | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | Completed | Cycle 1 (Jun-Aug 2026)
Health Inspection Form | US-BETUL-012 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As the Betul District GIS Cell, I want the 'Health Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Development and deployment completed; form is live. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Mining Inspection Form | US-BETUL-013 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As the Betul District GIS Cell, I want the 'Mining Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Questions and master data formatted and shared; awaiting developer team update. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Aadhaar Centre Inspection Form | US-BETUL-014 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As the Betul District GIS Cell, I want the 'Aadhaar Centre Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Email shared with department; awaiting confirmation. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
Tribal Hostel Inspection Form | US-BETUL-015 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As the Betul District GIS Cell, I want the 'Tribal Hostel Inspection Form' finalized and go-live ready on Parakh, so that this is one of the 8 department forms completing Betul's full district onboarding. | Awaiting login credentials for Betul Collectorate Tribal Department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)

## Damoh US
District GIS Parakh – Consolidated User Stories ¦ Damoh District – 13-Form Rollout ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Zila Karyalay Panchayat Form | US-DAMOH-001 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'BBGRAMJI Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Pradhan Mantri Awas Yojana (PMAY) Inspection Form | US-DAMOH-002 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Pradhan Mantri Awas Yojana (PMAY) Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Gram Nal Jal Praday Yojana Inspection Form | US-DAMOH-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Gram Nal Jal Praday Yojana Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
School/Institute Inspection Form | US-DAMOH-004 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'School/Institute Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Anganwadi Inspection Form | US-DAMOH-005 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Anganwadi Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Jan Vishwas Abhiyaan - Health Department Form | US-DAMOH-006 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Jan Vishwas Abhiyaan - Health Department Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Govt. Uchit Mulya Ki Dukan (Fair Price Shop) Inspection Form | US-DAMOH-007 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Govt. Uchit Mulya Ki Dukan (Fair Price Shop) Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Petrol Pump Inspection Form | US-DAMOH-008 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Petrol Pump Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
LPG Dealer Inspection Form | US-DAMOH-009 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'LPG Dealer Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
CM Jan Vishwas Abhiyaan - Farm & Dairy Department Inspection Form | US-DAMOH-010 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'CM Jan Vishwas Abhiyaan - Farm & Dairy Department Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Liquor Department Inspection Form | US-DAMOH-011 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Liquor Department Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Hostel/Ashram Inspection Form | US-DAMOH-012 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Hostel/Ashram Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Krishi Saakh and Sahkari Samiti (Agri Credit & Cooperative Society) Inspection Form | US-DAMOH-013 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Damoh Zila Panchayat / District Officer, I want the 'Krishi Saakh and Sahkari Samiti (Agri Credit & Cooperative Society) Inspection Form' configured on District GIS Parakh, so that this department's inspections in Damoh district can be captured, tracked, and reported digitally as part of the district's 13-form rollout. | Zila Panchayat form created and live in Production (batch status per PSR log, Damoh row). Department is sharing master data for the remaining forms; parallel check underway for any required Change Requests. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)

## Indore US
District GIS Parakh – Consolidated User Stories ¦ Indore Division – 17-Department / 58-Type Rollout ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Higher Education Department Inspection Form (4 institution/asset types) | US-INDORE-001 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the Higher Education Department in Indore Division, I want a checklist inspection form covering all 4 institution/asset type(s) under Higher Education built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that Higher Education inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 4 institution/asset type(s) for Higher Education; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by Higher Education HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Education Department Inspection Form (4 institution/asset types) | US-INDORE-002 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the Education Department in Indore Division, I want a checklist inspection form covering all 4 institution/asset type(s) under Education built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that Education inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 4 institution/asset type(s) for Education; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by Education HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Panchayat & Rural Development Department Inspection Form (5 institution/asset types) | US-INDORE-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the Panchayat & Rural Development Department in Indore Division, I want a checklist inspection form covering all 5 institution/asset type(s) under Panchayat & Rural Development built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that Panchayat & Rural Development inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 5 institution/asset type(s) for Panchayat & Rural Development; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by Panchayat & Rural Development HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Health Department Inspection Form (11 institution/asset types) | US-INDORE-004 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the Health Department in Indore Division, I want a checklist inspection form covering all 11 institution/asset type(s) under Health built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that Health inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 11 institution/asset type(s) for Health; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by Health HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Agriculture Department Inspection Form (3 institution/asset types) | US-INDORE-005 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the Agriculture Department in Indore Division, I want a checklist inspection form covering all 3 institution/asset type(s) under Agriculture built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that Agriculture inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 3 institution/asset type(s) for Agriculture; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by Agriculture HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Forest Department Inspection Form (3 institution/asset types) | US-INDORE-006 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the Forest Department in Indore Division, I want a checklist inspection form covering all 3 institution/asset type(s) under Forest built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that Forest inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 3 institution/asset type(s) for Forest; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by Forest HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Revenue Department Inspection Form (3 institution/asset types) | US-INDORE-007 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the Revenue Department in Indore Division, I want a checklist inspection form covering all 3 institution/asset type(s) under Revenue built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that Revenue inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 3 institution/asset type(s) for Revenue; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by Revenue HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
PWD Department Inspection Form (3 institution/asset types) | US-INDORE-008 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the PWD Department in Indore Division, I want a checklist inspection form covering all 3 institution/asset type(s) under PWD built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that PWD inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 3 institution/asset type(s) for PWD; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by PWD HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
UADD Department Inspection Form (3 institution/asset types) | US-INDORE-009 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the UADD Department in Indore Division, I want a checklist inspection form covering all 3 institution/asset type(s) under UADD built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that UADD inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 3 institution/asset type(s) for UADD; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by UADD HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
WCD Department Inspection Form (3 institution/asset types) | US-INDORE-010 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the WCD Department in Indore Division, I want a checklist inspection form covering all 3 institution/asset type(s) under WCD built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that WCD inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 3 institution/asset type(s) for WCD; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by WCD HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
MPEB Department Inspection Form (2 institution/asset types) | US-INDORE-011 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the MPEB Department in Indore Division, I want a checklist inspection form covering all 2 institution/asset type(s) under MPEB built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that MPEB inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 2 institution/asset type(s) for MPEB; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by MPEB HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
RTO Department Inspection Form (2 institution/asset types) | US-INDORE-012 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the RTO Department in Indore Division, I want a checklist inspection form covering all 2 institution/asset type(s) under RTO built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that RTO inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 2 institution/asset type(s) for RTO; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by RTO HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
MPRDC Department Inspection Form (3 institution/asset types) | US-INDORE-013 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the MPRDC Department in Indore Division, I want a checklist inspection form covering all 3 institution/asset type(s) under MPRDC built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that MPRDC inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 3 institution/asset type(s) for MPRDC; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by MPRDC HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
PHE Department Inspection Form (3 institution/asset types) | US-INDORE-014 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the PHE Department in Indore Division, I want a checklist inspection form covering all 3 institution/asset type(s) under PHE built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that PHE inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 3 institution/asset type(s) for PHE; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by PHE HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Ayush Department Inspection Form (2 institution/asset types) | US-INDORE-015 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the Ayush Department in Indore Division, I want a checklist inspection form covering all 2 institution/asset type(s) under Ayush built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that Ayush inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 2 institution/asset type(s) for Ayush; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by Ayush HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
OBC Department Inspection Form (2 institution/asset types) | US-INDORE-016 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the OBC Department in Indore Division, I want a checklist inspection form covering all 2 institution/asset type(s) under OBC built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that OBC inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 2 institution/asset type(s) for OBC; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by OBC HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
GMDIC Department Inspection Form (2 institution/asset types) | US-INDORE-017 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Inspector for the GMDIC Department in Indore Division, I want a checklist inspection form covering all 2 institution/asset type(s) under GMDIC built on the standard Parakh checklist shell (General Header, Asset Identification, 16-24 dept-specific checklist points rated Satisfactory/Unsatisfactory/N.A., geo-tagged photo evidence, and Findings & Closure), so that GMDIC inspections in Indore are captured digitally on both web and mobile with identical behaviour. | Form covers all 2 institution/asset type(s) for GMDIC; common 5-section shell followed (Header, Asset ID, Checklist Body, Evidence, Findings & Closure); available on Web and Mobile with identical behaviour; department-specific checklist points reviewed and signed off by GMDIC HOD. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Divisional Commissioner Login & Dashboard | US-INDORE-018 | Implementation | Dashboard & Monitoring | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As the Divisional Commissioner for Indore Division, I want a role-scoped dashboard showing summary inspection status across all districts and departments in the division, so that I can monitor division-wide inspection compliance without drilling into individual records. | Commissioner login is role-scoped and read-only for individual inspection records; dashboard shows summary status only (per Sec 5.5); covers all districts within the division. | Complexity: High ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | In Progress | Cycle 1 (Jun-Aug 2026)
District Collector Monitoring View | US-INDORE-019 | Implementation | Dashboard & Monitoring | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As the District Collector, I want a monitoring view showing all departments within my district and their HOD action/protocol compliance status, so that I can track SLA adherence for pending inspection findings. | Collector view scoped to own district, all departments visible; SLA (department response timeframe) monitored; role-based access enforced per Sec 6.3 access-control matrix. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Department HOD / RO Setup as Reviewing Officer | US-INDORE-020 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Admin, I want each Department HOD to be created and configured as a Reviewing Officer (RO) with visibility limited to their own department, so that action-taken updates and evidence uploads route to the correct authority. | RO created as Department HOD; HOD visible in the User list; access scoped to own department only (per Sec 3 stakeholder hierarchy). | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
User–Department Assignment (Inspector Mapping) Screen | US-INDORE-021 | Implementation | User, Role & Access Management | Non-Functional Requirement | Non-Functional — an access-control/security constraint governing who may see or act on data, rather than a feature the end user directly invokes. | High | As a District Admin, I want a User–Department Assignment screen to map Field Inspectors to their assigned department/sub-department (including the 56 RO mappings), so that inspection submissions are correctly routed and attributable. | Assignment screen supports list/search/edit with department-wise filters; 56 RO mappings finalized as part of master data setup (Build Roadmap step 1 & 5). | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
General Form Report — HOD Review & Action | US-INDORE-022 | Implementation | Reporting & Analytics | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Department HOD, I want a General Form Report showing all inspection submissions for my department with the ability to record action taken, upload supporting evidence, and change status, so that findings are formally closed with an audit trail. | Report available to HOD; supports remark, evidence upload, and status control (Submitted / Pending / Verified-Closed / Unapproved-Rejected); status changes logged. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Reports | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Assignment & Action-Tracking Workflow (Status States) | US-INDORE-023 | Implementation | Workflow & Approval Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Department HOD, I want inspection submissions to move through a defined workflow (Submitted -> Pending -> Verified/Closed, or Unapproved/Rejected with re-inspection), so that every finding has a clear, trackable resolution path. | On submission, record is auto-routed to Dept. HOD and made read-only to Collector & Commissioner; Pending state awaits HOD action; Verified/Closed requires evidence; Unapproved/Rejected returns to inspector with remark for re-inspection. | Complexity: High ¦ Work Type: New Development ¦ Component Category: Queries or Business rules for the application | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | In Progress | Cycle 1 (Jun-Aug 2026)
Mobile App Offline Field Capture with Sync-on-Reconnect | US-INDORE-024 | Enhancement | Mobile Offline Field Capture | Non-Functional Requirement | Non-Functional — a reliability/availability constraint (offline capability, sync integrity) the system must satisfy under poor-connectivity conditions. | High | As a Field Inspector, I want to fill inspection checklists offline in areas with poor connectivity (with dropdown and mandatory-field validation and photo capture) and have the draft sync automatically once reconnected, so that field visits are not blocked by network availability. | Offline draft save supported; dropdown & mandatory-field validation enforced client-side; photo capture supported; sync-on-reconnect pushes drafts to Central Parakh Server without data loss. | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Mobile App-UI | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | In Progress | Cycle 1 (Jun-Aug 2026)
Role-Scoped Access Control Matrix | US-INDORE-025 | Enhancement | Workflow & Approval Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a System Admin, I want role-based access control across Inspector, HOD, Collector, and Divisional Commissioner logins, so that each role sees only the data appropriate to their level in the organisational hierarchy. | Access-control matrix defined per Sec 6.3; Inspector sees own submissions; HOD sees own department; Collector sees own district (all departments); Commissioner sees division-wide summary only. | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Queries or Business rules for the application | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | Completed | Cycle 1 (Jun-Aug 2026)
Master Data Layer — Department / Sub-Department / Checklist Template (Versioned) | US-INDORE-026 | Enhancement | Master Data Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a System Admin, I want a versioned master data layer covering Department, Sub-Department (Institution Type), and Checklist Template, so that checklist changes over time are tracked and historical inspection records remain consistent with the template version used at capture time. | Master data layer supports Department and Sub-Department (58 institution types across 17 departments); Checklist Templates are versioned; Central Parakh Server stores and serves this master data. | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Data Migration | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | In Progress | Cycle 1 (Jun-Aug 2026)
Department-wise Report with Filter Columns | US-INDORE-027 | Implementation | Reporting & Analytics | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Collector, I want a department-wise inspection report with filter columns (department, sub-department, status, date range, officer), so that I can quickly identify pending or overdue inspections by any dimension. | Report supports filtering by department, institution type, status, and date range; exportable for offline review (Build Roadmap step 8). | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Reports | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
Auto-Assignment / Work Allocation to HOD | US-INDORE-028 | Defect | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a System Admin, I want submitted inspections to be auto-assigned/allocated to the correct Department HOD without manual routing, so that no finding is missed due to a routing error. | Auto-assignment logic routes each submission to the HOD mapped to that department/sub-department at submission time (Build Roadmap step 9). | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Web Page / Screen with no of input fields | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | Proposed | Cycle 1 (Jun-Aug 2026)
SLA-based Escalation & Automated Closure Workflow (Phase 2 — Deferred) | US-INDORE-029 | Enhancement | Workflow & Approval Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Low | As a Divisional Commissioner, I want SLA-based automatic escalation when a department fails to act within the defined timeframe, and automated closure once evidence is verified, so that inspection findings cannot silently go unresolved. | Explicitly out of current build scope; deferred to Phase 2 per Sec 2 (Scope — Phase 2) and Slide 9 (SLA/closure automation — Planned Phase 2). | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Queries or Business rules for the application | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | Proposed | Cycle 1 (Jun-Aug 2026)

## Hostel-School-AWW US
District GIS Parakh – Consolidated User Stories ¦ Hostel, School & Anganwadi Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Hostel Survey (Parakh) | US-HSA-001 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Field Surveyor in Alirajpur, I want the 'Hostel Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
School Survey (Parakh) | US-HSA-002 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Field Surveyor in Chhindwara, I want the 'School Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT completed. Go Live | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
School Survey, Hostel, Anganbadi, PDS Center Extra Inspection App (Parakh) | US-HSA-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Field Surveyor in Dindori , Collectorate, I want the 'School Survey, Hostel, Anganbadi, PDS Center Extra Inspection App (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Hostel Survey (Parakh) | US-HSA-004 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Field Surveyor in Vidisha, I want the 'Hostel Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Hostel Survey (Parakh) | US-HSA-005 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Field Surveyor in Bhind, I want the 'Hostel Survey (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Bhind Collectorate is onboarded. Development work completed. Awaiting list of Hostels from the Collectorate office, so to initiate UAT. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
Hostel Inpection , Adharcard Inpection , aganwadi Inpection, Goverment School Inpection | US-HSA-006 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Hostel Inspecting Officer in Narmadapuram, I want the 'Hostel Inpection , Adharcard Inpection , aganwadi Inpection, Goverment School Inpection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म | US-HSA-007 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Narmadapuram, I want the 'Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | The form has arrived, UAT has been sent, and testing has started. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey | US-HSA-008 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Field Surveyor in rajgarh, I want the 'छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | The form has arrived, UAT has been sent, and testing has started. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म | US-HSA-009 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in seoni, I want the 'छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र | US-HSA-010 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Tribale department, I want the 'जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work complete | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Parakh _Survey Form ST/SC hostel | US-HSA-011 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Field Surveyor in Seoni District, I want the 'Parakh _Survey Form ST/SC hostel' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Parakh _App_Hostel Survey | US-HSA-012 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Surveyor in कार्यालय कलेक्टर भोपाल म.प्र, I want the 'Parakh _App_Hostel Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Hostel Survey on Parakh App | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Parakh _App_Hostel Survey | US-HSA-013 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Surveyor in कार्यालय कलेक्टर (अनुसूचित जाति एवं जनजातीय कार्य विभाग ) भोपाल, I want the 'Parakh _App_Hostel Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Hostel Survey on Parakh App | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Parakh _App_Hostel Survey | US-HSA-014 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Surveyor in कार्यालय कलेक्टर (पिछड़ा वर्ग तथा अल्पसंख्यक कल्याण ) भोपाल, I want the 'Parakh _App_Hostel Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Hostel Survey on Parakh App | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Grocery, Hostel , & General Inspection form | US-HSA-015 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Chhattarpur, I want the 'Grocery, Hostel , & General Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
Hostel Inspection Form | US-HSA-016 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Vidisha, I want the 'Hostel Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
NRC Inspection Form, Primary middle school Inspection Form | US-HSA-017 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Vidisha, I want the 'NRC Inspection Form, Primary middle school Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Pharmacist Medical Drug store form, Anganwadi inspection form | US-HSA-018 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Vidisha, I want the 'Pharmacist Medical Drug store form, Anganwadi inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Need Clarifications form department on few questions ¦ Pending with: District Collectorate | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
PM School, Awas and AAdhar center | US-HSA-019 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a School Inspecting Officer in Mandla, I want the 'PM School, Awas and AAdhar center' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form and report Deployed ¦ Pending with: Distrcit collectorate - GIS executive - Ankita Soni 1) to clarify on pm poshan form to incorporate same like mgnrega one | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
School Inspection FOrm | US-HSA-020 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Sehore, I want the 'School Inspection FOrm' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in UAT. Email sent to District collectorate & GIS executive ¦ Pending with: District Collectorate | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Anganwadi | US-HSA-021 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Anganwadi Inspecting Officer in Guna, I want the 'Anganwadi' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created in Uat, Email sent to District collectorate & GIS executive, confirmation required from the District Collectorate & GIS executive ¦ Pending with: Manisha | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
This form comes Under Sate coordinator PM Poshan Department Social Audit of schools Scheme | US-HSA-022 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a School Inspecting Officer in MGNREGA PM Poshan Department, I want the 'This form comes Under Sate coordinator PM Poshan Department Social Audit of schools Scheme' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Deployed to Prod ¦ Pending with: Department | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Hostel Inspection | US-HSA-023 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Ashoknagar Distrct, I want the 'Hostel Inspection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | adopted tribal department form | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
School, Hostel, Anganwadi, Health Center | US-HSA-024 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Hostel Inspecting Officer in Gwalior, I want the 'School, Hostel, Anganwadi, Health Center' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form/report created and deployed,email sent ¦ Pending with: Waiting for mail confirmation | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
School Inspection Form | US-HSA-025 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Rajgarh, I want the 'School Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created, awaiting for confirmation | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
Aganwadi | US-HSA-026 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Ashoknagar Distrct, I want the 'Aganwadi' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created ¦ Pending with: Madhur and arindham | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Hostel Inspection Form(SC/ST category) | US-HSA-027 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Inspecting Officer in Bhopal commissioner office, I want the 'Hostel Inspection Form(SC/ST category)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form is same as tribal department. Bhopal Commissioner Office has raised request for creation of the Tribal Inspection Form. This form is same as of the Tribal Hostel Inspection Forms launched by the Tribal Department. T | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
सरकारी स्कूल में शौचालय | US-HSA-028 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a District Nodal Officer in Ujjain, I want the 'सरकारी स्कूल में शौचालय' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is still not finalized from CEO ZP ¦ Pending with: Sakshi / ON Hold | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Hostel Inspection form | US-HSA-029 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Directorate Public Instructions, I want the 'Hostel Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created ¦ Pending with: Madhur | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
5 forms - Anganwadi, PMPoshan, Godown, Hostel Monitoring, Health Form, | US-HSA-030 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Hostel Inspecting Officer in Chhindwara, I want the '5 forms - Anganwadi, PMPoshan, Godown, Hostel Monitoring, Health Form,' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Forms are created and Live in Production. Report work is going on ¦ Pending with: Pending from Chhindwara Collectorate Department & Development team for Report | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
OBC Triabl Hostel form | US-HSA-031 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Hostel Inspecting Officer in Rajgarh, I want the 'OBC Triabl Hostel form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created in UAT ¦ Pending with: Department to verify | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)

## Health Facility US
District GIS Parakh – Consolidated User Stories ¦ Health & Medical Facility Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Hospital Inspection form | US-HMF-001 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Jabalpur, I want the 'Hospital Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
Health Inspection Form | US-HMF-002 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Narmadapuram, I want the 'Health Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
1. DISTRICT / CIVIL / SUPER SPECIALITY HOSPITAL (जिला / सिविल / सुपर स्पेशियलिटी अस्पताल) 2. COMMUNITY HEALTH CENTRE (सामुदायिक स्वास्थ्य केंद्र (सीएच | US-HMF-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Health Inspecting Officer in Health Department, I want the '1. DISTRICT / CIVIL / SUPER SPECIALITY HOSPITAL (जिला / सिविल / सुपर स्पेशियलिटी अस्पताल) 2. COMMUNITY HEALTH CENTRE (सा' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in prod . chase department for progress ¦ Pending with: Ajeet | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
Health Inspection form ,निरीक्षण प्रतिवेदन,गोदाम निरीक्षण | US-HMF-004 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Inspecting Officer in Burhanpur, I want the 'Health Inspection form ,निरीक्षण प्रतिवेदन,गोदाम निरीक्षण' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form is live,report is created ¦ Pending with: Department | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Patient Feedback Form | US-HMF-005 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Department Feedback Coordinator in Guna & Gwalior, I want the 'Patient Feedback Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | HTML Form and QR Code Created | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Ayush Department | US-HMF-006 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a District Nodal Officer in Guna, I want the 'Ayush Department' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Patient Feedback form OPD/IPD Patient Satisfaction Survey Forms | US-HMF-007 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Surveyor in Bhind, I want the 'Patient Feedback form OPD/IPD Patient Satisfaction Survey Forms' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form copied from Guna form format and new questions to be added for Bhind requirement | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)

## GIS Survey-Land US
District GIS Parakh – Consolidated User Stories ¦ GIS Survey, Land & Property Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Drone Survey | US-GSL-001 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Field Surveyor in Bhind, I want the 'Drone Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Drone Urban Survey | US-GSL-002 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Surveyor in Khandwa, I want the 'Drone Urban Survey' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Drone survey is in process. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Scanning of (Old Revenue / Naksha Record of Rewa (14399 Sheets) | US-GSL-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Rewa, I want the 'Scanning of (Old Revenue / Naksha Record of Rewa (14399 Sheets)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work in Progress (Till Date 2793 sheets done) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Satellite data based maps for Urban Local Body boundary extension | US-GSL-004 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Patan, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Satellite data based maps for Urban Local Body boundary extension | US-GSL-005 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Sidhi, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Satellite data based maps for Urban Local Body boundary extension | US-GSL-006 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Sagar, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Satellite data based maps for Urban Local Body boundary extension | US-GSL-007 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Narsinghpur, I want the 'Satellite data based maps for Urban Local Body boundary extension' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Survey completed. Data Shared with Department | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Sugamya Abhiyaan | US-GSL-008 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Indore, I want the 'Sugamya Abhiyaan' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created and live on production, report is created | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Property Inspection | US-GSL-009 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Inspecting Officer in Indore Collectorate, I want the 'Property Inspection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created and Tested | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Building Inspection Form | US-GSL-010 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Inspecting Officer in Jabalpur, I want the 'Building Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Forms are created and Testing needs to be done ¦ Pending with: Pending from Jabalpur Collectorate Department | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)

## Rural Dev-MGNREGA US
District GIS Parakh – Consolidated User Stories ¦ Rural Development & MGNREGA Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Anuppur Works Management System (Mobile wire frames for WMS) | US-RDM-001 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a District Nodal Officer in Zila Punchayat , Anuppur, I want the 'Anuppur Works Management System (Mobile wire frames for WMS)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Grameen Vikas Panchyat Grading live | US-RDM-002 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Jabalpur, I want the 'Grameen Vikas Panchyat Grading live' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed and went live | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Mgnrega work related inspection form | US-RDM-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Bhind, I want the 'Mgnrega work related inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Completed | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Inspection on Watershed projects ( project name and related work cost ) | US-RDM-004 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in PNRD NRM PMKSY, I want the 'Inspection on Watershed projects ( project name and related work cost )' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in UAT. Email sent to department, ¦ Pending with: Department | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
मनरेगा (MGNREGA) योजनांतगत नमाण काय के नर ण | US-RDM-005 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Mandla (On Hold), I want the 'मनरेगा (MGNREGA) योजनांतगत नमाण काय के नर ण' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Mandla district specific Department is not clear on requirement as conveyed by Ankita ¦ Pending with: Ankita Soni GIS Executive | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
SNA Sparsh अंतर्गत प्रशासकीय मद के भुगतान की जानकारी | US-RDM-006 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in PNRD-MGNREGA, I want the 'SNA Sparsh अंतर्गत प्रशासकीय मद के भुगतान की जानकारी' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live ¦ Pending with: Dheeraj,Aman | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Baseline Survey Form | US-RDM-007 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Field Surveyor in PNRD-SRLM, I want the 'Baseline Survey Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created,email sent and waiting for department confirmation ¦ Pending with: Department | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Road Inspection Form | US-RDM-008 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Inspecting Officer in MPRRD, I want the 'Road Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | In UAT ¦ Pending with: Dev Team | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)

## Govt Scheme-Welfare US
District GIS Parakh – Consolidated User Stories ¦ Govt. Scheme & Welfare Verification Forms ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Sarthak _Attendance / Parakh | US-GSW-001 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Nodal Attendance Officer in Narmadapuram, I want the 'Sarthak _Attendance / Parakh' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Parakh _Survey Form Adhar Kendra Inspection/Data Collection | US-GSW-002 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Field Surveyor in Satna District, I want the 'Parakh _Survey Form Adhar Kendra Inspection/Data Collection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work completed. Issued for UAT on 13/02/25 | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Sarthak App_Attendance Marking | US-GSW-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Nodal Attendance Officer in Ashoknagar Distrct, I want the 'Sarthak App_Attendance Marking' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Work In Progress_ Sarthak App_Attendance Marking | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
MP MLA CM A CM A+ & Ghoshna Form | US-GSW-004 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in PNRD RES, I want the 'MP MLA CM A CM A+ & Ghoshna Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
Narcotics Drug Form | US-GSW-005 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Agar Malwa, I want the 'Narcotics Drug Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Deployed to Prod, email need to be sent ¦ Pending with: Development team/ Dheeraj | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Feedback form | US-GSW-006 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Department Feedback Coordinator in Chhindwara, I want the 'Feedback form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | deployed to Prod , email sent ¦ Pending with: Manisha | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Aadhar account verification form | US-GSW-007 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Gwalior, I want the 'Aadhar account verification form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form/report created and deployed,email sent ¦ Pending with: Waiting for mail confirmation | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
75 वर्ष या उससे अधिक आयुके बिना सन्त लाभार्थियो हेतु मासिक सुविधा मॉनिटरिंग करने के लिए | US-GSW-008 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Bhind, I want the '75 वर्ष या उससे अधिक आयुके बिना सन्त लाभार्थियो हेतु मासिक सुविधा मॉनिटरिंग करने के लिए' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | form and report is deployed on production, ¦ Pending with: Sakshi | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Adhar inspection | US-GSW-009 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Chhindwara, I want the 'Adhar inspection' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is live,report is created,email sent confirmed | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Ujjain Mela | US-GSW-010 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Ujjain Mela, I want the 'Ujjain Mela' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created and live | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Jan Vishwas forms like Damoh | US-GSW-011 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a District Nodal Officer in Indore, I want the 'Jan Vishwas forms like Damoh' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)

## Institutional Dept US
District GIS Parakh – Consolidated User Stories ¦ Institutional & Departmental Inspection Forms ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Inspection Mobile App on (Parakh) | US-IDI-001 | Implementation | Mobile Offline Field Capture | Non-Functional Requirement | Non-Functional — a reliability/availability constraint (offline capability, sync integrity) the system must satisfy under poor-connectivity conditions. | High | As a Inspecting Officer in Khargone, I want the 'Inspection Mobile App on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | The current collector of Khargone has changed. The new collector will decide whether this project will proceed or not, and if it does, how the work will be carried forward. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Mobile App-UI | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Inspection Mobile App on (Parakh) | US-IDI-002 | Implementation | Mobile Offline Field Capture | Non-Functional Requirement | Non-Functional — a reliability/availability constraint (offline capability, sync integrity) the system must satisfy under poor-connectivity conditions. | Medium | As a Inspecting Officer in Burhanpur, I want the 'Inspection Mobile App on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form configured, tested in UAT, and confirmed with department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Mobile App-UI | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Inspection Mobile App on (Parakh) | US-IDI-003 | Implementation | Mobile Offline Field Capture | Non-Functional Requirement | Non-Functional — a reliability/availability constraint (offline capability, sync integrity) the system must satisfy under poor-connectivity conditions. | Medium | As a Inspecting Officer in Tikamgarh , Collectorate, I want the 'Inspection Mobile App on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT completed. Awaiting approval from the Collectorate to Go Live | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Mobile App-UI | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
Creation Google form , Login ID Password | US-IDI-004 | Implementation | User, Role & Access Management | Non-Functional Requirement | Non-Functional — an access-control/security constraint governing who may see or act on data, rather than a feature the end user directly invokes. | High | As a District Nodal Officer in Chhatarpur Dist, I want the 'Creation Google form , Login ID Password' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | they will preparing our form and sending it from the Tikamgarh department, but they have also requested Alirajgarh's Parhak credentials for review. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
General Inspection on (Parakh) | US-IDI-005 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Bhopal commissioner office, I want the 'General Inspection on (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Live | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Creation Google form , Login ID Password | US-IDI-006 | Implementation | User, Role & Access Management | Non-Functional Requirement | Non-Functional — an access-control/security constraint governing who may see or act on data, rather than a feature the end user directly invokes. | High | As a District Nodal Officer in Chhatarpur Dist, I want the 'Creation Google form , Login ID Password' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Live | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
LKS Inspection Form | US-IDI-007 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Saps, I want the 'LKS Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Go-live | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Inspection Form | US-IDI-008 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Ayush Department, I want the 'Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Departement onboarded on uat. department to share survey form ¦ Pending with: Subhee Nema | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
Inspection Form | US-IDI-009 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in MPHIDB, I want the 'Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form created on UAT ¦ Pending with: Ajeet | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
Temple and Temple Land Details Form | US-IDI-010 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a District Nodal Officer in Religious and Trust Endowment, I want the 'Temple and Temple Land Details Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form is created on UAT ¦ Pending with: Bharat/Aman | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)
Kharidi Kendra | US-IDI-011 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Bhopal - Food Department, I want the 'Kharidi Kendra' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form received from bhopal collectorate ¦ Pending with: Sakshi / Madhur | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
Hand-Pump Inspection form | US-IDI-012 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Rajgarh Collectorate, I want the 'Hand-Pump Inspection form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form Created & live | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Mining Inspection Form | US-IDI-013 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Inspecting Officer in Mining Department, I want the 'Mining Inspection Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Forms created and Live in Production | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
Plantation Form | US-IDI-014 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a District Nodal Officer in MP Metro, I want the 'Plantation Form' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | QR Code based functionality . Form created | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)

## Other District US
District GIS Parakh – Consolidated User Stories ¦ Other District Inspection Forms ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Wash on wheel (Parakh) | US-ODF-001 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Chhindwara, I want the 'Wash on wheel (Parakh)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
lnspection Module (Parakh App) | US-ODF-002 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in SAPS, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
lnspection Module (Parakh App) | US-ODF-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Rajgarh, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | UAT Completed & Went Live (In use by Dept) | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
lnspection Module (Parakh App) | US-ODF-004 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in MGNREGA Dynamic Form Creation, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Dynamic Form - Meeting Video Link Meeting Recording Notes | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
lnspection Module (Parakh App) | US-ODF-005 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Bhopal - UADD Department SQM Inspection Form, I want the 'lnspection Module (Parakh App)' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Form in UAT. But no call back from the department. Waiting for their confirmation. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Proposed | Cycle 1 (Jun-Aug 2026)
form is live but awaiting for autopopulation | US-ODF-006 | Defect | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in School Education Department, I want the 'form is live but awaiting for autopopulation' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Implemented in prod . chase department for autopopulation of School list ¦ Pending with: Madhur/ Dheeraj and Altamsah | Complexity: Medium ¦ Work Type: Enhancement and customization ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
Intergration with CIS system for user onboarding , establishment, and form to establishment mapping | US-ODF-007 | Implementation | Data Sync & System Integration | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a District Nodal Officer in Labour Department, I want the 'Intergration with CIS system for user onboarding , establishment, and form to establishment mapping' onboarded and configured on District GIS Parakh, so that the department can digitally capture, submit, and report on this inspection/survey instead of using manual/paper-based methods. | Completed ¦ Pending with: Madhur | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: No of API Integrations | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)

## PM Poshan US
District GIS Parakh – Consolidated User Stories ¦ PM Poshan Social Audit Program ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
PM Poshan Social Audit Inspection Form | US-PMP-001 | CR / Change Request | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As the State Coordinator for the PM Poshan (Social Audit of Schools) Scheme, I want the PM Poshan Social Audit inspection form deployed on Parakh, so that field auditors can capture school meal-scheme compliance data digitally across all onboarded districts. | Form completed and deployed to Production (per PSR Log, PM Poshan/MGNREGA row). Mandla district requested one question be aligned with the MGNREGA form format and a correction to the '270 sq ft' related question. | Complexity: Medium ¦ Work Type: Enhancement and customization ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)
PM Poshan Social Audit Training | US-PMP-002 | Implementation | Training & Capacity Building | Non-Functional Requirement | Non-Functional — a process/capability-enablement requirement (staff training) that supports system adoption rather than describing a specific system behaviour. | Medium | As a PM Poshan Program Coordinator, I want the Social Audit training session conducted and photo evidence of the training uploaded/tracked, so that we have documented proof that field auditors were trained on the inspection form and process before rollout. | Training conducted; photo documentation shared by Dheeraj on 1-Jul-2026 and again on 3-Jul-2026. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)

## Asset Survey US
District GIS Parakh – Consolidated User Stories ¦ Asset Survey Module ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Asset Survey Module - End-to-End Workflow | US-ASM-001 | Enhancement | Workflow & Approval Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Department using District GIS Parakh (Mobile & Web), I want an end-to-end Asset Survey workflow covering User Creation & Approval -> Asset Creation -> Asset Assignment to Department User -> Asset Survey, so that government assets can be inventoried, assigned, and periodically surveyed digitally. | Bilingual (English/Hindi) Asset Survey User Manual v1.2 produced, dated 24-Jul-2026, covering Introduction, Roles & Responsibilities, Pre-Requisites, 4-step Process Overview, Validation & Exception Handling, and Reports. | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Queries or Business rules for the application | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | Completed | Cycle 1 (Jun-Aug 2026)
Asset Survey - Bulk Asset Upload | US-ASM-002 | Enhancement | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a Department Admin, I want to bulk-upload assets (instead of single entry only), so that large asset inventories can be onboarded quickly ahead of survey assignment. | Documented as part of Asset Creation scope in the Asset Survey User Manual (Section 6/1.2 Scope). | Complexity: Medium ¦ Work Type: Enhancement and customization ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)

## CTA Treasury-JD US
District GIS Parakh – Consolidated User Stories ¦ CTA – Treasury & JD Inspection ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Treasury Inspection Form | US-CTA-001 | CR / Change Request | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Treasury Officer under CTA, I want a Treasury Accounts inspection form implemented on Parakh, so that treasury account inspections/audits can be digitally recorded, submitted, and reported instead of paper-based inspection registers. | Form created; awaiting Change Requests (CRs) and confirmation from CTA Department (per PSR log, rows: 'CTA' and 'CTA - CRs Updates from Department'). | Complexity: Medium ¦ Work Type: Enhancement and customization ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
JD (Joint Director) Inspection Form | US-CTA-002 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Joint Director (JD) at CTA, I want a JD-level inspection form implemented on Parakh, so that JD-level treasury inspections are captured with the appropriate authority and reporting level distinct from the base Treasury Officer form. | Form created; pending CRs and confirmation from CTA Department. | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Pending Department Action | Cycle 1 (Jun-Aug 2026)
Checklist Form | US-CTA-003 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement

## Workflow Mgmt US
District GIS Parakh – Consolidated User Stories ¦ Workflow Management (ATR & Roster) ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Action Taken Report (ATR) Workflow | US-WFM-001 | Enhancement | Workflow & Approval Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As a Tribal Department reviewing officer, I want an Action Taken Report (ATR) workflow implemented within Parakh, so that follow-up/corrective actions raised against an inspection finding can be logged, assigned, and tracked through to closure instead of being tracked manually outside the system. | Item logged in Parakh Internal Work Enhancement log ('ATR Report for Tribal'). Requires: ATR entry against inspection record, action-owner assignment, status tracking (Open/In Progress/Closed), and closure report. | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Queries or Business rules for the application | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | In Progress | Cycle 1 (Jun-Aug 2026)
Roster of Nirikshan Karta (Inspector Roster/Assignment) | US-WFM-002 | CR / Change Request | Workflow & Approval Management | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | High | As an MP Cooperative Department Nodal Officer, I want a 'Rooster of Nirikshan Karta' (inspector roster/assignment list) feature added to the Nirikshan module, so that inspectors can be formally rostered and assigned to specific societies/units for inspection, with visibility into who is assigned where. | Referenced in PSR log under MP Cooperative (Changes): 'Revamping Inspection and including Rooster of Nirikshan karta.' Summary CR and BRD document shared with department (ICMIS - Devendra, Priya, Jyoti) for review. | Complexity: Medium ¦ Work Type: Enhancement and customization ¦ Component Category: Queries or Business rules for the application | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | In Progress | Cycle 1 (Jun-Aug 2026)

## Platform Enhance US
District GIS Parakh – Consolidated User Stories ¦ Platform Enhancement ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Blank Form Download (Offline Reference) | US-PLAT-001 | Enhancement | Mobile Offline Field Capture | Non-Functional Requirement | Non-Functional — a reliability/availability constraint (offline capability, sync integrity) the system must satisfy under poor-connectivity conditions. | Low | As a District Nodal Officer (e.g. Narsinghpur), I want to download a blank copy of any onboarded form as a PDF/template, so that I do not have to manually screenshot every page to share the form structure with field staff. | Feature requested by Narsinghpur; logged in Parakh Internal Work Enhancement log. | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Mobile App-UI | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | Proposed | Cycle 1 (Jun-Aug 2026)
Dynamic Reports - Phase 1 | US-PLAT-002 | Enhancement | Reporting & Analytics | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As a State Admin, I want inspection reports to be generated dynamically and linked with the dashboard, so that report structures automatically reflect form changes without manual report redevelopment. | Phase 1 marked 'Done' in Parakh Internal Work Enhancement log. | Complexity: High ¦ Work Type: Enhancement and customization ¦ Component Category: Reports | 4.5 | 3 | 7 | 7 | 5.5 | 3 | 2 | 2 | 2 | 36 | Completed | Cycle 1 (Jun-Aug 2026)
Report Sync for Department Forms | US-PLAT-003 | Enhancement | Data Sync & System Integration | Non-Functional Requirement | Non-Functional — a data-integrity/performance constraint ensuring records reconcile correctly between mobile, web, and the central server. | Medium | As a State Admin, I want a 'Sync Data' action available from the Tabular View of Inspection screen, so that the latest submitted inspection data is pulled into reports on demand. | Functionality documented: Login as State Admin -> Tabular View of Inspection -> Sync Data -> Data Synced. | Complexity: Medium ¦ Work Type: Enhancement and customization ¦ Component Category: No of API Integrations | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)

## Master Form Std US
District GIS Parakh – Consolidated User Stories ¦ State-Level Master Form Standardization ¦ 30-Jun to 18-Aug 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Category | Type of Use Case | Requirement Type | Requirement Type Description | Priority | User Story Description | Acceptance Criteria | Estimation (Complexity ¦ Work Type ¦ Component) | Req. Gathering (hrs) | Meetings - Dept/Internal (hrs) | Form Development (hrs) | Coding Development (hrs) | Testing (hrs) | Verifying (hrs) | Monitoring (hrs) | Deployment (hrs) | Training to Dept (hrs) | Total Activity Hours (hrs) | Status | Sprint
Aadhar Center Inspection Form - State-Level Adoption | US-MSTR-001 | Implementation | Form Data Entry / Inspection Capture | Functional Requirement | Functional — defines a specific system behaviour the application must perform (e.g., capturing inspection data, enforcing conditional logic, generating a report, or routing a workflow step). | Medium | As the State Parakh Admin, I want the Narmadapuram district's Aadhar Center Inspection form adopted as the common state-level template, so that all districts (including Betul) use one consistent Aadhar verification form instead of building district-specific versions. | Confirmed by Dheeraj (1-Jul-2026): 'Narmadapuram Aadhar form can be used at the state level.' Referenced in Betul PSR row as 'Aadhar form taken at the state level - Common form for all districts.' | Complexity: Medium ¦ Work Type: New Development ¦ Component Category: Web Page / Screen with no of input fields | 2 | 1.5 | 3.5 | 3.5 | 2.5 | 1.5 | 1 | 1 | 1.5 | 18 | Completed | Cycle 1 (Jun-Aug 2026)