## Sheet1
S. No | District | Initiative | Request Received on (Letter / Verbal) | Lettes | District Level SPOC | Current status | ajeet pal | Vertical | OIC | DeGM Name | DeGM Contact Number | Model
1 | Alirajpur | Hostel Survey (Parakh) | Letter | LetterFromCollector-Alirajpur.pdf | Virendra Singh Baghel (Joint Collector) | Golive | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Vineet Vishwkarma | 6260437738 | Hostel Survey (Parakh) General inspection form आवेदन फॉर्म
2 | Chhindwara | Wash on wheel (Parakh) | Letter | LetterToOnboardParakh-Chindwara.pdf | Agrim (CEO Jila Panchayat) | Golive | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Atul Kumar Sharma | 7898452023 | Wash on wheel (Parakh)
3 | Chhindwara | School Survey (Parakh) | Letter | LetterToOnboardParakh-Chindwara.pdf | Agrim (CEO Jila Panchayat) | Today's UAT verification will arrive | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Atul Kumar Sharma | 7898452023 | Request completion Form School servey Form
4 | Bhopal commissioner office | General Inspection on (Parakh) | Letter | Comm. bpl letter for Parakh login.pdf | Alok (Consultant) MPSEDC | Work Complete & submiited to Dept. for (UAT) | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | vinod yadav (additional commissioner) | 9407511101 | Site Inspection & servey form Hostel Servey Form
5 | Khargone | Inspection Mobile App on (Parakh) | Direction by MD / APD Sir | - | - | The current collector of Khargone has changed. The new collector will decide whether this project will proceed or not, and if it does, how the work will be carried forward. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Pramod Pawar | 8989854171
6 | Damoh | School & Hostel Survey (Parakha) | Letter | Parakh Letter Damoh.pdf | No Name in Letter | Go-live | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Mahesh Agrawal | 9893691611 | School & Hostel Survey (Parakha) School monitoring Form
7 | Burhanpur | Inspection Mobile App on (Parakh) | Letter | PARAKH Burhanpur.pdf | Bhavya Mittal (Collector) | Work In Progress | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
8 | Tikamgarh , Collectorate | Inspection Mobile App on (Parakh) | Letter | parakh portal letter tikamgarh.pdf | - | In Tikamgarh Collectorate, forms are being prepared but have already taken considerable time. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Pushpendra Tiwari | 7415360791 | Hostel Inspection Form
9 | Dindori , Collectorate | School Survey, Hostel, Anganbadi, PDS Center Extra Inspection App (Parakh) | Letter | Parakh App dindori.pdf | - | In Dindori, UAT is currently under testing. A reply will be provided once the testing is fully completed. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Deepak Sahu | 9179173987 | Weekly Inspection Form Aaganwadi survey form स्वास्थ्य संस्थाओ का निरीक्षण फॉर्म
10 | Vidisha | Hostel Survey (Parakh) | Direction by MD / APD Sir | विदिशा जिले में स्_कूलों के निरीक्षण संबंधी APP उपलब्_ध कराने बाबत् तथा तकनीकी सहयोग.pdf | - | Go-live | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | AMIT AGARWAL | 9893276222 | आकदमिक अवलोकन निरीक्षण फॉर्म
11 | Bhind | Hostel Survey (Parakh) | Letter | PARAKH Hostel Survey Bhind 15.01.2025.pdf | - | Go-live | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Saurabh Upadhyay | 9893310941 | छात्रावास निरीक्षण फॉर्म
12 | Chhatarpur Dist | Creation Google form , Login ID Password | Letter | Creation Google form for Chattarpur DIst login id 15 01 2025.pdf | - | they will preparing our form and sending it from the Tikamgarh department, but they have also requested Alirajgarh's Parhak credentials for review. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Tiwari | 9993551020 | Grocery Store Inspection General Inspection Hostel Inspection Form दुकानों के निरीक्षण की जानकारी फॉर्म
13 | Narwadapuram | Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म | Letter |  |  | The form has arrived, UAT has been sent, and testing has started. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Sandeep | 9425966696 | Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म
14 | rajgarh | छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey | Letter |  |  | The form has arrived, UAT has been sent, and testing has started. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal |  |  | छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey
15 | seoni | छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म | Letter |  |  |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Shivhare | 9302469983 | छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म
16 | Satna | Aadhar Inspection Form |  |  |  | Uat shared Changes requrired | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal |  |  | Aadhar Inspection Form
17 | Saps | LKS Inspection Form |  |  |  | Go-live |  |  |  | Rahul tiwari | 9893404034 | LKS Inspection Form
18 | Tribale department | जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र |  | Hostel Survey (Parakha) |  | Work complete UAT shared | [5 empty] | जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र

## Sheet2
Task | Resource | No. of Resources | Monthly Salary (in Lakhs) | Total Cost (3 Months)
Overall Project Execution & Monitoring | Project Manager | 1 | Internal (MPSeDC) | N/A
Project Documentation & Requirement Gathering | Business Analyst | 1 | Internal (MPSeDC) | N/A
Dynamic Form Creation & Frontend Design | Sr. GIS Executive | 1 | 1.2 | 3.6
| GIS Executive | 2 | 0.8 | 4.8
Database Management & Update | Data Expert | 1 | 1.5 | 4.5
| GIS Database Developer (DBD) | 1 | 2 | 6
Backend & Frontend Report Section Development | Sr. Mobile Developer | 1 | 1.8 | 5.4
| Portal & Mobile App Developer | 1 | 1.8 | 5.4
UI Design | UI/UX Designer | 1 | Internal (MPSeDC) | N/A
Testing | Tester | 1 | Internal (MPSeDC) | N/A
Total Resource Cost |  |  |  | 29.70 Lakhs