## Indore Inspection Module
DAR Form
Group Name | Indore Collectorate GIS Cell / District GIS Parakh Inspection Management System |  |  | Project Name |  | District GIS Parakh – Indore Division Inspection Module
Decision Seeker | Ajeet Pal Singh (Project Manager) |  |  | Evaluation Date |  | 2026-08-24
Problem Statement | Selection of the Assignment & Action-Tracking workflow model for routing Indore Division inspection findings from Inspector through Department HOD to Collector/Divisional Commissioner oversight, across 17 departments and 58 institution types.
Scope of DAR | Covers the Phase-1 design decision for how a submitted inspection record is routed and monitored — from Inspector submission through Department HOD action to Collector/Commissioner-level oversight — for the Indore Division Inspection Management System.
DAR Team Members | Indore Collectorate GIS Cell, MPSeDC Development Team
Alternatives |  |  | Source of Alternatives |  |  | Remarks
A1 – Manual routing of inspection findings by District Admin, with no automated workflow or status tracking |  |  | Derived from the pre-digitization practice of routing inspection reports manually between offices without a system of record. |  |  | Rejected — meets 'Works within Phase-1 timeline' and 'No new infra dependency' but fails the 'Auditable status trail' must-have criterion.
A2 – Auto-route to Department HOD on submission, with manual Collector-level SLA monitoring |  |  | Derived from Phase-1 build constraints (17-department rollout timeline) and requirements raised by the Indore Collectorate GIS Cell for a traceable, low-infrastructure routing workflow. |  |  | Selected — meets all three must-have criteria (Phase-1 timeline, no new infra dependency, auditable status trail). Implemented in Phase 1.
A3 – Fully automated SLA-based escalation and auto-closure of inspection findings |  |  | Derived from the Phase-2 target architecture and the User Story Register's SLA-based escalation-engine requirement. |  |  | Rejected for Phase 1 only, on timeline/infrastructure grounds (requires a new escalation-rules engine) — explicitly retained as the Phase-2 target.
Criteria for Evaluation |  | Weightage (1 = Least important and 5 = Most important) |  | Rationale for Criteria and Weightage Selection
Ease of Implementation |  | 7 |  | Weighted for Phase-1 feasibility, since the workflow must go live without a new engine build, given the 17-department rollout timeline.
Time to Deploy |  | 9 |  | Highest-weighted criterion — the 17-department rollout timeline is the binding constraint for Phase 1.
Governance/Audit Control |  | 8 |  | Weighted highly since an auditable status trail was itself a must-have criterion for Collector/Commissioner oversight.
Scalability to Other Districts |  | 9 |  | Weighted highest — the design must extend cleanly to the Divisional hierarchy (Phase 2) and to other districts beyond Indore.
Officer Workload Impact |  | 6 |  | Moderate weight — the added routing/monitoring load on Reporting Officers and Department HODs should stay manageable.
Cost |  | 5 |  | Lowest weight — cost is a secondary factor relative to timeline and audit-control needs for this workflow decision.
Criteria for Evaluation
| Score | Weighted Score | Score | Weighted Score | Score | Weighted Score
4
4
4
5
4
5
Average Weighted Score
Score Range (1 - 5) : ( 1 = Minimum rating and 5 = Maximum rating)
Alternatives |  |  | Order (1 = Highest, 4 = Lowest) |  |  | Result
Solution Decision (Decision Authority) |  | Auto-route to Department HOD on submission, with manual Collector-level SLA monitoring (Alternative A2), is selected as the preferred Assignment & Action-Tracking workflow for Phase 1 of the Indore Division Inspection Management System. On submission, the record auto-routes to the mapped Department HOD and is made read-only to Collector/Commissioner; the Collector's dashboard gives a manual SLA-monitoring view.
Risk anticipated |  | Manual SLA monitoring by the Collector could miss slow-responding departments at scale (Impact 5/10, Probability 4/10, Risk Factor 20) as the number of departments and inspection volume grows.
Assumptions |  | Phase 1 must go live without waiting for a new escalation-rules engine, given the 17-department rollout timeline. The manual-routing alternative was rejected primarily on audit-control grounds: it does not guarantee a record reaches the correct Department HOD without human error. The fully-automated alternative was rejected for Phase 1 only due to timeline/infrastructure constraints, not on merit — it is explicitly retained as the Phase 2 target (per the User Story Register's SLA-based escalation requirement).
Remarks |  | This DAR documents the Assignment & Action-Tracking workflow decision for the Indore Division Inspection Management System (17 departments / 58 institution types). The selected Phase-1 design balances auditability and rollout speed; full SLA-based automation remains the Phase-2 target once the escalation-rules engine is built.
Decision Authority |  | Office of the Divisional Commissioner, Indore, in consultation with MPSeDC — authorized to approve the selected Assignment & Action-Tracking workflow design for the Indore Division Inspection Management System. |  |  |  | Date | 2026-08-24