## PM Poshan Module
DAR Form
Group Name | PM Poshan State Coordination Team / Mandla District GIS Cell |  |  | Project Name |  | District GIS Parakh – PM Poshan Social Audit Module
Decision Seeker | Ankita Soni (GIS Executive) |  |  | Evaluation Date |  | 2026-08-24
Problem Statement | Selection of field-design approach for the PM Poshan (Mid-Day Meal) Social Audit inspection form — independent bespoke form vs. alignment with the existing MGNREGA inspection form fields.
Scope of DAR | Covers the field-level design decision for the PM Poshan Social Audit form on District GIS Parakh, specifically whether/where to align its fields with the existing MGNREGA inspection form; does not cover a full form merger between the two modules.
DAR Team Members | PM Poshan State Coordination Team, Mandla District GIS Cell
Alternatives |  |  | Source of Alternatives |  |  | Remarks
A1 – Fully independent bespoke PM Poshan form (no reference to MGNREGA fields) |  |  | Derived from the PM Poshan-specific data requirements (meal quality, beneficiary count, stock register) that have no direct equivalent in the MGNREGA form. |  |  | Valid but not selected — meets both must-have criteria but scores lower overall (Total 136 vs 167) on department acceptance and consistency with existing reports.
A2 – Fully reuse the MGNREGA inspection form as-is for PM Poshan |  |  | Derived from the initial instinct to avoid building a new form when one already exists on Parakh. |  |  | Rejected — fails the must-have criterion of capturing PM Poshan-specific data (meal quality, beneficiary count, stock register).
A3 – PM Poshan form with select overlapping fields aligned to MGNREGA format (e.g. built-area/sq. ft. convention), rest bespoke |  |  | Derived from the specific request from Mandla district (1-Jul-2026, PSR Log) that the kitchen-shed/built-area question be aligned with the MGNREGA form's existing wording and units. |  |  | Selected — meets both must-have criteria and scores highest overall (Total 167). Implemented.
Criteria for Evaluation |  | Weightage (1 = Least important and 5 = Most important) |  | Rationale for Criteria and Weightage Selection
Consistency with Existing Reports |  | 7 |  | Weighted to keep cross-module reporting comparable where fields genuinely overlap with MGNREGA.
Department Acceptance |  | 8 |  | Weighted highly — the alignment was specifically requested by Mandla district, so department buy-in matters.
Development Effort |  | 5 |  | Lower weight — this is a field-level alignment, not a full rebuild, so development effort is a secondary factor.
Data Comparability |  | 7 |  | Weighted to support comparing overlapping metrics (e.g. built-area) across modules where relevant.
Flexibility for PM-Poshan-Specific Needs |  | 8 |  | Weighted highly — the form must still fully capture PM Poshan-specific data not present in MGNREGA.
Risk of Confusion |  | 6 |  | Moderate weight — partial alignment must not blur the distinction between PM Poshan and MGNREGA as separate modules.
Criteria for Evaluation
| Score | Weighted Score | Score | Weighted Score | Score | Weighted Score
| 2 |  |  |  | 4
| 3 |  |  |  | 5
| 4 |  |  |  | 3
| 2 |  |  |  | 4
| 5 |  |  |  | 4
| 4 |  |  |  | 4
Average Weighted Score
Score Range (1 - 5) : ( 1 = Minimum rating and 5 = Maximum rating)
Alternatives |  |  | Order (1 = Highest, 4 = Lowest) |  |  | Result
Solution Decision (Decision Authority) |  | PM Poshan form with select overlapping fields aligned to MGNREGA format (e.g. the built-area/sq. ft. convention), with the rest of the form remaining bespoke (Alternative A3), is selected. Following the request from Mandla district (1-Jul-2026, PSR Log), the kitchen-shed/built-area question was updated to match MGNREGA's existing wording and units rather than left as an independently-worded field.
Risk anticipated |  | Partial field alignment with MGNREGA could create confusion between the two modules if not clearly labelled; PM Poshan Social Audit remains a distinct form/module from MGNREGA on Parakh.
Assumptions |  | This DAR documents a field-level alignment decision, not a full form merger — PM Poshan Social Audit remains a distinct form/module from MGNREGA on Parakh. The 'fully reuse MGNREGA form' alternative was rejected as it does not capture PM Poshan-specific data (meal quality, beneficiary counts, stock register) and therefore fails a must-have criterion outright. This alignment specifically resolves the correction Mandla requested to the built-area question; no other MGNREGA fields were assessed for alignment at this time.
Remarks |  | The PM Poshan Social Audit form retains its independent identity while aligning one overlapping field (built-area/sq. ft. convention) with the existing MGNREGA form, following a specific district request. This balances department familiarity/acceptance against the need to capture PM Poshan-specific meal-quality and stock data.
Decision Authority |  | PM Poshan State Coordination Team, in consultation with the Mandla District GIS Cell — authorized to approve the field-alignment decision for the PM Poshan Social Audit module. |  |  |  | Date | 2026-08-24