MADHYA PRADESH STATE ELECTRONICS DEVELOPMENT CORPORATION (MPSEDC)

MPSSDI — GIS Division

MINUTES OF MEETING

District GIS Parakh — Monthly Project Review

Reporting Period: 01-Aug-2026 to 27-Aug-2026

Meeting Details

| Project | Parakh (District GIS) — MPSEDC / MPSSDI |
| --- | --- |
| Meeting Type | Monthly Project Status Review (MoM) |
| Period Covered | August 2026 (01-Aug-2026 to 27-Aug-2026) |
| Chaired By | K.V.S. Choudary (Managing Director, MPSEDC) |
| Also Present | Dr. Rakesh Dubey (GIS Head), Tapan Khandelwal (Senior PM), Kapil Sir |
| Minutes Prepared By | Dheeraj Motiyani, Senior Business Analyst — MPSSDI/GIS |
| Data Source | Date-Wise Team Time Sheet (01-Jul-2026 to 27-Aug-2026), District PSR Tracker, and August 2026 department correspondence |

## Attendees — Parakh Development & BA Team

- Dheeraj Motiyani — Senior Business Analyst

- Madhur Nema — Backend Developer

- Bharat Mishra — Full-Stack Developer

- Manisha Dadhore — QA / Form Configuration

- Aman Mishra — Backend Developer

- Jameel Khan — Mobile Developer

- Neetu Malviya — QA / Documentation

- Krati Pandey — ML/OCR Developer

- Nilesh Gangrade — UI/UX Developer

- Rini Kanik — QA (UAT)

# 1. Executive Summary

During August 2026, the Parakh team logged a total of 520.5 consumed hours across 84 tracked activities, spanning platform-level enhancements and district/department onboarding. Work continued in parallel on the Indore Collectorate 17-form inspection rollout (Phase 1 & 2), the Damoh Collectorate 12-form CM Jan Vishwas Abhiyaan rollout, the Betul 6-form programme nearing closure, and new onboarding requests from Chhindwara, Bhind, Guna, Rajgarh, MP Metro, and CTA (Directorate of Treasury & Accounts).

| Metric | August 2026 |
| --- | --- |
| Total consumed hours (all resources) | 520.5 hrs |
| Total tracked activities/tasks | 84 |
| Districts / Departments actively worked on | 13 (Indore, Damoh, Betul, Bhind, Guna, Chhindwara, Rajgarh, MP Metro, MPRRDA, CTA, Agar Malwa, MP Cooperative, Parakh Core) |
| New onboarding letters received in August | 4 (Chhindwara ×2, Bhind, Guna follow-up) |
| User manuals / BRDs delivered | Indore Inspection Manual (Ph.1 & 2), Consolidated Parakh Manual (updated), CMMI BRDs (generic + enhancement-specific) |

## 1.1 Effort Distribution by Resource

| Resource | Consumed Hrs (Aug) | Primary Focus Area |
| --- | --- | --- |
| Manisha Dadhore | 120.0 | Damoh, Indore, Rajgarh form config & QA |
| Madhur Nema | 112.0 | Indore workflow, MPRRDA, 2FA, Bhind, ATR |
| Bharat Mishra | 104.0 | Indore reports, Parakh Enhancement, CAPTCHA/2FA APIs |
| Dheeraj Motiyani | 57.0 | Requirement gathering (Indore, Damoh, Betul, Guna), manuals, BRDs |
| Aman Mishra | 48.0 | Indore divisional/district officer role customisation |
| Neetu Malviya | 40.0 | PM Poshan workflow validation, MP Metro, Bhind testing |
| Jameel Khan | 32.0 | MPRRDA offline SQLite road-geometry module |
| Krati Pandey | 7.5 | Agar Malwa — vehicle detection / OCR (TFLite) |

## 1.2 Effort Distribution by Module / District

| Module / District | Consumed Hrs | Status |
| --- | --- | --- |
| Parakh Enhancement (platform core) | 234.0 | Ongoing |
| Indore Collectorate (incl. Labour & Property) | 125.0 | WIP — Phase 2 |
| Damoh Collectorate | 46.0 | WIP — 12 forms finalised |
| Bhind Collectorate Office | 24.0 | Completed → Production |
| MP Metro / PM Poshan | 32.0 | WIP |
| Betul Collectorate | 13.0 | Near closure |
| Rajgarh Collectorate | 10.0 | UAT → Production |
| Indore - Labour Inspection | 8.0 | Live / stabilisation |
| Agar Malwa | 7.5 | WIP — vehicle detection |
| MPRRDA | 7.0 | UAT |
| CMMI Documentation | 5.0 | WIP |
| MP Cooperative | 5.0 | BRD shared, awaiting dept. review |
| Chhindwara Collectorate | 2.0 | Live; reports in progress |
| Guna Collectorate | 2.0 | Requirement stage |

# 2. Agenda Item 1 — Parakh Core Platform Enhancements

MD Sir reviewed the platform-hardening and feature work delivered under the 'Parakh Enhancement' track (234 consumed hours in August), which underpins all district rollouts. Key items closed during the month:

- Two-Factor Authentication (2FA) / OTP

Database logic, OTP generation & verification APIs, mandatory mobile-number verification component, and 2FA integration document completed (Bharat Mishra, Madhur Nema) — 12 to 21-Aug.

- Network-Layer Encryption (JWT)

Encryption methodology upgraded to JWT-based token validation at API and web level; deployed to a separate test site for verification (Madhur Nema) — 24 to 27-Jul carried into Aug sign-off.

- Inspection Action Taken Report (ATR)

Database design, table structure and query for department-wise custom status/action-history; 3 inspection-flow APIs created; code-reviewed and deployed to UAT (Madhur Nema) — 11 to 18-Aug.

- Dynamic Report Header Mapping

Header mapping for non-conditional question hierarchy with drag-and-drop reordering support (Bharat Mishra) — 03-Aug.

- CAPTCHA on Web Login

CAPTCHA generation & validation APIs implemented and integrated on the web login page (Bharat Mishra) — 12–13-Aug.

- Hierarchy-Based Verification & Action History

Survey-list verification enhanced to show prior actions across hierarchy levels with a dynamic action-master dropdown (Bharat Mishra) — 14–17-Aug.

- MPRRDA Offline Road Module

District-wise offline road-geometry download, SQLite storage, radius-based filtering, and offline map rendering completed (Jameel Khan) — 03–19-Aug.

- User Table Restructuring

User table updated to capture Govt. Department / Sub-Department; Insert/Update/Get user APIs and queries revised for the new Divisional hierarchy (Madhur Nema, Aman Mishra) — 03–14-Aug.

# 3. Agenda Item 2 — District / Department Onboarding Status

## 3.1 Indore Collectorate — 17-Form Inspection Programme

Requirement finalisation for all 17 Indore department forms continued through August in joint sessions with the Collectorate. Phase 1 (form + report build) is functionally complete; Phase 2 (Divisional-level hierarchy, Action-Taken visibility for Divisional Officers) is under active development.

- 04–20-Aug: Requirement gathering & finalisation meetings with Indore Collectorate team (Dheeraj Motiyani).

- 06–14-Aug: Divisional/District Officer role, department mapping, and modified report queries (General, Dynamic, Data Collection) delivered for the new hierarchy (Aman Mishra).

- 10-Aug: Women & Child Development department report created (Bharat Mishra).

- 10-Aug: Inspection workflow APIs & queries for Department HOD visibility (Madhur Nema).

- 12–24-Aug: User Manual for Phase 1 & Phase 2 (17 forms) drafted and shared; district asked to review on 24-Aug (Dheeraj Motiyani).

- 17-Aug: Division and District module tested end-to-end on UAT (Manisha Dadhore).

Note: PSR tracker shows Indore as the largest active item this month (89 in tracker) — Department is finalising the remaining forms; mail sent on 24-Aug asking them to confirm the user manual before Phase 2 go-live.

## 3.2 Damoh Collectorate — 12 Inspection Forms (CM Jan Vishwas Abhiyaan)

Requirement gathering for all 12 Damoh inspection forms was completed and finalised in August, covering: Zila Panchayat (BBRAMJI/PMAY/15th Finance), Gram Nal Jal Praday Yojana, School/Institute, Anganwadi, Jan Vishwas Abhiyaan (Health), Govt. Fair-Price Shop, Petrol Pump, LPG Dealer, Farm & Dairy, Liquor Department, Hostel/Ashram, and Krishi Sakh Sahakari Samiti Inspection forms.

- 11–25-Aug: Requirement gathering, team & departmental meetings for master data across all 12 forms (Dheeraj Motiyani).

- 12–13-Aug: All Damoh Collectorate forms created on UAT (Manisha Dadhore).

- 14-Aug: Damoh forms finalised; Division-module users created and tested (Manisha Dadhore).

- 18–21-Aug: Jan Vishwas Abhiyaan forms created and corrected on UAT; remaining forms completed (Manisha Dadhore).

- 23-Aug: All 12 forms finalised — department sharing master data and bulk asset upload in progress (Dheeraj Motiyani / PSR).

## 3.3 Betul Collectorate — 6-Form Programme

The Betul programme (KGBV, PM Poshan/PNRD, WCD Anganwadi, School Monitoring, Health, Mining, Aadhaar Centre, Tribal Hostel) is in its closing stage.

- 03-Aug: Change requests from July incorporated; issues in form submission resolved (Dheeraj Motiyani).

- 11-Aug: Three additional reports developed for the Betul department (Bharat Mishra).

- 13-Aug: Deployment fixes — Mining form Gram Panchayat visibility issue and related question changes resolved (Dheeraj Motiyani).

Note: Per the PSR tracker, pending items are: WCD form update, Mining form update, Aadhaar Centre form confirmation, and Tribal Department login credentials for Betul — all with the development team / department as of month-end.

## 3.4 Bhind Collectorate Office — Patient Feedback Form (OPD/IPD)

The Chief Medical & Health Officer, Bhind, formally requested (letter dated 13-Aug-2026) that Patients Satisfaction Survey & Satisfaction Index forms for OPD and IPD be added to the District GIS Parakh Portal with QR-code based access so patients can submit feedback directly from their mobile phones.

- 17-Aug: Form copied from the Guna format and Bhind-specific questions added; QR-code based access built (PSR).

- 19-Aug: Database table, insert and get queries created for the Patient Feedback form (Madhur Nema).

- 20-Aug: Patient Feedback UI and MIS report built (Madhur Nema).

- 21-Aug: Functional testing of the Patient Feedback form and web report completed — data sync, rating display and report generation validated (Neetu Malviya).

Note: Department has confirmed the form for move to Production (per PSR). Both OPD and IPD questionnaires (10 parameters each — signage, staff behaviour, cleanliness, diagnostics availability, medicine availability, and open feedback) are covered as per the attached CMHO letter.

## 3.5 Guna Collectorate — Ayush Health Inspection & Asset Mapping

Requirement understanding for the Guna Ayush Health Inspection form was completed on 10-Aug (Dheeraj Motiyani) — master data and formatting of the Ayush Vibhag (Ayurved/Homeopathy) inspection form finalised, drawing on the District Ayush Officer, Chhindwara letter format as a reference template for common Ayush inspection fields (staff presence, OPD/IPD data, medicine availability, camps conducted, physical verification).

- Guna Anganwadi inspection form: changes completed, awaiting UAT confirmation from the District Collectorate & GIS Executive (PSR).

- Guna & Gwalior Patient Feedback form: HTML form and QR code already completed in an earlier cycle and referenced as the base template for Bhind (Section 3.4).

## 3.6 Chhindwara Collectorate — New Requests (August)

Chhindwara's earlier 5-form programme (Anganwadi, PM Poshan, Godown, Hostel Monitoring, Health) remains live in Production with report-building in progress. Two fresh requests were received from the district in August under the Mukhyamantri Jan Vishwas Abhiyaan-2026:

- Letter dated 19-Aug-2026 from the District Supply Officer, Chhindwara — requesting two new inspection forms on Parakh Portal: (1) Gas Godam Jaanch/Nirikshan Prapatra (LPG godown inspection) and (2) Shaskiya Uchit Mulya Dukan Nirikshan Prapatra (Fair Price Shop / PDS inspection). Draft prapatra formats (प्रारूप) were enclosed with the letter, covering inspection date/time, inspecting officer details, agency/shop details, price & stock display board verification, stock register vs. physical stock reconciliation, explosive licence validity, registered consumer counts, refill supply status, and complaint/grievance register status.

- Forwarded by the District Ayush Officer, Chhindwara — request to formalise the Chikitsalaya/Ayush Wing/Aushdhalaya Nirikshan Prativedan (Hospital/Ayush Wing/Pharmacy Inspection Report) on Parakh, referencing the office letter from the Collector (Supply Branch), Chhindwara dated 19-Aug-2026. Covers staff attendance, facility status, OPD/IPD statistics, camps conducted, medicine availability, and physical verification of records over the preceding 3 months.

Note: Both Chhindwara forms are new intake for September build; BA team to complete master-data mapping and share a draft on Parakh UAT for department sign-off.

## 3.7 Rajgarh Collectorate — OBC Hostel Inspection Form

- 17-Aug: OBC Hostel Inspection Form created and tested on UAT (Manisha Dadhore).

- 17-Aug: Division and District module tested on UAT for Indore/Rajgarh rollout support (Manisha Dadhore).

- 18-Aug: Rajgarh OBC Hostel Inspection report created (Madhur Nema).

Note: Form is in UAT awaiting department confirmation before move to Production (PSR item 90).

## 3.8 MP Metro — Plantation Monitoring Form

A two-part Plantation form (Project Entry + Survival Survey) was built for MP Metro, covering City/Location/Agency masters, work name, species-wise plant counts planted vs. survived, and geo-tagged photo capture.

- 17–19-Aug: MP Metro Department and Form created and tested (Neetu Malviya).

- 13–24-Aug: Department to conduct first-time field survey to collect baseline data and onboard; demo held on 24-Aug with department feedback for further changes (Team: Madhur, Manisha, Neetu / PSR).

## 3.9 CTA — Directorate of Treasury & Accounts (JD & Treasury Inspection)

The JD Inspection (26-section questionnaire) and District Treasury Office Inspection (88-point, 10-branch questionnaire) forms, documented in the JD & Treasury Inspection BRD/User Manual, remain WIP with the CTA department for change-request sign-off.

- 13-Aug: Form updates incorporated per CTA department's change requests (Manisha Dadhore).

Note: Pending item: CTA department to confirm the updated JD/Treasury forms before Production release.

## 3.10 Other Districts — Requests Pending Department Input

- Dhar (shared via Indore Nidhi office): Jan Vishwas Abhiyaan forms similar to Damoh requested on 17-Aug; unformatted Word documents received — department to share a structured format before form-build can begin.

- Sagar: Jan Vishwas Abhiyaan forms and Action Taken Report (ATR) on Committee recommendations, on the same lines as Damoh, requested on 24-Aug; forms not yet shared by the department.

- Agar Malwa: Vehicle-detection/number-plate OCR module — TFLite model integration and PaddleOCR-based recognition completed and shared with the department for field testing (Krati Pandey, 03–06-Aug).

- MP Cooperative: BRD and change-summary document for the revised Nirikshan (Inspection) form shared with the department (ICMIS — Devendra, Priya, Jyoti) for review of CRs and structure/roster changes.

# 4. Agenda Item 3 — Documentation & Compliance Deliverables

| Deliverable | Status / Notes |
| --- | --- |
| Indore Inspection User Manual (Phase 1 & 2, 17 forms) | Drafted and shared with Indore Collectorate on 12-Aug; updated 24-Aug after Phase 2 (Divisional login/view) inputs. Department asked to review manuals (mail sent 24-Aug). |
| District GIS Parakh Consolidated Bilingual User Manual | Updated through V2.4 during the month with Data Collection form guidance (Narmadapuram example), header/footer corrections, and enhancement notes. |
| CMMI Documentation — BRDs (generic + enhancement-specific) | Generic and feature-specific BRDs updated to reflect August enhancements (2FA, ATR, hierarchy changes) — 18–24-Aug (Dheeraj Motiyani). |
| JD & Treasury Inspection BRD / User Manual | Form corrections completed; CTA department confirmation pending. |
| Asset Survey User Manual (EN/HI) | V1.3 in circulation, referenced for Asset Creation → Assignment → Survey workflow used across Guna, Bhind and Damoh asset-based forms. |

# 5. Decisions Taken

- Indore Phase 2 (Divisional hierarchy & Action Taken visibility) to proceed in parallel with Phase 1 stabilisation; department to confirm the 17-form user manual before go-live.

- Bhind Patient Feedback (OPD/IPD) form approved for Production release following successful UAT sign-off.

- Damoh's 12 forms are functionally finalised; department to complete bulk asset upload before forms are opened to field Inspectors.

- Chhindwara's two new Jan Vishwas Abhiyaan requests (Gas Godam, Fair Price Shop) and the Ayush inspection report to be picked up as the next build priority for the district.

- Dhar and Sagar to be onboarded only after they submit structured (Word/Excel) inspection formats — team not to build against unformatted content.

- 2FA/OTP and JWT-based encryption to be treated as mandatory platform baseline going forward and rolled into the CMMI BRD set.

# 6. Action Items

| Action Item | Owner | District / Module | Target Date |
| --- | --- | --- | --- |
| Share Indore 17-form user manual for department sign-off | Dheeraj Motiyani | Indore Collectorate | 05-Sep-2026 |
| Complete Phase 2 Divisional hierarchy & ATR visibility | Madhur Nema / Aman Mishra | Parakh Enhancement | 10-Sep-2026 |
| Move Bhind Patient Feedback form to Production | Madhur Nema | Bhind Collectorate | 01-Sep-2026 |
| Follow up on Damoh bulk asset upload from department | Dheeraj Motiyani | Damoh Collectorate | 05-Sep-2026 |
| Build Chhindwara Gas Godam & Fair Price Shop inspection forms on UAT | Manisha Dadhore | Chhindwara Collectorate | 10-Sep-2026 |
| Formalise Chhindwara Ayush (Hospital/Pharmacy) inspection report on Parakh | Manisha Dadhore / Dheeraj Motiyani | Chhindwara — Ayush Dept. | 12-Sep-2026 |
| Obtain structured inspection formats from Dhar and Sagar before form-build | Dheeraj Motiyani | Dhar / Sagar | Ongoing |
| Confirm CTA JD/Treasury form changes and move to Production | Manisha Dadhore | CTA — Treasury & Accounts | 08-Sep-2026 |
| Complete Guna Anganwadi UAT confirmation with District Collectorate | Dheeraj Motiyani | Guna Collectorate | 05-Sep-2026 |
| Field baseline survey and onboarding for MP Metro Plantation form | Department / Neetu Malviya | MP Metro | 15-Sep-2026 |
| Update Consolidated Parakh User Manual with September enhancements | Dheeraj Motiyani | Documentation | Ongoing |

# 7. Next Review

The next monthly project review (MoM — September 2026) is scheduled for the last week of September 2026, chaired by MD Sir, covering progress on all action items above.

— Minutes circulated for record; please share corrections within 2 working days —