## Sheet1
Action Point | Metric/Category | Phase | Action/Task | Description | Improvements | Expected Outcome | Implementation Date | Accountability | Responsibility | Status | Remarks / Notes | Process, Procedure, Implementation Plan
1 | Code Rate | Development | Enforce Coding Standards with SonarQube Quality Gates | 1. Define standardized coding guidelines. 2. Configure SonarQube quality gates and thresholds. 3. Make quality checks mandatory before code merge. 4. Allocate dedicated time to refactor high-complexity code. 5. Monitor technical debt metrics regularly. | Reduces rework and technical debt by 15–25% | Improved developer efficiency and faster future enhancements. | 4th Week Jan'26 | PM | TL, Developers | Complete | Especially important for billing module due to complex scenarios. | Integrate SonarQube into CI/CD pipeline. Block merges failing quality gates. Maintain technical debt register and review in sprint retrospectives.

## Sheet2
Phase | Action | Description | Steps Taken Improvement | Detail Impact | Category | Implementation Date | Responsibility | Complexity | % Improvement | Expected Outcome | Status | Remarks / Notes
| Focus testing on risk-prone areas | Regression testing on all impacted modules of the project | Decrease External defects | Component Dependency testing | DRE | Next Phase (15 december) |  | High | 1-2% | Minimized critical defects in production. | Planned