## Status 03rd&25th Aug
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | Sahbhagita | 1. At Approval time, Pagination done on Sahbhagita pages | Done
|  | 2. RA bill given to ISA (instead of CP Manager) | Done
|  | 3. FE specific to particular ISA are visible to them | Done
|  | 4. Password reset option given to ISA | Done
|  | 5. Village/Combined Wise drop down provided | Done
|  | 6. Edit option given ISA and can create activity | Done (Close by 25th Aug)
2 | Cube Testing | 1. Cube ID get generated before image upload | Done
|  | 2. Show rejected data to Contractor | Done
|  | 3. Re_inspection Loop working | Done
3 | Material Testing | 1. Re_inspection Loop working | Done
3 | SVS Water Supply Monitoring PHE | 1. Removed JJM Id, Village status fields | Done
|  | 2. According to login specific District, Block and GP should appear | Done
|  | 3. Daily Water Supply Completed - In No option added one more Reason and correct spelling | Done
|  | 4. Bilingual conversion for SVS Daily Water supply Page (Hindi English) and Report Column Header ( in Hindi) | Done
|  | 5. SVS Water Supply Dashboard Completed | Done
|  | 6. SVS Nirmal created and deployed to UAT | UAT Done
4 | Parinam | 1. FE name shown in reports | Done
|  | 2. FHTC Samgra Id - more than one survey on same ID | UAT Done
|  | 3. Dashboard shown to FE and updated in Mobile APK ( under approval from playstore) | Done
5 | Sopan | 1. Add Calendar functionality for Calendar year 2026-27 (on Contractor Login) | Done
6 | Mobile APK | 1. UI issues resolved login logout issues | Done
|  | 2. Bug Fixes in mobile apk and released new apk | Done
[2:43 PM, 8/21/2026] Tapan Sir Jal Rekha MPSeDC: Dera Team,The below Mobile App UI/functional issues have been fixed and are now live in Production:
1 .Logout navigation issue during ongoing survey/inspection has been fixed.
2. Material Testing module is now displayed directly on the Home Screen instead of under Anushravan.
3 .Duplicate Profile icon issue has been fixed; only one Profile icon is now displayed.
4. .Duplicate Logout buttons issue under Anushravan in FE Login has been fixed.
5 .Duplicate Logout buttons issue on the Dashboard in Contractor Login has been fixed.
[2:44 PM, 8/21/2026] Tapan Sir Jal Rekha MPSeDC: *New Functionality in FHTC -Parinam Module*Dear Team
A new tab named “Parinam Dashboard” shall be added to the HSC Survey screen. This tab will allow the Field Engineer (FE) to view survey summary data based on selected filters and display the result in a tabular report format.
[2:44 PM, 8/21/2026] Tapan Sir Jal Rekha MPSeDC: The APK update is available on the Play Store, we will inform you accordingly.
Dear Team,
A new Addition/Deduction feature has been added to the O&M Bill in the Aakalan module.
TL (SQC) and GM (PIU) can now adjust the Net Payable amount with a reason,
if required.
Only the officer who is currently reviewing the bill can make the change.
All changes will be tracked and will reflect in the Consolidated Abstract.

## Status 21st July
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | Sahbhagita | 1. At Approval time, Pagination done on Sahbhagita pages | Done
|  | 2. RA bill given to ISA (instead of CP Manager) | Done
|  | 3. FE specific to particular ISA are visible to them | Done
|  | 4. Password reset option given to ISA | Done
|  | 5. Village/Combined Wise drop down provided | Done
2 | Cube Testing | 1. Cube ID get generated before image upload | Done
|  | 2. Show rejected data to Contractor | Done
|  | 3. Re_inspection Loop working | Done
3 | Material Testing | 1. Re_inspection Loop working | In Progress
3 | SVS Water Supply Monitoring PHE | 1. Removed JJM Id, Village status fields | Done
|  | 2. According to login specific District, Block and GP should appear | Done
|  | 3. Daily Water Supply Completed - In No option added one more Reason and correct spelling | Done
|  | 4. Bilingual conversion for SVS Daily Water supply Page (Hindi English) and Report Column Header ( in Hindi) | Done
4 | Parinam | 1. FE name shown in reports | Done
|  | 2. FHTC Samgra Id - more than one survey on same ID | UAT Done
5 | Vistrit / Dhara | 1. Approved Report Data corrected as discussed with Kapil | Done
6 | Sopan | 1. Add Calendar functionality for Calendar year 2026-27 (on Contractor Login)

## Status All Module09th&16th June
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
| Anushravan/Cube/Material | 1. Remove Mandatory in Intake, WTP, MBR, RWPM, & CWPM in dropdown Village and GP | Done
|  | 2. Give Save as Draft functionality & Provide option to upload photo later on | Done
|  | 3. OHT Search option during RFI | Done
| Anusharavan | 1. Include multiple date in report - FE RFI Submission date & Block name also added | Done
| Asset Mapping | 1. SQC TPIA Contractor Data and Report on Web | Done
| Bharosa | 1. Factory Testing WEB - Add QAP 3rd Party & upload multiple images | Done
| Cube | 1. Structure components to be added against each Component | Done
|  | 2. Date of costing for RFI loop 7th and 28th day added | Done
|  | 3. Add Filter Bed as Sub Component under WTP Component | Done
| Cube Module Mobile CR | Add Mandatory multiple image upload functionality to the FE inspection form and Save as Draft | Done
| Dhara | New Dhara Report to be shown on all Jal Rekha logins | Done
|  | GM Approved Reports & Contractors Dispute | Done
| Sahbhagita | RA Bill Functionality to be added for Sahbhagita Activity on ISA Manager after approve activity and Edit option. | Done
| Sahbhagita Mobile CR | Add Save as draft functionality for video, images and documents | Done
| Vistrit | WTP Meter Mapping - New Column Addtion Date, Scheme & PIU | Done
|  | WTP Meter Name update naming convention - Example Narela-WTP-01 | Done
|  | WTP Meter Mapping, Intake Mapping - New Column addition such as Meter name, No of OHT connections with WTP, District, Block & GP for Intake | Done
|  | In Scheme Village mapping - Validation applied on Testing and Permitted fields and leave Census Population open at all level | Done
| Vistrit & Dhara | All Reports Visible in Contractor login (Vistrit Data Non Editable) | Done
| Vistrit | OHT Issue - For Some OHTs of some Schemes were not visible but visible at FE's Id. Because of Deactivate entries of OHT in Vistrit. Now it is resolved | Done
| Public Report DWSR | Open to Public | Done
| All Web Reports | Enabled Material, Cube & Bharosa Reports on Jal Rekha web user id - CGM,PMU | Done
| UI/UX | Change Module sequence on portal | Done
| Parinam | Contractor Search Option | Done
| PHE _Dhara GP Reading | GP wise Village Reading | Done

## O&M August26
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status

## O&M
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | O&M Billing - Dhara Reports | Dhara report integration in O&M Billing module | Done
2 | GM Side Login | Census population addition in Scheme Master (GM side report) | Done
3 | O&M Billing - Bill | Bill generation for total 64 Schemes
4 | Contractor Side login | Check final summary report | Some Changes Required
5 | Master | scheme village master.. scheme piu village DONE | Done
6 | Master | OHT village master | Done
7 | Bulk Consumer | Scheme bulk consumer | Done
8 | Bulk Consumer Mapping | Bulk consumer mapping - oht wtp | Done
9 | Mapped Report Status | Of all above 4 reports Mapped in Mapped status report . summary report - vidhan sabha district wise | Done
10 | DWSR Reports | DWSR report development (basic) | Done
11 | Data Validation | Duplicate Village Mapping validation across schemes | Done
12 | Open Platform | Restrict reports: Show only Dhara & DWSR | Done
13 | Open Platform | DWSR column clickable (Hyperlink integration) | Done
14 | Report Optimization | Remove extra reports (Date-wise DWSR, MWSR, UFW, Scheme-wise WSR, Village-wise MWSR, Bulk User MWSR) | Done
15 | PowerConsumption | Need To Change Contractor and GM Side (Contractor - Generate Bill - Add into Contract Details ( Basic Detail, Intermediate Raw Water Demand, and | In Progress
16 | Scheme Status | Need Two More Column Add in Water Supply During Construction Bill | In Progress
17 | GM Approval | Only final approval by GM ( No Provisional approval required) and Concern Remark Mandatory | Done
18 | O&M Villages | Villages where water Supply during construction is under consideration or approved | In Progress
19 | Aakalan | Dhara Report complete and release to O&M billing | Done
20 | Aaklan Contractor / Dhara | Contractor to check & Raise any discrepancies within time. Dhara data will be used for billing purposes | In Progress
21 | Additional Aaklan Updates | GM side if Pump Transformer column has YES then consolidate bill will have 10% deduction in total amount | In Progress