## Form responses
Timestamp | Scheme Name | Module | User Name | Mobile Number | Belong To | Describe Your Issue | Upload Screenshot
2026-07-20 13:30 | Test Scheme | Dhara | Awinash | 9876543210 | SQC | Testing Issue | https://drive.google.com/open?id=1NR2LQSfRuTzqcondSxSdFcBHR1_kWaTv
2026-07-20 15:07 | Arniya bahadur mvs | Dhara | Devesh kumar singh | 9873091799 | SQC | to be meter Reading correction. Please UNLOCK Dhara module. | https://drive.google.com/open?id=1wNkBGsX-8DXdOMuGjonLPKScJ9Qsr0xy
2026-07-20 16:16 | karanpura-1 MVS | Dhara | Govind Suthar | 9998098068 | Firm | 01. Meter reading of Rupond OHT is uploaded as not functional even meter is functional. Photos of reading also upload in dhara. OHT ID IS Rupond(rupaund) (OHT-069-16) , 02. Meter reading of Sandhi OHT is uploaded as not functional even meter is functional. Photos of reading also upload in dhara. OHT ID IS , Sandhi (OHT-069-73) 03. Meter reading of Ramgarah OHT is uploaded as not functional even meter is functional. Photos of reading also upload in dhara. OHT ID IS ,Ramgada (OHT-069-15) 04. Meter reading of Bharolla OHT is uploaded as not functional even meter is functional. Photos of reading also upload in dhara. OHT ID IS ,Bharola (OHT-069-22) | https://drive.google.com/open?id=1rrWXqjUsyYMQS8VIeY399LIcyDZHfzVf
2026-07-20 17:10 | Gangabawdi MVS | Dhara | PIU Neemuch | 9826068824 | PIU | Reading of OHT in dhara module in gangabawdi MVS for the villages bherpura, and malkheda has been incorrectly approved for few days for april-2026 month due to which there is excess quantity of water supplied is shown. Please unlock the reading for the day to ensure correct supply quantity | https://drive.google.com/open?id=106Y5sA2fxDd5qTBeogGkc_MSe4y5Zlbf
2026-07-20 22:37 | MADIA MVS | Dhara | SQC | 9806847193 | SQC | बल्क कंज्यूमर मीटर- Jalrekha ऐप में field Engineer द्वारा जो एंट्री मीटर रीडिंग की प्रविष्टि की जा रही है वह पोर्टल पर कुछ अलग प्रदर्शित हो रही है, साथ ही, सभी बल्क कंज्यूमर सभी मैप किए गए 13 ग्रामों में एक ही समान मीटर रीडिंग प्रदर्शित हो रही है, जबकि उक्त रीडिंग की प्रविष्टि FE द्वारा की ही नहीं गई है। | https://drive.google.com/open?id=1mBq_ZB2Wxo8V3brd9o1sCar4gvHEbBgU
2026-07-21 10:10 | madia | Dhara | MILAN JAIN SQC | 9806847193 | SQC | sir, to be meter Reading correction. Please UNLOCK Dhara module attached date bulk consumer . excel sheet attached. | https://drive.google.com/open?id=156ssPF-EkzZae8WVfvGZgSSNsPUoq0Uq
2026-07-21 11:36 | Begamganj-Gairatganj MVS | Dhara | Govind Suthar | 9998098068 | Firm | In our scheme other scheme Begamganj-Gairatganj Ex-2 water is taken from our pump house. That water entry is not done in dhara. So please add this extra meter as Bulk supply or any other mode.
2026-07-21 11:50 | karanpura-1 MVS | Aaklan | Govind Suthar | 9998098068 | Firm | During generating bill in Aaklan Details of lane line out of 04 auto taking automatically 01 after put 04 in that box and save as draft. Due to this penalty show. The screenshot is attached. | https://drive.google.com/open?id=1eO4grO-xrgWEn9tqlwvWZJ2krBHCc5wi
2026-07-21 12:20 | Arniya bahadur MVS | Dhara | Devesh kumar singh | 9873091799 | SQC | Intakewell meter reading to be edit. | https://drive.google.com/open?id=1h_ULKqj0scWF-Cvi-jVxxoCNrjKRAqHQ
2026-07-21 18:48 | Narhela MVS | Aaklan | dr_contractor_99@gmail.com | 8736066784 | Firm | 1. UFW Sheet not Matched 2. Power Consumption Sheet Total Minimum Supply does not match with allowable losses 3. Yearly factor does not match 4. Jhond village HSC connection no. change from GM id but not updated in Generate Bill 5. pagara village LPCD High pagara + buta ka pura reading merge but Both village hsc not merge | https://drive.google.com/open?id=1zRGIMqst-ZFe7K822jbmfXgIz6obqFwd
2026-07-22 10:35 | karanpura-1 MVS | Aaklan | Govind | 9998098068 | Firm | Even LPCD of village is above 70 LPCD penalty of this village show and amount deduct in deduction sheet. After reading change of unfreeze draft bill data is not changed. | https://drive.google.com/open?id=1BOUCYvRho8XAnVaLJZEmvEyGU68-RhAG
2026-07-23 12:53 | Narhela MVS | Aaklan | dr_contractor_99@gmail.com | 8736066784 | Firm | 1. UFW Not Match 2. Power consumption sheet Minimum water supply does not match | https://drive.google.com/open?id=1Ccxn3pzsZ2mnXAZlwiICmj7pJcaWJJDX
2026-07-23 13:48 | Basai-01 | Dhara | Vivek Rajpoot | 7897206140 | Firm | UFW did not matched According to raw water quantity & total bfm supply quantity | https://drive.google.com/open?id=15NFiym70o4vz-F_wCg_pGxKiF-MydLQv
2026-07-23 13:52 | Basai-01 | Dhara | Vivek Rajpoot | 7897206140 | Firm | OHT filling is showing less than the Total Village Supply | https://drive.google.com/open?id=1Fsn2hT7oa2vvOM-WLitXx3hDM-2GEcaY
2026-07-23 14:00 | Basai-01 | Dhara | Vivek Rajpoot | 7897206140 | Firm | No village is directly connected to the WTP, yet it is still being displayed as connected. Kindly investigate and resolve this issue. | https://drive.google.com/open?id=1S7_Dv5eNgHf_IXHbU3K9RVw8IZjIN_V_
2026-07-23 14:50 | M/s Kalyan toll infrastructure limited. | Aaklan | Dharmendra Singh bhadoriya | 9755616759 | Firm | Not meter reading match in aaklan
2026-07-23 16:35 | Udgawan | Aaklan | Dharmendra Singh bhadoriya | 9755616759 | Firm | Village water supply not correct in aaklan module. UFW and Power Consumption reading not correct.so that heavy penalty imposed in this bill.please resolved this matter.
2026-07-23 18:28 | Bankpura-kushalpura | Dhara | 9669612143 | 9669612143 | PIU | 19may 1320kl supplied from persulia OHT some more correction. | https://drive.google.com/open?id=1CuVLvRa3DUacG1nMwdI8wA3Fdrj8FZuJ
2026-07-24 11:31 | Neelkanth Nasrullaganj MVS | Aaklan | dr_contractor_0104@gmail.com | 8085125602 | Firm | 1. We have not assign RA bill number of O&M bill while generation of bill 2. While updating CPI - IW in April month it is not reflecting in O&M amount of month in summary sheet
2026-07-24 11:34 | niwadi mvs | Dhara | contractor_108@gmail.com | 95497 83353 | Firm | Please unlock these readings marked in yellow, they are filled incorrectly.The closing of 31st May is not matching from 1st June which is highlighted Please unlock these readings | https://drive.google.com/open?id=1B-L_OTqWBT5ez-0TurgjgPEv4ERipd9A
2026-07-24 14:02 | Pawai Dam MVS | Dhara | SHUBHAM CHOUBEY | 7691914580 | SQC | Subject: Request for Unlocking OHT Readings for April, May ,June and July It has been observed that the clear water readings are being displayed incorrectly. There are a total of four pumps; however, the system is capturing and displaying the reading of only one pump. Due to this incorrect reading, the UFW is showing a negative value for the months of April, May, and June. Therefore, it is requested to kindly unlock the OHT readings for April, May, and June so that the incorrect readings can be verified and corrected accordingly as discuss with Balkrishna sir
2026-07-27 09:14 | Mardanpur MVS | Vistrit | Amit Chouhan | 9200641229 | SQC | sir 4 villages needs to be deleted by OHT village master due to which our approved supply point wise village report get corrected | https://drive.google.com/open?id=1sZhOLmJ2BhNhDC9LfU71GxOMCfbzb-Lr
2026-07-27 09:25 | mardanpur mvs | Dhara | Amit chouhan | 9200641229 | SQC | in mobile application Dhannas OHT show 3 times to fill reading | https://drive.google.com/open?id=1MaCx2rZyRli4jvXZp8lkv1paPaH73MCp
2026-07-27 15:05 | Arniya bahadur MVS | Dhara | Devesh kumar singh | 9873091799 | SQC | Please Unlock date 22.07.26, to be reading correct. OHT - Ranayarapeer-(OHT-004-1) village Ranayarapeer kheda -(47131201) | https://drive.google.com/open?id=1wj_fu5AQUfNHTU4maP6yKRpqRFbU50mN
2026-07-27 15:06 | Nagda MVS | Dhara | Devesh kumar singh | 9873091799 | SQC | Please Unlock date 17.07.26, to be reading correct. OHT - Hebatpura bhimpura -(OHT-098-11), Village Hebatpura bhimpura -( 471169) | https://drive.google.com/open?id=1TmBCbYUHiMVfweEPpyKRMP2bVi6NcJ3t
2026-07-27 15:20 | Badonkalan | Dhara | Jaswant Kushwaha | 9399906993 | Firm | डोंगरपुर गांव जून 2026 महीने का kl डाटा गलत शो हो रहा है सही डाटा 1938 है जबकि धारा मे 129928.5 शो हो रहा है
2026-07-28 12:29 | Begumanj- Gairatganj MVS Raisen PIU- Bhopal | Dhara | Ashish Choudhary | 9584475131 | SQC | Unlock readings, In Karhola OHT, the ESR inlet readings were recorded as "No Water Supply" because one of the villages was not supplied. By mistake, during DHARA data entry, the WSM selected "No Supply" for the ESR readings of that village. As a result, the ESR readings became zero from 1 July to 5 July. However, the ESR was filled with water, and water supply to the connected villages continued without interruption. | https://drive.google.com/open?id=1cn02et2wyJNOuq2BMlaMUdpu6VAhyk6P
2026-07-29 12:10 | Udgawan | Dhara | PIU | 9074701014 | PIU | Please unlock udgawan scheme reading on Dhara module from 1st April because we have upload remaining sub meter cases reading on Dhara module as we discussed with Kapil sir
2026-07-31 15:10 | Bansujara Badamlhara MVS | Aaklan | Raghavendra Singh Narwariya | 8878519334 | PIU | Sir,In the Ankalan Module of Bansujara Badamlhara MVS, the Census Population (2011) and (2025) for the following habitations are showing as zero: 1.Putrikheda – Gram Panchayat Bachharawani 2.Nayakhera – Gram Panchayat Bhoyra 3.Gunjoura – Gram Panchayat Ramtouriya 4.Chainpura – Gram Panchayat Mankari 5.Bandhiyan – Gram Panchayat Sijwaha 6.Bahadurpur – Gram Panchayat Bamnora Kala 7.Badelenkhera – Gram Panchayat Pura Patti It is requested that the population data for these habitations may please be updated in the system. Alternatively, an option may be provided to enable data entry/editing from the PIU level through the GM Sir login so that the required population details can be filled and the assessment process can be completed. Kindly do the needful at the earliest. | https://drive.google.com/open?id=1E5G8pgZ7aDNSXTxj9PA4FVCFi-NUiH84
2026-08-03 20:25 | niwadi prithvipur-2 mvs | Dhara | ayushi vishwakarma | 7000853011 | PIU | in maniyan oht kunwarpura village readings are not shown in GM sir id for approval | https://drive.google.com/open?id=1FdN4Kq98j90jK8cij5ReVVo-EoP6VAOM
2026-08-03 20:43 | niwadi mvs | Dhara | ayushi vishwakarma | 7000853011 | PIU | in wtp meter readings, the start reading of 1st june should have been the end reading of 31st may but it became start reading of 31st. now when we are trying to edit start reading is showing freeze. i share the screenshots of it please resolve it. | https://drive.google.com/open?id=1bZ_zVW0_hkFeFaPdoWP_9bVm_3mZAt0y
2026-08-04 11:39 | All O&M MVS UNDER PIU BHOPAL | Dhara | Ashish Choudhary(DTL) | 9584475131 | SQC | Start readings of meters locked and we are unable to edit it on gm jalrekha portal, as discussed GM (O&M), only 1st of month start readings should be locked but when used dhara all dates start readings are locked and unable to edit it. | https://drive.google.com/open?id=1QvjKgnfJmdZb7CzTqtyRqhKvHndlT11Q
2026-08-04 12:52 | Udaipura | Dhara | Lavesh rathore | 9893732747 | Firm | Some updation/corrections are required in Dhara entries in Udaipura MVRWSS. Kindly open the access for entries for April to June.
2026-08-04 14:51 | Gangabawdi MVS | Dhara | PIU Neemuch | 9826068824 | PIU | To unlock the readings of following villages in dhara module since wrong data has been filled: 1. OHT name-Balaganj Village jamuniya raoji-April month 2. OHT name bawda- april month reading for all villages 3. OHT name- bhatkhedi buzurg- April,may and june month reading for all the villages 4.OHT name- Dantoli,VIllage - Sandbawdi-April month reading 5. OHT name padada, VIllage PAdada - April month reading | https://drive.google.com/open?id=11HjzwbRga5DrR550fUWdYDrQiZV-SjDf
2026-08-04 17:48 | Udgawan | Dhara | Kunal | 9074701014 | SQC | In udgawan scheme Kala Pahad Oht reading is not submitted at our FE end. At submitting time the poppy was shown it has already submitted so kalapahad reading is not submitted please do needfull
2026-08-05 11:06 | Neelkanth Nasrullaganj MVS | Dhara | dr_contractor_0104@gmail.com | 8085125602 | Firm | Sir in the month of April and May Readings of Some villages connected through WTP and OHT are entered as Not functional by SQC but they are actually functional meter so there for we want to unfreeze the meter reading so they can be made functional for billing | https://drive.google.com/open?id=1ebaLUy13c0OcRNEaDIQfEYyiypFHmZCI
2026-08-05 16:44 | Gunawad MVS | Dhara | Rajnish Kumar | 7011501128 | PIU | गुणावाद MVS अंतर्गत Intake Well एवं WTP के मीटर 10X होने के कारण माह अप्रैल 2026, मई 2026 एवं जून 2026 की मीटर रीडिंग पोर्टल पर दर्ज नहीं की जा सकी।अतः निवेदन है कि उक्त अवधि की मीटर रीडिंग दर्ज करने हेतु Gunawad MVS की GM ID से Intake Well एवं WTP की मीटर रीडिंग को अनफ्रीज़ करने का कष्ट करें, ताकि लंबित मीटर रीडिंग दर्ज की जा सके। | https://drive.google.com/open?id=1GxEP6-qQlbeANL3IMETesOVol6AoPB3Y
2026-08-05 18:14 | Gandhi Sagar-1 | Vistrit | Suyog Kumar Badal | 8770127323 | PIU | 1. ISSUE :- Village- Borkhedi (alot) (470291) is belong to Panchayt Borkhedi. UPDATION REQURIED :- Yet to be Village Name Replace With Bor khedi 2. ISSUE :- Village- Bor khedi (470213) is belong to Panchayt Barkheda kala UPDATION REQURIED :- Yet to be Village Name Replace With Bor khedi (alot) 3. ISSUE :- SammatKhedi Village Not Found in Sandhara Panchayat But This Village Found in Osarna Panchayat. UPDATION REQURIED :- This Village yet to be transfer From Osarna to Sandhara Panchayat 4. ISSUE :- BADODIYA Village Not found in Barodiya Panchayat UPDATION Required :- Yet to be Village & Panchayat Name Replace With Badodiya Pathar both. 5. ISSUE :- Farasali Village Not found in Aakli Shivdas Panchayat But This Village Found in Dasoriya Panchayat UPDATION REQURIED :- This Village yet to be transfer from Dasoriya to Aakli Shivdas Panchayat 6. ISSUE :- Juna Pani {Junapani Pawati} Village Not found in Nalkheda Panchayat But This Village Found in Kherkheda Panchayat UPDATION REQURIED :- This Village yet to be transfer From Kherkheda to Nalkheda Panchayat 7. ISSUE :- Lalpura Village Not found in Banjari Chandwasa Panchayat UPDATION REQURIED :- This Village yet to be add in Banjari Chandwasa Panchayat 8. ISSUE :- Balahedi Village Not found in Ranayara Panchayat But This Village Found in Payakhedi Panchayat UPDATION REQURIED :- This Village is yet to be transferred From Payakhedi to Ranayara Panchayat 9. ISSUE :- Rupani Village Not found in Betikhedi Panchayat But This Village Found in Ranayra Panchayat UPDATION Required :- This Village is yet to be transferred From Ranayra to Betikhedi Panchayat. | https://drive.google.com/open?id=1sx-WPkR_f_Fcpoc0uUzENrFsq-6lr6Av
2026-08-06 10:47 | Np-2 | Vistrit | Ayushi Vishwakarma | 7000853011 | PIU | I want to edit some villages in Scheme Village Master, move them to Bulk Village. Please make them editable | https://drive.google.com/open?id=1zdmtbnM6rN9zAvCydDCFoXz08GklgfPB

## Issue Tracker
Ticket ID | Timestamp | Scheme Name | Module | User Name | Mobile Number | Belong To | Issue Description | Screenshot | Status | Remarks | Resolved Date
MPJN-0001 | 2026-07-20 13:30 | Test Scheme | Dhara | Awinash | 9876543210 | SQC | Testing Issue | https://drive.google.com/open?id=1NR2LQSfRuTzqcondSxSdFcBHR1_kWaTv | Resolved
MPJN-0002 | 2026-07-20 15:07 | Arniya bahadur mvs | Dhara | Devesh kumar singh | 9873091799 | SQC | to be meter Reading correction. Please UNLOCK Dhara module. | https://drive.google.com/open?id=1wNkBGsX-8DXdOMuGjonLPKScJ9Qsr0xy | Resolved | Unlocked approved village meter readings for Village LGD 471319 for June 2026 as per client request to allow data correction. | 2026-07-21
MPJN-0003 | 2026-07-20 16:16 | karanpura-1 MVS | Dhara | Govind Suthar | 9998098068 | Firm | 01. Meter reading of Rupond OHT is uploaded as not functional even meter is functional. Photos of reading also upload in dhara. OHT ID IS Rupond(rupaund) (OHT-069-16) , 02. Meter reading of Sandhi OHT is uploaded as not functional even meter is functional. Photos of reading also upload in dhara. OHT ID IS , Sandhi (OHT-069-73) 03. Meter reading of Ramgarah OHT is uploaded as not functional even meter is functional. Photos of reading also upload in dhara. OHT ID IS ,Ramgada (OHT-069-15) 04. Meter reading of Bharolla OHT is uploaded as not functional even meter is functional. Photos of reading also upload in dhara. OHT ID IS ,Bharola (OHT-069-22) | https://drive.google.com/open?id=1rrWXqjUsyYMQS8VIeY399LIcyDZHfzVf | Resolved | Unlocked approved OHT meter readings for specified OHTs from April 2026 onwards due to incorrect approval of non-functional meter status reported by FIRM. | 2026-07-21
MPJN-0004 | 2026-07-20 17:10 | Gangabawdi MVS | Dhara | PIU Neemuch | 9826068824 | PIU | Reading of OHT in dhara module in gangabawdi MVS for the villages bherpura, and malkheda has been incorrectly approved for few days for april-2026 month due to which there is excess quantity of water supplied is shown. Please unlock the reading for the day to ensure correct supply quantity | https://drive.google.com/open?id=106Y5sA2fxDd5qTBeogGkc_MSe4y5Zlbf | Resolved | Unlocked approved village meter readings for Bherpura and Malkheda for April 2026 to correct excess water supply quantity reported after incorrect approval. | 2026-07-21
MPJN-0005 | 2026-07-20 22:37 | MADIA MVS | Dhara | SQC | 9806847193 | SQC | बल्क कंज्यूमर मीटर- Jalrekha ऐप में field Engineer द्वारा जो एंट्री मीटर रीडिंग की प्रविष्टि की जा रही है वह पोर्टल पर कुछ अलग प्रदर्शित हो रही है, साथ ही, सभी बल्क कंज्यूमर सभी मैप किए गए 13 ग्रामों में एक ही समान मीटर रीडिंग प्रदर्शित हो रही है, जबकि उक्त रीडिंग की प्रविष्टि FE द्वारा की ही नहीं गई है। | https://drive.google.com/open?id=1mBq_ZB2Wxo8V3brd9o1sCar4gvHEbBgU | Resolved | Bulk Consumer meter ki reading FE (Field Engineer) app mein abhi supply-point-wise / local-name-wise granular entry ki suvidha available nahi hai — isi wajah se ek bulk meter se jude sabhi mapped villages (13 grams) mein ek hi reading duplicate ho kar reflect ho rahi hai, chahe FE ne actual entry ki ho ya na ki ho. | 2026-07-21
MPJN-0006 | 2026-07-21 10:10 | madia | Dhara | MILAN JAIN SQC | 9806847193 | SQC | sir, to be meter Reading correction. Please UNLOCK Dhara module attached date bulk consumer . excel sheet attached. | https://drive.google.com/open?id=156ssPF-EkzZae8WVfvGZgSSNsPUoq0Uq | Resolved |  | 2026-07-21
MPJN-0007 | 2026-07-21 11:36 | Begamganj-Gairatganj MVS | Dhara | Govind Suthar | 9998098068 | Firm | In our scheme other scheme Begamganj-Gairatganj Ex-2 water is taken from our pump house. That water entry is not done in dhara. So please add this extra meter as Bulk supply or any other mode. |  | Resolved | Vistrit module me 'Scheme Bulk Consumer Master' me jaakar bulk consumer add kar sakta hai. Bulk consumer add hone ke baad, Supply Point me jaakar meter add kiya ja sakta hai. Iske liye pehle naya meter WTP Meter Mapping me verify/add karna hoga, uske baad Supply Point me us meter ko bulk consumer ke aadhar par map kiya ja sakta hai." | 2026-07-21
MPJN-0008 | 2026-07-21 11:50 | karanpura-1 MVS | Aaklan | Govind Suthar | 9998098068 | Firm | During generating bill in Aaklan Details of lane line out of 04 auto taking automatically 01 after put 04 in that box and save as draft. Due to this penalty show. The screenshot is attached. | https://drive.google.com/open?id=1eO4grO-xrgWEn9tqlwvWZJ2krBHCc5wi | Resolved |  | 2026-07-21
MPJN-0009 | 2026-07-21 12:20 | Arniya bahadur MVS | Dhara | Devesh kumar singh | 9873091799 | SQC | Intakewell meter reading to be edit. | https://drive.google.com/open?id=1h_ULKqj0scWF-Cvi-jVxxoCNrjKRAqHQ | Resolved |  | 2026-07-21
MPJN-0010 | 2026-07-21 18:48 | Narhela MVS | Aaklan | dr_contractor_99@gmail.com | 8736066784 | Firm | 1. UFW Sheet not Matched 2. Power Consumption Sheet Total Minimum Supply does not match with allowable losses 3. Yearly factor does not match 4. Jhond village HSC connection no. change from GM id but not updated in Generate Bill 5. pagara village LPCD High pagara + buta ka pura reading merge but Both village hsc not merge | https://drive.google.com/open?id=1zRGIMqst-ZFe7K822jbmfXgIz6obqFwd | Resolved | I have checked the data and the report is showing correct entries. We are considering only the meter volume and all ECM entries are correct. Kindly verify once from your end as well by referring to the report.Thank you | 2026-07-23
MPJN-0011 | 2026-07-22 10:35 | karanpura-1 MVS | Aaklan | Govind | 9998098068 | Firm | Even LPCD of village is above 70 LPCD penalty of this village show and amount deduct in deduction sheet. After reading change of unfreeze draft bill data is not changed. | https://drive.google.com/open?id=1BOUCYvRho8XAnVaLJZEmvEyGU68-RhAG | Resolved | All are data resolved | 2026-07-23
MPJN-0012 | 2026-07-23 12:53 | Narhela MVS | Aaklan | dr_contractor_99@gmail.com | 8736066784 | Firm | 1. UFW Not Match 2. Power consumption sheet Minimum water supply does not match | https://drive.google.com/open?id=1Ccxn3pzsZ2mnXAZlwiICmj7pJcaWJJDX | Resolved | I have checked the data and the report is showing correct entries. We are considering only the meter volume and all ECM entries are correct. Kindly verify once from your end as well by referring to the report.Thank you | 2026-07-23
MPJN-0013 | 2026-07-23 13:48 | Basai-01 | Dhara | Vivek Rajpoot | 7897206140 | Firm | UFW did not matched According to raw water quantity & total bfm supply quantity | https://drive.google.com/open?id=15NFiym70o4vz-F_wCg_pGxKiF-MydLQv | Resolved | I have checked the data and the report is showing correct entries. We are considering only the meter volume and all ECM entries are correct. Kindly verify once from your end as well by referring to the report.Thank you | 2026-07-23
MPJN-0014 | 2026-07-23 13:52 | Basai-01 | Dhara | Vivek Rajpoot | 7897206140 | Firm | OHT filling is showing less than the Total Village Supply | https://drive.google.com/open?id=1Fsn2hT7oa2vvOM-WLitXx3hDM-2GEcaY | Resolved | Please share more details. | 2026-07-27
MPJN-0015 | 2026-07-23 14:00 | Basai-01 | Dhara | Vivek Rajpoot | 7897206140 | Firm | No village is directly connected to the WTP, yet it is still being displayed as connected. Kindly investigate and resolve this issue. | https://drive.google.com/open?id=1S7_Dv5eNgHf_IXHbU3K9RVw8IZjIN_V_ | Resolved | we will fixed as soon as possible | 2026-07-27
MPJN-0016 | 2026-07-23 14:50 | M/s Kalyan toll infrastructure limited. | Aaklan | Dharmendra Singh bhadoriya | 9755616759 | Firm | Not meter reading match in aaklan |  | Resolved | All are data resolved | 2026-07-23
MPJN-0017 | 2026-07-23 16:35 | Udgawan | Aaklan | Dharmendra Singh bhadoriya | 9755616759 | Firm | Village water supply not correct in aaklan module. UFW and Power Consumption reading not correct.so that heavy penalty imposed in this bill.please resolved this matter. |  | Resolved | All are data resolved | 2026-07-23
MPJN-0018 | 2026-07-23 18:28 | Bankpura-kushalpura | Dhara | 9669612143 | 9669612143 | PIU | 19may 1320kl supplied from persulia OHT some more correction. | https://drive.google.com/open?id=1CuVLvRa3DUacG1nMwdI8wA3Fdrj8FZuJ | Resolved | Meter reading locked se unlocked karwane ke liye detail + form Trouble Shifting Group me bhej dijiye. Policy ke hisaab se WhatsApp group me bhejna mandatory hai. | 2026-07-23
MPJN-0019 | 2026-07-24 11:31 | Neelkanth Nasrullaganj MVS | Aaklan | dr_contractor_0104@gmail.com | 8085125602 | Firm | 1. We have not assign RA bill number of O&M bill while generation of bill 2. While updating CPI - IW in April month it is not reflecting in O&M amount of month in summary sheet |  | Resolved | All are the issue resolved | 2026-07-23
MPJN-0020 | 2026-07-24 11:34 | niwadi mvs | Dhara | contractor_108@gmail.com | 95497 83353 | Firm | Please unlock these readings marked in yellow, they are filled incorrectly.The closing of 31st May is not matching from 1st June which is highlighted Please unlock these readings | https://drive.google.com/open?id=1B-L_OTqWBT5ez-0TurgjgPEv4ERipd9A | Resolved |  | 2026-07-27
MPJN-0021 | 2026-07-24 14:02 | Pawai Dam MVS | Dhara | SHUBHAM CHOUBEY | 7691914580 | SQC | Subject: Request for Unlocking OHT Readings for April, May ,June and July It has been observed that the clear water readings are being displayed incorrectly. There are a total of four pumps; however, the system is capturing and displaying the reading of only one pump. Due to this incorrect reading, the UFW is showing a negative value for the months of April, May, and June. Therefore, it is requested to kindly unlock the OHT readings for April, May, and June so that the incorrect readings can be verified and corrected accordingly as discuss with Balkrishna sir |  | Resolved | Please share a screenshot also and mention the step for which reading you are talking about. Once we receive this, we will get it unlocked. | 2026-07-28 12:29
MPJN-0022 | 2026-07-27 09:14 | Mardanpur MVS | Vistrit | Amit Chouhan | 9200641229 | SQC | sir 4 villages needs to be deleted by OHT village master due to which our approved supply point wise village report get corrected | https://drive.google.com/open?id=1sZhOLmJ2BhNhDC9LfU71GxOMCfbzb-Lr | Resolved | This has already been provided in the GM PIU ID. You can delete from there. | 2026-07-27 09:14
MPJN-0023 | 2026-07-27 09:25 | mardanpur mvs | Dhara | Amit chouhan | 9200641229 | SQC | in mobile application Dhannas OHT show 3 times to fill reading | https://drive.google.com/open?id=1MaCx2rZyRli4jvXZp8lkv1paPaH73MCp | Resolved | Connect In Kailash Jii | 2026-07-27 09:14
MPJN-0024 | 2026-07-27 15:05 | Arniya bahadur MVS | Dhara | Devesh kumar singh | 9873091799 | SQC | Please Unlock date 22.07.26, to be reading correct. OHT - Ranayarapeer-(OHT-004-1) village Ranayarapeer kheda -(47131201) | https://drive.google.com/open?id=1wj_fu5AQUfNHTU4maP6yKRpqRFbU50mN | Resolved |  | 2026-07-27 09:14
MPJN-0025 | 2026-07-27 15:06 | Nagda MVS | Dhara | Devesh kumar singh | 9873091799 | SQC | Please Unlock date 17.07.26, to be reading correct. OHT - Hebatpura bhimpura -(OHT-098-11), Village Hebatpura bhimpura -( 471169) | https://drive.google.com/open?id=1TmBCbYUHiMVfweEPpyKRMP2bVi6NcJ3t | Resolved |  | 2026-07-27 09:14
MPJN-0026 | 2026-07-27 15:20 | Badonkalan | Dhara | Jaswant Kushwaha | 9399906993 | Firm | डोंगरपुर गांव जून 2026 महीने का kl डाटा गलत शो हो रहा है सही डाटा 1938 है जबकि धारा मे 129928.5 शो हो रहा है |  | Resolved |  | 2026-07-27 09:14
MPJN-0027 | 2026-07-28 12:29 | Begumanj- Gairatganj MVS Raisen PIU- Bhopal | Dhara | Ashish Choudhary | 9584475131 | SQC | Unlock readings, In Karhola OHT, the ESR inlet readings were recorded as "No Water Supply" because one of the villages was not supplied. By mistake, during DHARA data entry, the WSM selected "No Supply" for the ESR readings of that village. As a result, the ESR readings became zero from 1 July to 5 July. However, the ESR was filled with water, and water supply to the connected villages continued without interruption. | https://drive.google.com/open?id=1cn02et2wyJNOuq2BMlaMUdpu6VAhyk6P | Resolved |  | 2026-07-28 12:29
MPJN-0028 | 2026-07-29 12:10 | Udgawan | Dhara | PIU | 9074701014 | PIU | Please unlock udgawan scheme reading on Dhara module from 1st April because we have upload remaining sub meter cases reading on Dhara module as we discussed with Kapil sir |  | Resolved |  | 2026-07-29
MPJN-0029 | 2026-07-31 15:10 | Bansujara Badamlhara MVS | Aaklan | Raghavendra Singh Narwariya | 8878519334 | PIU | Sir,In the Ankalan Module of Bansujara Badamlhara MVS, the Census Population (2011) and (2025) for the following habitations are showing as zero: 1.Putrikheda – Gram Panchayat Bachharawani 2.Nayakhera – Gram Panchayat Bhoyra 3.Gunjoura – Gram Panchayat Ramtouriya 4.Chainpura – Gram Panchayat Mankari 5.Bandhiyan – Gram Panchayat Sijwaha 6.Bahadurpur – Gram Panchayat Bamnora Kala 7.Badelenkhera – Gram Panchayat Pura Patti It is requested that the population data for these habitations may please be updated in the system. Alternatively, an option may be provided to enable data entry/editing from the PIU level through the GM Sir login so that the required population details can be filled and the assessment process can be completed. Kindly do the needful at the earliest. | https://drive.google.com/open?id=1E5G8pgZ7aDNSXTxj9PA4FVCFi-NUiH84 | Resolved | Already avaible in GM PIU Id
MPJN-0030 | 2026-08-03 20:25 | niwadi prithvipur-2 mvs | Dhara | ayushi vishwakarma | 7000853011 | PIU | in maniyan oht kunwarpura village readings are not shown in GM sir id for approval | https://drive.google.com/open?id=1FdN4Kq98j90jK8cij5ReVVo-EoP6VAOM | Resolved
MPJN-0031 | 2026-08-03 20:43 | niwadi mvs | Dhara | ayushi vishwakarma | 7000853011 | PIU | in wtp meter readings, the start reading of 1st june should have been the end reading of 31st may but it became start reading of 31st. now when we are trying to edit start reading is showing freeze. i share the screenshots of it please resolve it. | https://drive.google.com/open?id=1bZ_zVW0_hkFeFaPdoWP_9bVm_3mZAt0y
MPJN-0032 | 2026-08-04 11:39 | All O&M MVS UNDER PIU BHOPAL | Dhara | Ashish Choudhary(DTL) | 9584475131 | SQC | Start readings of meters locked and we are unable to edit it on gm jalrekha portal, as discussed GM (O&M), only 1st of month start readings should be locked but when used dhara all dates start readings are locked and unable to edit it. | https://drive.google.com/open?id=1QvjKgnfJmdZb7CzTqtyRqhKvHndlT11Q
MPJN-0033 | 2026-08-04 12:52 | Udaipura | Dhara | Lavesh rathore | 9893732747 | Firm | Some updation/corrections are required in Dhara entries in Udaipura MVRWSS. Kindly open the access for entries for April to June. |  | Resolved | कृपया निम्नलिखित प्रक्रिया अपनाएं: 1. संलग्न/निर्धारित Unlock Request Form को पूर्ण विवरण सहित भरें (Scheme Name, OHT/Village Name, अवधि/Date Range, तथा Unlock का कारण अनिवार्य रूप से उल्लेखित करें)। 2. फॉर्म को संबंधित PIU के माध्यम से अग्रेषित (forward) करवाएं। 3. PIU के अनुमोदन उपरांत ही Unlock की कार्यवाही की जाएगी। बिना फॉर्म एवं PIU अनुमोदन के प्राप्त अनुरोधों पर कार्यवाही नहीं की जा सकेगी। सहयोग हेतु धन्यवाद।
MPJN-0034 | 2026-08-04 14:51 | Gangabawdi MVS | Dhara | PIU Neemuch | 9826068824 | PIU | To unlock the readings of following villages in dhara module since wrong data has been filled: 1. OHT name-Balaganj Village jamuniya raoji-April month 2. OHT name bawda- april month reading for all villages 3. OHT name- bhatkhedi buzurg- April,may and june month reading for all the villages 4.OHT name- Dantoli,VIllage - Sandbawdi-April month reading 5. OHT name padada, VIllage PAdada - April month reading | https://drive.google.com/open?id=11HjzwbRga5DrR550fUWdYDrQiZV-SjDf | Resolved | Done
MPJN-0035 | 2026-08-04 17:48 | Udgawan | Dhara | Kunal | 9074701014 | SQC | In udgawan scheme Kala Pahad Oht reading is not submitted at our FE end. At submitting time the poppy was shown it has already submitted so kalapahad reading is not submitted please do needfull
MPJN-0036 | 2026-08-05 11:06 | Neelkanth Nasrullaganj MVS | Dhara | dr_contractor_0104@gmail.com | 8085125602 | Firm | Sir in the month of April and May Readings of Some villages connected through WTP and OHT are entered as Not functional by SQC but they are actually functional meter so there for we want to unfreeze the meter reading so they can be made functional for billing | https://drive.google.com/open?id=1ebaLUy13c0OcRNEaDIQfEYyiypFHmZCI
MPJN-0037 | 2026-08-05 16:44 | Gunawad MVS | Dhara | Rajnish Kumar | 7011501128 | PIU | गुणावाद MVS अंतर्गत Intake Well एवं WTP के मीटर 10X होने के कारण माह अप्रैल 2026, मई 2026 एवं जून 2026 की मीटर रीडिंग पोर्टल पर दर्ज नहीं की जा सकी।अतः निवेदन है कि उक्त अवधि की मीटर रीडिंग दर्ज करने हेतु Gunawad MVS की GM ID से Intake Well एवं WTP की मीटर रीडिंग को अनफ्रीज़ करने का कष्ट करें, ताकि लंबित मीटर रीडिंग दर्ज की जा सके। | https://drive.google.com/open?id=1GxEP6-qQlbeANL3IMETesOVol6AoPB3Y
MPJN-0038 | 2026-08-05 18:14 | Gandhi Sagar-1 | Vistrit | Suyog Kumar Badal | 8770127323 | PIU | 1. ISSUE :- Village- Borkhedi (alot) (470291) is belong to Panchayt Borkhedi. UPDATION REQURIED :- Yet to be Village Name Replace With Bor khedi 2. ISSUE :- Village- Bor khedi (470213) is belong to Panchayt Barkheda kala UPDATION REQURIED :- Yet to be Village Name Replace With Bor khedi (alot) 3. ISSUE :- SammatKhedi Village Not Found in Sandhara Panchayat But This Village Found in Osarna Panchayat. UPDATION REQURIED :- This Village yet to be transfer From Osarna to Sandhara Panchayat 4. ISSUE :- BADODIYA Village Not found in Barodiya Panchayat UPDATION Required :- Yet to be Village & Panchayat Name Replace With Badodiya Pathar both. 5. ISSUE :- Farasali Village Not found in Aakli Shivdas Panchayat But This Village Found in Dasoriya Panchayat UPDATION REQURIED :- This Village yet to be transfer from Dasoriya to Aakli Shivdas Panchayat 6. ISSUE :- Juna Pani {Junapani Pawati} Village Not found in Nalkheda Panchayat But This Village Found in Kherkheda Panchayat UPDATION REQURIED :- This Village yet to be transfer From Kherkheda to Nalkheda Panchayat 7. ISSUE :- Lalpura Village Not found in Banjari Chandwasa Panchayat UPDATION REQURIED :- This Village yet to be add in Banjari Chandwasa Panchayat 8. ISSUE :- Balahedi Village Not found in Ranayara Panchayat But This Village Found in Payakhedi Panchayat UPDATION REQURIED :- This Village is yet to be transferred From Payakhedi to Ranayara Panchayat 9. ISSUE :- Rupani Village Not found in Betikhedi Panchayat But This Village Found in Ranayra Panchayat UPDATION Required :- This Village is yet to be transferred From Ranayra to Betikhedi Panchayat. | https://drive.google.com/open?id=1sx-WPkR_f_Fcpoc0uUzENrFsq-6lr6Av
MPJN-0039 | 2026-08-06 10:47 | Np-2 | Vistrit | Ayushi Vishwakarma | 7000853011 | PIU | I want to edit some villages in Scheme Village Master, move them to Bulk Village. Please make them editable | https://drive.google.com/open?id=1zdmtbnM6rN9zAvCydDCFoXz08GklgfPB