## Status 21st July
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | Sahbhagita | 1. At Approval time, Pagination done on Sahbhagita pages | Done
|  | 2. RA bill given to ISA (instead of CP Manager) | Done
|  | 3. FE specific to particular ISA are visible to them | Done
|  | 4. Password reset option given to ISA | Done
|  | 5. Village/Combined Wise drop down provided | Done
2 | Cube Testing | 1. Cube ID get generated before image upload | Done
|  | 2. Show rejected data to Contractor | Done
|  | 3. Re_inspection Loop working | Done
3 | Material Testing | 1. Re_inspection Loop working | In Progress
3 | SVS Water Supply Monitoring PHE | 1. Removed JJM Id, Village status fields | Done
|  | 2. According to login specific District, Block and GP should appear | Done
|  | 3. Daily Water Supply Completed - In No option added one more Reason and correct spelling | Done
|  | 4. Bilingual conversion for SVS Daily Water supply Page (Hindi English) and Report Column Header ( in Hindi) | Done
4 | Parinam | 1. FE name shown in reports | Done
|  | 2. FHTC Samgra Id - more than one survey on same ID | UAT Done
5 | Vistrit / Dhara | 1. Approved Report Data corrected as discussed with Kapil | Done
6 | Sopan | 1. Add Calendar functionality for Calendar year 2026-27 (on Contractor Login)

## Status All Module 09th June
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
| Anushravan/Cube/Material | 1. Remove Mandatory in Intake, WTP, MBR, RWPM, & CWPM in dropdown Village and GP | Done
|  | 2. Give Save as Draft functionality & Provide option to upload photo later on | Done
|  | 3. OHT Search option during RFI | Done
| Anusharavan | 1. Include multiple date in report - FE RFI Submission date & Block name also added | Done
| Asset Mapping | 1. SQC TPIA Contractor Data and Report on Web | Done
| Bharosa | 1. Factory Testing WEB - Add QAP 3rd Party & upload multiple images | Done
| Cube | 1. Structure components to be added against each Component | Done
|  | 2. Date of costing for RFI loop 7th and 28th day added | Done
|  | 3. Add Filter Bed as Sub Component under WTP Component | Done
| Cube Module Mobile CR | Add Mandatory multiple image upload functionality to the FE inspection form and Save as Draft | Done
| Dhara | New Dhara Report to be shown on all Jal Rekha logins | Done
|  | GM Approved Reports & Contractors Dispute | Done
| Sahbhagita | RA Bill Functionality to be added for Sahbhagita Activity on ISA Manager after approve activity and Edit option. | Done
| Sahbhagita Mobile CR | Add Save as draft functionality for video, images and documents | Done
| Vistrit | WTP Meter Mapping - New Column Addtion Date, Scheme & PIU | Done
|  | WTP Meter Name update naming convention - Example Narela-WTP-01 | Done
|  | WTP Meter Mapping, Intake Mapping - New Column addition such as Meter name, No of OHT connections with WTP, District, Block & GP for Intake | Done
|  | In Scheme Village mapping - Validation applied on Testing and Permitted fields and leave Census Population open at all level | Done
| Vistrit & Dhara | All Reports Visible in Contractor login (Vistrit Data Non Editable) | Done
| Vistrit | OHT Issue - For Some OHTs of some Schemes were not visible but visible at FE's Id. Because of Deactivate entries of OHT in Vistrit. Now it is resolved | Done
| Public Report DWSR | Open to Public | Done
| All Web Reports | Enabled Material, Cube & Bharosa Reports on Jal Rekha web user id - CGM,PMU | Done
| UI/UX | Change Module sequence on portal | Done
| Parinam | Contractor Search Option | Done
| PHE _Dhara GP Reading | GP wise Village Reading | Done

## O&M
S. No. | Module/Activity | Tasks/ Changes/Enhancements | Status
1 | O&M Billing - Dhara Reports | Dhara report integration in O&M Billing module | Done
2 | GM Side Login | Census population addition in Scheme Master (GM side report) | Done
3 | O&M Billing - Bill | Bill generation for total 64 Schemes
4 | Contractor Side login | Check final summary report | Some Changes Required
5 | Master | scheme village master.. scheme piu village DONE | Done
6 | Master | OHT village master | Done
7 | Bulk Consumer | Scheme bulk consumer | Done
8 | Bulk Consumer Mapping | Bulk consumer mapping - oht wtp | Done
9 | Mapped Report Status | Of all above 4 reports Mapped in Mapped status report . summary report - vidhan sabha district wise | Done
10 | DWSR Reports | DWSR report development (basic) | Done
11 | Data Validation | Duplicate Village Mapping validation across schemes | Done
12 | Open Platform | Restrict reports: Show only Dhara & DWSR | Done
13 | Open Platform | DWSR column clickable (Hyperlink integration) | Done
14 | Report Optimization | Remove extra reports (Date-wise DWSR, MWSR, UFW, Scheme-wise WSR, Village-wise MWSR, Bulk User MWSR) | Done
15 | PowerConsumption | Need To Change Contractor and GM Side (Contractor - Generate Bill - Add into Contract Details ( Basic Detail, Intermediate Raw Water Demand, and | In Progress
16 | Scheme Status | Need Two More Column Add in Water Supply During Construction Bill | In Progress
17 | GM Approval | Only final approval by GM ( No Provisional approval required) and Concern Remark Mandatory | Done
18 | O&M Villages | Villages where water Supply during construction is under consideration or approved | In Progress
19 | Aakalan | Dhara Report complete and release to O&M billing | Done
20 | Aaklan Contractor / Dhara | Contractor to check & Raise any discrepancies within time. Dhara data will be used for billing purposes | In Progress
21 | Additional Aaklan Updates | GM side if Pump Transformer column has YES then consolidate bill will have 10% deduction in total amount | In Progress