## INDEX
JAL REKHA - CONSOLIDATED USER STORY REGISTER ¦ Cycle 5 (June-July 2026) + CR Backlog Cross-Reference ¦ CMMI Level 5 ¦ PHED, Madhya Pradesh
Prepared by: Dheeraj Motiyani, Senior Business Analyst ¦ Reviewed by: Tapan Khandelwal, Senior Project Manager ¦ Consolidated: 07-Aug-2026
Sr. No. | Sheet Name | Module / Area | No. of User Stories | Coverage
1 | O&M Billing US | O&M Billing – Aaklan | 17 | Jun+Jul 2026 consolidated
2 | Sahbhagita US | Sahbhagita | 11 | Jun+Jul 2026 consolidated
3 | Dhara US | Dhara (Reports, Corrections, Disputes) | 8 | Jun+Jul 2026 consolidated
4 | Vistrit US | Vistrit (Master Module) | 5 | Jun+Jul 2026 consolidated
5 | FHTC Parinam US | FHTC Parinam | 5 | Jun+Jul 2026 consolidated
6 | BISAC Integration US | BISAC / NIC Asset Integration | 3 | Jun+Jul 2026 consolidated
7 | e-Sign CDAC US | e-Sign via CDAC (Aadhaar) | 4 | Jun+Jul 2026 consolidated
8 | Anusharavan US | Anusharavan (June CR) | 3 | Jun+Jul 2026 consolidated
9 | Cube Testing US | Cube Testing (June CR) | 5 | Jun+Jul 2026 consolidated
10 | SVS US | SVS Water Supply Monitoring (June CR) | 4 | Jun+Jul 2026 consolidated
11 | Vistrit OTP US | Vistrit OTP & Validation | 2 | Jun+Jul 2026 consolidated
12 | CMMI Doc US | CMMI Documentation | 2 | Jun+Jul 2026 consolidated
13 | O&M Billing Workflow US | O&M Billing Workflow Module (Multi-Level Approval Chain) | 16 | Jun+Jul 2026 consolidated
14 | Material Testing US | Material Testing | 3 | Jun+Jul 2026 consolidated
15 | Nirmal US | Nirmal Module | 4 | Jun+Jul 2026 consolidated
16 | AI Module FHTC Tap US | AI Module - FHTC Tap Connection Detection | 3 | Jun+Jul 2026 consolidated
17 | Master US | Master Data Module | 3 | Jun+Jul 2026 consolidated
18 | Asset Mapping US | Asset Mapping (BISAC) | 2 | Jun+Jul 2026 consolidated
19 | Bharosa US | Bharosa (Factory Testing) | 2 | Jun+Jul 2026 consolidated
20 | Daily Inspection US | Daily Inspection | 2 | Jun+Jul 2026 consolidated
21 | Sopan US | Sopan | 1 | Jun+Jul 2026 consolidated
22 | QA Automation US | QA - User & Role Management Automation | 2 | Jun+Jul 2026 consolidated
| TOTAL USER STORIES (Cycle 5, Jun+Jul 2026) |  | 107
Notes:
1. All 58 stories from the original Cycle 5 (June 2026) register and all 16 stories from the O&M Billing Workflow (Cycle 4) register are preserved unchanged.
2. New user stories (marked with sprint 'Sprint 18' in most cases) have been appended to existing sheets or added as new sheets, covering July 2026 status-review items and timesheet activity not previously captured as formal stories.
3. New sheets added: Material Testing US, Nirmal US, AI Module - FHTC Tap Connection US, Master US, Asset Mapping US, Bharosa US, Daily Inspection US, Sopan US, QA Automation US.
4. See the 'CR Cross-Reference' sheet for a quick mapping of every logged Change Request to its corresponding user story ID(s), and the 'CR Log - Full Details' sheet for the complete CR record (raised by, logging date, full description, module/sub-module, impact area & analysis, implementation status/date, approval status, priority, risk level and remarks) for all 24 CRs (21 formally logged + 3 identified in the July status review).

## CR Log - Full Details
Jal Rekha Project — Change Request Log (Full Details) ¦ Cycle 4 (Jun-Jul 2026), Sprint Jal Rekha/17 ¦ Prepared by: Dheeraj Motiyani, Sr. BA ¦ Reviewed by: Tapan Khandelwal, SPM
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Remarks | Linked User Story ID(s)
1 | OMB-JUN-2026-001 | MD Sir / Kapil Sir | Dheeraj Motiyani | 01-Jun-2026 | Contractor/Firm login – make key document uploads (Submission Letter, Tax Invoice) mandatory before a bill can move out of “Save as Draft” state; draft can be saved with partial data but cannot be forwarded to GM (PIU) until mandatory documents are attached. | O&M Billing | Save as Draft – Mandatory Upload (Contractor) | Contractor/Firm Login – Bill Workflow | Draft-save behaviour unchanged; new gate added only on the Forward action. Mirrors pattern already delivered for Cube Testing and Sahbhagita Mobile Save-as-Draft CRs. | Done |  | Pending | High | Medium | New CR – raised to align O&M Billing with Cube/Sahbhagita Save-as-Draft pattern. | US-OMWF-C4-001
2 | OMB-MAY-2026-020 | MD Sir | Dheeraj Motiyani | 16-Jun-2026 | O&M Billing – Residual Pressure & Complaint Redressal screen changes. Pressure Threshold Report format update per OM_RA_Bill_Report.pdf. Complaint Redressal - Is complaint resolved in this month ? Renaming Complaint Redressal page :- Date on which complaint received to contractor, Date on which complaint resolved, Total Days taken in Resolving complaint (Days) | O&M Billing | Residual Pressure & Complaint Redressal | GM PIU / O&M Login – RA Bill | Residual Pressure: columns per OM_RA_Bill_Report.pdf (District, Block, GP, Village, Consumer Name, Mobile, Measured Pressure, Remark, Affected HSCs, Days, Penalty calc). Complaint Redressal: label and status changes. | Done |  | Pending | Medium | Low | Ref: OM_RA_Bill_Report.pdf – Pressure_Threshold_Report. RA/19/50/2025-26/Q1/1 format. | US-OM-C5-015 (NEW)
3 | OMB-JUN-2026-002 | MD Sir | Dheeraj Motiyani | 20-Jun-2026 | Complaint Redressal Sheet – add Complaint Received Date to Contractor, Event-above-48-hours flag and Penalty Relaxation (Yes/No) fields; document upload as per submeter reading. | O&M Billing | Complaint Redressal Sheet | GM PIU / O&M Login – RA Bill | Auto-derived Event-above-48-hours flag from received/resolved dates. Penalty Relaxation = Yes routes relaxation letter into GM (PIU) document set. | Done |  | Pending | Medium | Low | New CR – extends Residual Pressure CR (OMB-MAY-2026-020) into the Complaint Redressal tab. | US-OM-C5-016 (NEW)
4 | OMB-MAY-2026-006 | MD Sir | Dheeraj Motiyani | 01-Jun-2026 | O&M Billing – Workflow Redesign: Firm → GM PIU → TL SQC → GM PIU → GM O&M → DGM → TL PMC → CFO → CA → P.D. → MD. | O&M Billing | Billing Workflow Redesign | Firm, GM PIU, TL SQC, GM O&M, All Hierarchy | Two workflow paths defined. “Manage Bill” option used for GM PIU. “View Pending Bills” accessible before Pending stage. Ref: O&M_Billing_Workflow diagrams and process flow PDF. | In Progress |  | Pending | High | High | Use Manage Page (not old flow). Refer O&M Billing Workflow PDF + JPEG diagrams. | US-OMWF-C4-001 to 016
5 | OMB-MAY-2026-002 | MD Sir / Kapil Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – Contractor Generate Bill: Abstract generation from Contractor login. Select Bill → Generate Abstract → With all villages, scheme (Dhara readings, Master Module tables and UFW Approved report and other documents with Abstract bill ) | O&M Billing | Contractor Bill – Abstract | Contractor Login – Bill Workflow | Abstract screen added under Contractor login for RA billing. Links to selected bill and tags all villages. GM/SQC approval chain unaffected. | In Progress |  | Pending | High | Medium | Abstract linked to 8th Bill; Tag all villages flag needed. | US-OM-C5-001, US-OM-C5-012
6 | OMB-JUN-2026-003 | MD Sir | Dheeraj Motiyani | 18-Jun-2026 | Sahbhagita – Village-wise and Combined Activity abstract report; Category filter (Village/Combined/All); quarterly RA Bill numbering (RA/1–RA/12) reflected on abstract header. | Sahbhagita | Abstract Bill – Category Filter | GM PIU / Contractor Login – Abstract Report | Reuses Sahbhagita Category(V/C/A) filter logic for the O&M Abstract report; RA numbering aligned to the RA(1)-RA(12) cycle used in Sahbhagita. | Open |  | Pending | High | Medium | New CR – aligns O&M Abstract Bill with Sahbhagita Village/Combined activity structure. | US-SAH-C5-002, US-SAH-C5-006
7 | OMB-MAY-2026-005 | MD Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – Bill PDF consolidation: approx. 19–20 documents merged into one PDF (GM, SQC, Firm, Form 27A, MB, Abstract). 3-month combined PDF for static docs; monthly for variable docs. | O&M Billing | Bill PDF Merge – All Documents | All Logins – Bill Generation | Merged PDF includes: 1.GM letter, 2.SQC letter, 3.Firm docs, 4.Form 27A, 5.MB, 6.Abstract. Static docs = 1 copy for 3 months; variable = per month. Total ~19–20 docs. | In Progress |  | Approved | High | Medium | Landscape issue in O&M Bill PDF also fixed in this CR. | US-OM-C5-004, US-OM-C5-011
8 | OMB-MAY-2026-008 | MD Sir | Dheeraj Motiyani | 03-Jun-2026 | O&M Billing – Contractor mistakes visible to SQC/TL and GM. Show all records on all IDs for GM and SQC. Merge PDF of all O&M documents. | O&M Billing | Contractor Mistake Visibility & PDF Merge | GM, SQC, TL Logins | Contractor error entries visible across SQC/TL and GM logins. All records shown on all IDs. O&M merged PDF available per bill. | Open |  | Pending | Medium | Medium | Related to Bill PDF CR (OMB-MAY-2026-005). SQC 7L/4–GM mapping check needed. | US-OM-C5-002, US-OM-C5-003
9 | OMB-MAY-2026-015 | MD Sir | Dheeraj Motiyani | 09-Jun-2026 | O&M Billing – Document Upload Screen: Firm: Firm Submission Letter, Tax Invoice, Any Other (Multiple). TL/SQC: SQC Recommendation Letter, Third Party Water Quality Test Report (Multiple + Remark). GM PIU: PIU Recommendation Letter, Signed Form 27A, Signed Scanned MB, Signed Abstract, Signed Monthly Bill Sheet (Multiple), Any Other Docs (Multiple + Remark). | O&M Billing | Document Upload Screen Design | Firm, TL/SQC, GM PIU Logins | Upload UI: Download + View PDF buttons per doc type. Multiple upload for Water Quality Test Report, Monthly Bill Sheet, Any Other Docs. Remark field for selected doc types. | In Progress |  | Approved | High | Medium | Ref: Handwritten wireframe (Contractor/Firm, TL SQC, GM PIU sections). Upload + Download + View PDF per doc. | US-OMWF-C4-014
10 | OMB-MAY-2026-003 | MD Sir / Kapil Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – GST No. Integration with O&M Billing Jal Rekha portal. GST number to be captured and linked at firm/contractor level. | O&M Billing | GST Integration | Contractor / GM PIU Login | GST No. field added at contractor master level. Appears on bill PDF and abstract. Rakesh Sir to validate GST API/manual entry approach. | Open |  | Pending | Medium | Low | GST No. (150/215) – Rakesh Sir to confirm data source. | US-OM-C5-017 (NEW)
11 | OMB-MAY-2026-001 | MD Sir / Kapil Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – E-Sign Integration via CDAC for all parties (Firm/FE-eSign, Web & Mobile). CDAC integration for e-sign on Bill, Submission Letter, and Tax Invoice. FE (e-sign) → Web & Mobile flow. | O&M Billing | E-Sign – CDAC Integration | Web & Mobile – Bill Workflow | CDAC API integration required. Affects Firm, FE, TL, GM PIU login flows. Bill PDF and submission letter to carry e-sign. System-generated bill – physical sign NOT required. | Open |  | Pending | High | High | CDAC Rakesh Sir to coordinate. FE (e-sign) ↔ Web/Mobile dual flow. | US-ESIGN-C5-001, US-ESIGN-C5-002
12 | OMB-MAY-2026-004 | MD Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – TL Recommendation Letter to be E-Office generated (system-generated). TL (PMC) → E-Office → Account Office Jal Rekha. | O&M Billing | TL Recommendation Letter – E-Office | TL (PMC) & Account Office Login | TL recommendation letter generated from E-Office system, not manual upload. Integration with Account Office Jal Rekha to be established. | Open |  | Pending | High | High | TL SQC integration also required. E-Office API/link to be confirmed. | US-ESIGN-C5-003
13 | OMB-MAY-2026-014 | MD Sir | Dheeraj Motiyani | 08-Jun-2026 | O&M Billing (Aaklan) – GM (PIU Login) & GM (O&M) / Deputy O&M: View Pending Bills and Manage Bills. Bills already generated shown in table. | O&M Billing (Aaklan) | Pending Bills View – GM Logins | GM PIU & GM O&M Login | GM PIU: View Pending Bills, Manage Bill under O&M. GM O&M: View Pending Bills + Manage Bill. Already generated bills shown in table. Ref: 18-Jun handwritten flow. | In Progress |  | Approved | High | Medium | Aaklan module O&M section. GM PIU & GM O&M/Deputy flows defined. | US-OMWF-C4-013
14 | SHB-JUN-2026-004 | MD Sir | Dheeraj Motiyani | 18-Jun-2026 | Sahbhagita – Report: Category → Activity. Village Wise (32/27 activities) & Combined (22). Filter: V, C, A. Category V/C/A cross-filter. Ref: Sahbhagita_master_activity_matched.xlsx. | Sahbhagita | Activity Report – Village/Combined Category Filter | Sahbhagita Report Module | Report shows Village Wise (32 listed, 27 unique) and Combined (22). Category filter: V=Village, C=Combined, A=All. Sub-activity linked. Ref: Sahbhagita master activity doc. | In Progress |  | Approved | High | Medium | Village 32/27 activities; Combined 22; V/C/A cross-filter. Ref master activity matched xlsx. | US-SAH-C5-002, US-SAH-C5-003
15 | SHB-MAY-2026-007 | MD Sir | Dheeraj Motiyani | 01-Jun-2026 | Sahbhagita – Multi-select dropdown for bill selection. RA(1) to RA(12) bill range with Withhold Bills option. | Sahbhagita | Multi-Select Bill Dropdown | Sahbhagita Login – Bill Management | Sahbhagita module: multi-select in bill dropdown. RA Bill range RA(1)–RA(12). Withhold Bills toggle added. | Open |  | Pending | Medium | Low | Generate Abstract → Select Bill → Tag all villages. Village-wise & Combined Activities in scope. | US-SAH-C5-006
16 | SHB-MAY-2026-013 | MD Sir | Dheeraj Motiyani | 04-Jun-2026 | Sahbhagita – Hyperlink: Village Name → Village Activity Document Preview popup. Two hyperlinks: (1) Village Name, (2) Village Activity Document (Reviewed) & Other Column names | Sahbhagita | Hyperlink – Village Activity Document Preview | Sahbhagita Report View | Village Name clickable hyperlink. On click: popup showing Village Activity Document with preview. Two separate hyperlink areas. | In Progress |  | Approved | Medium | Low | Popup with village activity doc preview. | US-SAH-C5-005
17 | SHB-MAY-2026-012 | MD Sir | Dheeraj Motiyani | 04-Jun-2026 | Sahbhagita – Future Scope: Photo Scan → Face/Background AI Model (CP Manager). Video option. Duplicate/Repeated photo detection → flag message to CP Manager. | Sahbhagita | AI Photo Verification – CP Manager | CP Manager Login | Photo/video capture at CP Manager login. AI model (face + background). Duplicate/repeated → show flag: “Already Used Before”. Future scope item. | Open |  | Pending | Low | High | Future scope. AI model (Photo Scan face + background). Video in scope. | US-SAH-C5-004
18 | CUBE-JUN-2026-005 | MD Sir | Dheeraj Motiyani | 16-Jun-2026 | Cube Testing – Cube ID get generated before image upload; Show rejected data to Contractor. | Cube Testing | Cube ID Generation & Rejected-Data Visibility | Contractor Login – Cube Inspection | Cube ID no longer depends on a successful image upload. Rejected inspection records surfaced back to Contractor login for correction and resubmission. | Completed | 16-Jun-2026 | Approved | Medium | Low | Delivered per MoM 16-Jun-2026, Point 2. | US-CUBE-C5-001, US-CUBE-C5-002
19 | MSTR-JUN-2026-006 | MD Sir | Dheeraj Motiyani | 18-Jun-2026 | Master – Lock Scheme Master, Village Master and OHT Master entries once linked to live transactions (Dhara, O&M Billing, Asset Mapping); GM (PIU) side all details lock. | Master | Scheme / Village / OHT Master – Entry Lock | GM PIU Login – Master Data | Record becomes read-only once tagged/used in a Dhara report, O&M Billing entry or Asset Mapping (BISAC) record. Further correction routed through a controlled change/relaxation flow rather than direct edit. | Open |  | Pending | High | High | Extends the Dhara approved-report lock principle (CR OMB/DHARA-MAY-2026-009) to the Master data layer. | US-MSTR-C5-001 (NEW)
20 | DHARA-MAY-2026-009 | MD Sir | Dheeraj Motiyani | 03-Jun-2026 | Dhara– Approved report data entry should NOT change once approved. UI lock for GM PIU. GM PIU/TL can ADD (not edit). GM can add new penalty point on Contractor bill. | Dhara | Approved Report Lock – Entry Freeze | GM PIU Login – Report Approval | Once GM PIU approves Dhara report, entry locked across all logins. GM PIU/TL can add info but cannot edit Contractor data. Penalty by GM is addable on top. | In Progress |  | Approved | High | High | GM can add new point (Penalty applied). Cannot edit existing Contractor-generated bill data. | US-DHR-C5-005
21 | DHARA-MAY-2026-021 | MD Sir | Dheeraj Motiyani | 01-Jun-2026 | O&M Billing – Mandatory options & go-live on 19th June across all logins: (1) Remark, (2) Photo Upload, (3) Forward, (4) Backward Options. | Dhara | Non-Mandatory Options – Go Live 19-Jun | All Logins – Dhara Module | mandatory options (Remark, Photo Upload, Forward, Backward) enabled on 19-Jun across all logins. These actions do NOT block submission if not filled. | In Progress | 19-Jun-2026 | Approved | High | Low | Go-live 19-Jun-2026 confirmed. Non-mandatory: Remark, Photo Upload, Forward, Backward. | US-DHR-C5-008 (NEW)
22 | (unassigned) | MD Sir | Dheeraj Motiyani | 21-Jul-2026 | O&M Billing – Landscape orientation for the O&M Abstract Bill report; wide tabular data was being cut off in portrait layout. | O&M Billing | Abstract Bill – Report Orientation | GM PIU Login – Report | Abstract Bill report page orientation changed from portrait to landscape so all columns fit without truncation. | Done |  | Pending | Medium | Low | Identified during July status review; resolved alongside Cube/Material Testing PDF fixes. | US-OM-C5-013
23 | (unassigned) | MD Sir | Dheeraj Motiyani | 21-Jul-2026 | Cube Testing & Material Testing – Second-loop re-inspection cycle after GM rejection: FE → GM → Contractor → GM → SQC/TPIA, re-routing to a new FE if reassigned. | Cube Testing / Material Testing | Re-Inspection Loop (2nd Cycle) | FE / GM / Contractor / SQC / TPIA Logins | On GM rejection, record must route back through the full chain in the correct order and preserve loop history; new FE assignment must re-route correctly. | Cube: Done / Material: In Progress |  | Pending | High | Medium | Cube Testing loop confirmed working as of 21-Jul-2026 status review; Material Testing loop still in progress. | US-CUBE-C5-004 (NEW), US-MAT-C5-001 (NEW)
24 | (unassigned) | MD Sir | Dheeraj Motiyani | 21-Jul-2026 | Cube Testing & Material Testing – Image upload should be optional (not mandatory) on the second RFI loop pass, since images were already captured on the first pass. | Cube Testing / Material Testing | Optional Image Upload – 2nd RFI Loop | FE / Contractor Logins | First RFI submission keeps image upload mandatory; second (re-inspection) pass makes it optional while retaining first-pass images. | Open |  | Pending | Medium | Low | Raised alongside the re-inspection loop CR; targeted for Sprint 18. | US-CUBE-C5-005 (NEW), US-MAT-C5-002 (NEW)

## CR Cross-Reference
Jal Rekha - Change Request Cross-Reference ¦ Cycle 4 (Jun-Jul 2026) ¦ Maps every logged CR to its user story ¦ Full CR descriptions, impact analysis, dates & remarks are in the 'CR Log - Full Details' sheet
CR Code | CR Title / Description | Linked User Story ID(s) | Coverage Note
OMB-JUN-2026-001 | Mandatory doc upload gate before forwarding bill from Draft | US-OMWF-C4-001 | Covered by existing Workflow story (Firm Bill Submission) — CR reconfirms this rule for the Draft state specifically.
OMB-MAY-2026-020 | Residual Pressure report format + Complaint Redressal relabeling | US-OM-C5-015 (NEW) | New story added.
OMB-JUN-2026-002 | Extended Complaint Redressal fields + Penalty Relaxation | US-OM-C5-016 (NEW) | New story added.
(unassigned) | Landscape orientation for O&M Abstract Bill report | US-OM-C5-013 | Already covered (Landscape Issue Fix).
OMB-MAY-2026-006 | O&M Billing workflow redesign (Firm -> ... -> MD) | US-OMWF-C4-001 to 016 | Fully covered by the dedicated O&M Billing Workflow US sheet (16 stories).
OMB-MAY-2026-002 | Contractor-side Abstract generation for RA billing | US-OM-C5-001, US-OM-C5-012 | Covered by existing Abstract Report Generation & Sahbhagita Generate Abstract stories.
OMB-JUN-2026-003 | Sahbhagita village/combined abstract report + RA numbering | US-SAH-C5-002, US-SAH-C5-006 | Covered by existing Village/Combined report + RA Bill numbering stories.
OMB-MAY-2026-005 | Merge ~19-20 bill documents into one PDF | US-OM-C5-004, US-OM-C5-011 | Already covered (Merge PDF stories).
OMB-MAY-2026-008 | Contractor mistakes visible to SQC/TL/GM + merged PDF | US-OM-C5-002, US-OM-C5-003 | Covered by existing Contractor Mistake Correction & Show All Records stories.
OMB-MAY-2026-015 | Document upload screen design by role | US-OMWF-C4-014 | Covered by existing Document Upload Hub story.
OMB-MAY-2026-003 | GST No. integration | US-OM-C5-017 (NEW) | New story added.
OMB-MAY-2026-001 | CDAC e-Sign integration (all parties) | US-ESIGN-C5-001, US-ESIGN-C5-002 | Already covered by e-Sign CDAC US sheet.
OMB-MAY-2026-004 | TL Recommendation Letter via E-Office | US-ESIGN-C5-003 | Already covered.
OMB-MAY-2026-014 | GM Pending Bills / Manage Bill view | US-OMWF-C4-013 | Already covered (Manage Bill story).
SHB-JUN-2026-004 | Sahbhagita Category->Activity report | US-SAH-C5-002, US-SAH-C5-003 | Already covered.
SHB-MAY-2026-007 | Multi-select bill dropdown + Withhold Bills | US-SAH-C5-006 | Already covered.
SHB-MAY-2026-013 | Hyperlink village name -> document preview | US-SAH-C5-005 | Already covered.
SHB-MAY-2026-012 | AI photo verification for CP Manager (future scope) | US-SAH-C5-004 | Already covered.
CUBE-JUN-2026-005 | Cube ID before upload + rejected data visibility | US-CUBE-C5-001, US-CUBE-C5-002 | Already covered.
(unassigned) | Material/Cube Testing 2nd-loop re-inspection cycle | US-CUBE-C5-004 (NEW), US-MAT-C5-001 (NEW) | New stories added for both modules.
(unassigned) | Optional image upload on 2nd RFI loop | US-CUBE-C5-005 (NEW), US-MAT-C5-002 (NEW) | New stories added for both modules.
MSTR-JUN-2026-006 | Lock Scheme/Village/OHT Master on live transaction link | US-MSTR-C5-001 (NEW) | New story added.
DHARA-MAY-2026-009 | Approved Dhara report data lock (add-only) | US-DHR-C5-005 | Already covered.
DHARA-MAY-2026-021 | Non-mandatory Remark/Photo/Forward/Backward | US-DHR-C5-008 (NEW) | New story added.

## O&M Billing US
Jal Rekha – Cycle 5 User Stories ¦ O&M Billing – Aaklan ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
O&M Billing – Abstract Report Generation | US-OM-C5-001 | High | As a GM and Contractor user, I want the Abstract Report auto-generated and available for download from the O&M Billing module so that billing summaries are formally captured without manual preparation. | AC1: Abstract Report is auto-generated on Save & Submit of the Contractor Bill; AC2: Report includes Gross O&M Bill, deduction breakdowns, and net payable amount; AC3: PDF download option is available from both GM (PIU) and Contractor login; AC4: Abstract PDF is included in the Bill PDF merge (19–20 documents per bill); AC5: Abstract is locked from editing after Final Bill Submission; AC6: Changes tested in staging and production | Done | Sprint 17 | 20
O&M Billing – Contractor Mistake Correction by SQC/TL → GM | US-OM-C5-002 | High | As a TL (SQC/CSC), I want the ability to add or edit bill data fields on behalf of the Contractor before forwarding to GM so that contractor data entry mistakes are corrected without returning the full bill. | AC1: TL (CSC) Add/Edit access is available for all editable bill data fields; AC2: Correction history is logged with TL user ID and timestamp for audit; AC3: GM (PIU) can view original and corrected values side by side; AC4: Show All Records across all login IDs (GM, SQC) is enabled per MoM requirement; AC5: Changes are tested end-to-end in UAT and production | Done | Sprint 17 | 16
O&M Billing – Show All Records on All IDs (GM, SQC) | US-OM-C5-003 | High | As a GM (PIU) user, I want all O&M billing records from all contractor/firm submissions visible on GM and SQC login so that I do not miss any bill regardless of which login it was submitted from. | AC1: GM (PIU) Manage page shows all bills across all schemes and firms assigned to the PIU; AC2: SQC login shows all bills forwarded to their role; AC3: Filter by PIU, Scheme, Firm Name, and Date Range is operational; AC4: Bills not yet actioned are highlighted with days pending; AC5: No cross-role data leakage; AC6: Changes deployed to production | Done | Sprint 17 | 8
O&M Billing – Merge PDF of All O&M Bill Documents | US-OM-C5-004 | High | As a GM and Contractor user, I want all O&M bill documents (approx. 19–20 documents per bill: GM, SQC, Firm, Form 27A, MB, Abstract, etc.) merged into a single PDF for a 3-month consolidated bill so that submission to higher authorities is a single file. | AC1: Bill PDF merge combines GM, SQC, Firm, Form 27A, MB, and Abstract as one consolidated PDF; AC2: For 3-month consolidated bill, only 1 combined PDF is generated (not per month); AC3: Other monthly documents are included per month within the same consolidated PDF; AC4: PDF merge service is tested for all bill types (RA Bill Q1–Q4); AC5: Merged PDF is downloadable from both GM and Contractor login | Done | Sprint 17 | 16
O&M Billing – Power Consumption: Contractor & GM Side Changes | US-OM-C5-005 | High | As a Contractor and GM user, I want the Power Consumption tab updated to include Contract Details (Basic Detail, Intermediate Raw Water Demand) and correct calculation logic so that electricity cost billing is accurate. | AC1: Contractor side – Generate Bill – Contract Details tab includes Basic Detail and Intermediate Raw Water Demand sections; AC2: Power Consumption calculation formula is updated per revised department specification; AC3: GM side shows consolidated power consumption total with correct component breakdowns; AC4: All fields are tested for correct formula output; AC5: Changes are deployed after UAT sign-off | In Progress | Sprint 17-18 | 24
O&M Billing – Two New Columns in Water Supply During Construction Bill | US-OM-C5-006 | Medium | As a GM user, I want two new columns added to the Water Supply During Construction Bill so that construction-phase water supply data is captured completely. | AC1: Two new columns are defined and implemented per department specification; AC2: Column headers and data types are approved by the department; AC3: Existing data is not impacted by the new column additions; AC4: Report display reflects the new columns; AC5: Changes tested in staging and production | In Progress | Sprint 17 | 8
O&M Billing – O&M Villages: Construction Approval Status | US-OM-C5-007 | Medium | As a GM user, I want O&M Villages to include villages where Water Supply During Construction is under consideration or approved so that construction-phase billing is inclusive and accurate. | AC1: Village master list in O&M Billing includes villages with Water Supply During Construction status = Under Consideration or Approved; AC2: Status column is visible on the O&M Villages page; AC3: Filter by status (Under Consideration / Approved) is available; AC4: Bill generated for such villages reflects correct construction-phase tariff; AC5: Changes are tested and deployed | In Progress | Sprint 18 | 8
O&M Billing – Aaklan Contractor Dispute: Dhara Data Discrepancy Window | US-OM-C5-008 | High | As a Contractor, I want a time-bound window to check Dhara meter reading data and raise a discrepancy before the O&M bill is finalised so that billing disputes are pre-empted and Dhara data is used as the authoritative source. | AC1: Contractor sees Dhara report data linked to the current RA Bill; AC2: Contractor can raise a discrepancy within a defined time window (e.g., 5 working days); AC3: Discrepancy flag is visible to GM and is resolved before bill finalisation; AC4: If no discrepancy is raised within the window, Dhara data is locked as the billing basis; AC5: Workflow tested end-to-end from Contractor dispute raise to GM resolution | In Progress | Sprint 18 | 16
O&M Billing – GM: Pump Transformer 10% Deduction Logic | US-OM-C5-009 | High | As a GM user, I want the consolidated bill to automatically apply a 10% deduction on the total amount when the Pump Transformer column is marked YES so that penalty deductions are system-enforced. | AC1: Pump Transformer YES/NO column is visible on the GM billing page; AC2: When YES is selected, a 10% deduction is automatically applied to the Total O&M Bill Amount; AC3: Deduction amount is displayed as a separate line item in the Abstract; AC4: GM cannot override the deduction without supervisor unlock; AC5: Deduction logic is tested with correct calculation verification in production | In Progress | Sprint 18 | 8
O&M Billing Workflow – e-Sign via CDAC (Contractor & GM) | US-OM-C5-010 | High | As a Contractor and GM user, I want all O&M Bill documents digitally signed using e-Sign via CDAC (Aadhaar-based) so that the bill submission process is legally compliant and paperless. | AC1: CDAC e-Sign API is integrated for FE and Contractor document signing; AC2: O&M Bill Submission Letter, Abstract, and Form 27A can be e-Signed by Contractor; AC3: GM can e-Sign the Signed Bill Sheet and Signed MB Sheet digitally; AC4: e-Sign flow: Mobile/Web → CDAC OTPLESS → Aadhaar-based e-Sign; AC5: e-Signed documents are stored with signature metadata (timestamp, Aadhaar hash); AC6: Note: System-generated bills do NOT require physical signature – e-Sign only | In Progress | Sprint 17-18 | 40
O&M Billing – GM (PIU) Login: Bill PDF (19–20 Docs) & 3-Month Consolidation | US-OM-C5-011 | High | As a GM (PIU) user, I want to view and download a consolidated Bill PDF comprising 19–20 documents for a 3-month bill cycle so that I can submit a single complete document package to GM (O&M). | AC1: Bill PDF includes: GM document, SQC document, Firm document, Form 27A, MB, Abstract and other supporting files; AC2: 3-month consolidated bill produces 1 merged PDF (not 3 separate); AC3: Each monthly document is correctly tagged with its month; AC4: Merged PDF opens correctly and all pages are legible; AC5: Download button is visible on GM (PIU) Manage page | Done | Sprint 17 | 12
O&M Billing – Sahbhagita Generate Abstract: Select RA Bill & Tag All | US-OM-C5-012 | Medium | As a Sahbhagita PM user, I want to generate an Abstract report by selecting a specific RA Bill number and tagging all activities to that bill so that Sahbhagita billing is linked to O&M billing cycles. | AC1: Select RA Bill dropdown is available on the Sahbhagita Abstract generation page; AC2: All activities under the scheme can be tagged to the selected RA Bill; AC3: Abstract PDF is generated per the RA Bill with activity-wise summary; AC4: Tagged activities cannot be re-tagged to a different RA Bill without deselection; AC5: Changes deployed and tested | Done | Sprint 17 | 8
O&M Billing – Landscape Issue Fix in O&M Bill Layout | US-OM-C5-013 | Medium | As a GM user, I want the Landscape orientation issue in the O&M Bill PDF resolved so that all pages print and display correctly without layout distortion. | AC1: O&M Bill PDF renders correctly in both landscape and portrait orientations as defined per page; AC2: No content is cut off or overflowing in the generated PDF; AC3: Fix is applied to all bill types (RA Q1–Q4 and consolidated); AC4: Bill PDF is verified in Chrome, Edge, and mobile PDF viewers; AC5: Changes deployed to production | Done | Sprint 17 | 4
O&M Billing – LGD Code Integration: LG Directory → MPSQC | US-OM-C5-014 | Medium | As a system admin, I want LGD Code integration from the LG Directory into MPSQC (Revenue Portal) so that O&M village and scheme data is aligned with national LGD codes. | AC1: LGD Code is fetched from LG Directory for each village used in O&M Billing; AC2: LGD Code column is visible in the O&M Village listing and reports; AC3: Revenue Portal LGD integration is tested for all districts; AC4: Mismatched or missing LGD codes are flagged for admin resolution; AC5: Changes deployed after data validation | In Progress | Sprint 18 | 8
O&M Billing - Residual Pressure & Complaint Redressal Report Format | US-OM-C5-015 | Medium | As a GM (PIU)/O&M user, I want the Residual Pressure report reformatted to the OM_RA_Bill_Report.pdf column layout and the Complaint Redressal screen relabeled with resolution status, so that pressure exceptions and complaint outcomes are captured in the department-approved format. | AC1: Residual Pressure report includes District, Block, GP, Village, Consumer Name, Mobile, Measured Pressure, Remark, Affected HSCs, Days, and Penalty calculation columns; AC2: Complaint Redressal screen adds an 'Is complaint resolved in this month?' indicator; AC3: Fields relabeled to Date Received / Date Resolved / Total Days Taken; AC4: Report matches RA/19/50/2025-26/Q1/1 reference format; AC5: Deployed and verified in production. | Done | Sprint 17 | 8
O&M Billing - Complaint Redressal: 48-Hour Flag & Penalty Relaxation | US-OM-C5-016 | Medium | As a GM (PIU)/O&M user, I want the Complaint Redressal sheet to capture the received date, auto-flag complaints unresolved beyond 48 hours, and support a Penalty Relaxation (Yes/No) field with document upload, so that penalty calculation and relaxation are auditable. | AC1: Complaint Received Date (to Contractor) field added; AC2: System auto-derives an 'Event above 48 hours' flag from received/resolved dates; AC3: Penalty Relaxation = Yes routes the relaxation letter into the GM (PIU) document set; AC4: Document upload available against sub-meter reading entry; AC5: Deployed and tested. | Done | Sprint 17 | 6
O&M Billing - GST Number Integration | US-OM-C5-017 | Medium | As a Contractor and GM (PIU) user, I want my GST number captured at the firm/contractor level and reflected on the bill PDF and abstract, so that generated bills are GST-compliant. | AC1: GST No. field added at contractor/firm master level; AC2: GST number appears on the generated bill PDF and abstract; AC3: Data source (manual entry vs. API validation) confirmed and applied consistently; AC4: Field validated for correct GST format; AC5: Changes tested and deployed. | Open | Sprint 18 | 8

## Sahbhagita US
Jal Rekha – Cycle 5 User Stories ¦ Sahbhagita ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Sahbhagita – RA Bill for ISA (replacing CP Manager) | US-SAH-C5-001 | High | As an ISA Manager user, I want RA Bill functionality moved from CP Manager to ISA Manager login so that ISA-specific billing is role-accurate and ISA can raise bills independently. | AC1: RA Bill functionality is available on the ISA Manager login page; AC2: ISA Manager can raise RA Bills only for their assigned schemes and activities; AC3: CP Manager retains Approved/Rejected/No Action view for ISA bills; AC4: Approved Bill generates RA Bill number (RA/1 to RA/12); AC5: ISA Bill history is visible to CP Manager with status indicators | Done | Sprint 17 | 12
Sahbhagita – Village-wise & Combined Activity Report | US-SAH-C5-002 | High | As a GM and ISA user, I want Sahbhagita reports available in both Village-wise and Combined Activity views so that activity tracking is possible at both individual village and aggregate levels. | AC1: Village-wise report shows all activities per village with document status (32 village-wise activities); AC2: Combined Activity report shows activity-wise count across all villages (22 combined activities); AC3: Both reports support filter by ISA, Scheme, Date Range, and Activity Category; AC4: Report columns include: S.No., Activity Name, Category, Status, Photos/Docs uploaded; AC5: Export to Excel is functional for both views | Done | Sprint 17 | 16
Sahbhagita – Master Activity List Update (22 Combined + 32 Village-wise) | US-SAH-C5-003 | High | As a system admin, I want the Sahbhagita master activity list updated to the finalised 22 Combined Activities and 32 Village-wise Activities so that all ISA submissions are mapped to the correct master. | AC1: Master activity table is updated with exactly 22 Combined Activities (Office Opening, Deployment HR, Inception Report, District/Block/Cluster Workshops, PRA, VAP, VWSC, Stationary, Social Media, Success Stories, MPR, Deliverable Report, etc.); AC2: 32 Village-wise activities are loaded (Jan Sabha, Gram Sabha, PRA, VAP, VWSC Formation, VWSC Account Opening, FTK Training, Har Ghar Jal Certification, Community Contribution, etc.); AC3: Old activity entries are archived not deleted; AC4: Mobile and web activity dropdowns reflect the updated master; AC5: Documents to upload are mapped per activity per master list | Done | Sprint 17 | 8
Sahbhagita – Photo Scan AI: Face & Background Detection (CP Manager Review) | US-SAH-C5-004 | Medium | As a CP Manager, I want an AI-based photo scan to detect duplicate face and background at the time of CP Manager review so that fraudulent or repeated activity submissions are flagged automatically. | AC1: AI model scans uploaded activity photos for face recognition and background similarity; AC2: Duplicate or already-used photo is flagged with a message to CP Manager before approval; AC3: CP Manager sees a flag badge on flagged submissions with a reason (Duplicate Face / Repeated Background); AC4: CP Manager can override the flag with mandatory remark if deemed genuine; AC5: AI scan is triggered on each photo upload at CP Manager review stage | In Progress | Sprint 18 | 20
Sahbhagita – Hyperlink: Village Name → Village Activity → Document Preview | US-SAH-C5-005 | Medium | As a GM and ISA user, I want a hyperlink on Village Name in the Sahbhagita report that drills down to Village Activity list and then opens Document Preview popup so that I can review all field evidence without leaving the report. | AC1: Village Name in the report is a clickable hyperlink; AC2: Click opens a popup with all activities completed in that village; AC3: Each activity row has a Document Preview link that opens the uploaded photo/doc inline; AC4: Back navigation returns to the previous report level; AC5: Hyperlink and popup work on both desktop and tablet view | Done | Sprint 17 | 8
Sahbhagita – RA Bill: RA(1) till RA(12) Withhold Bills | US-SAH-C5-006 | Medium | As a PM user, I want RA Bill numbers from RA(1) to RA(12) to be supported, with the ability to withhold specific RA Bills so that billing cycles are properly managed per ISA contract. | AC1: RA Bill numbering supports RA/1 through RA/12 for each ISA per scheme; AC2: Withhold Bill option is available on the ISA billing page for PM and CP Manager; AC3: Withheld bills are flagged in the billing list with Withheld status; AC4: Withheld bills cannot be included in payment processing; AC5: Withhold reason is mandatory and logged for audit | Done | Sprint 17 | 8
Sahbhagita – Customised Report (ISA – Mainly Contractor Convention) | US-SAH-C5-007 | Medium | As an ISA user, I want a customised Sahbhagita report primarily aligned to the contractor-convention billing structure so that ISA RA bills are correctly mapped to MPJN billing norms. | AC1: Customised report layout follows contractor billing convention with ISA-specific columns; AC2: Report includes: ISA Name, Scheme, RA Bill No., Activity Category, Activity Name, No. of Activities, Rate, Amount; AC3: Subtotals per category (Combined / Village-wise) are shown; AC4: Export to PDF and Excel is available; AC5: Report tested and approved by department | Done | Sprint 17 | 8
Sahbhagita – Save as Draft for Video, Image & Document (Mobile CR) | US-SAH-C5-008 | Medium | As an FE mobile user, I want Save as Draft functionality for activity submissions that include video, image, and document uploads so that field evidence can be captured in stages without losing partial submissions. | AC1: Save as Draft saves all currently entered fields and uploaded files without final submission; AC2: Drafted records appear in FE history list with Draft status badge; AC3: Video upload (up to 5 MB) is supported in draft; AC4: Image and document uploads are retained across draft sessions; AC5: Final submission is triggered only when the Submit button is pressed; AC6: Drafted records are synced to web portal on connectivity | Done | Sprint 17 | 8
Sahbhagita - Pagination on Approval Pages | US-SAH-C5-009 | Medium | As an ISA Manager/CP Manager, I want the Sahbhagita approval listing pages paginated, so that I can review and approve activity records in manageable batches instead of one long scrolling page. | AC1: Approval listing pages load records in pages, not a single continuous list; AC2: Page size and navigation controls are visible; AC3: Selecting a different page preserves applied filters; AC4: Deployed and verified in production. | Done | Sprint 17 | 6
Sahbhagita - FE Visibility Scoped to Assigned ISA | US-SAH-C5-010 | Medium | As an ISA user, I want to see only the Field Executives (FE) specifically mapped to my ISA, so that I don't have to sift through FE records belonging to other ISAs. | AC1: FE listing on ISA login is filtered to FEs mapped to that ISA only; AC2: FEs mapped to a different ISA are not visible/selectable; AC3: Mapping changes reflect on next login/refresh; AC4: Deployed and tested. | Done | Sprint 17 | 6
Sahbhagita - Self-Service Password Reset for ISA Login | US-SAH-C5-011 | Low | As an ISA user, I want a self-service password reset option on my login, so that I can regain access without waiting on the admin team. | AC1: 'Forgot/Reset Password' option available on the ISA login screen; AC2: Reset flow verifies registered mobile/email before allowing a new password; AC3: Successful reset invalidates the old password immediately; AC4: Deployed and tested. | Done | Sprint 17 | 4

## Dhara US
Jal Rekha – Cycle 5 User Stories ¦ Dhara (Reports, Corrections, Disputes) ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Dhara – Report Corrections (Approved Village MWSR, DWSR, OHT) | US-DHR-C5-001 | High | As a GM user, I want Dhara report corrections applied to Approved Village MWSR, DWSR, and OHT report pages so that report data is accurate and error-free for O&M billing purposes. | AC1: All report column values match source meter reading data; AC2: Approved Village MWSR shows correct metered and unmetered volumes per village; AC3: DWSR date-wise data displays without blank or null cells; AC4: OHT report corrections applied as per the DHARA_corrections specification; AC5: All corrected reports are deployed to production; AC6: Data approved days and entry counts are accurate | Done | Sprint 17 | 16
Dhara – Report Format Standardisation (27 May 2026 Format) | US-DHR-C5-002 | High | As a GM user, I want Dhara reports standardised to the approved format of 27 May 2026 so that all Dhara reports across all logins have consistent column layout, headers, and data ordering. | AC1: Report format follows the approved 27-May-2026 column structure; AC2: Column headers in both Hindi and English are applied consistently; AC3: All Dhara report pages (MWSR, DWSR, UFW, OHT-WTP, Bulk Consumer) reflect the new format; AC4: LGD Code column is included in village-level reports; AC5: Format changes deployed and verified in production; AC6: Contractor login Dhara reports are read-only (Vistrit data non-editable) | Done | Sprint 17 | 12
Dhara – Approved Reports & Contractor Dispute Window | US-DHR-C5-003 | High | As a Contractor user, I want to view GM-approved Dhara meter reading reports and raise a dispute within a defined time window so that incorrect meter data is challenged before O&M billing is finalised. | AC1: Contractor login shows GM-approved Dhara reports linked to the current RA Bill; AC2: Dispute/Discrepancy raise option is available for a defined window (configurable by admin); AC3: Contractor can enter a dispute remark and optionally upload supporting document; AC4: Dispute is visible to GM with status: Pending Resolution; AC5: Once the window closes without dispute, data is locked as approved billing basis; AC6: Dispute resolution by GM is logged with timestamp | In Progress | Sprint 17-18 | 16
Dhara – New Dhara Reports Visible on All Jal Rekha Logins | US-DHR-C5-004 | High | As a CGM, PMU, and higher official user, I want the new Dhara reports (MWSR, DWSR, OHT, UFW) visible on all Jal Rekha logins (not just GM) so that scheme water supply data is accessible at all governance levels. | AC1: Dhara reports are enabled for CGM, PMU, State-level, and higher official logins; AC2: Reports are role-filtered (CGM sees all PIUs; GM sees own PIU only); AC3: Public DWSR report is accessible without authentication; AC4: DWSR column hyperlink is clickable for drill-down to village-level data; AC5: Material, Cube, and Bharosa reports are also enabled for CGM and PMU logins (per MoM 9 June 2026) | Done | Sprint 17 | 8
Dhara – Dhara Entry Lock (Approved Data Should Not Change) | US-DHR-C5-005 | High | As a GM user, I want approved Dhara meter reading entries locked from further changes so that billing data integrity is maintained after GM approval. | AC1: Once GM approves a Dhara meter reading record, it is locked from all user edits; AC2: FE and PE cannot edit an approved record; AC3: Contractor sees approved data as read-only in their Dhara view; AC4: Any necessary correction post-approval requires a formal unlock request with supervisor sign-off; AC5: Lock status is visible on the record with approval date and GM user ID | Done | Sprint 17 | 8
Dhara – OHT/WTP/Intake Base Capacity Column in Report | US-DHR-C5-006 | Medium | As a GM user, I want OHT, WTP, and Intake Base Capacity columns added to the relevant Dhara reports so that water supply adequacy can be assessed against infrastructure capacity. | AC1: OHT Base Capacity column is added to the OHT-WTP Village Meter Survey report; AC2: WTP Capacity and Intake Capacity columns are added to relevant report views; AC3: Capacity data is sourced from the Master module asset records; AC4: Report load performance is not impacted by additional columns; AC5: Changes deployed to production and verified | In Progress | Sprint 18 | 8
Dhara - Approved Report Data Correction (Agreed with Kapil Sir) | US-DHR-C5-007 | High | As a GM (PIU) user, I want the previously identified data discrepancies in the Approved Report corrected as agreed with Kapil Sir, so that approved data accurately reflects the correct figures before it is used downstream for O&M billing. | AC1: Identified incorrect values in the Approved Report corrected per the agreed resolution; AC2: Correction applied consistently wherever the Approved Report data is consumed (Vistrit, Dhara, O&M Billing); AC3: Change is logged/traceable given the existing Approved Report Lock (US-DHR-C5-005); AC4: Verified in production as of 21-Jul-2026 status review. | Done | Sprint 18 | 8
Dhara - Non-Mandatory Remark, Photo Upload, Forward & Backward Options | US-DHR-C5-008 | High | As a user on any Jal Rekha login, I want the Remark, Photo Upload, Forward and Backward options in Dhara to be available but not mandatory, so that I can use them when relevant without being blocked from submitting. | AC1: Remark, Photo Upload, Forward and Backward options present on all applicable logins; AC2: None of the four actions blocks submission if left empty/unused; AC3: Change went live on 19-Jun-2026 as agreed; AC4: Confirmed working across all logins in production. | Done | Sprint 17 | 6

## Vistrit US
Jal Rekha – Cycle 5 User Stories ¦ Vistrit (Master Module) ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Vistrit – WTP Meter Mapping: New Columns (Date, Scheme, PIU, Meter Name) | US-VST-C5-001 | High | As a GM user, I want new columns – Date, Scheme, PIU, and Meter Name (e.g., Narela-WTP-01) – added to WTP Meter Mapping and Intake Mapping so that asset identification is standardised. | AC1: WTP Meter Mapping page includes new columns: Date Added, Scheme Name, PIU Name, Meter Name; AC2: Meter Name follows naming convention: <Scheme>-WTP-<Sequence> (e.g., Narela-WTP-01); AC3: Intake Mapping also includes Meter Name, No. of OHT Connections with WTP, District, Block, GP fields; AC4: Existing mapping records show default/blank for new columns without breaking existing data; AC5: Changes tested and deployed | Done | Sprint 17 | 8
Vistrit – OTP Verification for GM Edit/Delete on Scheme, OHT, Bulk Master | US-VST-C5-002 | High | As a system admin, I want OTP verification applied to GM login when performing Edit or Delete operations on Scheme Village Mapping, OHT Mapping, and Bulk Consumer Mapping so that master data changes are authenticated. | AC1: OTP is sent to the registered GM mobile number when Edit or Delete is clicked on Scheme, OHT, or Bulk Master; AC2: OTP expires in 5 minutes; AC3: Edit/Delete is blocked until OTP is correctly entered; AC4: OTP verification log is maintained with action, user ID, and timestamp; AC5: OTP bypass is not available; failed OTP blocks action for 30 minutes | Done | Sprint 17 | 8
Vistrit – Scheme Village Mapping: Testing/Permitted Field Validation & Census Population | US-VST-C5-003 | Medium | As a data admin, I want validation applied to Testing and Permitted fields in Scheme Village Mapping and Census Population left open at all levels so that mapping data quality is enforced without blocking census entries. | AC1: Testing field accepts only numeric values within a defined range; AC2: Permitted field validation prevents duplicate or conflicting entries; AC3: Census Population field remains editable at all user levels (GP, Block, District, PIU); AC4: Validation error messages are displayed inline without page reload; AC5: Changes are backward-compatible with existing mapping records | Done | Sprint 17 | 6
Vistrit – OHT Deactivate Bug Fix (OHT Not Visible in FE Login) | US-VST-C5-004 | High | As an FE user, I want OHTs that are deactivated in Vistrit but active in FE login to be correctly displayed so that field engineers do not miss active OHTs due to a master data deactivation bug. | AC1: Root cause of the OHT visibility bug (deactivate entries in Vistrit causing OHTs to not appear in FE login) is identified and documented; AC2: Fix ensures that only explicitly deactivated OHTs with full deactivation workflow are hidden from FE login; AC3: All OHTs affected by the bug are re-activated or correctly categorised; AC4: Regression test confirms no new OHTs are incorrectly hidden; AC5: Fix is deployed to production | Done | Sprint 17 | 8
Vistrit – WTP Meter Naming Convention Standardisation | US-VST-C5-005 | Low | As a system admin, I want WTP Meter names standardised to a consistent naming convention (e.g., Narela-WTP-01) across the Vistrit Master module so that meter asset identification is uniform. | AC1: Naming convention rule is documented: <Scheme/Location>-WTP-<Sequence Number>; AC2: Existing meter names are updated in bulk where they do not follow the convention; AC3: New meter creation enforces the naming convention via validation; AC4: Updated names are reflected in all Dhara reports and OHT-WTP survey forms; AC5: Changes are tested and deployed | Done | Sprint 17 | 4

## FHTC Parinam US
Jal Rekha – Cycle 5 User Stories ¦ FHTC Parinam ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
FHTC Parinam – Nasamajh Family Head ID & Add Connection | US-FHTC-C5-001 | High | As a Contractor user, I want to access Family Head ID for Nasamajh (uncategorised) families with an upper cap of 3 household connections per family and add tap connections for them so that all eligible households including uncategorised families are covered. | AC1: Nasamajh (uncategorised) family records are accessible via Family Head ID on Contractor login; AC2: Upper cap of 3 connections per Nasamajh family is enforced at submission; AC3: Add Connection flow: 4 → 1 → 4-8 → 2 (as per handwritten specification); AC4: Family Member ID is auto-populated once Family Head ID is entered; AC5: Connections added for Nasamajh families are visible in FE and GM reports | In Progress | Sprint 17 | 16
FHTC Parinam – FE Name Shown in Reports | US-FHTC-C5-002 | Medium | As a GM user, I want the FE (Field Engineer) name to appear in FHTC Parinam reports so that inspection accountability is traceable at the individual FE level. | AC1: FE Name column is added to FHTC Parinam report for GM login; AC2: FE Name is sourced from the inspection record's user ID mapping; AC3: Report filter by FE Name is available; AC4: Export to Excel includes FE Name column; AC5: Changes deployed to production | Done | Sprint 17 | 4
FHTC Parinam – Contractor Search Option | US-FHTC-C5-003 | Medium | As a Contractor user, I want a search option on the FHTC Parinam Contractor login page so that I can locate specific tap connection records quickly across large datasets. | AC1: Search is available by Village Name, GP Name, Block, and Connection Status; AC2: Search results load within 3 seconds; AC3: Partial search (minimum 3 characters) is supported; AC4: Search state is retained on page navigation; AC5: Changes deployed to production | Done | Sprint 17 | 4
FHTC Parinam – Samagra API Integration for Household Data | US-FHTC-C5-004 | High | As a system developer, I want Samagra API integrated with FHTC Parinam so that household data (Family Head ID, Member ID, address) is auto-fetched from the state Samagra citizen database without manual entry. | AC1: Samagra API endpoint is integrated and credentials configured; AC2: Family Head ID search returns household data from Samagra automatically; AC3: Family Member IDs are auto-populated from Samagra for the selected Head ID; AC4: API response handles error cases (no record found, API timeout) gracefully; AC5: Integration is tested for all 7 zones; AC6: API call logs are maintained for audit | In Progress | Sprint 17-18 | 24
FHTC Parinam - Multiple Surveys per Samagra ID | US-FHTC-C5-005 | Medium | As an FE/GM (PIU) user, I want the system to allow more than one survey to be recorded against the same FHTC Samagra ID, so that genuine repeat/revisit surveys aren't blocked by a false duplicate restriction. | AC1: System permits a second (and subsequent) survey entry for the same Samagra ID without error; AC2: All surveys against that ID are retrievable and distinguishable (by date/sequence) in reports; AC3: UAT confirms no unintended duplicate-record side effects in existing reports; AC4: Marked UAT Done as of 21-Jul-2026 status review. | UAT Done | Sprint 18 | 8

## BISAC Integration US
Jal Rekha – Cycle 5 User Stories ¦ BISAC / NIC Asset Integration ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
BISAC – NIC Asset ID Mapping (Asset & Junction Mapping) | US-BISAC-C5-001 | High | As a system admin, I want NIC Asset IDs integrated with BISAC for Junction-to-Junction Map, Asset Mapping, and Pipeline Tracking so that Jal Rekha asset data is aligned with the national GIS system. | AC1: NIC Asset ID is fetched and stored for each OHT, WTP, and Pipeline asset in the Jal Rekha system; AC2: Asset ID mapping covers: 1 Scheme = 250 OHTs, 175 × 250 = mapping capacity; AC3: Junction-to-Junction map uses BISAC data for pipeline route visualisation; AC4: OHT Asset mapping is confirmed as already completed; AC5: Pipeline Asset mapping is initiated per the BISAC specification | In Progress | Sprint 18 | 24
BISAC – Pipeline Mapping with BISAC Junction Data | US-BISAC-C5-002 | High | As a project manager, I want pipeline asset data mapped using BISAC Junction-to-Junction track data so that complete pipeline route and network is visualised on the Jal Rekha GIS portal. | AC1: BISAC junction data is consumed via API for pipeline route mapping; AC2: Pipeline segments are displayed on the Jal Rekha GIS map with correct coordinates; AC3: Junction points are marked with BISAC Asset IDs; AC4: Pipeline map is accessible to CGM, PMU, and GM logins; AC5: OHT and pipeline data layers can be toggled on the map view | In Progress | Sprint 18 | 20
BISAC – Village LGD Code Integration (Village without LGD = Habitation) | US-BISAC-C5-003 | Medium | As a data admin, I want BISAC LGD Code logic applied so that villages without an LGD Code are automatically classified as Habitations so that data quality is maintained across BISAC and LGD master sources. | AC1: Logic: If a village record does not have an LGD Code, it is classified as a Habitation; AC2: Habitation records are displayed with their parent village name; AC3: LGD Code field is visible in village master and all Dhara/SVS reports; AC4: Village master update script correctly classifies all existing records; AC5: Future entries enforce LGD Code entry or Habitation flag | Done | Sprint 17 | 8

## e-Sign CDAC US
Jal Rekha – Cycle 5 User Stories ¦ e-Sign via CDAC (Aadhaar) ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
e-Sign CDAC – FE e-Sign via Mobile/Web (All Logins) | US-ESIGN-C5-001 | High | As a Field Engineer, I want to e-Sign inspection records and reports using CDAC Aadhaar-based e-Sign so that digital signatures are legally valid and the system is fully paperless. | AC1: CDAC e-Sign API is integrated at FE login for all modules (Anusharavan, Cube Testing, Material Testing, Bharosa); AC2: e-Sign flow: FE selects document → CDAC OTPLESS → Aadhaar OTP on registered mobile → e-Sign applied; AC3: e-Signed document is stored with certificate metadata (timestamp, Aadhaar hash); AC4: e-Sign is triggered on final inspection submission; AC5: e-Sign works on both Mobile App and Web browser | In Progress | Sprint 17-18 | 30
e-Sign CDAC – Contractor/Firm e-Sign for O&M Bill Documents | US-ESIGN-C5-002 | High | As a Contractor user, I want to e-Sign the O&M Bill Submission Letter, Abstract, and Tax Invoice using CDAC e-Sign so that bill submission is legally compliant without physical signatures. | AC1: CDAC e-Sign is available for Contractor on: Submission Letter, Abstract, and Tax Invoice; AC2: e-Sign is mandatory before the Forward button to GM (PIU) is activated; AC3: Note: System-generated bill does not require separate physical signature; AC4: e-Signed documents are stored and downloadable by all downstream workflow users; AC5: e-Sign failure handling shows a clear error message and retry option | In Progress | Sprint 17-18 | 20
e-Sign CDAC – TL (PMC) Recommendation Letter (E-Office Generated) | US-ESIGN-C5-003 | Medium | As a TL (PMC) user, I want to generate and e-Sign the Recommendation Letter as an E-Office generated document via CDAC so that the PMC review is formally certified. | AC1: Recommendation Letter template is pre-defined and auto-filled from bill data; AC2: TL (PMC) e-Signs the letter via CDAC flow; AC3: E-Office document tracking number is attached to the e-Signed letter; AC4: Signed letter is attached to the bill package and visible to all downstream users; AC5: E-Office integration is tested for all 7 regional offices | In Progress | Sprint 18 | 16
e-Sign CDAC – TL (SQC) & TL (PMC) Account Office Jal Rekha Integration | US-ESIGN-C5-004 | Medium | As a TL (SQC) and TL (PMC) user, I want CDAC e-Sign integrated with Jal Rekha Account Office workflow so that billing documents are routed and signed digitally through the Account Office system. | AC1: TL (SQC) can e-Sign their recommendation via CDAC integrated with the Jal Rekha Account Office; AC2: TL (PMC) can e-Sign via CDAC and the signed document is logged in the Account Office Jal Rekha trail; AC3: Both TL (SQC) and TL (PMC) e-Sign actions are visible in the Bill Document Hub; AC4: Integration is tested end-to-end for a complete bill cycle; AC5: e-Sign audit log includes role, user ID, timestamp, and Aadhaar hash | In Progress | Sprint 18 | 16

## Anusharavan US
Jal Rekha – Cycle 5 User Stories ¦ Anusharavan (June CR) ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Anusharavan – Multi-Date in Report: FE RFI Submission Date & Block Name | US-ANS-C5-001 | High | As a GM user, I want the Anusharavan RFI report to include multiple dates (FE RFI Submission Date alongside inspection date) and Block Name column so that inspection traceability is enhanced. | AC1: FE RFI Submission Date column is added to the Anusharavan report; AC2: Block Name column is added to the report; AC3: Both columns are sortable and filterable; AC4: Excel export includes new columns; AC5: Changes deployed to production and verified | Done | Sprint 17 | 8
Anusharavan – OHT Search Option During RFI | US-ANS-C5-002 | Medium | As a Contractor and FE user, I want an OHT search option during the RFI creation process so that the correct OHT can be quickly identified without scrolling through large dropdown lists. | AC1: OHT search box is available on the RFI creation form; AC2: Search accepts partial OHT name or OHT ID; AC3: Results display within 2 seconds; AC4: Selected OHT auto-populates related fields (Scheme, Village, Location); AC5: Search works offline for the last-synced OHT list on mobile | Done | Sprint 17 | 6
Anusharavan – Remove Mandatory GPS/Village for Intake, WTP, MBR, RWPM, CWPM | US-ANS-C5-003 | Medium | As a Contractor user, I want District, Block, GP, and Village selection to be non-mandatory for Intake, WTP, MBR, RWPM, and CWPM components during RFI creation so that non-site-specific components can be registered without location barrier. | AC1: Mandatory location fields (District, Block, GP, Village) are made optional for: Intake, WTP, MBR, RWPM, CWPM components; AC2: Validation message is updated to indicate optional nature; AC3: Other component types still enforce mandatory location; AC4: Changes applied to both web and mobile RFI forms; AC5: Regression tested to confirm no impact on site-specific components | Done | Sprint 17 | 4

## Cube Testing US
Jal Rekha – Cycle 5 User Stories ¦ Cube Testing (June CR) ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Cube Testing – Show Rejected Data to Contractor | US-CUBE-C5-001 | High | As a Contractor user, I want to see rejected cube test records in my login so that I can re-submit or address the rejection reason without contacting GM separately. | AC1: Rejected cube test records are visible in Contractor login with Rejected status badge; AC2: Rejection reason entered by GM/SQC is displayed on the record; AC3: Contractor can raise a re-inspection request from the rejected record; AC4: Rejected records history is maintained and not deletable; AC5: Changes deployed to production | Done | Sprint 17 | 6
Cube Testing – Cube ID Generated Before Image Upload | US-CUBE-C5-002 | High | As a Contractor user, I want the Cube Test ID to be generated first before uploading images so that images are linked to a confirmed Cube ID and cannot be submitted without a valid record. | AC1: System generates a Cube Test ID upon initial record creation (before image upload); AC2: Image upload form shows the generated Cube Test ID as reference; AC3: Images uploaded are linked to the specific Cube Test ID in the database; AC4: If session expires, partially uploaded images are discarded and Cube ID remains pending; AC5: Changes tested and deployed | Done | Sprint 17 | 6
Cube Testing – Filter Bed Sub-Component Under WTP | US-CUBE-C5-003 | Low | As a Contractor user, I want 'Filter Bed' added as a sub-component under the WTP component in the Cube Testing module so that filter bed quality testing is properly recorded. | AC1: Filter Bed is added to the sub-component master under WTP; AC2: Dropdown displays Filter Bed as an option when WTP is selected as the primary component; AC3: Existing cube test records are not affected; AC4: Mobile app reflects the new sub-component; AC5: Changes deployed to production | Done | Sprint 17 | 4
Cube Testing - Re-Inspection Loop (2nd Loop after GM Rejection) | US-CUBE-C5-004 | High | As an FE/GM/Contractor/SQC/TPIA user, I want a working re-inspection loop so a rejected cube record cycles back through FE to GM to Contractor, back to GM, then SQC/TPIA, then to a newly assigned FE if applicable, so that corrections are fully re-verified through the quality chain. | AC1: Rejected record re-enters the workflow at Contractor correction rather than restarting; AC2: Each subsequent reviewer sees the resubmitted record with prior rejection history intact; AC3: If a new FE is assigned mid-cycle, record routes correctly to that FE; AC4: Loop completes and record reaches Approved status once all stages clear; AC5: Confirmed Done as of 21-Jul-2026 status review. | Done | Sprint 18 | 16
Cube Testing - Optional Image Upload on Second RFI Loop | US-CUBE-C5-005 | Medium | As an FE/Contractor user, I want image upload to be optional (not mandatory) on the second RFI loop pass for Cube Testing, so that minor re-inspection corrections aren't blocked by recapturing images already provided the first time. | AC1: First RFI submission keeps image upload mandatory (unchanged); AC2: Second (re-inspection) RFI loop pass makes image upload optional; AC3: Previously uploaded images from the first pass remain attached and visible; AC4: Deployed and tested. | Done | Sprint 18 | 6

## SVS US
Jal Rekha – Cycle 5 User Stories ¦ SVS Water Supply Monitoring (June CR) ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
SVS – Bilingual Conversion (Hindi/English) for Water Supply Entry Page | US-SVS-C5-001 | High | As an MP government user, I want the SVS Daily Water Supply entry page to support bilingual labels (Hindi and English) and report column headers to be in Hindi so that GP-level users can operate in their native language. | AC1: All SVS form field labels are bilingual (English label above, Hindi below); AC2: Report column headers are displayed in Hindi for the SVS dashboard and exports; AC3: Language toggle is available for users who prefer English-only interface; AC4: Hindi rendering is tested on Chrome, Firefox, and Android mobile; AC5: MP Shasan standard Hindi fonts are applied | Done | Sprint 17 | 8
SVS – Login-Specific District, Block, GP Auto-Selection | US-SVS-C5-002 | High | As a GP or Block-level user, I want District, Block, and GP pre-selected according to my login credentials so that I do not need to manually navigate the location hierarchy on every submission. | AC1: On login, system identifies user's assigned District, Block, and GP from user profile; AC2: District, Block, and GP fields are pre-filled and locked for GP-level users; AC3: Block-level users see their Block pre-filled but can change Village within scope; AC4: District-level users can view all Blocks and GPs; AC5: Scope restriction is tested for all login levels | Done | Sprint 17 | 4
SVS – Additional Reason for NO Supply & Spelling Correction | US-SVS-C5-003 | Medium | As a GP user, I want one additional reason option added to the NO supply dropdown and any spelling errors in existing reason options corrected so that supply failure recording is accurate. | AC1: New reason option is added to the NO supply Reason dropdown; AC2: Existing reason option spelling errors are corrected in both English and Hindi; AC3: New reason is stored in the master table and reflected in all reports; AC4: Mobile app dropdown reflects the updated reasons list; AC5: Changes deployed to production | Done | Sprint 17 | 4
SVS – Remove JJM ID and Village Status Fields | US-SVS-C5-004 | Medium | As a PHE department stakeholder, I want the JJM ID field and Village Status field removed from the SVS Daily Water Supply monitoring form so that the form is simplified to current operational requirements. | AC1: JJM ID field is removed from the SVS data entry form, reports, and Excel exports; AC2: Village Status field is removed from the form; AC3: Database columns are retained for historical records but not exposed in UI; AC4: Historical data remains accessible via admin view; AC5: Changes deployed and regression tested | Done | Sprint 17 | 4

## Vistrit OTP US
Jal Rekha – Cycle 5 User Stories ¦ Vistrit OTP & Validation ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Vistrit – OTP Verification on Scheme/OHT/Bulk Master (GM Edit/Delete) | US-VST-OTP-C5-001 | High | As a GM user, I want OTP verification required before performing Edit or Delete on Scheme Village Mapping, OHT Mapping, and Bulk Consumer Master so that unauthorised master data changes are prevented. | AC1: Edit and Delete buttons on Scheme, OHT, and Bulk Master trigger an OTP request; AC2: OTP is sent to the GM's registered mobile number via SMS; AC3: OTP is valid for 5 minutes; AC4: OTP verification failure blocks action for 30 minutes after 3 failed attempts; AC5: All OTP-triggered actions are logged with user ID, timestamp, and action type | Done | Sprint 17 | 8
Vistrit – Scheme Village Mapping: Duplicate Village Validation | US-VST-OTP-C5-002 | Medium | As a data admin, I want duplicate village mapping validation applied across schemes so that a village is not accidentally mapped to multiple schemes resulting in data conflicts. | AC1: On adding a village to a scheme, system checks for existing mapping in other schemes; AC2: If a duplicate is found, a warning is shown with the existing scheme name; AC3: Admin can override with explicit confirmation and reason; AC4: Duplicate validation does not block habitation-level mappings within the same village; AC5: Changes deployed and tested | Done | Sprint 17 | 4

## CMMI Doc US
Jal Rekha – Cycle 5 User Stories ¦ CMMI Documentation ¦ June 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
CMMI Doc – Cycle 5 Data Collection (June 2026) | US-CMMI-C5-001 | High | As a SEPG team member, I want to initiate and maintain data collection for Cycle 5 (June–July 2026) so that project performance metrics are captured for CMMI Level 5 audit preparation. | AC1: Cycle 5 data collection sheet is created with all required fields (Requirement, Design, Coding, Code Review, Testing Efforts); AC2: Data is collected and recorded for all Cycle 5 modules (O&M Billing, Sahbhagita, Dhara, Vistrit, FHTC, BISAC, e-Sign, SVS); AC3: Defect data is captured across all review stages; AC4: Productivity, DRE, and Cycle Time are calculated per CMMI L5 formula; AC5: Data is validated before submission to SEPG Head | In Progress | Sprint 17-18 | 40
CMMI Doc – Streamline Documentation for Cycle 5 Modules | US-CMMI-C5-002 | High | As a quality manager, I want CMMI documentation streamlined for all Cycle 5 modules (O&M Billing Workflow, Sahbhagita, Dhara, e-Sign, BISAC) so that audit artifacts are consistent and complete for CMMI L5 standards. | AC1: Documentation is completed for O&M Billing Workflow, Sahbhagita, Dhara, and BISAC modules per CMMI L5 standards; AC2: User Stories, FRS, SRS, and Design documents are updated for Cycle 5; AC3: Documents are archived in the SVN repository with correct version tagging; AC4: Internal review by SEPG Head is completed before external audit; AC5: Promote activity is completed for CMMI L5 Benchmark tracking | In Progress | Sprint 17-18 | 60

## O&M Billing Workflow US
Jal Rekha – Cycle 4 User Stories ¦ O&M Billing Workflow Module (Multi-Level Approval Chain) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
O&M Billing Workflow – Firm Bill Submission | US-OMWF-C4-001 | High | As a Firm/Contractor, I want to generate the O&M bill along with submission letter and supporting documents (electricity bills, PHE test reports, tax invoice) so that the billing process can begin with complete documentation. | AC1: Firm can generate Bill on the Contractor login screen via Bill Workflow option; AC2: Submission letter is uploaded along with supporting documents (electricity bills, PHE test reports, etc.); AC3: Tax Invoice document is mandatorily uploaded before submission; AC4: All uploaded documents support View PDF and Download actions; AC5: Bill cannot be forwarded to GM (PIU) until mandatory documents are uploaded; AC6: Forward button becomes active only after Bill Generated + Submission Letter + Tax Invoice are completed | Done | Sprint 12
O&M Billing Workflow – GM (PIU) Forward to TL (CSC) | US-OMWF-C4-002 | High | As a GM (PIU), I want to review the firm-submitted bill and forward it to TL (CSC) so that the bill proceeds for committee-level scrutiny. | AC1: GM (PIU) Manage page displays list of pending bills submitted by Firm; AC2: GM (PIU) can view all uploaded documents (Firm Submission Letter, Tax Invoice, etc.) before forwarding; AC3: Forward to TL (CSC) action is available on each pending bill row; AC4: Bill status changes to 'Forwarded to TL (CSC)' after action; AC5: GM (PIU) cannot edit firm-uploaded documents, only forward or hold | Done | Sprint 12
O&M Billing Workflow – TL (CSC) Review & Recommendation | US-OMWF-C4-003 | High | As a TL (CSC/SQC), I want to add or edit bill data and provide a recommendation letter so that GM (PIU) receives a vetted bill for final data entry. | AC1: TL (CSC) screen lists all bills forwarded by GM (PIU) as Pending; AC2: TL (CSC) can Add/Edit each data field of the bill; AC3: Recommendation Letter upload is mandatory before forwarding back to GM (PIU); AC4: Edit history of TL (CSC) changes is logged for audit; AC5: Bill status updates to 'Reviewed by TL (CSC)' after recommendation is uploaded | Done | Sprint 12-13
O&M Billing Workflow – GM (PIU) Final Data Entry & Signed Document Upload | US-OMWF-C4-004 | High | As a GM (PIU), I want to add/edit final bill data and upload the signed MB, signed abstract, signed bill sheet, Form 27A, and relaxation letter so that the bill is certified and ready for O&M escalation. | AC1: GM (PIU) can Add/Edit each data field after TL (CSC) recommendation; AC2: System auto-generates Abstract and Monthly Bill (MB) sheet for GM (PIU) to download, sign, and re-upload; AC3: Signed Bill Sheet upload is validated as duly signed by GM (PIU); AC4: Signed Form 27A upload is mandatory; AC5: Signed relaxation letter upload is optional/conditional, with a flag 'Relaxation Applicable (Yes/No)'; AC6: GM (PIU) cannot forward to GM (O&M) until all four signed documents are uploaded | Done | Sprint 13
O&M Billing Workflow – GM (O&M) to TL (PMC) Routing | US-OMWF-C4-005 | High | As a GM (O&M), I want the bill forwarded from GM (PIU) to be routed to TL (PMC) for recommendation with supporting documents so that the bill undergoes project management consultant review. | AC1: GM (O&M) Manage page lists all bills received from GM (PIU); AC2: GM (O&M) can forward the bill to TL (PMC) without data edit rights at this stage; AC3: TL (PMC) receives the bill in their pending queue automatically; AC4: TL (PMC) uploads a Recommendation Letter with any supporting documents; AC5: Bill status updates to 'Reviewed by TL (PMC)' after recommendation is submitted | Done | Sprint 13
O&M Billing Workflow – DGM (O&M) Review | US-OMWF-C4-006 | High | As a DGM (O&M), I want to review bills recommended by TL (PMC) so that I can validate billing accuracy before passing the order. | AC1: DGM (O&M) Manage page lists bills with TL (PMC) recommendation attached; AC2: DGM (O&M) can view all historical documents from Firm, GM (PIU), TL (CSC), and TL (PMC) stages; AC3: DGM (O&M) can Approve or Hold the bill with remarks; AC4: On Approve, bill proceeds to GM (O&M) for Pass Order upload; AC5: On Hold, bill returns to TL (PMC) with DGM remarks visible | Done | Sprint 13-14
O&M Billing Workflow – GM (O&M) Pass Order & HO Letter Upload | US-OMWF-C4-007 | High | As a GM (O&M), I want to upload the Pass Order copy (signed by DGM O&M) and the signed letter received from HO so that the bill is certified for regional CGM-level processing. | AC1: GM (O&M) can upload Pass Order copy signed by DGM (O&M); AC2: GM (O&M) can upload signed letter received from Head Office (HO); AC3: Both documents are mandatory before forwarding to CGM; AC4: System validates file format and size for each uploaded document; AC5: Bill status updates to 'Forwarded to CGM' after both uploads are completed | Done | Sprint 14
O&M Billing Workflow – CGM Regional Office Routing | US-OMWF-C4-008 | High | As a CGM (Regional Office user), I want to receive and process O&M bills routed from GM (O&M) for my respective region so that regional-level billing escalation is managed correctly. | AC1: CGM login is mapped to one of seven regional offices: Bhopal, Gwalior, Jabalpur, Rewa, Sagar, Indore, Ujjain; AC2: CGM Manage page filters and displays only bills belonging to the CGM's mapped region; AC3: CGM can view the complete document trail from Firm through GM (O&M); AC4: CGM can forward the bill to CA for financial review; AC5: Region-wise bill count is visible on the CGM dashboard | Done | Sprint 14
O&M Billing Workflow – CA Financial Review | US-OMWF-C4-009 | High | As a CA (Chartered Accountant/Finance reviewer), I want to review the financial accuracy of bills forwarded from CGM so that billing figures are validated before CFO sign-off. | AC1: CA Manage page lists all bills forwarded by CGM; AC2: CA can view bill amount breakdown, deductions, and tax details; AC3: CA can Approve or flag discrepancies with remarks; AC4: Flagged bills are routed back to CGM with CA remarks; AC5: Approved bills proceed automatically to CFO queue | Done | Sprint 14
O&M Billing Workflow – CFO Sign-off | US-OMWF-C4-010 | High | As a CFO, I want to review CA-approved bills and provide financial sign-off so that the bill is cleared for Project Director review. | AC1: CFO Manage page lists CA-approved bills pending sign-off; AC2: CFO can view the consolidated financial summary and all upstream documents; AC3: CFO Approve action forwards bill to P.D. automatically; AC4: CFO Hold action returns the bill to CA with remarks; AC5: CFO sign-off timestamp is logged for audit trail | Done | Sprint 15
O&M Billing Workflow – P.D. Review | US-OMWF-C4-011 | High | As a Project Director (P.D.), I want to review CFO-approved bills so that I can endorse them for final MD approval. | AC1: P.D. Manage page lists CFO-approved bills pending review; AC2: P.D. can view the full multi-level approval trail with all signed documents; AC3: P.D. Approve action forwards bill to MD for final approval; AC4: P.D. Hold/Reject action routes bill back to CFO with remarks; AC5: P.D. dashboard shows bill ageing (days pending at each stage) | Done | Sprint 15
O&M Billing Workflow – MD Final Approval | US-OMWF-C4-012 | High | As an MD (Managing Director), I want to give final approval on bills that have passed through the complete approval chain so that payment processing can be initiated. | AC1: MD Manage page lists P.D.-endorsed bills pending final approval; AC2: MD can view the complete end-to-end document and approval trail from Firm through P.D.; AC3: MD Approve action marks the bill as 'Finally Approved' and locks it from further edits; AC4: MD Reject action returns the bill to P.D. with mandatory remarks; AC5: Finally Approved bills are flagged for downstream payment/accounting integration | Done | Sprint 15
O&M Billing Workflow – Manage Bill (View Pending Bills) | US-OMWF-C4-013 | High | As any workflow-stage user (GM PIU, TL CSC, GM O&M, TL PMC, DGM O&M, CGM, CA, CFO, P.D., MD), I want a 'Manage' page showing all bills pending at my login so that I can take timely action without searching across modules. | AC1: Manage page is available at every workflow stage login with a consistent UI pattern; AC2: View Pending Bills list shows Bill No., Firm Name, Scheme, Submission Date, and Days Pending; AC3: Each row provides View, Edit/Add, and Forward/Recommend actions as applicable to that role; AC4: List supports filter by PIU, Scheme, and Date Range; AC5: Resolution/Recommendation letter status (Uploaded/Pending) is visible as a column | Done | Sprint 13-14
O&M Billing Workflow – Document Upload Hub (Multi-Document Per Bill) | US-OMWF-C4-014 | High | As any workflow user, I want a consolidated document section on each bill (Firm Submission Letter, SQC/TL Recommendation, PIU Recommendation, Signed Abstract, Signed Monthly Bill Sheet, Tax Invoice, Form 27A, Third Party Water Quality Test Report, Signed Scanned MB, and Any Other Documents) so that all certifications are traceable in one place. | AC1: Each document type has independent Upload, Download, and View PDF actions; AC2: Third Party Water Quality Test Report and Any Other Documents sections support multiple file uploads per bill; AC3: Any Other Documents section allows custom document Name entry alongside upload; AC4: Remark field is available against document sections requiring clarification; AC5: Uploaded document history (who uploaded, when) is logged and viewable by all downstream roles | Done | Sprint 13
O&M Billing Workflow – GM (PIU) Login Screen Structure | US-OMWF-C4-015 | Medium | As a GM (PIU) user, I want the O&M login dashboard organised into Contractor/Firm view, View Pending Bills, and Manage sections so that I can navigate the bill workflow efficiently. | AC1: O&M left-menu shows View Pending Bills and Manage as separate sections; AC2: Contractor/Firm tab displays Summary, Bill Workflow, Complete Bill, Bill Generated, Submission Letter, Documents, and Tax Invoice sub-sections; AC3: GM Dashboard displays a Forward to TL/SQC button on each in-progress bill; AC4: GM (PIU) dashboard tile shows count of bills pending GM action; AC5: Navigation is consistent between GM (PIU) and TL/SQC login screens | Done | Sprint 14
O&M Billing Workflow – End-to-End Workflow Testing | US-OMWF-C4-016 | High | As a QA engineer, I want end-to-end testing of the complete O&M Billing Workflow (Firm → GM PIU → TL CSC → GM PIU → GM O&M → TL PMC → DGM O&M → GM O&M → CGM → CA → CFO → P.D. → MD) so that the multi-level approval chain functions correctly across all 13 roles. | AC1: Test scenarios are created covering all 13 workflow stages and their forward/hold/reject paths; AC2: Each stage's mandatory document checks are verified to block premature forwarding; AC3: Role-based access is tested to confirm no stage can be skipped; AC4: Bill ageing and status tracking is verified across the full chain; AC5: Regression testing confirms no data loss when a bill is held or rejected at any stage; AC6: UAT sign-off is obtained from at least one user per role | WIP | Sprint 15-16

## Material Testing US
Jal Rekha - Cycle 5 User Stories ¦ Material Testing ¦ June-July 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Material Testing - Re-Inspection Loop (2nd Loop after GM Rejection) | US-MAT-C5-001 | High | As an FE/GM/Contractor/SQC/TPIA user, I want the same re-inspection loop implemented for Cube Testing to also work for Material Testing, so that rejected material test records can be corrected and re-verified through the full approval chain. | AC1: Rejected Material Testing record routes back to Contractor for correction; AC2: On resubmission, record flows FE to GM to SQC/TPIA (and to a newly assigned FE if reassigned); AC3: Loop history is retained and visible to all reviewers; AC4: Record reaches final Approved status once the loop clears; AC5: In progress as of 21-Jul-2026 status review, targeted for Sprint 18 close. | In Progress | Sprint 18 | 16
Material Testing - Optional Image Upload on Second RFI Loop | US-MAT-C5-002 | Medium | As an FE/Contractor user, I want image upload to be optional on the second (re-inspection) RFI loop pass for Material Testing, consistent with Cube Testing, so that minor corrections aren't blocked by re-capturing images. | AC1: First RFI submission keeps image upload mandatory; AC2: Second RFI loop pass makes image upload optional; AC3: Previously uploaded images remain attached; AC4: Behaviour verified consistent with the Cube Testing implementation. | Open | Sprint 18 | 6
Material Testing - GM/Contractor Login Database & API Enhancements | US-MAT-C5-003 | Medium | As a system developer, I want the Material Testing database functions and web/mobile API services updated for GM and Contractor logins, so that the re-inspection loop and related business logic work reliably end-to-end. | AC1: Database functions updated to support the re-inspection loop state machine; AC2: Web and mobile API services updated and versioned; AC3: Business logic APIs tested for GM and Contractor login flows; AC4: Regression tested against existing Material Testing records. | In Progress | Sprint 18 | 20

## Nirmal US
Jal Rekha - Cycle 5 User Stories ¦ Nirmal Module ¦ June-July 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Nirmal - Beneficiary Report Issue Fix | US-NRM-C5-001 | Medium | As a Nirmal module user, I want the reported issue in the Beneficiary Report resolved, so that beneficiary data displays correctly across the Nirmal inner pages. | AC1: Identified UI/data issue in the Beneficiary Report is corrected; AC2: Fix verified across all inner pages affected; AC3: No regression introduced in related Nirmal reports; AC4: Deployed to production. | Done | Sprint 17 | 8
Nirmal - Contractor Login Report Counting Bug Fix | US-NRM-C5-002 | Medium | As a Contractor user, I want the Nirmal report counting issue on my login corrected, so that reported totals reflect the actual number of records. | AC1: Root cause of the counting discrepancy identified and fixed; AC2: Counts verified against source data for a sample of schemes; AC3: Production bug fix deployed and confirmed resolved; AC4: No related report is impacted by the fix. | Done | Sprint 17 | 6
Nirmal - FE Mobile Reports Validation & Bug Fixes | US-NRM-C5-003 | Medium | As a Field Executive, I want the Nirmal Reports on my mobile login validated and any bugs fixed, so that the data I submit and view in the field is accurate. | AC1: Nirmal Reports on FE mobile login are validated against expected data; AC2: Identified bugs are fixed and verified; AC3: Reports tested on Android devices used by field staff; AC4: Deployed to production. | Done | Sprint 17 | 8
Nirmal - Test Scenario and Test Case Creation | US-NRM-C5-004 | Low | As a QA engineer, I want documented test scenarios and test cases for the Nirmal Change Request, so that regression coverage is in place for future releases. | AC1: Test scenarios cover all Nirmal Change Request functionality; AC2: Test cases are documented with expected results; AC3: Test artifacts are stored for reuse in future sprints; AC4: Sign-off obtained from QA lead. | Done | Sprint 17 | 6

## AI Module FHTC Tap US
Jal Rekha - Cycle 5 User Stories ¦ AI Module - FHTC Tap Connection Detection ¦ June-July 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
AI Module - Tap & Person Detection Predictive Model | US-AI-C5-001 | High | As a project data scientist, I want a machine learning predictive model built for tap and person detection on FHTC connection photos, so that tap connection evidence can be automatically verified instead of relying solely on manual review. | AC1: YOLO-based tap detection and person detection model is trained on collected FHTC image data; AC2: Model is fine-tuned to be robust to blurred/low-quality field photos (Blur-Robust Fine-Tuning); AC3: Final model inferencing is validated against a labelled test set with acceptable accuracy; AC4: Model artifacts are versioned for deployment. | Done | Sprint 17 | 40
AI Module - Tap Connection Buffer Region Validation (LLM/Pretrained Model Integration) | US-AI-C5-002 | High | As a project data scientist, I want the tap connection monitoring buffer region validated using an LLM-assisted identification approach and an integrated human-pretrained model, so that tap identification accuracy improves in ambiguous or edge-case images. | AC1: LLM-based tap identification approach is implemented and tested; AC2: A pretrained human-detection model is integrated for buffer-region validation; AC3: Model is retrained iteratively based on validation results; AC4: Retrained model is tested for tap identification accuracy improvement over the baseline. | Done | Sprint 17 | 32
AI Module - FHTC Data Processing & Model Training Pipeline | US-AI-C5-003 | Medium | As a project data scientist, I want a repeatable data processing pipeline (including YOLOv8-based tap identification) for FHTC tap connection images, so that new field data can be efficiently prepared for model training and retraining. | AC1: Data processing pipeline ingests and prepares FHTC tap connection images for training; AC2: YOLOv8-based tap identification is implemented and tested; AC3: Pipeline supports re-collecting and reprocessing data for retraining cycles; AC4: Training/testing of the tap detection model is completed and results documented. | Done | Sprint 17 | 32

## Master US
Jal Rekha - Cycle 5 User Stories ¦ Master Data Module ¦ June-July 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Master - Lock Scheme/Village/OHT Master Once Linked to Live Transactions | US-MSTR-C5-001 | High | As a GM (PIU) user, I want Scheme Master, Village Master and OHT Master entries to become locked once linked to live Dhara, O&M Billing or Asset Mapping transactions, so that master data can't be altered in a way that silently breaks downstream billing and reporting. | AC1: A master record becomes read-only once tagged/used in a Dhara report, O&M Billing entry, or Asset Mapping (BISAC) record; AC2: Attempted edits on a locked record are blocked with a clear message; AC3: Corrections are routed through a controlled change/relaxation flow instead of direct edit; AC4: Extends the same locking principle already applied to the Dhara Approved Report Lock (US-DHR-C5-005). | Open | Sprint 18 | 16
Master - Dhara Mapped Summary Report Search Debugging & Enhancement | US-MSTR-C5-002 | Medium | As a GM (PIU) user, I want the search functionality on the Dhara Mapped Summary report (used in Abstract report generation) debugged and enhanced, so that I can reliably locate the mapped records I need. | AC1: Identified search defects on the Dhara Mapped Summary report are fixed; AC2: Search supports the key fields used in Abstract report lookups; AC3: Search performance is acceptable for the full dataset size; AC4: Deployed and verified in production. | Done | Sprint 17 | 8
Master - Village Deletion Restriction & Database Validation Message | US-MSTR-C5-003 | Medium | As a data admin, I want village deletion restricted with a clear database validation message when a village is in use, so that master data integrity is preserved and users understand why a deletion is blocked. | AC1: Deletion of a village linked to any active mapping/transaction is blocked; AC2: A clear validation message explains why deletion is restricted; AC3: Villages with no active links can still be deleted; AC4: Change deployed and tested across Scheme Village OHT Mapping and related reports. | Done | Sprint 17 | 6

## Asset Mapping US
Jal Rekha - Cycle 5 User Stories ¦ Asset Mapping (BISAC) ¦ June-July 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Asset Mapping - SQC/TPIA Contractor Data & Report on Web | US-AST-C5-001 | Medium | As an SQC/TPIA/Contractor user, I want Asset Mapping data and reports available on the web portal, so that I can review and verify asset mapping records without relying solely on the mobile app. | AC1: SQC, TPIA, and Contractor asset mapping data is visible on the web login; AC2: Report supports filter by District, Scheme, and Asset Type; AC3: Data matches the mobile-app-submitted records; AC4: Deployed to production. | Done | Sprint 17 | 12
Asset Mapping - API Integration & Frontend Bug Fixes | US-AST-C5-002 | Low | As a system developer, I want Asset Mapping API integrations completed and identified frontend bugs fixed, so that asset data flows correctly between the mobile app, web portal, and BISAC integration. | AC1: Required API integrations for Asset Mapping are completed and tested; AC2: Identified frontend bugs are fixed and verified; AC3: Regression tested against existing asset records; AC4: Changes deployed to production. | Done | Sprint 17 | 10

## Bharosa US
Jal Rekha - Cycle 5 User Stories ¦ Bharosa (Factory Testing) ¦ June-July 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Bharosa - Item Master Duplicate Dropdown Entry Fix | US-BHR-C5-001 | Medium | As a Bharosa Factory Testing (Web) user, I want the duplicate data entry issue in the item master dropdown fixed, so that I don't select or record duplicate item entries during factory testing. | AC1: Duplicate entries in the item master dropdown are identified and removed; AC2: Dropdown enforces uniqueness for new item master entries going forward; AC3: Fix verified in production; AC4: No existing factory testing records are impacted. | Done | Sprint 18 | 6
Bharosa - Factory Testing Mobile Bug Fixes | US-BHR-C5-002 | Medium | As a Bharosa Factory Testing (Mobile) user, I want identified bugs in the mobile factory testing flow fixed, so that factory test submissions are reliable in the field. | AC1: Identified factory testing mobile bugs are fixed; AC2: Internal testing confirms the fixes resolve the reported issues; AC3: No regression in QAP third-party or multiple-image-upload functionality; AC4: Deployed to production. | Done | Sprint 18 | 8

## Daily Inspection US
Jal Rekha - Cycle 5 User Stories ¦ Daily Inspection ¦ June-July 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Daily Inspection - Role-Based Report Modifications | US-DIN-C5-001 | Medium | As an SQC/TPIA/Contractor/GM/CGM/TL user, I want the Daily Inspection Report module modified to reflect the correct fields and views for my role, so that daily inspection data is relevant and actionable for each reviewer level. | AC1: Daily Inspection Report is updated for SQC, TPIA, and Contractor roles per the agreed changes; AC2: Daily Inspection Report is updated for GM, CGM, and TL roles per the agreed changes; AC3: Each role sees only the fields/actions relevant to it; AC4: Deployed and verified in production. | Done | Sprint 17 | 12
Daily Inspection - Mobile App Bug Fixes | US-DIN-C5-002 | Low | As a field user, I want identified bugs in the Daily Inspection mobile app fixed, so that daily inspection entries can be submitted reliably from the field. | AC1: Identified mobile app bugs in Daily Inspection are fixed; AC2: Fixes verified on representative Android devices; AC3: No regression in existing inspection submission flow; AC4: Deployed to production. | Done | Sprint 17 | 6

## Sopan US
Jal Rekha - Cycle 5 User Stories ¦ Sopan ¦ July 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Sopan - Calendar Functionality for 2026-27 | US-SOP-C5-001 | Medium | As a Contractor (Web/Mobile), I want a calendar feature reflecting the 2026-27 calendar year on my Sopan login, so that I can plan and track activities against the correct project calendar year. | AC1: Calendar control is added to the Contractor login (web and mobile) under Sopan; AC2: Calendar correctly reflects the 2026-27 year range and date boundaries; AC3: Selecting a date/period on the calendar filters or drives the relevant Sopan screen; AC4: Open as of 21-Jul-2026 status review, targeted for Sprint 18. | Open | Sprint 18 | 10

## QA Automation US
Jal Rekha - Cycle 5 User Stories ¦ QA - User & Role Management Automation ¦ June-July 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
QA Automation - Selenium Scripts for User Login & Registration | US-QA-C5-001 | Medium | As a QA engineer, I want automated Selenium scripts for User Login and User Registration flows, so that regression testing of core access functionality is faster and repeatable across releases. | AC1: Automation framework (TestNG) is set up and documented; AC2: Selenium script automates the User Login flow end-to-end; AC3: Selenium script automates the User Registration flow end-to-end; AC4: Scripts are runnable as part of the regression suite. | Done | Sprint 17 | 16
QA Automation - Internal Review Process for Automation Testing | US-QA-C5-002 | Low | As a quality manager, I want a recurring internal review meeting for automation testing progress, so that automation coverage and defects are tracked consistently across sprints. | AC1: Recurring internal review meeting scheduled for automation testing status; AC2: Automation coverage and open defects are reviewed each cycle; AC3: Action items are logged and tracked to closure; AC4: Review outcomes feed into CMMI documentation. | Done | Sprint 17-18 | 4