## INDEX
JAL REKHA – CYCLE 4 USER STORIES REGISTER (Jan 2026 – May 2026) Prepared for: CMMI Level 5 Audit ¦ Project: Jal Rekha ¦ Department: PHED, Madhya Pradesh
Sr. No. | Sheet Name | Module / Area | No. of User Stories | Total Effort (hrs)
1 | Anusharavan US | Anusharavan (RFI, Stages, Reports) | 8 | 250
2 | Asset Mapping US | Asset Mapping (GIS, Survey) | 3 | 53
3 | Bharosa US | Bharosa Factory Testing (Web + Mobile) | 5 | 191
4 | Cube Testing US | Cube Testing (Contractor / FE / GM / SQC) | 9 | 631
5 | Daily Inspection US | Daily Inspection | 2 | 20
6 | Dashboard US | Dashboard & Public Reports | 3 | 78
7 | Dhara US | Dhara (Reports, Meter, Mobile) | 10 | 915
8 | FHTC US | FHTC + AI Tap Connection | 5 | 365
9 | Master US | Master Module (GM / CR / Schema) | 4 | 226
10 | Material Testing US | Material Testing (GM / Contractor / FE) | 5 | 344
11 | Nirmal US | Nirmal (FE Mobile, GM, CR) | 4 | 153
12 | O&M Billing US | O&M Billing (GM / Contractor / Workflow) | 7 | 624
13 | Sahbhagita US | Sahbhagita (GM / CR / Reports) | 4 | 57
14 | SVS US | SVS Water Supply Monitoring – Har Ghar Jal | 15 | 104
15 | CMMI Doc US | CMMI Documentation + Dept Meetings | 4 | 756
16 | Site Security US | Site Security Audit | 2 | 32
17 | Sopan US | Sopan Contractor | 2 | 10
18 | User Role US | User & Role Management | 2 | 24
| TOTAL USER STORIES – CYCLE 4 |  | 94

## Anusharavan US
Jal Rekha – Cycle 4 User Stories ¦ Anusharavan (RFI, Stages, Reports) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Anusharavan – RFI Stage Changes | US-ANS-C4-001 | High | As a system user, I want new RFI stages added to the Anusharavan module so that the inspection workflow captures all required stages accurately. | AC1: New RFI stages are defined in the workflow configuration with appropriate role-based permissions; AC2: Stage transitions are validated and cannot be skipped out of sequence; AC3: Contractor and Field Engineer mobile app reflects all new stages correctly; AC4: GM dashboard displays stage-wise inspection counts in real time; AC5: Automated notifications are triggered upon each stage change | Done | Sprint 12-14 | 120
Anusharavan – RFI Stage Changes | US-ANS-C4-002 | High | As a Field Engineer (FE), I want PIU inspection details added to the RFI form so that I can capture field-level data accurately during inspection. | AC1: FE inspection fields (PIU, Inspection Date, GPS Coordinates, Remarks) are added to the RFI form; AC2: All mandatory fields enforce validation before submission; AC3: Inspection date is auto-populated from the device but remains editable; AC4: PIU-wise data is visible and filterable in GM reports; AC5: Entered data persists correctly across user sessions | Done | Sprint 14 | 16
Anusharavan – Stage Updation | US-ANS-C4-003 | Medium | As a developer, I want existing RFI stages updated and History screen search enhanced so that users can quickly locate past inspection records. | AC1: History screen search is functional using Scheme, Date Range, and Status filters; AC2: Search results load within 3 seconds for standard datasets; AC3: Pipeline details on the History Detail screen are verified and displayed correctly; AC4: Play Store live build is tested and confirmed working; AC5: No regression is introduced in existing Anusharavan functionality | Done | Sprint 13 | 21
Anusharavan – Report Creation | US-ANS-C4-004 | High | As a GM user, I want customised RFI reports with FE inspection details so that I can generate PIU-wise performance reports. | AC1: Customised report includes PIU Name, Inspector Name, and Inspection Date columns; AC2: Report supports filters for PIU, Scheme, and Date Range; AC3: Excel and PDF export are operational; AC4: Summary section shows aggregate inspection counts per PIU; AC5: Report loads within 5 seconds for datasets with 500 or more records | Done | Sprint 14-15 | 24
Anusharavan – Testing & Video | US-ANS-C4-005 | Medium | As a QA engineer, I want complete testing of Anusharavan module changes including a demo video so that all functionalities are validated before production. | AC1: Test cases are created covering all new stage changes and report modifications; AC2: Internal testing pass rate reaches 100% before UAT handover; AC3: UAT is conducted with PHED representatives and sign-off is obtained; AC4: Production defects are logged, tracked, and resolved; AC5: Demo video covering new stages and reports is recorded and shared with stakeholders | Done | Sprint 14 | 8
Anusharavan CR – FE Inspection PIU & Report | US-ANS-C4-006 | Medium | As a contractor, I want the updated RFI workflow with FE Inspection Date visible in PIU Pending-for-Action web page so that I can track pending inspections efficiently. | AC1: FE Inspection Date column is added to the PIU Pending for Action web page; AC2: Data is sourced accurately from the corresponding inspection records; AC3: The column is sortable and filterable on the web page; AC4: Customised report is updated to include the FE Inspection Date field; AC5: CR changes are tested in the staging environment before production deployment | Done | Sprint 15 | 21
Anusharavan – UI Enhancement Contractor & FE Login | US-ANS-C4-007 | Low | As a UI/UX developer, I want the Anusharavan Contractor and FE login pages redesigned with card-based layout so that the user interface is consistent and mobile-responsive. | AC1: Card-based HTML layout is applied consistently to all inner pages of Contractor and FE login; AC2: Table alignment is corrected on the Approved Supply Point Wise Village MWSR page; AC3: Modal popup design is corrected and visually consistent; AC4: Mobile responsiveness is verified on Android devices; AC5: Changes are deployed and regression-tested with no new defects | Done | Sprint 14-15 | 16
Anusharavan – View Details, Log View & Inspection Request Enhancement | US-ANS-C4-008 | Medium | As an FE and GM user, I want enhanced View Details, Log View, and Inspection Request Form in Anusharavan so that all field activities are traceable. | AC1: View Details screen displays all RFI stages with corresponding timestamps; AC2: Log View screen shows a complete audit trail for each RFI record; AC3: Inspection Request Form is enhanced with all required new fields; AC4: Accuracy field changes are applied correctly at both API and local database levels; AC5: All enhancements are tested on both mobile app and web portal | Done | Sprint 14 | 24

## Asset Mapping US
Jal Rekha – Cycle 4 User Stories ¦ Asset Mapping (GIS, Survey) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Asset Mapping – Bug Fixing & Redesign | US-AST-C4-001 | High | As a user, I want the Asset Mapping module redesigned and deployed to live server so that the interface is modern and all known bugs are resolved. | AC1: Redesigned Asset Mapping pages are deployed and accessible on the live server; AC2: OHT search box is functional with real-time filtering on the map view; AC3: All known frontend bugs are identified and resolved; AC4: Accuracy field changes are implemented at the API and database levels; AC5: Data GET method is updated as per the revised technical specifications | Done | Sprint 13-14 | 30
Asset Mapping – Data Correction & Reports | US-AST-C4-002 | High | As an SQC/TPIA/Contractor user, I want dedicated report pages in Asset Mapping so that I can view and download survey and GIS data efficiently. | AC1: Dedicated report pages are created for SQC, TPIA, and Contractor login roles; AC2: Survey data download in D&D format is operational; AC3: Data correction tools are available with a complete audit trail; AC4: OHT village testing bug is resolved; AC5: Move OHTs feature is functional; AC6: Demo video documenting the new features is created | Done | Sprint 15 | 15
Asset Mapping – SQC Login Data Visualisation | US-AST-C4-003 | Medium | As an SQC user, I want data visualisation and asset mapping views in SQC login so that I can audit GIS asset data independently. | AC1: SQC login view shows district, block, and village-filtered asset map; AC2: Data visualisation charts display asset counts by category; AC3: Survey data download is available to users with the SQC role; AC4: Internal testing is completed with all cases passing; AC5: UAT is conducted and sign-off is obtained from the department | Done | Sprint 15 | 8

## Bharosa US
Jal Rekha – Cycle 4 User Stories ¦ Bharosa Factory Testing (Web + Mobile) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Bharosa – Factory Testing Web CR | US-BHR-C4-001 | High | As a developer, I want multiple document upload functionality added to the Bharosa Factory Testing web module so that inspectors can attach all evidence in one submission. | AC1: Multiple file upload (PDF, DOC, JPG, PNG) is implemented with a progress indicator; AC2: Upload is restricted to a maximum of 10 files with each file not exceeding 10 MB; AC3: Uploaded documents are viewable and downloadable by authorised users; AC4: QAP document upload is included within the same upload flow; AC5: UI is updated on all existing Bharosa web pages; AC6: Post-deployment bugs are identified and resolved | Done | Sprint 12-13 | 78
Bharosa – Factory Testing DB & API | US-BHR-C4-002 | High | As a system architect, I want database architecture designed and service APIs created for Bharosa Factory Testing so that all web and mobile components are supported by a robust backend. | AC1: Database schema is designed with master table validation for Bharosa Factory Testing; AC2: APIs are created for all Bharosa web and mobile pages; AC3: Contractor login mobile page for Factory Testing is developed; AC4: Unit testing, SIT, and UAT are completed with documented results; AC5: Test cases are created and maintained for all API endpoints | Done | Sprint 13 | 40
Bharosa – Factory Testing UI & Wireframes | US-BHR-C4-003 | Medium | As a UI/UX designer, I want wireframes for Bharosa Factory Testing module and UI enhanced so that development has clear specifications and the deployed UI is consistent. | AC1: Wireframes are prepared for all screens including Inspector, GM, and TPIA login; AC2: UI is updated on all pages as per the approved wireframes; AC3: Unit input field with unit display is added to the relevant forms; AC4: Save as Draft, Image upload, and Video upload functionalities are implemented; AC5: Production deployment is completed and verified | Done | Sprint 13 | 24
Bharosa CR – Factory Testing Mobile | US-BHR-C4-004 | Medium | As a mobile user, I want QAP document download functionality on the Bharosa mobile app so that field users can access quality assurance documents offline. | AC1: QAP document download is added to the Bharosa mobile application; AC2: Download supports PDF and DOC file formats; AC3: Downloaded documents are accessible in offline mode after initial download; AC4: Internal testing is completed with zero critical defects; AC5: CR changes are tested in the production environment | Done | Sprint 15 | 25
Bharosa CR – Save as Draft & Document Upload | US-BHR-C4-005 | Medium | As a Bharosa inspector user, I want Save as Draft functionality and document upload enhancement in Bharosa so that partial inspections can be resumed without data loss. | AC1: Save as Draft saves the current form state without final submission; AC2: Drafted records are visible in the history list with a Draft status indicator; AC3: Duplicate document upload validation is applied during final submission; AC4: Final submission handling is correct and complete; AC5: UAT is conducted and signed off by the PHED team | Done | Sprint 15 | 24

## Cube Testing US
Jal Rekha – Cycle 4 User Stories ¦ Cube Testing (Contractor / FE / GM / SQC) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Cube Testing – Requirement Gathering & Design | US-CUBE-C4-001 | High | As a business analyst, I want Cube Testing requirements gathered and wireframes created so that the development team has complete specifications for implementation. | AC1: Requirement gathering sessions are conducted with Civil Engineers, Lab Technicians, and GM; AC2: Wireframes are prepared for both web and mobile interfaces; AC3: Workflow is documented covering the full lifecycle: Sample Collection → Curing → 7-Day Check → 28-Day Check → Result → TPIA Review → GM Approval; AC4: Database schema, master tables, and design tables are defined; AC5: Business logic APIs and stored procedures are developed as per finalised specifications | Done | Sprint 13-14 | 130
Cube Testing – Development | US-CUBE-C4-002 | High | As a developer, I want Cube Testing database functions, stored procedures, and web pages created so that the full testing lifecycle is supported. | AC1: Database schema is created with query optimisation; AC2: New web pages are developed as per approved wireframes; AC3: Data validation is implemented at both UI and API levels; AC4: Reports are functional and display accurate data; AC5: Internal testing and production deployment are completed; AC6: Test cases, test scenarios, and test plan documents are created | Done | Sprint 13-15 | 120
Cube Testing – Contractor Login | US-CUBE-C4-003 | High | As a contractor, I want to create cube inspection entries through the web application so that sample data is captured at the point of collection. | AC1: Contractor can create cube inspection records including Component, Casting Date, Mix Design, and Quantity; AC2: RFI Survey form API is integrated with Contractor login; AC3: Survey form includes pagination and contractor history list is displayed correctly; AC4: Internal testing and UAT/Production testing are completed with no critical defects | Done | Sprint 14 | 64
Cube Testing – FE Login | US-CUBE-C4-004 | High | As a Field Engineer, I want to record and submit cube test results after 7-day and 28-day curing periods so that compressive strength data is captured accurately. | AC1: FE Sync API is integrated and data synchronisation is verified; AC2: System enforces the 7-day and 28-day curing period before allowing result submission; AC3: Cube inspection form captures GPS coordinates at submission; AC4: FE Insert document bug is identified and resolved; AC5: End-to-end testing is completed for the full FE inspection workflow; AC6: Security test cases are created and executed | Done | Sprint 13-15 | 120
Cube Testing – GM / SQC / TPIA | US-CUBE-C4-005 | High | As a GM user, I want summary reports and Pending for Action page in Cube Testing so that I can monitor and approve cube test results across all schemes. | AC1: Summary reports are generated for both 7-day and 28-day inspection scenarios; AC2: GM Action Page with Pending for Action list is developed and functional; AC3: RFI request status update and status list view are functional; AC4: Customised reports are available for GM login; AC5: All production issues are identified, tracked, and resolved | Done | Sprint 14 | 48
Cube Testing – SQC/TPIA Login | US-CUBE-C4-006 | High | As an SQC/TPIA user, I want web pages and APIs for SQC and TPIA login in Cube Testing so that I can verify and approve cube test results. | AC1: SQC login web pages and corresponding APIs are developed; AC2: TPIA login web pages and corresponding APIs are developed; AC3: Bug fixing is completed for all issues in SQC and TPIA login; AC4: End-to-end testing is completed across all flows; AC5: Test scenarios are documented for future regression testing | Done | Sprint 14-15 | 47
Cube Testing CR – Mandatory Image Upload & Manual Component | US-CUBE-C4-007 | Medium | As a department stakeholder, I want change requests for Cube Testing implemented including mandatory multiple image upload and manual component entry so that data quality is enhanced. | AC1: Mandatory multiple image upload is enforced on the Cube Testing submission form; AC2: Manual entry option for components is available where dropdown selection is not applicable; AC3: New web page modifications are implemented as per CR specifications; AC4: CR changes are tested in staging before production deployment; AC5: All CR items are reviewed and closed with documented results | Done | Sprint 15-16 | 70
Cube Testing CR – Remove Inspection Date & Calculate Days from Casting | US-CUBE-C4-008 | Medium | As a QA engineer, I want the Cube Testing module to remove the manual inspection date field and automatically calculate 7-day or 28-day check validity from the Casting Date so that test validity is enforced without manual entry errors. | AC1: Manual inspection date field is removed from the Cube Testing form; AC2: System automatically calculates days elapsed from the Casting Date only; AC3: 7-day and 28-day threshold validation is enforced at both API and UI levels; AC4: FE is prevented from submitting results before the required threshold days; AC5: Changes are tested in staging and production environments | Done | Sprint 15-16 | 16
Cube Testing CR – Remove Compulsion for Structural Location on Non-Site Components | US-CUBE-C4-009 | Low | As a contractor, I want District/Block/GP/Village selection removed as mandatory for components like Intakewell, WTP, MBR, RWPM, CWPM so that I can raise cube inspections for non-site-specific components without barrier. | AC1: Mandatory District, Block, GP, and Village selection is removed for components: Intakewell, WTP, MBR, RWPM, and CWPM; AC2: Location fields are optional for these listed components; AC3: Village and GP selection remains mandatory only for site-specific components; AC4: Changes are tested in staging and production with all edge cases verified | Done | Sprint 15-16 | 16

## Daily Inspection US
Jal Rekha – Cycle 4 User Stories ¦ Daily Inspection ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Daily Inspection – Development & Bug Fixes | US-DI-C4-001 | High | As a developer, I want Daily Inspection module bug fixes and new functionality implemented so that FE and GM users can perform inspections without technical issues. | AC1: Frontend, API, database, and mobile bugs are fixed with root cause documented; AC2: New web pages are created as per requirement specifications; AC3: GET and SET data access methods are created and updated correctly; AC4: Database architecture is designed with master table validation; AC5: APIs are developed for all new features; AC6: Production deployment and unit testing are completed | Done | Sprint 12 | 12
Daily Inspection – Accuracy Field Changes | US-DI-C4-002 | Medium | As a mobile developer, I want accuracy field changes applied to Daily Inspection on Android so that GPS precision data is captured correctly. | AC1: Accuracy field is added at the API level and stored in the local database; AC2: Accuracy data is synchronised with the web portal; AC3: Changes are tested on multiple Android devices; AC4: No regression is introduced in the existing Daily Inspection workflow; AC5: Changes are deployed to the production environment | Done | Sprint 14 | 8

## Dashboard US
Jal Rekha – Cycle 4 User Stories ¦ Dashboard & Public Reports ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Dashboard – Data Verification & Wireframe | US-DASH-C4-001 | High | As a PM user, I want Dashboard data verified and Excel reports modified for all Jal Rekha modules so that the management dashboard reflects accurate real-time data. | AC1: Data verification is completed for all Jal Rekha modules to ensure dashboard accuracy; AC2: Modified Excel reports are generated with correct data binding; AC3: Wireframes are created for new dashboard widgets and reviewed by stakeholders; AC4: Requirement gathering is formally documented; AC5: All KPIs on the dashboard are tested for accuracy against source data | Done | Sprint 13 | 30
Dashboard – All Public Reports | US-DASH-C4-002 | High | As a public user, I want all Jal Rekha module reports accessible on the public dashboard so that scheme performance data is transparently available. | AC1: Public reports are enabled and accessible for all applicable Jal Rekha modules; AC2: CR, production, and UAT bug testing is completed; AC3: Internal testing pass rate reaches 100% before public access is enabled; AC4: Report load time is within 5 seconds; AC5: No authentication is required for public-facing reports | Done | Sprint 14-15 | 32
Dashboard – Sidebar Menu UI Improvement | US-DASH-C4-003 | Low | As a UI developer, I want the sidebar menu icons, scroll colour, and table alignment improved on the dashboard so that the visual design is consistent and mobile-responsive. | AC1: Sidebar menu icons are updated with a consistent design; AC2: Scroll colour is customised to match the overall design theme; AC3: Table alignment is corrected on all dashboard inner pages; AC4: Sidebar menu is fully mobile responsive; AC5: Unused and redundant CSS is removed from the codebase | Done | Sprint 13 | 16

## Dhara US
Jal Rekha – Cycle 4 User Stories ¦ Dhara (Reports, Meter, Mobile) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Dhara – Reports & UI Enhancement | US-DHR-C4-001 | High | As a GM user, I want updated DWSR, MWSR, UFW reports and new Approved Village Wise MWSR report so that I can monitor water supply performance at all levels. | AC1: DWSR Detailed and Datewise Report pages are created with correct data binding; AC2: Approved Village Wise MWSR page is developed with supporting backend service; AC3: Bulk Consumer MWSR Report is developed and displays correct data; AC4: HSC Summary Report page is developed with date filter enhancement in DWSR; AC5: Date filter is enhanced and functional across all DWSR reports; AC6: UFW Report data corrections are applied and validated | Done | Sprint 12-16 | 163
Dhara – UI Update & Bug Fixes | US-DHR-C4-002 | High | As a developer, I want Dhara module inner pages redesigned and existing bugs fixed so that users experience a consistent and error-free interface. | AC1: New UI design is applied consistently to all Dhara module inner pages; AC2: District data mismatch in the DWSR DateWise Detailed Report is fixed; AC3: WTP Meter Mapping page issue and delete restriction bug are resolved; AC4: Public page data visibility issue for PIU and Scheme ALL selection is resolved; AC5: SIT and UAT are completed with all defects resolved | Done | Sprint 12-16 | 120
Dhara – Meter Reading & Contractor Objection | US-DHR-C4-003 | High | As a GM and Contractor user, I want meter reading survey changes and contractor objection module implemented so that meter disputes are formally managed. | AC1: Contractor Objection Module UI and modal are developed for Intake, WTP, and ESR/OHT survey pages; AC2: Contractor Objection API and database integration are completed; AC3: Meter reading survey is updated for Intake, WTP, OHT, and Bulk Consumer (web and mobile); AC4: Approval status flow (FE → GM → Contractor) is enforced; AC5: Bulk Consumer mapping is added with correct supply point linkage | Done | Sprint 15-16 | 141
Dhara CR – Reports (MWSR, DWSR, UFW) | US-DHR-C4-004 | High | As a QA analyst, I want requirement gathering and internal testing for Dhara report changes so that MWSR, DWSR, and UFW reports are accurate. | AC1: Requirement gathering for all Dhara report changes is documented; AC2: DWSR, MWSR, Bulk Consumer, Approved Reports, and UFW reports are updated and recreated per requirements; AC3: Internal testing is completed for all new and modified reports; AC4: DWSR public report enhancements are deployed and accessible; AC5: JavaScript modification for the data loading issue in DWSR public report is applied | Done | Sprint 14-16 | 236
Dhara – GM PIU User Change Request | US-DHR-C4-005 | High | As a GM PIU user, I want Dhara WTP meter reading issues resolved and intake meter reading survey changes implemented so that meter data is captured correctly. | AC1: WTP Meter Reading issue is resolved for all affected schemes; AC2: Intake meter reading survey changes are implemented correctly; AC3: Bulk Consumer meter reading survey is updated per the revised flow; AC4: Test cases and test scenarios are created for all new changes; AC5: Changes are deployed to both staging and production environments | Done | Sprint 15-16 | 91
Dhara – Mobile Application | US-DHR-C4-006 | High | As a field user, I want a mobile application developed for Dhara module so that meter readings and survey data can be captured in the field. | AC1: Dhara mobile application development is completed; AC2: All meter survey types (Intake, WTP, OHT, Bulk Consumer) are supported; AC3: GPS capture and offline mode are functional; AC4: Data synchronisation is triggered on network connectivity; AC5: Mobile UAT and production testing are completed; AC6: Knowledge transfer session is conducted for the field team | Done | Sprint 13 | 40
Dhara CR – OHT-WTP Village Meter Survey Rename & New Fields | US-DHR-C4-007 | High | As a GM and Contractor user, I want the OHT Meter Survey renamed to 'OHT-WTP Village Meter Survey' and new report fields added (Survey Date, Scheme, Component Name, Village Meter details, Reading Start/End, Total Clear Water Supplied, PE Remark) so that the survey captures complete village-level meter data. | AC1: Module is renamed to OHT-WTP Village Meter Survey across all web and mobile screens; AC2: All 13 new fields are added including Survey Date, Scheme, Component Name, Village Meter Status, Reading Start/End, Total Clear Water (KL), PE Remark, GM Remark, and Local Name; AC3: Conditional GM review flow includes options (Objection / Approved / Any Concern) with Contractor Remark and Document Upload; AC4: Database schema is updated; AC5: Existing records are migrated without data loss; AC6: All 13 fields are tested in staging and production | Done | Sprint 15-16 | 60
Dhara CR – GM Work Process Flow (Intake / WTP / OHT Meter Surveys) | US-DHR-C4-008 | High | As a GM user, I want a structured work process flow for reviewing Intake, WTP, and OHT-WTP Village Meter Survey pages after login so that GM can systematically review field data and take approval decisions. | AC1: GM can navigate to Dhara Module and select Intake, WTP, or OHT-WTP Village Meter Survey for review; AC2: Each survey page displays Survey Date, Scheme, Component, Total Water (KL), Meter Reading Start/End, and FE/PE Remark; AC3: GM is required to add a GM Review Remark before making a decision; AC4: Decision options include: Objection (Contractor Remark + Document Upload), Approved, and Any Concern (Contractor Remark + Upload); AC5: Decision status with timestamp and GM user ID is visible on the record; AC6: Workflow is tested end-to-end for all three survey types | Done | Sprint 15-16 | 40
Dhara CR – Contractor Objection Module – Intake & WTP | US-DHR-C4-009 | High | As a contractor, I want a dedicated Contractor Objection page for Intake Meter Survey and WTP Meter Survey so that I can raise objections against GM-reviewed readings with supporting documents. | AC1: New page Frm_DharaIntakeMeterSurveyForContractor.aspx is created; AC2: New page Frm_DharaWTPMeterSurveyForContractor.aspx is created; AC3: Contractor objection popup includes survey details, contractor remark field, and PDF upload; AC4: Services Update_contractor_objection_intake and Update_contractor_objection_wtp are implemented; AC5: Row lock handling prevents concurrent edits; AC6: End-to-end workflow is tested | Done | Sprint 16 | 16
Dhara CR – Contractor Objection Module – ESR/OHT | US-DHR-C4-010 | High | As a contractor, I want a dedicated Contractor Objection page for ESR/OHT Meter Survey so that I can raise objections with remarks and uploaded supporting documents. | AC1: New page Frm_DharaESRMeterSurveyForContractor.aspx is developed; AC2: DharaESRMeterSurveyForContractor.js is created with modal handling and input validation; AC3: Service Update_contractor_objection_esr is implemented for saving objection data; AC4: All survey fields in the contractor objection popup are set to read-only mode; AC5: End-to-end testing covers modal binding, validation, file upload, and data refresh | Done | Sprint 16 | 8

## FHTC US
Jal Rekha – Cycle 4 User Stories ¦ FHTC + AI Tap Connection ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
FHTC FE Reports – Development | US-FHTC-C4-001 | High | As a developer, I want FHTC FE report pages created, APIs integrated, and existing queries/SPs modified so that FE and GM users have accurate tap connection reports. | AC1: New FHTC web pages for FE reports are created and deployed; AC2: Mobile API integration is completed and verified; AC3: Database queries and stored procedures are created and modified as required; AC4: SIT testing, test cases, and test scenarios are documented; AC5: UAT, production, and CR testing are completed | Done | Sprint 12 | 51
FHTC CR – Loop / Re-Inspection Functionality | US-FHTC-C4-002 | High | As a contractor and FE user, I want FHTC Loop (Re-Inspection) functionality implemented so that failed tap connections can be re-inspected through a structured flow. | AC1: Loop (Re-Inspection) functionality is implemented for Contractor, FE, SQC, and TPIA login roles; AC2: Re-Inspection Form UI design and API data submission are completed for FE login; AC3: Re-Inspection List Screen with API integration is developed for FE login; AC4: History, Accepted List, and Rejected List screens are implemented correctly; AC5: FHTC Loop functionality is tested on mobile and PIU side; AC6: View Logs functionality is added and functional | Done | Sprint 14-15 | 180
FHTC CR – Search & Reports | US-FHTC-C4-003 | Medium | As an FE and Contractor user, I want search functionality and customised summary report changes in FHTC so that I can locate specific tap connection records quickly. | AC1: Search functionality is added to FE and Contractor login pages; AC2: Customised and summary report changes are implemented; AC3: Report filter issues at column level are resolved for GM and Contractor reports; AC4: Excel export includes dynamic file name, sheet name, and non-export columns hidden; AC5: Regression testing is completed in staging and production | Done | Sprint 14-16 | 57
FHTC – AI Module Tap Connection | US-FHTC-C4-004 | Medium | As a data scientist, I want AI/ML models implemented for FHTC Tap Connection monitoring so that predictive analytics can identify non-functional connections proactively. | AC1: ML model implementation for tap connection monitoring buffer region is completed; AC2: Data processing of FHTC Tap Connections using AI models is completed; AC3: Model is trained on rfdetr with 2000 annotated tap images; AC4: Testing is categorised into three outcome categories; AC5: Human detection model (YOLOv8x) is integrated alongside the custom tap connection model | WIP | Sprint 16 | 69
FHTC – UI Enhancement & Excel Export Standardisation | US-FHTC-C4-005 | Low | As a GM and contractor user, I want FHTC module UI enhanced and Excel exports standardised with module-wise file name, sheet name, and header title so that reports are professional and consistent. | AC1: FHTC module UI is enhanced consistently across all login pages; AC2: Excel export includes a dynamic file name based on the module; AC3: Sheet name and header title in Excel are set per module; AC4: Non-export columns (Action, Image, Document) are hidden in Excel output; AC5: Changes are deployed to production and verified | Done | Sprint 15 | 8

## Master US
Jal Rekha – Cycle 4 User Stories ¦ Master Module (GM / CR / Schema) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Master GM – Pipeline & Wireframes | US-MST-C4-001 | High | As a GM user, I want Pipeline Master data management with updated wireframes in the Master module so that infrastructure data is accurately maintained. | AC1: Pipeline Master data entry page is created with all required fields; AC2: New wireframes are implemented as per department-approved designs; AC3: Wireframes are reviewed and approved by stakeholders before development begins; AC4: GET and SET data access methods are created; AC5: SIT and UAT/Production/CR testing are completed | Done | Sprint 12 | 32
Master CR – Scheme Village OHT & Bulk Consumer | US-MST-C4-002 | High | As a data admin, I want Scheme Village OHT Mapping and Bulk Consumer Master updated with delete functionality so that master data management is complete. | AC1: Scheme Village OHT Mapping is updated and corresponding reports are modified; AC2: Bulk Consumer Master supports Add, Update, Get, and Delete operations; AC3: Dhara Mapped Summary Report changes are applied; AC4: Dhara Master DWSR updates are implemented; AC5: All master data changes are tested across all affected modules | Done | Sprint 13-16 | 140
Master CR – Bulk Consumer Meter Mapping | US-MST-C4-003 | High | As a developer, I want Bulk Consumer Supply Mapping enhanced with meter_id column for WTP and multiple mapping enabled so that bulk consumers can be mapped to multiple sources. | AC1: meter_id column is added to the Bulk Consumer Supply Mapping table; AC2: Multiple mapping from the same source is enabled per the revised business rule; AC3: Urban records where vill_cd = 0 are handled correctly; AC4: Validation and dropdown reset are triggered on Scheme change; AC5: Bulk Meter Update Fix is applied; AC6: Changes are tested and verified in production | Done | Sprint 14-16 | 38
Master CR – Census Population Integration | US-MST-C4-004 | Medium | As a data admin, I want Census Population auto-fetched from Scheme Village Master instead of manual entry so that census data is always consistent with the master. | AC1: Manual Census Population Add/Delete functionality is removed from O&M Contract details; AC2: Auto-fetch of census data from Scheme Village Mapping is implemented; AC3: Direct save flow in the om_contract_census_population table is functional; AC4: Old trigger-based logic is disabled; AC5: Get_CensusByScheme shows saved data first, then falls back to master data | Done | Sprint 15 | 16

## Material Testing US
Jal Rekha – Cycle 4 User Stories ¦ Material Testing (GM / Contractor / FE) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Material Testing – GM/Contractor Login Development | US-MAT-C4-001 | High | As a development team, I want Material Testing module built with complete backend, frontend, and mobile support so that construction material quality is systematically recorded. | AC1: Database schema, master tables, and design tables are created; AC2: Business logic APIs are developed for all Material Testing workflows; AC3: GET and SET data access methods and stored procedures are developed; AC4: New web pages and UI are developed for GM and Contractor login; AC5: Mobile development for FE login is completed; AC6: SQC and TPIA login pages and APIs are developed | Done | Sprint 12-15 | 250
Material Testing – GM/Contractor Login Testing | US-MAT-C4-002 | High | As a QA engineer, I want comprehensive testing of Material Testing module including wireframing, workflows, and production validation so that the module is ready for PHED. | AC1: Wireframing and workflow documentation are completed for all login types; AC2: Requirement gathering sessions are conducted with stakeholder sign-off; AC3: Test cases and test scenarios are created for all login types and workflows; AC4: Internal, SIT, staging, and UAT/Production/CR testing are completed; AC5: All production bugs are identified, tracked, and resolved | Done | Sprint 12-15 | 40
Material Testing – FE Login | US-MAT-C4-003 | High | As a Field Engineer, I want to receive material testing assignments and submit field test results through the mobile application so that testing data is captured at the site. | AC1: FE receives assignment notification on the mobile application; AC2: Test result entry supports photo upload from the field; AC3: GPS coordinates are captured at the time of result submission; AC4: Internal testing is completed with all test cases passing; AC5: UAT, production, and CR testing are completed with sign-off | Done | Sprint 12-13 | 30
Material Testing CR – FE Inspection Date in GM/SQC/TPIA | US-MAT-C4-004 | Medium | As a GM/SQC/TPIA user, I want the FE Inspection Date field visible on all Material Testing web pages for GM, SQC, and TPIA login so that the inspection timeline is traceable. | AC1: FE Inspection Date column is added to Material Testing web pages for GM login; AC2: FE Inspection Date is added to the SQC login view; AC3: FE Inspection Date is added to the TPIA login view; AC4: Date is sourced correctly from the corresponding inspection records; AC5: Changes are tested and deployed to production | Done | Sprint 15 | 8
Material Testing – OHT Search & Sub-Component Search | US-MAT-C4-005 | Low | As a mobile user, I want OHT search and Sub-Component search functionality in Material Testing mobile so that users can quickly locate the asset or component they need. | AC1: OHT search functionality is added to the Material Testing mobile application; AC2: Sub-Component search is added (shared with Cube Testing module); AC3: Search results are filtered correctly based on input; AC4: Search works in offline mode; AC5: Changes are tested and deployed to the Play Store | Done | Sprint 15 | 16

## Nirmal US
Jal Rekha – Cycle 4 User Stories ¦ Nirmal (FE Mobile, GM, CR) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Nirmal FE Mobile – Development | US-NRM-C4-001 | High | As a Field Engineer, I want the Nirmal mobile app enhanced with geofencing, new water sampling module, and WTP/Raw Water reporting so that water quality monitoring is comprehensive. | AC1: Water Sampling Collection by Contractor is functional on the mobile app; AC2: Geofencing with a 200-metre buffer is enforced for WTP and Intake sample collection; AC3: New Nirmal water quality module is available on mobile; AC4: New web pages are created for Nirmal reports (Beneficiary, OHT, WTP, Raw Water); AC5: All four report types are available on the web portal; AC6: SIT, UAT, production, and CR testing are completed | Done | Sprint 12 | 95
Nirmal FE Mobile – API & Wireframe | US-NRM-C4-002 | High | As a developer, I want API creation, UI updates, and unit testing for Nirmal FE mobile completed so that all Nirmal module endpoints are functional. | AC1: APIs are created for all Nirmal mobile endpoints; AC2: UI is updated on all existing Nirmal mobile pages; AC3: Requirement gathering and wireframe are completed and documented; AC4: Unit testing is completed for the Nirmal module; AC5: Testing is completed with a defect log maintained | Done | Sprint 12-13 | 30
Nirmal GM – Report Modification | US-NRM-C4-003 | High | As a GM user, I want Nirmal reports created/modified and beneficiary report issue resolved so that water quality data is accurately represented. | AC1: Reports are created and modified for GM Nirmal login; AC2: Beneficiary report issue is identified and fixed; AC3: Reports load within 5 seconds for datasets with 1000 or more records; AC4: Export to Excel and PDF is functional; AC5: Report changes are validated and verified in production | Done | Sprint 12 | 8
Nirmal CR – Beneficiary & All Reports | US-NRM-C4-004 | High | As an FE and contractor user, I want Nirmal Beneficiary, OHT, WTP, and Raw Water reports updated per change request with remarks column and contractor-scheme filtering so that water quality reports are role-specific and complete. | AC1: Remarks column is added to the Beneficiary report for both Contractor and GM login; AC2: Only contractor-assigned schemes are displayed in contractor view across all reports; AC3: Beneficiary Report UI popup changes are applied per the Change Request; AC4: WTP, OHT, and Raw Water reports are updated per the Change Request; AC5: All changes are moved to production after unit testing; AC6: Residual chlorine field is correctly disabled in WTP Intake FRC test data | Done | Sprint 13 | 20

## O&M Billing US
Jal Rekha – Cycle 4 User Stories ¦ O&M Billing (GM / Contractor / Workflow) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
O&M Billing GM – Development & Reports | US-OM-C4-001 | High | As a GM user, I want O&M Billing module with new web pages, reports, and partial billing support developed so that billing operations are accurate and auditable. | AC1: New web pages and UI are developed for GM login; AC2: Partial O&M Bill functionality is implemented; AC3: Frontend and database bugs are identified and fixed; AC4: GET and SET data access methods and APIs are created; AC5: Database architecture is designed with master table validation; AC6: SIT and UAT/Production/CR testing are completed; AC7: Test cases and test scenarios are documented | Done | Sprint 12-15 | 222
O&M Billing GM – Requirement & CR | US-OM-C4-002 | High | As a BA/PM, I want requirement gathering, analysis, and change request implementation for O&M Billing GM module so that department expectations are met. | AC1: Requirement gathering for GM and Contractor billing flow is formally documented; AC2: Internal meetings are conducted with minutes recorded; AC3: Census Population is auto-fetched from Scheme Village Master; AC4: GM HSC Change request is implemented; AC5: Monitoring changes requirement is documented and tracked | Done | Sprint 12-15 | 34
O&M Billing Workflow | US-OM-C4-003 | High | As a higher official, I want O&M Billing workflow between GM and higher officials defined and implemented so that billing approvals follow a structured escalation path. | AC1: Billing workflow is documented covering: Contractor → GM → Higher Officials; AC2: Requirement gathering sessions are completed and signed off; AC3: Approval hierarchy with notifications is implemented; AC4: Workflow is tested end-to-end with all roles; AC5: Workflow diagram is reviewed and approved by the department | Done | Sprint 12 | 27
O&M Billing CR – Contractor | US-OM-C4-004 | High | As a contractor, I want bill generation flow, abstract page generation, complaint and pressure redressal sheets, and summary page changes implemented so that contractor billing is complete and compliant. | AC1: Contractor Bill generation flow is updated to include Approved Reports; AC2: Generate Abstract Page and Pressure Redressal Sheet are enabled after Save and Submit; AC3: Summary Page generation for Contractor is implemented; AC4: CR in Contractor Summary Page Abstract Report is applied; AC5: Complaint Date column modification is completed; AC6: Dhara Reports from the Contractor side are updated and validated | Done | Sprint 13-15 | 249
O&M Billing CR – Summary Page, Final Submission & Dynamic Buttons | US-OM-C4-005 | High | As a contractor, I want the O&M Billing Summary page to correctly show/hide Draft and Submit buttons based on bill submission status and prevent data modification after final submission so that billing integrity is maintained. | AC1: Draft and Save buttons are hidden after final bill submission on the Summary page; AC2: Bulk, Village, and Deduction Details buttons are disabled after final submission; AC3: Add and Update operations in Residual Pressure, Complaint Redressal, and Power Consumption tabs are restricted after final submission; AC4: is_draft flag is returned correctly by the database function; AC5: End-to-end testing is completed for both Draft and Final submission states | Done | Sprint 14-15 | 40
O&M Billing CR – PDF Generation (Residual Pressure & Bulk Report) | US-OM-C4-006 | Medium | As a GM and contractor user, I want PDF generation for Residual Pressure and Bulk reports in O&M Billing so that billing documents can be formally printed and submitted. | AC1: PDF generation is implemented for the Residual Pressure report; AC2: PDF generation is implemented for the Bulk report; AC3: Dynamic RA Bill No is auto-generated in the PDF header; AC4: PDF service creation and modification are completed; AC5: Generated PDFs are tested and validated for accuracy | Done | Sprint 15 | 20
O&M Billing CR – Power Consumption & CPWI Calculation | US-OM-C4-007 | Medium | As a GM user, I want Power Consumption tab calculation logic and CPWI/Yearly Factor mapping in O&M Billing so that utility cost data is accurately computed. | AC1: Power Consumption tab calculation logic is updated per the revised formula; AC2: CPWI and Yearly Factor parameters are mapped per bill context; AC3: Data is displayed based on bill context; AC4: Summary tab shows Gross O&M Bill with editable fields and correct totals; AC5: Save VillageDeductionDetails with Draft Save is implemented | Done | Sprint 14-15 | 32

## Sahbhagita US
Jal Rekha – Cycle 4 User Stories ¦ Sahbhagita (GM / CR / Reports) ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Sahbhagita GM – Reports & Approval | US-SAH-C4-001 | High | As a GM user, I want Sahbhagita survey approval page and updated reports so that community participation surveys can be reviewed and approved formally. | AC1: New Survey Approval page is created with a pending survey list for GM review; AC2: Approve and Reject buttons are functional with mandatory remarks on rejection; AC3: Report modifications are visible in the Sahbhagita Reports menu; AC4: Frontend bug fixes are applied; AC5: SIT and UAT/Production/CR testing are completed; AC6: Upload Activities through Web Portal is verified as functional | Done | Sprint 12 | 6
Sahbhagita CR – RA Bill & Save as Draft | US-SAH-C4-002 | High | As a PM user, I want RA Bill functionality on CP Manager and Save as Draft feature added to Sahbhagita module so that ISA billing and survey submissions are managed effectively. | AC1: RA Bill functionality on CP Manager page is implemented; AC2: Save as Draft feature is added to Sahbhagita forms; AC3: ISA Bill Form is linked to Scheme and District; AC4: Bill amount is auto-calculated based on defined parameters; AC5: Report changes are tested and verified in production | Done | Sprint 14-16 | 23
Sahbhagita Report – New Web Page | US-SAH-C4-003 | Medium | As a developer, I want new Sahbhagita report web pages created so that GM and PM users can access community participation data in a structured format. | AC1: New web page for Sahbhagita reports is created; AC2: Report columns include Activity Type, Participation Count, NGO, ISA, and Video Evidence; AC3: Filter options are available for Date, Village, ISA, and NGO; AC4: Export to Excel and PDF is functional; AC5: Report loads within 3 seconds | Done | Sprint 12 | 6
Sahbhagita CR – NGO Count Segregation & PIU Dropdown | US-SAH-C4-004 | Medium | As a GM user, I want the Sahbhagita Summary Page NGO count segregation issue fixed and role-based PIU Dropdown applied in reports so that data is accurate and role-filtered. | AC1: NGO Count Segregation issue on the Summary Page is fixed; AC2: Role-based PIU Dropdown is applied in the report search; AC3: Search validation changes are applied; AC4: Live issue of ISA not displaying per scheme is fixed; AC5: Changes are tested and deployed to the production environment | Done | Sprint 15-16 | 22

## SVS US
Jal Rekha – Cycle 4 User Stories ¦ SVS Water Supply Monitoring – Har Ghar Jal ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
SVS – Module Initiation & NIC API Integration | US-SVS-C4-001 | High | As a project manager, I want the SVS Water Supply Monitoring module initiated with formal requirement gathering and NIC Panchayat Darpan API finalised so that the development team has complete specifications and integration details before build begins. | AC1: Project module initiation meeting is conducted and MoM is documented; AC2: Requirement gathering sessions are conducted with PHE stakeholders; AC3: API endpoints and data contract from NIC Panchayat Darpan are finalised; AC4: Village Master data structure is confirmed and mapped to SVS fields; AC5: SVS Daily Water Supply Wireframe is reviewed and approved; AC6: Database schema is designed with field-level mapping | Done | Sprint 16 | 4
SVS – Daily Water Supply Data Entry Form | US-SVS-C4-002 | High | As a GP user or PHE field officer, I want a structured daily water supply data entry form with District, Block, GP, Village, and Household Connections pre-filled so that I can quickly record supply status. | AC1: Form displays District, Block, GP, and Village based on logged-in user jurisdiction; AC2: Household Connections Established is auto-populated from Village Master; AC3: Water Supply Date defaults to the current date; AC4: Mandatory field validation is enforced before submission; AC5: Submission confirmation is displayed; AC6: Record is saved with user ID, timestamp, and village code | Done | Sprint 16 | 12
SVS – Water Supply Date Picker | US-SVS-C4-003 | High | As a GP user, I want a date picker control on the SVS water supply entry form so that I can accurately select the date of water supply without manual text entry errors. | AC1: Calendar date picker is displayed for the Water Supply Date field; AC2: Default date is set to the current system date; AC3: Future dates are restricted; AC4: Date is stored in DD-MM-YYYY format in the database; AC5: Date picker works on desktop and Android mobile browsers; AC6: Selected date is visible before final submission | Done | Sprint 16 | 4
SVS – Water Supply Status – YES Flow | US-SVS-C4-004 | High | As a GP user, I want to record YES (हाँ) water supply status for my village on a given date so that the system reflects successful daily supply. | AC1: YES can be selected from the Water Supply Status field; AC2: No additional mandatory fields are shown when YES is selected; AC3: Record is saved with Status = YES, date, village code, and user ID; AC4: Dashboard reflects the YES count; AC5: GP and PHE login can view YES records in the daily report; AC6: Reason/Remark field is not shown when YES is selected | Done | Sprint 16 | 8
SVS – Water Supply Status – NO Flow with Reason | US-SVS-C4-005 | High | As a GP user, I want to record NO (नहीं) supply status with a mandatory reason selection and remarks box so that the department can track and address supply failures with root cause data. | AC1: Selecting NO shows a mandatory Reason dropdown (Tubewell Failure, OHT Not Filled, Motor Pump, Valve/Pump Operator, Electricity, Pipeline Damage, Any Other + Remarks); AC2: Reason is mandatory when status is NO; AC3: Any Other option opens a mandatory free-text Remarks box; AC4: Remarks box is shown by default when NO is selected; AC5: Record is saved with Status = NO, reason code, and remarks; AC6: GM dashboard shows NO count with reason breakdown | Done | Sprint 16 | 8
SVS – Water Supply Status – PARTIAL Flow | US-SVS-C4-006 | High | As a GP user, I want to record PARTIAL (आंशिक) supply status with the number of connections that received water and a mandatory remarks box so that partial supply incidents are tracked with quantitative data. | AC1: PARTIAL status shows a mandatory numeric Connections Supplied Water input; AC2: Connections Supplied cannot exceed total HSC Connections; AC3: Remarks box opens automatically when PARTIAL is selected; AC4: Remarks are mandatory for PARTIAL status; AC5: Record is saved with Status = PARTIAL, connection count, and remarks; AC6: Dashboard shows PARTIAL count and connections percentage | Done | Sprint 16 | 8
SVS – Partial Edit Feature | US-SVS-C4-007 | High | As a GP user or PHE officer, I want to partially edit a previously submitted daily water supply record so that data corrections can be made without deleting the full record. | AC1: Partial Edit is available within a configurable edit window (same day or 24 hours); AC2: Status, Reason (NO), Connections (PARTIAL), and Remarks are editable without changing Date or Village; AC3: Edit log captures original and updated values with editor user ID and timestamp; AC4: Edited records are flagged as Modified in all reports; AC5: Only authorised roles can perform edits; AC6: Records beyond the edit window require supervisor approval | Done | Sprint 16 | 4
SVS – Default Hierarchy Selection by Login | US-SVS-C4-008 | High | As a logged-in GP or PHE user, I want District, Block, and GP auto-selected by default based on my login credentials so that I do not need to manually navigate the location hierarchy. | AC1: System identifies user District, Block, and GP from profile on login; AC2: District, Block, and GP are pre-filled and locked for GP-level users; AC3: PHE and Block-level users see defaults but may change Block and Village within scope; AC4: District-level users can view all Blocks and GPs; AC5: Default hierarchy is applied in all SVS forms; AC6: GP users do not need to re-select location for daily submissions | Done | Sprint 16 | 4
SVS – Hindi Interface (MP Shasan Labels) | US-SVS-C4-009 | High | As an MP government user, I want the SVS water supply entry form to display field labels in Hindi (MP Shasan standard) so that GP-level and rural users can use the system in their native language. | AC1: All SVS form labels are displayed in bilingual or Hindi-only mode based on language settings; AC2: Labels used include: जल प्रदाय दिनांक, जल प्रदाय की स्थिति, हाँ, नहीं, आंशिक, स्थापित घरेलू नल कनेक्शन; AC3: Reason dropdown options are in Hindi; AC4: MP Shasan branding is applied; AC5: Hindi rendering is tested on Chrome and Android | Done | Sprint 16 | 4
SVS – Remove Unwanted Fields (JJM, Village Status, Hand Over Community) | US-SVS-C4-010 | Medium | As a PHE department stakeholder, I want the JJM field, Village Status field, and Hand Over Community field removed from the SVS supply monitoring form so that the form is focused and aligned to current department requirements. | AC1: JJM field is removed from SVS data entry form and all report columns; AC2: Village Status field is removed from the form; AC3: Hand Over Community field is removed from the form; AC4: Database columns are retained but not exposed in UI or reports; AC5: Historical records remain accessible through the admin view; AC6: Field removal is tested in staging; AC7: Report templates are updated accordingly | Done | Sprint 16 | 4
SVS – Excel Report with LGD Code and Household Join | US-SVS-C4-011 | High | As a PHE data analyst or district officer, I want Excel downloadable reports from SVS that include the LGD Code and Household Connections data joined to each village record so that reports can be cross-referenced with national LGD data. | AC1: SVS Excel download includes the LGD Code column; AC2: Household Connections Established is joined from Village Master; AC3: LGD Code and Household data are sourced from IMS and Panchayat Darpan master; AC4: Excel columns include: District, Block, GP, Village, LGD Code, HSC, Supply Date, Status, Reason, Connections Supplied, Remarks; AC5: Date range filter is available; AC6: Excel file is generated within 10 seconds for 1000 records | Done | Sprint 16 | 8
SVS – Dashboard: Village / Block / District Level Monitoring | US-SVS-C4-012 | High | As a PHE department official, I want a SVS monitoring dashboard showing daily water supply status (YES / NO / PARTIAL counts) at village, block, and district level with drill-down navigation so that supply performance is visible at all governance levels. | AC1: Dashboard shows total villages versus submitted records for the selected date; AC2: Status breakdown is displayed as YES (green), NO (red), PARTIAL (amber), and Not Submitted (grey); AC3: Drill-down navigation is available from District → Block → GP → Village; AC4: Date filter is available on the dashboard; AC5: Reason for NO supply is visible in a sub-panel; AC6: Dashboard refreshes on demand; AC7: Dashboard is accessible to PHE, GM, District, and Block login roles with scope restriction; AC8: 1 Scheme = 1 Handpump monitoring alignment is applied | Done | Sprint 16 | 16
SVS – Panchayat Sachiv DWSR Entry at Rural Level | US-SVS-C4-013 | High | As a Panchayat Sachiv, I want a dedicated Daily Water Supply Report (DWSR) entry form on the web portal so that I can record village-level water supply data for each SVS village under my Gram Panchayat on a daily basis. | AC1: DWSR entry form is accessible to Panchayat Sachiv login on the web portal; AC2: SVS scheme approach (1 Village = 1 Scheme) is applied; AC3: Form pre-fills District, Block, GP, Village, and HSC from user profile and Village Master; AC4: Water Supply Status options are: Yes, No, and Partial; AC5: No supply reason is mandatory when status is No or Partial; AC6: Geo-tagged photo upload is supported; AC7: Record is saved with GP user ID, timestamp, and village code | Done | Sprint 16 | 8
SVS – DWSR Report Generation | US-SVS-C4-014 | High | As a PHE officer or Panchayat Sachiv, I want a DWSR (Daily Water Supply Report) generated from submitted data showing village-wise supply status, meter readings, and volumes so that daily performance can be formally reported. | AC1: DWSR report is generated per GP per date; AC2: Report columns include Village, SVS Code, Total HH, HSC Connections, HH Supplied, Supply Hours, Volume (kl), Schools, Status, Reason; AC3: Block and District consolidated totals are displayed; AC4: Excel download is available; AC5: Date range filter is operational; AC6: Report loads within 5 seconds for a GP with up to 50 villages | Done | Sprint 16 | 8
SVS – DWSR Summary Report | US-SVS-C4-015 | High | As a district officer, I want a consolidated DWSR Summary Report at Block, GP, and District level so that I can monitor submission compliance and identify non-reporting GPs. | AC1: Summary Report includes tabs for Block-wise, GP-wise, Village-wise, and 7-Day Trend; AC2: GP-wise submission status (Submitted, Partial, Not Reported) is displayed; AC3: SVS versus MVS supply performance comparison is available; AC4: Not Reported GP count is prominently displayed; AC5: Excel download of the summary is available; AC6: Report is accessible to District, Block, PHE, and GM roles | Done | Sprint 16 | 4

## CMMI Doc US
Jal Rekha – Cycle 4 User Stories ¦ CMMI Documentation + Dept Meetings ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
CMMI Doc – Data Collection Cycle 4 | US-CMMI-C4-001 | High | As a SEPG team member, I want to collect data for Cycle 4 (Jan to May 2026) so that I can measure project performance metrics and prepare CMMI Level 5 audit artifacts. | AC1: Data collection sheet includes all required fields (Requirement, Design, Coding, Code Review, Testing Efforts); AC2: Data is collected and recorded for all Cycle 4 modules; AC3: Defect data is captured across all review stages; AC4: Productivity, DRE, and Cycle Time are calculated automatically; AC5: Data is validated for accuracy before submission to the SEPG team | Done | Sprint 12-16 | 108
CMMI Doc – Streamline Documentation | US-CMMI-C4-002 | High | As a quality manager, I want CMMI documentation streamlined for O&M Billing, Bharosa, and Material modules so that audit artifacts are consistent and complete. | AC1: Streamline documentation is completed for O&M Billing, Bharosa, and Material Testing modules; AC2: Documents are reviewed and aligned with CMMI L5 standards; AC3: Induction training session is attended by relevant team members; AC4: Promote activity for CMMI L5 Audit is completed; AC5: Documents are archived in the SVN repository with proper version control | Done | Sprint 13 | 60
CMMI Doc – Phase 1 to 4 Completion | US-CMMI-C4-003 | High | As a SEPG team member, I want CMMI documentation completed across all four phases for Cycle 4 so that the project is fully prepared for CMMI Level 5 audit. | AC1: Phase 1 documentation (Planning and Estimation) is completed; AC2: Phase 2 documentation (Requirements and Design) is completed; AC3: Phase 3 documentation (Coding and Code Review) is completed; AC4: Phase 4 documentation (Testing and Deployment) is completed; AC5: All phases are reviewed and approved by the SEPG Head; AC6: Data collection for Jan–May Cycle 4 is baselined | Done | Sprint 12-16 | 531
Department Meetings – Requirement Gathering | US-CMMI-C4-004 | High | As a BA/PM, I want department meetings conducted for all module requirements and changes so that all stakeholder needs are documented and tracked. | AC1: Department meetings are conducted for all modules and formally documented; AC2: New Material Testing and Cube Testing module requirements are discussed and captured; AC3: Requirement gathering for all module changes is completed; AC4: Meeting minutes are prepared and distributed within 24 hours; AC5: Requirements are tracked via the traceability matrix | Done | Sprint 12-16 | 57

## Site Security US
Jal Rekha – Cycle 4 User Stories ¦ Site Security Audit ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Site Security Audit | US-SEC-C4-001 | High | As a security team member, I want Jal Rekha site Fortify security audit conducted so that all security vulnerabilities are identified and remediated before production. | AC1: Fortify security audit is configured and executed on the Jal Rekha codebase; AC2: Critical and high severity vulnerabilities are documented with full details; AC3: Remediation plan is created with assigned owners and target timelines; AC4: Security audit report is submitted to the department; AC5: Dhara module-specific security issues are identified and resolved | Done | Sprint 15 | 16
Site Security – Code-Level Vulnerability Fixes | US-SEC-C4-002 | High | As a developer, I want all critical and high vulnerabilities identified by Fortify remediated in the codebase so that Jal Rekha meets security compliance before production release. | AC1: All critical vulnerabilities identified by Fortify are patched in the codebase; AC2: High severity vulnerabilities are patched or accepted with documented risk justification; AC3: Fortify re-scan post-fix shows zero critical issues; AC4: Security fix code is reviewed by a senior developer; AC5: All security fixes are deployed to the production environment | WIP | Sprint 15-16 | 16

## Sopan US
Jal Rekha – Cycle 4 User Stories ¦ Sopan Contractor ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
Sopan Contractor – Development & Testing | US-SOP-C4-001 | High | As a contractor, I want the Sopan Contractor module with dashboard, data upload, and new web pages functional so that scheme-level contractor activities are properly managed. | AC1: Dashboard for Sopan Contractor is developed and functional; AC2: Upload Activities through Web Portal is implemented and working; AC3: New web pages and GET/SET data access methods are created; AC4: OHT data correction functionality is available; AC5: Database bug fixes are applied; AC6: Requirement gathering is completed and documented; AC7: SIT, UAT, production, and CR testing are completed | Done | Sprint 13 | 6
Sopan CR – OHT Data Correction | US-SOP-C4-002 | Medium | As a data admin, I want OHT data correction functionality in Sopan so that incorrect OHT entries can be identified and fixed without affecting production data. | AC1: OHT data correction page is available in the Sopan module; AC2: Audit log is maintained for all data corrections; AC3: Only Admin and Superuser roles can perform OHT data corrections; AC4: Correction is tested in staging before deployment; AC5: Changes are deployed and verified in the production environment | Done | Sprint 13 | 4

## User Role US
Jal Rekha – Cycle 4 User Stories ¦ User & Role Management ¦ Jan 2026 – May 2026 ¦ CMMI Level 5
Module / Sub-Module | User Story ID | Priority | User Story Description | Acceptance Criteria | Status | Sprint | Effort (hrs)
User & Role Management – Testing | US-URM-C4-001 | High | As a QA engineer, I want functional and SIT testing of User and Role Management module completed so that all access controls and permissions are verified before release. | AC1: Functional testing is completed for all user roles across all Jal Rekha modules; AC2: SIT testing is completed with all cases passing; AC3: Permission matrix is verified for all roles; AC4: No unauthorised access is identified during testing; AC5: Test report is submitted with complete coverage details | Done | Sprint 14 | 12
User & Role Management – Role-Based Data Scope Enforcement | US-URM-C4-002 | High | As a system admin, I want role-based data scope enforcement applied to all Jal Rekha modules so that each user only sees data within their assigned geography and role. | AC1: District-level users can view data only within their assigned district; AC2: Block-level users are restricted to data within their assigned block; AC3: GP-level users are restricted to data within their assigned GP; AC4: Contractor users can view data only for their assigned schemes; AC5: Role-based scope is tested for Dhara, SVS, FHTC, Nirmal, and O&M Billing; AC6: No cross-role data leakage is identified | Done | Sprint 14-15 | 12