## Jal Rekha Master Tracker
JAL REKHA PROJECT — MODULE-WISE IMPLEMENTATION & CHANGE REQUEST TRACKER (April–July 2026)
Client: Govt. of MP – PHED (Jal Nigam) ¦ Contract: MPSEDC/MPSSDI(GIS)/2025/00423 ¦ Prepared by: Dheeraj Motiyani, Sr. BA ¦ Source: MoM (MD Sir) 28-Apr/19-May/9-Jun/16-Jun 2026, CR Log Cycle 4-5 (Jun-Jul 2026)
S.No | Module Name | Sub-Module Name | Feature / Functionality Implemented | Type (New Requirement / CR) | Month | Date Raised | Date Completed | Status | Remarks / Reference
1 | Anushravan | Anusharavan | Include multiple date in report - FE RFI Submission date & Block name also added | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
2 | Anushravan | RFI Workflow | RFI Pull Back & Reassign option for GM PIU (deferred, low priority) | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | Raised in May 2026 MoM Section 2 (New Discussion Points)
3 | Anushravan | Contractor Mobile | Abstract of Anusharavan at Contractor mobile login | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | Raised in May 2026 MoM Section 2 (New Discussion Points)
4 | Anushravan / Cube / Material Testing | Anushravan/Cube/Material | Remove Mandatory in Intake, WTP, MBR, RWPM, & CWPM in dropdown Village and GP | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
5 | Anushravan / Cube / Material Testing | Anushravan/Cube/Material | Give Save as Draft functionality & Provide option to upload photo later on | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-05-19 | Completed | Done
6 | Anushravan / Cube / Material Testing | Anushravan/Cube/Material | OHT Search option during RFI | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
7 | Asset Mapping | Asset Mapping | SQC TPIA Contractor Data and Report on Web | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
8 | Bharosa | Bharosa | Factory Testing WEB - Add QAP 3rd Party & upload multiple images | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
9 | Cross-Module | Data Consistency | No Water Supply = 0 KL & Meter Not Functional = 'X KL' display consistency across logins | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Raised in May 2026 MoM Section 2 (New Discussion Points)
10 | Cross-Module | External Integration | Sujalam Bharat App (BISAG/Gati Shakti) data API and PM Gati Shakti data link - master data pending from Jal Nigam | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | Raised in May 2026 MoM Section 2 (New Discussion Points)
11 | Cube Testing | Cube | Structure components to be added against each Component | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
12 | Cube Testing | Cube | Date of costing for RFI loop 7th and 28th day added | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
13 | Cube Testing | Cube | Add Filter Bed as Sub Component under WTP Component | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Done
14 | Cube Testing | Cube Module Mobile CR | Add Mandatory multiple image upload functionality to the FE inspection form | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Done (UAT)
15 | Cube Testing | Cube Module Mobile CR | Add Mandatory multiple image upload functionality to the FE inspection form and Save as Draft | New Requirement (MoM) | June 2026 | 2026-06-09 | 2026-06-09 | Completed | Done
16 | Cube Testing | Cube Testing | Cube ID get generated before image upload | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
17 | Cube Testing | Cube Testing | Show rejected data to Contractor | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
18 | Cube Testing | Cube ID Generation & Rejected-Data Visibility | Cube Testing – Cube ID get generated before image upload; Show rejected data to Contractor. | Change Request | June 2026 | 2026-06-16 | 2026-07-08 | Completed | CR Code: CUBE-JUN-2026-005; Delivered per MoM 16-Jun-2026, Point 2.
19 | DWSR Public Report | Public Report DWSR | Open to Public | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-06-09 | Completed | Done
20 | Dhara | Dhara | New Dhara Report to be shown on all Jal Rekha logins | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-05-19 | Completed | Done
21 | Dhara | Dhara | GM Approved Reports & Contractors Dispute | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-06-09 | Completed | Done
22 | Dhara | Meter Reading Workflow | Mohkhed scheme - meter reading replication bug (multiple source tapping points) - critical issue | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | Raised in May 2026 MoM Section 2 (New Discussion Points)
23 | Dhara | Meter Reading Workflow | Contractor Remark/Objection on KL reading routed to GM Approve/Reject with 3-day auto-approve | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | Raised in May 2026 MoM Section 2 (New Discussion Points)
24 | Dhara | Non-Mandatory Options – Go Live 19-Jun | O&M Billing – Mandatory options & go-live on 19th June across all logins: (1) Remark, (2) Photo Upload, (3) Forward, (4) Backward Options. | Change Request | June 2026 | 2026-06-01 |  | In Progress | CR Code: DHARA-MAY-2026-021; Go-live 19-Jun-2026 confirmed. Non-mandatory: Remark, Photo Upload, Forward, Backward.
25 | Dhara | Approved Report Lock – Entry Freeze | Dhara– Approved report data entry should NOT change once approved. UI lock for GM PIU. GM PIU/TL can ADD (not edit). GM can add new penalty point on Contractor bill. | Change Request | June 2026 | 2026-06-03 |  | In Progress | CR Code: DHARA-MAY-2026-009; GM can add new point (Penalty applied). Cannot edit existing Contractor-generated bill data.
26 | Dhara | PHE _Dhara GP Reading | GP wise Village Reading | New Requirement (MoM) | June 2026 | 2026-06-09 | 2026-06-09 | Completed | Done
27 | Jal Samadhan | Complaint Management | New Complaint related queries page for Jal Samadhan | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | Raised in May 2026 MoM Section 2 (New Discussion Points)
28 | Jal Samadhan | Complaint Management | Complaint tracking with status view for public users and GM login | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | Raised in May 2026 MoM Section 2 (New Discussion Points)
29 | Jal Samadhan | Complaint Management | SLA-based escalation workflow to PIU with notification timelines | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | Raised in May 2026 MoM Section 2 (New Discussion Points)
30 | Master | Bulk Consumer | scheme bulk consumer | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
31 | Master | Bulk Consumer Mapping | Bulk consumer mapping - oht wtp | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
32 | Master | Data Validation | Duplicate Village Mapping validation across schemes | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
33 | Master | Mapped Report Status | Of all above 4 reports Mapped in Mapped status report . summary report - vidhan sabha district wise | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
34 | Master | Master | scheme village master.. scheme piu village DONE | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
35 | Master | Master | oht village master | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
36 | Master | Scheme / Village / OHT Master – Entry Lock | Master – Lock Scheme Master, Village Master and OHT Master entries once linked to live transactions (Dhara, O&M Billing, Asset Mapping); GM (PIU) side all details lock. | Change Request | June 2026 | 2026-06-18 |  | In Progress | CR Code: MSTR-JUN-2026-006; Extends the Dhara approved-report lock principle (CR OMB/DHARA-MAY-2026-009) to the Master data layer.
37 | Material testing and cube testing | Re-Inspection Loop (2nd Cycle – After GM Rejection) | Material testing & Cube testing - cycle loop runs 2nd time after rejction from GM. FE to GM to contractor back to GM again to SQC TPIA then to FE again (if new FE added) | Change Request | June 2026 | 2026-06-20 |  | In Progress | CR Code: CUBEMAT-JUN-2026-007; 2nd loop post-rejection: FE → GM → Contractor → GM → SQC → TPIA → FE (new). Complex state machine; must retain original submission data alongside new loop data.
38 | Material testing and cube testing | RFI 2nd Loop – Image Upload Optional | Material testing & Cube testing - cycle loop run - Image optional in RFI 2nd time loop (in Cube and Material testing) | Change Request | June 2026 | 2026-06-20 |  | In Progress | CR Code: CUBEMAT-JUN-2026-008; Image optional flag must not apply to 1st cycle. CR depends on CUBEMAT-JUN-2026-007 (loop CR) being implemented first.
39 | O&M | O&M | Power Consumption - Need To Change Contractor and GM Side (Contractor - Generate Bill - Add into Contract Details ( Basic Detail, Intermediate Raw Water Demand, and | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
40 | O&M | O&M | Need Two More Column Add in Water Supply During Construction Bill | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
41 | O&M | O&M | O&M Villages - Villages where water Supply during construction is under consideration or approved | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
42 | O&M | O&M | Aaklan Contractor / Dhara - Contractor to check & Raise any discrepancies within time. Dhara data will be used for billing purposes | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
43 | O&M | O&M | GM side if Pump Transformer column has YES then consolidate bill will have 10% deduction in total amount | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
44 | O&M Billing | Contractor Side login | Check final summary report | New Requirement (MoM) | April 2026 | 2026-04-28 |  | In Progress | Some Changes Required
45 | O&M Billing | DWSR Reports | DWSR report development (basic) | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
46 | O&M Billing | GM Side Login | Census population addition in Scheme Master (GM side report) | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
47 | O&M Billing | O&M Billing - Bill | Bill generation for total 64 Schemes | New Requirement (MoM) | April 2026 | 2026-04-28 |  | In Progress | Not Specified
48 | O&M Billing | O&M Billing - Dhara Reports | Dhara report integration in O&M Billing module | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
49 | O&M Billing | Open Platform | Restrict reports: Show only Dhara & DWSR | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
50 | O&M Billing | Open Platform | DWSR column clickable (Hyperlink integration) | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
51 | O&M Billing | Report Optimization | Remove extra reports (Date-wise DWSR, MWSR, UFW, Scheme-wise WSR, Village-wise MWSR, Bulk User MWSR) | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
52 | O&M Billing | GM Approval | Only final approval by GM ( No Provisional approval required) and Concern Remark Mandatory | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Done
53 | O&M Billing | O&M Villages | Villages where water Supply during construction is under consideration or approved | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | In Progress
54 | O&M Billing | PowerConsumption | Need To Change Contractor and GM Side (Contractor - Generate Bill - Add into Contract Details ( Basic Detail, Intermediate Raw Water Demand, and | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | In Progress
55 | O&M Billing | Scheme Status | Need Two More Column Add in Water Supply During Construction Bill | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | In Progress
56 | O&M Billing | Contractor Bill – Abstract | O&M Billing – Contractor Generate Bill: Abstract generation from Contractor login. Select Bill → Generate Abstract → With all villages, scheme (Dhara readings, Master Module tables and UFW Approved report and other documents with Abstract bill ) | Change Request | May 2026 | 2026-05-22 |  | In Progress | CR Code: OMB-MAY-2026-002; Abstract linked to 8th Bill; Tag all villages flag needed.
57 | O&M Billing | Bill PDF Merge – All Documents | O&M Billing – Bill PDF consolidation: approx. 19–20 documents merged into one PDF (GM, SQC, Firm, Form 27A, MB, Abstract). 3-month combined PDF for static docs; monthly for variable docs. | Change Request | May 2026 | 2026-05-22 |  | In Progress | CR Code: OMB-MAY-2026-005; Landscape issue in O&M Bill PDF also fixed in this CR.
58 | O&M Billing | GST Integration | O&M Billing – GST No. Integration with O&M Billing Jal Rekha portal. GST number to be captured and linked at firm/contractor level. | Change Request | May 2026 | 2026-05-22 |  | In Progress | CR Code: OMB-MAY-2026-003; GST No. (150/215) – Rakesh Sir to confirm data source.
59 | O&M Billing | E-Sign – CDAC Integration | O&M Billing – E-Sign Integration via CDAC for all parties (Firm/FE-eSign, Web & Mobile). CDAC integration for e-sign on Bill, Submission Letter, and Tax Invoice. FE (e-sign) → Web & Mobile flow. | Change Request | May 2026 | 2026-05-22 |  | In Progress | CR Code: OMB-MAY-2026-001; CDAC Rakesh Sir to coordinate. FE (e-sign) ↔ Web/Mobile dual flow.
60 | O&M Billing | TL Recommendation Letter – E-Office | O&M Billing – TL Recommendation Letter to be E-Office generated (system-generated). TL (PMC) → E-Office → Account Office Jal Rekha. | Change Request | May 2026 | 2026-05-22 |  | In Progress | CR Code: OMB-MAY-2026-004; TL SQC integration also required. E-Office API/link to be confirmed.
61 | O&M Billing | Billing Workflow Redesign | O&M Billing – Workflow Redesign: Firm → GM PIU → TL SQC → GM PIU → GM O&M → DGM → TL PMC → CFO → CA → P.D. → MD. | Change Request | June 2026 | 2026-06-01 |  | In Progress | CR Code: OMB-MAY-2026-006; Use Manage Page (not old flow). Refer O&M Billing Workflow PDF + JPEG diagrams.
62 | O&M Billing | Contractor Mistake Visibility & PDF Merge | O&M Billing – Contractor mistakes visible to SQC/TL and GM. Show all records on all IDs for GM and SQC. Merge PDF of all O&M documents. | Change Request | June 2026 | 2026-06-03 |  | In Progress | CR Code: OMB-MAY-2026-008; Related to Bill PDF CR (OMB-MAY-2026-005). SQC 7L/4–GM mapping check needed.
63 | O&M Billing | Document Upload Screen Design | O&M Billing – Document Upload Screen: Firm: Firm Submission Letter, Tax Invoice, Any Other (Multiple). TL/SQC: SQC Recommendation Letter, Third Party Water Quality Test Report (Multiple + Remark). GM PIU: PIU Recommendation Letter, Signed Form 27A, Signed Scanned MB, Signed Abstract, Signed Monthly Bill Sheet (Multiple), Any Other Docs (Multiple + Remark). | Change Request | June 2026 | 2026-06-09 |  | In Progress | CR Code: OMB-MAY-2026-015; Ref: Handwritten wireframe (Contractor/Firm, TL SQC, GM PIU sections). Upload + Download + View PDF per doc.
64 | O&M Billing | Abstract Bill – Portrait to Landscape | O&M Billing - Desgin changes portrait to landscape for O&M Report for Abstract Bill | Change Request | June 2026 | 2026-06-20 |  | In Progress | CR Code: OMB-JUN-2026-004; Ref: RA Bill landscape format request. Landscape layout wider table required for Abstract Bill header + village-wise summary columns.
65 | O&M Billing | Save as Draft – Mandatory Upload (Contractor) | Contractor/Firm login – make key document uploads (Submission Letter, Tax Invoice) mandatory before a bill can move out of “Save as Draft” state; draft can be saved with partial data but cannot be forwarded to GM (PIU) until mandatory documents are attached. | Change Request (New) | July 2026 | 2026-07-01 | 2026-07-06 | Completed | CR Code: OMB-JULY-2026-001; New CR – raised to align O&M Billing with Cube/Sahbhagita Save-as-Draft pattern.
66 | O&M Billing | Residual Pressure & Complaint Redressal | O&M Billing – Residual Pressure & Complaint Redressal screen changes. Pressure Threshold Report format update per OM_RA_Bill_Report.pdf. Complaint Redressal - Is complaint resolved in this month ? Renaming Complaint Redressal page :- Date on which complaint received to contractor, Date on which complaint resolved, Total Days taken in Resolving complaint (Days) | Change Request | July 2026 | 2026-07-02 | 2026-07-07 | Completed | CR Code: OMB-JUN-2026-002; Ref: OM_RA_Bill_Report.pdf – Pressure_Threshold_Report. RA/19/50/2025-26/Q1/1 format.
67 | O&M Billing | Complaint Redressal Sheet | Complaint Redressal Sheet – add Complaint Received Date to Contractor, Event-above-48-hours flag and Penalty Relaxation (Yes/No) fields; document upload as per submeter reading. | Change Request (New) | July 2026 | 2026-07-02 | 2026-07-08 | Completed | CR Code: OMB-JUN-2026-003; New CR – extends Residual Pressure CR (OMB-MAY-2026-020) into the Complaint Redressal tab.
68 | O&M Billing | - | Naming and formatting of all pages and corrections needed on O&M Contractor login | Change Request | July 2026 | 2026-07-13 |  | In Progress | CR Code: OMB-JULY-2026-005;
69 | O&M Billing | - | UFW Report taken from Dhara will be shown on O&M Billling Contractor login Page attached with bill | Change Request | July 2026 | 2026-07-13 |  | In Progress | CR Code: OMB-JULY-2026-006;
70 | O&M Billing | - | On Contractor Login Only => Additional document upload by contractor - Firm Letter, Tax Invoice and any other document with remark mandatory - ( on New page - "View Bills") | Change Request | July 2026 | 2026-07-14 |  | In Progress | CR Code: OMB-JULY-2026-007;
71 | O&M Billing | - | FHTC & Sahbhagita Bug Fix and API Service and External API Updations in both modules | Change Request | July 2026 | 2026-07-14 |  | In Progress | CR Code: OMB-JULY-2026-008;
72 | O&M Billing (Aaklan) | Aakalan | 1 Dhara Report complete and release to O&M billing | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
73 | O&M Billing (Aaklan) | Aakalan | Dhara Report complete and release to O&M billing | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Done
74 | O&M Billing (Aaklan) | Aaklan Contractor / Dhara | Contractor to check & Raise any discrepancies within time. Dhara data will be used for billing purposes | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | In Progress
75 | O&M Billing (Aaklan) | Additional Aaklan Updates | GM side if Pump Transformer column has YES then consolidate bill will have 10% deduction in total amount | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | In Progress
76 | O&M Billing (Aaklan) | Pending Bills View – GM Logins | O&M Billing (Aaklan) – GM (PIU Login) & GM (O&M) / Deputy O&M: View Pending Bills and Manage Bills. Bills already generated shown in table. | Change Request | June 2026 | 2026-06-08 |  | In Progress | CR Code: OMB-MAY-2026-014; Aaklan module O&M section. GM PIU & GM O&M/Deputy flows defined.
77 | Parinaam (FHTC) | Parinam | Contractor Search Option | New Requirement (MoM) | June 2026 | 2026-06-09 | 2026-06-09 | Completed | Done
78 | Parinaam (FHTC) | Parinam | FE name shown in reports | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
79 | SVS - Har Ghar Jal (PHE) | SVS Water Supply Monitoring PHE | Removed JJM Id, Village status fields | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
80 | SVS - Har Ghar Jal (PHE) | SVS Water Supply Monitoring PHE | According to login specific District, Block and GP should appear | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
81 | SVS - Har Ghar Jal (PHE) | SVS Water Supply Monitoring PHE | Daily Water Supply Completed - In No option added one more Reason and correct spelling | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
82 | SVS - Har Ghar Jal (PHE) | SVS Water Supply Monitoring PHE | Bilingual conversion for SVS Daily Water supply Page (Hindi English) and Report Column Header ( in Hindi) | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
83 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | New SVS Water Supply Monitoring module - Gram Panchayat/PHE daily water supply data entry form | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
84 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | Form fields: District, Block, GP, Village, No. of Connections Established, Date of Water Supply (Date Picker) | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
85 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | Water Supply Status field with options: Yes / No / Partial | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
86 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | If 'No' - Reason for No Supply dropdown (Tubewell Failure, OHT Not Filled by MVS Contractor, Motor Pump Not Working, Valve cum Pump Operator Problem, Electricity Supply Problem, Pipeline Damage, Any Other with Remarks) | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
87 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | If 'Partial' - Number of Connections Supplied + open Remarks text box | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
88 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | Partial Edit option (DD) to allow correction of submitted entries | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
89 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | MP Shashan (Hindi) interface for GP-level users | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
90 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | District, Block, GP fields pre-filled/default from user profile (login-specific) | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
91 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | Remove JJM ID and Village Status fields; remove 'hand over to community' field - not required | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
92 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | LGD code and household data joined in Excel export | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
93 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | Water Date Picker - calendar control for supply date entry | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
94 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | Open text box for Remarks in 'No' and 'Partial' supply cases | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
95 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | Bilingual conversion for SVS Daily Water Supply page and report column headers (Hindi/English) | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
96 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | Login-specific District, Block and GP auto-population | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
97 | SVS - Har Ghar Jal (PHE) | Daily Water Supply Entry Form | Additional 'Reason' option added for Daily Water Supply Completed = No, plus spelling correction | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Discussed 16-Jun-2026; confirmed Done in 16-Jun MoM (module-level items)
98 | Sahbhagita | Sahbhagita | RA Bill Functionality to be added for Sahbhagita Activity on CP Manager after approve activity | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Done
99 | Sahbhagita | Sahbhagita Mobile CR | Add Save as draft functionality for video, images and documents | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-06-09 | Completed | Done
100 | Sahbhagita | Multi-Select Bill Dropdown | Sahbhagita – Multi-select dropdown for bill selection. RA(1) to RA(12) bill range with Withhold Bills option. | Change Request | June 2026 | 2026-06-01 |  | In Progress | CR Code: SHB-MAY-2026-007; Generate Abstract → Select Bill → Tag all villages. Village-wise & Combined Activities in scope.
101 | Sahbhagita | Hyperlink – Village Activity Document Preview | Sahbhagita – Hyperlink: Village Name → Village Activity Document Preview popup. Two hyperlinks: (1) Village Name, (2) Village Activity Document (Reviewed) & Other Column names | Change Request | June 2026 | 2026-06-04 |  | In Progress | CR Code: SHB-MAY-2026-013; Popup with village activity doc preview.
102 | Sahbhagita | AI Photo Verification – CP Manager | Sahbhagita – Future Scope: Photo Scan → Face/Background AI Model (CP Manager). Video option. Duplicate/Repeated photo detection → flag message to CP Manager. | Change Request | June 2026 | 2026-06-04 |  | In Progress | CR Code: SHB-MAY-2026-012; Future scope. AI model (Photo Scan face + background). Video in scope.
103 | Sahbhagita | Sahbhagita | RA Bill Functionality to be added for Sahbhagita Activity on ISA Manager after approve activity and Edit option. | New Requirement (MoM) | June 2026 | 2026-06-09 | 2026-06-09 | Completed | Done
104 | Sahbhagita | Sahbhagita | At Approval time, Pagination done on Sahbhagita pages | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
105 | Sahbhagita | Sahbhagita | RA bill given to ISA (instead of CP Manager) | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
106 | Sahbhagita | Sahbhagita | FE specific to particular ISA are visible to them | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
107 | Sahbhagita | Sahbhagita | Password reset option given to ISA | New Requirement (MoM) | June 2026 | 2026-06-16 | 2026-06-16 | Completed | Done
108 | Sahbhagita | Abstract Bill – Category Filter | Sahbhagita – Village-wise and Combined Activity abstract report; Category filter (Village/Combined/All); quarterly RA Bill numbering (RA/1–RA/12) reflected on abstract header. | Change Request (New) | June 2026 | 2026-06-18 |  | In Progress | CR Code: OMB-JUN-2026-003; New CR – aligns O&M Abstract Bill with Sahbhagita Village/Combined activity structure.
109 | Sahbhagita | Activity Report – Village/Combined Category Filter | Sahbhagita – Report: Category → Activity. Village Wise (32/27 activities) & Combined (22). Filter: V, C, A. Category V/C/A cross-filter. Ref: Sahbhagita_master_activity_matched.xlsx. | Change Request | June 2026 | 2026-06-18 |  | In Progress | CR Code: SHB-JUN-2026-004; Village 32/27 activities; Combined 22; V/C/A cross-filter. Ref master activity matched xlsx.
110 | UI/UX | UI/UX | Change Module sequence on portal | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-06-09 | Completed | Done
111 | UI/UX | Jal Rekha UI UX | Grouping sequence of Left Menu and Color Coding of Menu | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | In Progress
112 | User Manual | User Manual | Send in the group | New Requirement (MoM) | April 2026 | 2026-04-28 | 2026-04-28 | Completed | Done
113 | Vistrit / Master | Vistrit | WTP Meter Mapping - New Column Addtion Date, Scheme & PIU | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-06-09 | Completed | Done
114 | Vistrit / Master | Vistrit | WTP Meter Name update naming convention - Example Narela-WTP-01 | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-06-09 | Completed | Done
115 | Vistrit / Master | Vistrit | WTP Meter Mapping, Intake Mapping - New Column addition such as Meter name, No of OHT connections with WTP, District, Block & GP for Intake | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-06-09 | Completed | Done
116 | Vistrit / Master | Vistrit | In Scheme Village mapping - Validation applied on Testing and Permitted fields and leave Census Population open at all level | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Done
117 | Vistrit / Master | Vistrit | OHT Issue - For Some OHTs of some Schemes were not visible but visible at FE's Id. Because of Deactivate entries of OHT in Vistrit. Now it is resolved | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Done
118 | Vistrit / Master | Vistrit & Dhara | All Reports Visible in Contractor Dashboard (Vistrit Data Non Editable) | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Done
119 | Vistrit / Master | Vistrit Report | On GM login Id add SMS integration functionality & authenticate it through OTP | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | In Progress
120 | Vistrit / Master | Pipeline Master | Pipeline Master - details and report pages to be completed and released | New Requirement (MoM) | May 2026 | 2026-05-19 |  | In Progress | Raised in May 2026 MoM Section 2 (New Discussion Points)
121 | Vistrit / Master | Vistrit & Dhara | All Reports Visible in Contractor login (Vistrit Data Non Editable) | New Requirement (MoM) | June 2026 | 2026-06-09 | 2026-06-09 | Completed | Done
122 | Vistrit / Master | Vistrit | OTP Verification for GM Login on Scheme, OHT and Bulk Master while Edit Delete | New Requirement (MoM) | June 2026 | 2026-06-16 |  | In Progress | Not Specified
123 | Web Reports (CGM/PMU) | All Web Reports | Enabled Material, Cube & Bharosa Reports on Jal Rekha web user id - CGM,PMU | New Requirement (MoM) | May 2026 | 2026-05-19 | 2026-05-19 | Completed | Done

## Module Summary
MODULE-WISE STATUS SUMMARY (April–July 2026)
Module Name | Total Items | Completed | In Progress | % Complete
Anushravan | 3 | 1 | 2 | 33.33%
Anushravan / Cube / Material Testing | 3 | 3 | 0 | 100%
Asset Mapping | 1 | 1 | 0 | 100%
Bharosa | 1 | 1 | 0 | 100%
Cross-Module | 2 | 1 | 1 | 50%
Cube Testing | 8 | 8 | 0 | 100%
DWSR Public Report | 1 | 1 | 0 | 100%
Dhara | 7 | 3 | 4 | 42.86%
Jal Samadhan | 3 | 0 | 3 | 0%
Master | 7 | 6 | 1 | 85.71%
Material testing and cube testing | 2 | 0 | 2 | 0%
O&M | 5 | 5 | 0 | 100%
O&M Billing | 28 | 10 | 18 | 35.71%
O&M Billing (Aaklan) | 5 | 2 | 3 | 40%
Parinaam (FHTC) | 2 | 2 | 0 | 100%
SVS - Har Ghar Jal (PHE) | 19 | 19 | 0 | 100%
Sahbhagita | 12 | 7 | 5 | 58.33%
UI/UX | 2 | 1 | 1 | 50%
User Manual | 1 | 1 | 0 | 100%
Vistrit / Master | 10 | 7 | 3 | 70%
Web Reports (CGM/PMU) | 1 | 1 | 0 | 100%
TOTAL | 123 | 80 | 43 | 65.04%