## Module Work Summary
JAL REKHA PROJECT — MODULE-WISE WORK DONE SUMMARY (April–July 2026)
Prepared by: Dheeraj Motiyani, Sr. BA ¦ Source: MD Sir MoM (28-Apr/19-May/9-Jun/16-Jun 2026) & CR Log Cycle 4-5 (Jun-Jul 2026)
S.No | Module Name | Work / Task Done (Summary) | Completed Items | Total Items Tracked
1 | O&M Billing | • Dhara report data integrated into O&M Billing module • Census population added to Scheme Master (GM side report) • Redundant reports removed; DWSR made clickable (hyperlink) • GM final-approval-only workflow with mandatory Concern Remark • Power Consumption, Water-Supply-During-Construction columns completed • O&M Villages list (under-construction/approved) finalised • 10% Pump-Transformer deduction logic implemented • Mandatory document upload gate (Submission Letter/Tax Invoice) before Contractor can forward a bill • Residual Pressure & Complaint Redressal screens redesigned per report format • PENDING: Bill generation (64 schemes), Contractor summary report, Abstract generation, multi-doc PDF merge, Document Upload screen, GST integration, CDAC e-Sign, TL E-Office letter, billing workflow redesign | 15 | 33
2 | SVS - Har Ghar Jal (PHE) | • New GP/PHE daily water-supply entry form built (District/Block/GP/Village, connections, date picker) • Water Supply Status (Yes/No/Partial) with reason dropdown and remarks added • Login-specific auto-filled District/Block/GP • Hindi (MP Shashan) bilingual interface delivered • JJM ID, Village Status & 'hand-over-to-community' fields removed • LGD code and household data joined in Excel export • Partial-entry edit option added • All items confirmed complete as of 16-Jun MoM | 19 | 19
3 | Sahbhagita | • RA Bill functionality enabled on ISA/CP Manager login after activity approval (with edit option) • Pagination added on approval screens • RA bill routing moved from CP Manager to ISA • FE visibility restricted to their assigned ISA • ISA password-reset option added • Save-as-Draft for video/image/document uploads completed • PENDING: Village/Combined activity abstract report with V/C/A filter, multi-select RA(1)-RA(12) dropdown with Withhold option, Village Activity Document hyperlink/preview, AI photo duplicate-detection (future scope) | 7 | 12
4 | Vistrit / Master | • WTP Meter Mapping given new columns (Date, Scheme, PIU) • Standard meter naming convention enforced (e.g. Narela-WTP-01) • Intake Mapping enriched with Meter Name/OHT connections/District/Block/GP • Scheme Village Mapping validation applied to Testing & Permitted fields • OHT visibility bug (deactivated entries) fixed • All Vistrit reports made visible (read-only) on Contractor dashboard • PENDING: OTP verification for GM login on Master edit/delete, SMS+OTP auth for Vistrit reports, Pipeline Master pages | 7 | 10
5 | Cube Testing | • Structural components added per component type • RFI-loop costing dates (7th/28th day) captured • Filter Bed added as WTP sub-component • Mandatory multi-image upload with Save-as-Draft enabled on FE mobile inspection form • Cube ID now generates before image upload • Rejected records surfaced back to Contractor for correction • Module fully complete – no pending items | 8 | 8
6 | Master | • Scheme/PIU/Village master completed • OHT village master completed • Bulk-consumer master and bulk-consumer-to-OHT/WTP mapping completed • Duplicate village-mapping validation delivered • Consolidated Mapped Status report (Vidhan Sabha/district-wise) delivered • PENDING: Lock Scheme/Village/OHT Master records once linked to live Dhara/O&M/Asset Mapping transactions | 6 | 7
7 | Dhara | • New Dhara report rolled out on all Jal Rekha logins • GM-Approved-Reports & Contractor-Dispute view released • GP-wise village reading report completed • PENDING: Lock approved report data (GM PIU can add, not edit) • PENDING: Make Remark/Photo-Upload/Forward/Backward optional platform-wide • PENDING: Fix Mohkhed multi-source meter-reading replication bug (critical) • PENDING: Contractor KL-reading objection workflow with 3-day auto-approve | 3 | 7
8 | O&M Billing (Aaklan) | • Dhara report data completed and released into O&M Billing for Aaklan use • PENDING: Contractor discrepancy-raising window against Dhara data • PENDING: Pump-Transformer 10% deduction logic • PENDING: GM (PIU)/GM (O&M)/Deputy O&M 'View Pending Bills' & 'Manage Bill' screens | 2 | 5
9 | Anushravan | • FE RFI report enhanced with multiple submission dates and Block name • PENDING: RFI Pull-Back & Reassign option for GM PIU (deferred/low priority) • PENDING: Anusharavan Abstract view on Contractor mobile login | 1 | 3
10 | Anushravan / Cube / Material Testing | • Village/GP dropdown mandatory-field restriction removed (Intake, WTP, MBR, RWPM, CWPM) • Save-as-Draft with later photo upload enabled • OHT search added during RFI • Module fully complete – no pending items | 3 | 3
11 | Jal Samadhan | • PENDING: Complaint-query submission page • PENDING: Complaint status tracking for public + GM login • PENDING: SLA-based escalation workflow to PIU • New module still in discussion/build – nothing completed yet | 0 | 3
12 | UI/UX | • Module sequence on portal reordered and released • PENDING: Left-menu grouping and colour-coding | 1 | 2
13 | Parinaam (FHTC) | • Contractor search option added • FE name now shown in Parinaam/FHTC reports • Module fully complete – no pending items | 2 | 2
14 | Material testing and cube testing | • PENDING: 2nd-cycle re-inspection loop after GM rejection (FE→GM→Contractor→GM→SQC/TPIA→FE) • PENDING: Optional image upload on 2nd RFI loop • Both items still open/in design | 0 | 2
15 | Cross-Module | • Water-supply display standardised (No Supply = 0 KL, Meter Not Functional = 'X KL') across all logins • PENDING: Sujalam Bharat App (BISAG/Gati Shakti) data-API integration – awaiting master data from Jal Nigam | 1 | 2
16 | Web Reports (CGM/PMU) | • Material, Cube & Bharosa reports enabled for Jal Rekha web user IDs (CGM, PMU) | 1 | 1
17 | Asset Mapping | • SQC/TPIA Contractor inspection data and reporting delivered on web application | 1 | 1
18 | Bharosa | • Factory Testing (Web) completed with 3rd-party QAP and multiple-image upload support | 1 | 1
19 | DWSR Public Report | • DWSR report opened for public access without login | 1 | 1
20 | User Manual | • User manual finalised and circulated to project group | 1 | 1
TOTAL |  |  | 80 | 123