JAL REKHA PROJECT

Module-Wise Work Done Summary

April 2025 – July 2026

      Module-Wise Work / Task Done (Detailed)

## 1. Anushravan

- Village/GP dropdown mandatory-field restriction removed (Intake, WTP, MBR, RWPM, CWPM)

- Save-as-Draft with later photo upload enabled

- OHT search added during RFI

- FE RFI report enhanced with multiple submission dates and Block name

- RFI Pull-Back & Reassign option for GM PIU (deferred/low priority)

- Anusharavan Abstract view on Contractor mobile login

## 2. Asset Mapping

- Users can map assets/component-point data (Intake Well, OHT, BPT, WTP, etc.) across schemes and capture geo-tagged photographs associated with these components

- Design & Drawing: all approved scheme components (Intake Well, WTP, Pipelines, OHTs) mapped onto the GIS-based Jal Rekha portal

- Field Survey Data: geotagged location and photo of each component uploaded via the mobile app by field officers, capturing the actual as-built position

- Data Visualization: approved design/drawing overlaid with updated as-built (surveyed) data on the map, with Proposed vs. Surveyed layer toggle and satellite-image overlay

- Pipe-network mapping progress (as last reported, 24-Nov-25): Planned length 2,16,754 km vs. Uploaded 2,06,234 km (95%); Pipeline laid 1,50,286 km vs. Surveyed 1,24,347 km (83%)

- Point-data mapping progress – Intake Well/WTP/MBR (as last reported, 24-Nov-25): Total Points 12,428 vs. Uploaded 11,448 (92%); Executed Qty 12,772 vs. Surveyed 12,220 (95%)

## 3. Master / Vistrit

- Scheme/PIU/Village master completed

- OHT village master completed

- Bulk-consumer master and bulk-consumer-to-OHT/WTP mapping completed

- Duplicate village-mapping validation delivered

- Consolidated Mapped Status report (Vidhan Sabha/district-wise) delivered

- WTP Meter Mapping given new columns (Date, Scheme, PIU)

- Standard meter naming convention enforced (e.g. Narela-WTP-01)

- Intake Mapping enriched with Meter Name/OHT connections/District/Block/GP

- Scheme Village Mapping validation applied to Testing & Permitted fields

- OHT visibility bug (deactivated entries) fixed

- All Vistrit reports made visible (read-only) on Contractor dashboard

- Lock Scheme/Village/OHT Master records once linked to live Dhara/O&M/Asset Mapping transactions

- OTP verification for GM login on Master edit/delete, SMS+OTP auth for Vistrit reports, Pipeline Master pages

Change Requests (Cycle 5, Jun–Jul 2026)

- MSTR-JUN-2026-006 — Lock Scheme/Village/OHT Master records once tagged to a live Dhara, O&M Billing, or Asset Mapping (BISAC) transaction; record becomes read-only and further correction is routed through a controlled change/relaxation flow instead of direct edit. (Open)

## 4. Dhara

- New Dhara report rolled out on all Jal Rekha logins

- GM-Approved-Reports & Contractor-Dispute view released

- GP-wise village reading report completed

- Lock approved report data (GM PIU can add, not edit)

- Make Remark/Photo-Upload/Forward/Backward optional platform-wide

- Fix Mohkhed multi-source meter-reading replication bug (critical)

- Contractor KL-reading objection workflow with 3-day auto-approve

Change Requests (Cycle 5, Jun–Jul 2026)

- DHARA-MAY-2026-009 — Approved Dhara report data locked once GM PIU approves; GM PIU/TL may add information but cannot edit Contractor-generated data; GM can add a new penalty point on top. (In Progress, Approved)

- DHARA-MAY-2026-021 — Remark, Photo Upload, Forward and Backward options made non-mandatory across all logins, live from 19-Jun-2026. (In Progress, Approved)

## 5. Nirmal (Water Quality)

- No new work items or change requests recorded for this module during the current reporting period.

## 6. Sopan

- Sopan module developed to streamline capturing and monitoring of contractors' commitments to timely construction of Over Head Tanks (OHTs) — bringing accountability, improved planning and stronger monitoring of construction works

- Contractor workflow: contractor selects the OHT from a dropdown, chooses OHT type (Pre-Cast or Conventional), and enters planned start date and planned completion date

- GM workflow: General Manager reviews details, uploads documents, and adds remarks where clarification is needed; system maintains a communication log between GM and Contractor

- Construction Work Progress Monitoring of Structures (WTP, OHT, etc.) — tracks stage-wise activities performed during implementation of Over Head Tanks

- Key benefits: tracks the actual stage of work completed, tracks delays in stage-wise development, and tracks financial liabilities procured at site

- Components covered: OHT, WTP, Intake Well, IPS

- Mapped-OHTs-with-Scheme report and OHT Details-to-be-Entered screens delivered

- Module status: Completed & Updation (per latest module-status tracker)

- No change requests logged for this module during Cycle 5 (Jun–Jul 2026).

## 7. Parinaam (FHTC)

- Contractor search option added

- FE name now shown in Parinaam/FHTC reports

Change Requests (Cycle 5, Jun–Jul 2026)

- OMB-JULY-2026-008 — Bug fixes and internal/external API service updates applied across FHTC (Parinaam) and Sahbhagita modules. (Open, logged 14-Jul-2026)

## 8. Bharosa (Factory Testing)

- Factory Testing (Web) completed with 3rd-party QAP and multiple-image upload support

- QAPs: approved Quality Assurance Plans uploaded for all material to be procured

- Material testing record-keeping: comprehensive pre-dispatch material-testing details captured to ensure quality and standards compliance

- Real-time notifications and updates on testing results, improving transparency and decision-making

- Streamlined, integrated process for pre-dispatch material inspection by TPIA, reducing dispatch delays

- No change requests logged for this module during Cycle 5 (Jun–Jul 2026).

## 9. Cube Testing & Re-Inspection Loop

- Structural components added per component type

- RFI-loop costing dates (7th/28th day) captured

- Filter Bed added as WTP sub-component

- Mandatory multi-image upload with Save-as-Draft enabled on FE mobile inspection form

- Cube ID now generates before image upload

- Rejected records surfaced back to Contractor for correction

- 2nd-cycle re-inspection loop after GM rejection (FE→GM→Contractor→GM→SQC/TPIA→FE)

- Optional image upload on 2nd RFI loop

Change Requests (Cycle 5, Jun–Jul 2026)

- CUBE-JUN-2026-005 — Cube ID now generates independently of a successful image upload; rejected inspection records surfaced back to Contractor login for correction and resubmission. (Completed/Done, delivered per MoM 16-Jun-2026)

## 10. Material Testing (Re-Inspection Loop)

- 2nd-cycle re-inspection loop after GM rejection: FE → GM → Contractor → GM → SQC/TPIA → FE (new FE, if reassigned)

- Image/photo upload optional during the 2nd-cycle RFI loop (remains mandatory on the 1st cycle)

Change Requests (Cycle 5, Jun–Jul 2026)

- CUBEMAT-JUN-2026-007 — Second-cycle re-inspection loop defined after GM rejection for both Cube Testing and Material Testing (FE→GM→Contractor→GM→SQC/TPIA→FE); loop retains the original submission data alongside the new loop data. (Open, complex state-machine change)

- CUBEMAT-JUN-2026-008 — Image/photo upload marked optional on the RFI 2nd-cycle loop only (remains mandatory on the 1st cycle); dependent on CR CUBEMAT-JUN-2026-007. (Open)

## 11. Sahbhagita

- RA Bill functionality enabled on ISA/CP Manager login after activity approval (with edit option)

- Pagination added on approval screens

- RA bill routing moved from CP Manager to ISA

- FE visibility restricted to their assigned ISA

- ISA password-reset option added

- Save-as-Draft for video/image/document uploads completed

- Village/Combined activity abstract report with V/C/A filter, multi-select RA(1)-RA(12) dropdown with Withhold option, Village Activity Document hyperlink/preview, AI photo duplicate-detection (future scope)

Change Requests (Cycle 5, Jun–Jul 2026)

- SHB-JUN-2026-004 — Activity report restructured into Village-wise (32 listed/27 unique activities) and Combined (22 activities) views, with a Village/Combined/All (V/C/A) category filter. Ref: Sahbhagita master activity matched sheet. (In Progress, Approved)

- SHB-MAY-2026-007 — Multi-select bill dropdown covering RA(1)–RA(12) with a Withhold Bills toggle. (Open)

- SHB-MAY-2026-013 — Village Name and Village Activity Document hyperlinks added, with a preview popup shown on click. (In Progress, Approved)

- SHB-MAY-2026-012 — AI-based photo verification (face/background match) with duplicate/repeated-photo flagging at CP Manager login — future scope. (Open, Low priority)

- OMB-JULY-2026-008 — Bug fixes and API service updates applied jointly across Sahbhagita and FHTC (Parinaam) modules. (Open, logged 14-Jul-2026)

## 12. O&M Billing / Aaklan

- Dhara report data integrated into O&M Billing module (incl. Aaklan billing use)

- Census population added to Scheme Master (GM side report)

- Redundant reports removed; DWSR made clickable (hyperlink)

- GM final-approval-only workflow with mandatory Concern Remark

- Power Consumption, Water-Supply-During-Construction columns completed

- O&M Villages list (under-construction/approved) finalised

- 10% Pump-Transformer deduction logic implemented

- Mandatory document upload gate (Submission Letter/Tax Invoice) before Contractor can forward a bill

- Residual Pressure & Complaint Redressal screens redesigned per report format

- Bill generation (64 schemes), Contractor summary report, Abstract generation, multi-doc PDF merge, Document Upload screen, GST integration, CDAC e-Sign, TL E-Office letter, billing workflow redesign

- Contractor discrepancy-raising window against Dhara data

- GM (PIU)/GM (O&M)/Deputy O&M 'View Pending Bills' & 'Manage Bill' screens

Change Requests (Cycle 5, Jun–Jul 2026)

- OMB-JULY-2026-001 — Mandatory document upload gate (Submission Letter, Tax Invoice) before a bill can move out of Save-as-Draft on Contractor/Firm login; draft-save behaviour unchanged, new gate applies only on Forward. (Done, 06-Jul-2026)

- OMB-JUN-2026-002 — Residual Pressure & Complaint Redressal screen changes; Pressure Threshold Report reformatted per OM_RA_Bill_Report.pdf; Complaint Redressal fields relabelled (received/resolved dates, days taken to resolve). (Done, 07-Jul-2026)

- OMB-JUN-2026-003 — Complaint Redressal sheet: added Complaint-Received-Date, an auto-derived Event-above-48-hours flag, and a Penalty Relaxation (Yes/No) field. (Done, 08-Jul-2026)

- OMB-JUN-2026-004 — Abstract Bill PDF orientation changed from portrait to landscape; layout redesign required across all table/column headers. (Open)

- OMB-JULY-2026-005 — Naming and formatting corrections across O&M Contractor-login pages. (Open, target 14-Jul-2026)

- OMB-JULY-2026-006 — UFW report (sourced from Dhara) to display on the O&M Billing Contractor login, attached with the bill. (Open, target 15-Jul-2026)

- OMB-JULY-2026-007 — Mandatory additional-document upload by Contractor (Firm Letter, Tax Invoice, any other document + remark) on a new "View Bills" page. (Open, target 16-Jul-2026)

- OMB-MAY-2026-006 — Billing workflow redesigned: Firm → GM PIU → TL SQC → GM PIU → GM O&M → DGM → TL PMC → CFO → CA → P.D. → MD. (In Progress)

- OMB-MAY-2026-002 — Contractor-side Abstract generation from a selected bill, tagging all villages/scheme and pulling in Dhara readings, Master-module tables and the UFW-approved report. (In Progress)

- OMB-MAY-2026-005 — Bill PDF consolidation: approx. 19–20 supporting documents (GM/SQC/Firm letters, Form 27A, MB, Abstract) merged into a single PDF; static documents carried once per 3 months, variable documents per month. (In Progress, Approved)

- OMB-MAY-2026-008 — Contractor data-entry errors made visible to SQC/TL and GM across all IDs; consolidated O&M document PDF merge. (Open)

- OMB-MAY-2026-015 — Document Upload Screen designed for Firm, TL/SQC and GM PIU logins, with Download/View-PDF actions and remark fields on selected document types. (In Progress, Approved)

- OMB-MAY-2026-003 — GST number captured and linked at contractor/firm level; carried onto the bill PDF and abstract. (Open)

- OMB-MAY-2026-001 — CDAC e-Sign integration for Firm/FE across Web and Mobile, applied to Bill, Submission Letter and Tax Invoice. (Open, High risk)

- OMB-MAY-2026-004 — TL Recommendation Letter generated via E-Office instead of manual upload, integrated with Account Office Jal Rekha. (Open, High risk)

- OMB-MAY-2026-014 — GM (PIU) and GM (O&M)/Deputy O&M given 'View Pending Bills' and 'Manage Bill' screens under the Aaklan module, listing already-generated bills. (In Progress, Approved)

## 13. SVS – Har Ghar Jal (PHE)

- New GP/PHE daily water-supply entry form built (District/Block/GP/Village, connections, date picker)

- Water Supply Status (Yes/No/Partial) with reason dropdown and remarks added

- Login-specific auto-filled District/Block/GP

- Hindi (MP Shashan) bilingual interface delivered

- JJM ID, Village Status & 'hand-over-to-community' fields removed

- LGD code and household data joined in Excel export

- Partial-entry edit option added

- All items confirmed complete as of 16-Jun MoM

- No new change requests logged for this module during Cycle 5 (Jun–Jul 2026).