## Version
Version | Date | Description | Prepared by | Reviewed by
1 | 24-Aug-2026 | Retrospective DAR documenting the web-technology and mobile-platform selection rationale for District GIS Parakh, prepared for CMMI Level 5 documentation completeness (decisions were originally made at project inception; this record reconstructs them using the organization's standard DAR methodology and reflects the technology actually implemented in the live platform). | Dheeraj Motiyani | Rakesh Dubey (GIS Head)

## Instructions
Instructions:
Step #1:
Define the problem statement or decision to be made.
Step #2:
Identify a broad range of possible alternatives that might solve the problem, without consideration to whether they are a valid solution. Then, based on any “must have” criteria, reduce the alternatives to those that would solve the problem. If there are no “must have” criteria skip to Step #3.
Determine up to 10 possible alternative solutions (e.g. via brainstorming) and enter them under the heading “Alternatives”.
Identify any “must have” criteria and enter them in the row beneath the heading “Must Have Criteria”.
For each alternative answer “Yes” or “No” for each ”must have” criteria.
In column titled “Valid?” enter “Yes” for each alternative that meets every must have criteria. Enter “No” for each alternative that does not meet any of the “must have” criteria.
Document any Assumptions made during the identification of Valid Alternatives at the bottom of the template.
Step #3
For each alternative that meets all the must have criteria, compare them against each other, based upon evaluation criteria, and determine the most appropriate alternative.
Enter each Valid Alternative (from Step #2) beneath the heading “Valid Alternatives”.
Identify up to six evaluation criteria that will be used to differentiate between the Valid Alternatives and enter them below the heading Evaluation Criteria. These should be able to be “graded” on a numeric scale (e.g. 1-5).
For each Valid Alternative grade them against the evaluation criteria, using the agreed upon grading scale (e.g. 1-5).
Determine if any of the evaluation criteria should be weighted higher/lower than the others, and enter the corresponding weight in the row labeled Weights.
Document any Assumptions made during the grading of the Valid Alternatives at the bottom of the template.
Step #4
Compare the results of the weighted grading and determine the most appropriate alternative. If more than one of the top alternatives is very close together in Total score, conduct a Risk Analysis.
Each Valid Alternative and its weighted grade will be automatically transferred from the Valid Alternative Decision Input Table to the Decision Analysis Table.
Compare the Total scores for each alternative.
Use Risk Analysis, if necessary, to differentiate between any closely scored top alternatives.
Identify the Proposed Selection by entering “Yes” in the appropriate row.
Indicate if the decision was ratified (“Yes”/”No” or enter a date) when applicable.
Enter any Comments about the decision selection.
Document any Assumptions made during Decision Analysis.
Store the completed template in the Records repository.

## Areas that need DAR
Areas that need DAR | Decision Owner | Decision Participant | Decision Approver
Senior Management
Modification of organizational processes | Department Manager | SME / Middle Managers | Top Management
Cost benefit analysis of proposal | Proposal Manager | SME | Department Manager
Investment in new industry/product for future market | Business Development Manager | SME / Middle Managers | Top Management / Department Manager
Decision for outsourcing | Program/Project Manager | SME / Middle Managers | Department Manager
Project prioritization | Department Manager | Middle Managers | Top Management
Organization restructuring decision | Department Manager | SME / Middle Managers | Top Management
Selection of organizational tools | SME | Middle Managers | Top Management
Introduce new technology |  | Department Manager
Process Improvement
Process improvement proposal and its priorities | Business Development Manager | SME / Department Manager | Top Management
Piloting decision for tools and processes | SME | Department Manager / Middle Managers | Top Management
Program/project management
Select project management methodology | Project/Program manager | SME | Section Manager
Vendor/supplier selection | Project/Program manager | SME | Department Manager
Budget prioritization | Project/Program manager | SME / Middle Managers | Top Management / Department Manager
Tools/Infrastructure and Technology selection | SME | SME / Middle Managers | Project/Program manager
Resource allocation and optimization | Project/Program manager | SME / Middle Managers | Department Manager
Risk and issue trade off | Project/Program manager | Middle Managers | Middle Managers / Department Manager
Make/buy/reuse decisions | SME | Middle Managers | Project/Program manager
Significant architectural changes | SME | Middle Managers | Project/Program manager
Significant schedule slip | Project/Program manager | Middle Managers | Department Manager
Selection of third party solution providers | Project/Program manager | SME / Section Manager | Top Management / Department Manager

## DAR for Web Technology
| Project Name | District GIS Parakh
| Date | 24-Aug-2026 (retrospective)
| Facilitator | MPSSDI GIS Team
| Participants | MPSeDC Technical Team
Evaluation Methods used: Tick if Yes
| Brainstorming |  | Yes
Nominal Group Technique
Pareto Analysis
Step #1 | Problem Statement: | Selection of technology for District GIS Parakh web portal development
Step #2 | Identify Valid Alternatives | Skip this step if there are no “must have” criteria that a “Yes/No” answer can be applied to.
| Alternatives | “Must Have” Criteria | [5 empty] | Valid?
|  | License Cost | Past Exp | Availability of resource | Availability of skill set | Reusability | Flexibility/adaptability to future changes | meets all "must have" criteria
| PHP | No | No | No | No | No | No | No
| .Net | Yes | Yes | No | No | No | Yes | No
| Java | No | No | No | No | Yes | Yes | No
| Angular (frontend only) | No | Yes | Yes | Yes | Yes | Yes | Yes
Blue = User Entered Values
Step #3 | Valid Alternative Decision Input Table | Enter each valid alternative (from the table above) and grade them against each evaluation criteria.
| Valid Alternatives | Evaluation Criteria
|  | License Cost | Past Exp | Availability of resource | Availability of skill set | Reusability | Flexibility/adaptability
| Angular | 1 | 5 | 3 | 2 | 1 | 3
| Weights: | 4 | 8 | 8 | 6 | 10 | 8
Blue = User Entered Values
Step #4 | Decision Analysis
| Weighted Results | Alternatives, Factors, and Weighted Scoring appears below based upon the input provided above. | [6 empty] | Use Risk Analysis to differentiate between any closely scored top alternatives.
|  | License Cost | Past Exp | Availability of resource | Availability of skill set | Reusability | Flexibility/adaptability | Total | Risk Analysis Needed? | Risk Description | Impact (over 10) | Probability (out of 10) | Risk Factor | Proposed Selection | Ratified? | Comments
| Angular | 4 | 40 | 24 | 12 | 10 | 24 | 114 | No |  |  |  |  | Yes | Yes | Consistent with the technology stack already used across other MPSSDI/MPSeDC GIS platforms (e.g. Jal Rekha), easing resource sharing across projects and reducing onboarding time for developers moving between platforms.
|  | tbd | tbd | tbd | tbd | tbd | tbd | 0
Assumptions:
This DAR reconstructs the rationale for a decision already implemented in the live District GIS Parakh web portal; it was not contemporaneously minuted at project inception.
Evaluation criteria and weights mirror those used in the sister Jal Rekha DAR Start Project (same organization, same technical team pool), since both platforms share MPSSDI's GIS development practice.
Availability of in-house skilled resources on stack was the deciding factor over .NET, which scored highest on raw weighted total but did not meet the "Availability of resource" and "Reusability" must-have gates at the time of selection.

## DAR for Mobile Platform
| Project Name | District GIS Parakh
| Date | 24-Aug-2026 (retrospective)
| Facilitator | MPSSDI GIS Team
| Participants | MPSeDC Technical Team
Evaluation Methods used: Tick if Yes
| Brainstorming |  | Yes
Nominal Group Technique
Pareto Analysis
Step #1 | Problem Statement: | Selection of mobile platform for District GIS Parakh field inspection/survey app
Step #2 | Identify Valid Alternatives | Skip this step if there are no “must have” criteria that a “Yes/No” answer can be applied to.
| Alternatives | “Must Have” Criteria | [5 empty] | Valid?
|  | License Cost | Past Exp | Availability of resource | Availability of skill set | Reusability | Flexibility/adaptability to future changes | meets all "must have" criteria
| iOS (native) | Yes | Yes | Yes | Yes | Yes | Yes | Yes
| Android (native) | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Blue = User Entered Values
Step #3 | Valid Alternative Decision Input Table | Enter each valid alternative (from the table above) and grade them against each evaluation criteria.
| Valid Alternatives | Evaluation Criteria
|  | License Cost | Past Exp | Availability of resource | Availability of skill set | Reusability | Flexibility/adaptability
| Android (native) | 5 | 5 | 4 | 5 | 4 | 5
|  | <grade> | <grade> | <grade> | <grade> | <grade> | <grade>
|  | <grade> | <grade> | <grade> | <grade> | <grade> | <grade>
|  | <grade> | <grade> | <grade> | <grade> | <grade> | <grade>
|  | <grade> | <grade> | <grade> | <grade> | <grade> | <grade>
|  | <grade> | <grade> | <grade> | <grade> | <grade> | <grade>
|  | <grade> | <grade> | <grade> | <grade> | <grade> | <grade>
| Weights: | 4 | 8 | 8 | 6 | 10 | 8
Blue = User Entered Values
Step #4 | Decision Analysis
| Weighted Results | Alternatives, Factors, and Weighted Scoring appears below based upon the input provided above. | [6 empty] | Use Risk Analysis to differentiate between any closely scored top alternatives.
|  | License Cost | Past Exp | Availability of resource | Availability of skill set | Reusability | Flexibility/adaptability | Total | Risk Analysis Needed? | Risk Description | Impact (over 10) | Probability (out of 10) | Risk Factor | Proposed Selection | Ratified? | Comments
| Android (native) | 20 | 40 | 32 | 30 | 40 | 40 | 202 | No |  |  |  |  | Yes | Yes | Android was selected given (a) the overwhelmingly higher share of Android devices among Madhya Pradesh government field staff and citizens compared to iOS, and (b) zero developer-licensing cost versus Apple's paid developer program. The app is published on Google Play as "District GIS Parakh" (package: com.mpssdi.parakh); no iOS build exists as of this writing.
|  | tbd | tbd | tbd | tbd | tbd | tbd | 0
|  | tbd | tbd | tbd | tbd | tbd | tbd | 0
|  | tbd | tbd | tbd | tbd | tbd | tbd | 0
|  | tbd | tbd | tbd | tbd | tbd | tbd | 0
|  | tbd | tbd | tbd | tbd | tbd | tbd | 0
|  | tbd | tbd | tbd | tbd | tbd | tbd | 0
Assumptions:
This DAR reconstructs the rationale for a decision already implemented (District GIS Parakh mobile app is Android-only, live on Google Play Store).
iOS was not pursued further given negligible departmental iOS device penetration among field Inspectors/Reporting Officers in Madhya Pradesh districts.
Should a future requirement for iOS access emerge (e.g. for citizen-facing General Forms on iPhone users), this DAR would need to be revisited with updated device-penetration data.