## Version Hisotry
0.12 ( According to MPSeDC GIS Entity E-Abkari Project)
Date | Version | Description | Prepared by | Reviewed & approved by
2025-08-19 | 1 | Size base Estimation Model First baseline | SEPG Team | SEPG Head

## Master
Estimation Elements
New Development | Enhancement and customization
Web Page / Screen with no of input fields | Web Page / Screen with no of input fields
Type of exit scenario | Type of exit scenario | 0.12 ( According to MPSeDC GIS Entity E-Abkari Project)
No of Validation on the fields | No of Validation on the fields
No of Prefilled fields | No of Prefilled fields
No of API Integrations | No of API Integrations
No API integrations for saving the data | No API integrations for saving the data
Queries or Business rules for the application | Queries or Business rules for the application
No of Integration | No of Integration
mobile App-UI | mobile App-UI
Data Migration | Data Migration
Reports | Reports
Complexity | Type of work | VAF Rating
Low | New Development | 5 | 5 - Very Strong Influence
Medium | Enhancement and customization | 4 | 4 - Strong Influence
High |  | 3 | 3 - Average Influence
Complex |  | 2 | 2 - Moderate Influence
|  | 1 | 1- Slight Influence
|  | 0 | 0 - No Influence
Effort Distribution Guidelines
| Effort Distribution | Cost
|  | Min | Max
Business Analyst | 15% | 4000 | 6000
Solution Architecht | 10% | 6000 | 8000
Developer / Data Scientist | 40% | 3000 | 5000
Tester | 20% | 2500 | 5000
Project Manager | 10% | 8000 | 10000
Infrastructure Setup | 5% | 3000 | 5000
Business Analyst | 15%
Solution Architecht | 10%
Developer / Data Scientist | 40%
Tester | 20%
Project Manager | 10%
Infrastructure Setup | 5%

## Baseline Productivity
Type of work | Calculated Productivity | Targated Productivity | Unit
Development & Enhancement |  | 0.12 ( According to MPSeDC GIS Entity E-Abkari Project) | Point / per hour
|  | 1 Point | 8.3 Hours

## Guidelines
| Complexity | 1 | 3 | 5
Work Type | Component | Low | Medium | High
Development | Web Page / Screen with no of input fields | 0.12 ( According to MPSeDC GIS Entity E-Abkari Project) | 10-15 | > 15 | Elements Label Graph Tile Grid Pop-up Drop Down Data Entery Field Button Custom Built element |  |  | 1
| Type of exit scenario | 1 | 1 to 2 | >3 |  | label | text box
| No of Validation on the fields | 1 to 5 | 5 To 10 | >10 |  | button
| No of Prefilled fields | 10 to 30 | 30 to 50 | >50 |  | drop down
| No of API Integrations | 2 | 2 to 5 | > 5 |  | checkbox
| No API integrations for saving the data | 3 | 8.3 Hours | >5 |  | aadhar
| Queries or Business rules for the application | No validation or business rules. One data store | No validation or business rules. Up to 3 data stores | Validation or business rules involved. Multiple data stores |  | samagra integration
| No of Integration | 2 | 2 to 5 | >5 |  | report
| mobile App-UI | Static screen | Screen with 2-4 internal components | Screen with external components |  | MObile app
| Data Migration | Master Table | Table with data errors and involves Data validation and cleansing | Table with relationship with data errors and requires data validation and cleansing |  | submit
| Reports | tabular report. <10 columns. 1 data source Elements( Table, PIE chart, Report count: 1-2 | 2-3 data source. Simple (Pie/Bar) chart Elements( Stack,Line etc.) Report type: 3-5 | >3 data source. Multiple complex graphs Elements( Doughnut, Trend analysis etc.) Report type: More than 5 |  | clear
reset
Code element Data Tranformation Data Pre-processing Custom Build element API creation for UI\UX API Integration

## Estimation_DAMOH
| Type Of work |  | New Development / Enhancement (Mixed)
| Project Name |  | District GIS Parakh - Damoh District (13-Form Rollout)
| Remark |  | All 14 Damoh user stories rated Complexity: Medium in source requirement sheet. Source sheet also provides bottom-up activity-hour estimate (Req. Gathering, Meetings, Form/Coding Dev, Testing, Verifying, Monitoring, Deployment, Training) totalling 252 hrs across 14 stories - shown here for cross-reference; the effort below uses the Function-Point-style method (Size / Baseline Productivity) per Jal Rekha format.
|  |  | Volume/Count of elements |  |  |  | Traceability
Module + sub MOdule | Functionality ( Sub Module) | Elements (Refer Guidelines and Put here for reference) | Low Complexity | Medium compexity | High Complexity | Size | User Story ID | Priority | Work Type
|  |  | 1 | 3 | 5
Damoh District - 12-Form Rollout (Implementation) | Zila Karyalay Panchayat Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-001 | Medium | New Development |  |  | 1*1+3*1+5*0 =4
| Gram Nal Jal Praday Yojana Inspection Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-002 | Medium | New Development
| School/Institute Inspection Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-003 | Medium | New Development
| Anganwadi Inspection Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-004 | Medium | New Development
| Jan Vishwas Abhiyaan - Health Department Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-005 | Medium | New Development
| Govt. Uchit Mulya Ki Dukan (Fair Price Shop) Inspection Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-006 | Medium | New Development | Value added factors
| Petrol Pump Inspection Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-007 | Medium | New Development | Factor | Rating
| LPG Dealer Inspection Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-008 | Medium | New Development | Data Communications | 0
| CM Jan Vishwas Abhiyaan - Farm & Dairy Department Inspection Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-009 | Medium | New Development | Distributed Data Processing | 0
| Krishi Saakh and Sahkari Samiti (Agri Credit & Cooperative Society) Inspection Form | Web Page / Screen with no of input fields Form Data Entry / Inspection Capture | 0 | 1 | 0 | 3 | US-DAMOH-010 | Medium | New Development
| 12-Form Programme — UAT Finalization & Bulk Asset Upload | Data Migration Master Data Management | 0 | 1 | 0 | 3 | US-DAMOH-011 | Medium | New Development | Performance | 0
[5 empty] | Total Size | 33 | US-DAMOH-012 | Medium | New Development | Heavily used Configuration | 3
[7 empty] | US-DAMOH-013 | Medium | New Development | Transaction Rate | 4
12-Form Programme - UAT Finalization & Bulk Asset Upload (CR) | [6 empty] | US-DAMOH-014 | High | Enhancement and customization
|  | Productivity | 0.12 | Point / per hour | [5 empty] | Online Data Entry | 3
|  | Size | 33 | Point | [5 empty] | End-User Efficiency | 2
|  | Effort | 275 | Man hours | [5 empty] | Online Update | 1
|  | VAF | 1.01 | [6 empty] | Complex Processing | 3
|  | Risk contingency | 5% | [6 empty] | Reusability | 4
|  | Project Management | 10% | [6 empty] | Installation Ease | 4
|  | Total Planned effort | 320.8012 | Man hours | [5 empty] | Operational Ease | 4
[10 empty] | Multiple Sites | 4
|  | Permissible Range(Man hours) | 336.8413 | 304.7612 | [5 empty] | Facilitate Change | 4
[10 empty] | Total | 36