## Sheet1
Sr.No | Resource Name | Resource_Location | Project Name | Sprint Name | Sprint Start Date ¦ End date | Module Name | Activity Name | Task Assign Date | TimeSheet Entry date | Task Name | Assign Hours | Consumed Hrs | Work Status By Resource | Work Status By PM | Action Performed by Resource
1 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 25/06/2026 | 01/07/2026 | Create Establishment Login for Labour Department | 16.00 | 8.00 | Completed | Yet To Update | Completed enhancements and implementation of the Establishment Login module for the Labour Portal.
2 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 01/07/2026 | 02/07/2026 | Create Establishment Report for Labour Portal | 16.00 | 8.00 | Completed | Yet To Update | Developed the Establishment Report module for the Labour Portal.
3 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 03/07/2026 | 03/07/2026 | Create Database Table Structure and Relationships for Labour Documents and Document Status | 16.00 | 8.00 | Completed | Yet To Update | Designed and implemented the database schema, table structure, and relationships for Labour Documents and Document Status.
4 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 06/07/2026 | 06/07/2026 | Create Compliance Document Upload Page for Establishments | 16.00 | 8.00 | WIP | Yet To Update | Developed the Compliance Document Upload page for Establishments.
5 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 06/07/2026 | 08/07/2026 | Create Compliance Document Upload Page for Establishments | 16.00 | 8.00 | Completed | Yet To Update | Completed enhancements, validation, and integration for the Compliance Document Upload page for Establishments.
6 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 02/07/2026 | 09/07/2026 | document view page for labour dept | 16.00 | 8.00 | WIP | Yet To Update | Work on document view page for labour department
7 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 02/07/2026 | 10/07/2026 | document view page for labour dept | 16.00 | 8.00 | Completed | Yet To Update | developed document view page for labour dept
8 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 01/07/2026 | 13/07/2026 | Create diffrent landing page for CIS Labour department | 16.00 | 8.00 | WIP | Yet To Update | created diffrent landing page for CIS Labour department
9 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 01/07/2026 | 14/07/2026 | Create diffrent landing page for CIS Labour department | 16.00 | 8.00 | Completed | Yet To Update | Developed diffrent landing page for CIS Labour department
10 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 10/07/2026 | 15/07/2026 | Fix the logout function link with diffrent landing page | 16.00 | 8 | Completed | Yet To Update | Fixed the bug for logout function so it will redirect the respected login page
11 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 13/07/2026 | 16/07/2026 | Fixed login fun in case of sub-menu | 16.00 | 8 | Completed | Yet To Update | Fixed login fun in case of sub-menu Now it will login function will work in both case sub menu and menu
12 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | New web page creation/ Modification | 06/08/2026 | 07/08/2026 | Cretate web page, api and db query for new role divisional and district officer department mapping | 16.00 | 8 | WIP | Yet To Update | Worked on table structure, db query and API for new role divisional and district officer department mapping
13 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | New web page creation/ Modification | 06/08/2026 | 10/08/2026 | Cretate web page, api and db query for new role divisional and district officer department mapping | 16.00 | 8 | Completed | Yet To Update | Worked on web page, api for new role divisional and district officer department mapping
14 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | New web page creation/ Modification | 10/08/2026 | 11/08/2026 | Modify old pages of web so it work for both new role(divisional and district officer) and old hierarchical role | 16.00 | 8 | WIP | Yet To Update | Worked on web pages it work for both new role(divisional and district officer) and old hierarchical role
15 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | New web page creation/ Modification | 10/08/2026 | 12/08/2026 | Modify old pages of web so it work for both new role(divisional and district officer) and old hierarchical role | 16.00 | 8 | Completed | Yet To Update | configure all the menu given to new role (divisional and district officer)
16 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Query/SP creation/Modification | 12/08/2026 | 13/08/2026 | Modify General report query, dynamic report query, Data Collection report query for new role Divisional and District Officer | 16.00 | 8 | WIP | Yet To Update | Modify General report query for new role Divisional and District Officer
17 | Aman Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Query/SP creation/Modification | 12/08/2026 | 14/08/2026 | Modify General report query, dynamic report query, Data Collection report query for new role Divisional and District Officer | 16.00 | 8 | Completed | Yet To Update | Modify Dynamic report query and Data Collection report query for new role Divisional and District Officer
18 | Arindam Kumar | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | P&RD Department | Production deployment | 14/07/2026 | 15/07/2026 | PMPOSON production Development and support | 8.00 | 8 | Completed | Yet To Update | PMPOSON production Development and support
19 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 02/07/2026 | 02/07/2026 | Implemented the View Inspected Area functionality with interactive map layers and submission markers for Sehore, Seoni, Health Department, and all remaining department reports. | 8.00 | 8 | Completed | Yet To Update | Implemented View Inspected Area functionality for Sehore, Seoni, Health Department, and all remaining department reports. Added interactive map layers with submission markers. Integrated inspection location data for map visualization. Implemented filled form preview functionality. Added filled form download functionality.
20 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Mandir Nyas | Solution and bussiness logic design | 03/07/2026 | 03/07/2026 | added a dedicated page of login for the Religious Trust and Endowments (Amrit) department | 8.00 | 8 | Completed | Yet To Update | Developed a dedicated login page for the Religious Trust and Endowments (Amrit) department. Implemented a department-specific user interface and authentication flow. Integrated the login page with the existing authentication mechanism and routing. Configured redirection and session handling for department users.
21 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | New web page creation/ Modification | 06/07/2026 | 06/07/2026 | Develop Form Workflow Mapping Component | 8.00 | 8 | Completed | Yet To Update | Developed the Form Workflow Mapping web component. Implemented the user interface and form controls for workflow mapping. Added input validation and user interaction handling. Integrated the component with frontend services.
22 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Business Logic APIs creation/Changes | 08/07/2026 | 08/07/2026 | Develop Form Workflow Mapping Insertion API | 8.00 | 8 | Completed | Yet To Update | Developed the API for inserting Form Workflow Mapping records. Implemented backend validation and database insertion logic. Added response and exception handling.
23 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Query/SP creation/Modification | 09/07/2026 | 09/07/2026 | Develop Database Report for Mining Department Site Inspection | 8.00 | 8 | Completed | Yet To Update | Developed the database query for the Mining Department Site Inspection report. Retrieved and structured inspection data based on reporting requirements. Implemented the required filters and data retrieval logic.
24 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | New web page creation/ Modification | 10/07/2026 | 10/07/2026 | Develop Web Report for Mining Department | 8.00 | 8 | Completed | Yet To Update | Developed the web report interface for the Mining Department. Integrated backend report data with the frontend. Implemented report filters and structured data presentation. Enhanced the report UI for improved usability and readability.
25 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Data Processing | 15/07/2026 | 15/07/2026 | Create and Resolve Database Report Issues for PNRD_PMPOSHAN | 8.00 | 8 | Completed | Yet To Update | Developed the database report for the PNRD_PMPOSHAN module. Identified and fixed report-related issues in the database queries. Updated query logic to ensure accurate data retrieval.
26 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | New web page creation/ Modification | 16/07/2026 | 16/07/2026 | Develop PNRD PMPOSHAN Web Report with Pagination | 8.00 | 8 | Completed | Yet To Update | Developed the web report for the module and integrated it with the backend data source. Implemented correct pagination logic to efficiently display report records. Ensured accurate record count and seamless page navigation. added the excel report to download of real time inspection data
27 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 17/07/2026 | 17/07/2026 | Develop Chhindwara Madhyan Bhojan Nirikshan Prapatra Report | 8.00 | 8 | Completed | Yet To Update | Developed the Chhindwara Madhyan Bhojan Nirikshan Prapatra report. Retrieved and mapped the required data fields for report generation. Implemented the report layout according to the specified format.
28 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | Unit Testing for module | 20/07/2026 | 20/07/2026 | Test Labour Commissioner Organization Inspection Workflow | 8.00 | 8 | Completed | Yet To Update | Performed end-to-end testing of the Labour Commissioner Organization inspection workflow. Verified form submission, inspection processing, and workflow execution. Validated frontend and backend data synchronization. Identified and documented functional issues during testing.
29 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | Unit Testing for module | 21/07/2026 | 21/07/2026 | Functional Verification of Labour Commissioner Inspection Module | 8.00 | 8 | Completed | Yet To Update | Perform functional verification of inspection features. Validate user actions and workflow execution. Verify data accuracy and report outputs. Identify and log defects. Retest after fixes.
30 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 24/07/2026 | 24/07/2026 | Develop Database Reports for Chhindwara Collectorate Forms | 8.00 | 8 | Completed | Yet To Update | Developed database-side reports for Chhindwara Collectorate Form IDs 499, 500, 501, 502, and 461. Created and optimized SQL queries to retrieve the required report data. Mapped report fields according to the specified report format. Validated data accuracy and ensured correct report generation
31 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 27/07/2026 | 27/07/2026 | Develop Web Reports for Chhindwara Collectorate Forms | 8.00 | 8 | Completed | Yet To Update | Developed web reports for Chhindwara Collectorate Form IDs 499, 500, 501, 502, and 461. Integrated backend report data with the frontend. Implemented the report layout and ensured accurate data presentation. Verified report functionality, navigation, and data consistency.
32 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 28/07/2026 | 28/07/2026 | Resolve Reported Issues Assigned on Promot | 8.00 | 8 | Completed | Yet To Update | Resolved all reported bugs assigned on Promot. Fixed frontend and backend issues based on reported defects. Verified the implemented fixes across affected modules.
33 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore - Labour Inspection | Unit Testing for module | 29/07/2026 | 29/07/2026 | Testing Labour Department Workflow | 6.00 | 6 | Completed | Yet To Update | Test the Assigning functionality of the Inspection. download and signed document submission by inspector, taking followup for documents from establishment, file legacy and assigned inspection prosecution, document submission of the establishment. test the reports and marked the bugs.
34 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Business Logic APIs creation/Changes | 29/07/2026 | 29/07/2026 | Creat Api For Active Form List of Department | 2.00 | 2 | Completed | Yet To Update | create API for getting the active form list of the Department.
35 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 30/07/2026 | 30/07/2026 | Integrate Active Forms API Across Application Components | 8.00 | 8 | Completed | Yet To Update | Implement the Active Forms API in the service. Integrate the Active Forms API into all required components.
36 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | New web page creation/ Modification | 31/07/2026 | 31/07/2026 | Develop Drag-and-Drop Question Ordering Component | 12.00 | 8 | Completed | Yet To Update | Developed a drag-and-drop component for reordering form questions. Implemented functionality to rearrange questions dynamically through drag-and-drop. Updated the question sequence based on the user's selected order. Ensured the reordered question list was maintained correctly within the application.
37 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Dynamic Report: Phase 1 (For Parent Question Only) | 03/08/2026 | 03/08/2026 | Implement Dynamic Report Header Mapping for Question Hierarchy | 16.00 | 8 | WIP | Yet To Update | Implemented dynamic report header mapping for the non-conditional question hierarchy. Developed functionality to edit report header labels dynamically. Added drag-and-drop support to reorder report headers as per user requirements. Ensured header mapping and display order were updated correctly after modifications.
38 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore - Labour Inspection | Report creation/ Modification | 04/08/2026 | 04/08/2026 | Develop Database Reports for Indore Collectorate | 8.00 | 8 | Completed | Yet To Update | Developed database-side reports for the Indore Collectorate module. Created and optimized SQL queries to retrieve the required report data. Mapped report fields according to the specified report format.
39 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | New web page creation/ Modification | 06/08/2026 | 06/08/2026 | Develop Web Report for Indore Education Department | 16.00 | 8 | WIP | Yet To Update | Developed the web report for the Indore Education Department. Integrated backend report data with the frontend. Implemented the report layout and ensured accurate data presentation. Added report functionality, including filtering and pagination where applicable.
40 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | New web page creation/ Modification | 06/08/2026 | 07/08/2026 | Develop Web Report for Indore Education Department | 16.00 | 8 | Completed | Yet To Update | created cards for multiple categories of the institution created the excel reports for all categories added the action button for Department Hod approval
41 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | New web page creation/ Modification | 10/08/2026 | 10/08/2026 | Develop Indore Collectorate Women and Child Development Report | 8.00 | 8 | Completed | Yet To Update | Created the Indore Collectorate Women and Child Development Department report. Implemented the required report structure and data mapping. Developed and configured the database query for retrieving report data. Validated the report data and field mapping according to the requirements.
42 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 11/08/2026 | 11/08/2026 | Develop Three Reports for Betul Department | 8.00 | 8 | Completed | Yet To Update | Developed three reports for the Betul department as per the specified requirements. Created and configured the required database queries for report generation. Mapped and structured the required data fields for each report. Validated report data and ensured consistency with the defined formats.
43 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Business Logic APIs creation/Changes | 12/08/2026 | 12/08/2026 | Implement Captcha Generation and Validation API | 8.00 | 8 | Completed | Yet To Update | Implemented the CAPTCHA generation API. Developed the CAPTCHA validation API to verify user-entered values. Integrated CAPTCHA generation and validation with the application workflow. Added handling for invalid CAPTCHA submissions and validation failures.
44 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | New web page creation/ Modification | 13/08/2026 | 13/08/2026 | mplement CAPTCHA Functionality on Web | 8.00 | 8 | Completed | Yet To Update | Integrated the CAPTCHA generation and validation APIs with the web application. Added CAPTCHA display and user input functionality to the required web page. Implemented CAPTCHA validation during form submission. Added handling for invalid CAPTCHA entries and CAPTCHA refresh.
45 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | New web page creation/ Modification | 14/08/2026 | 14/08/2026 | Implement Verification Functionality with Hierarchy-Based Action History | 16.00 | 8 | WIP | Yet To Update | Implemented the verification functionality in the Survey List and integrated hierarchy-based action history. Added the structure to display previously performed actions across different hierarchy levels along with their associated action data.
46 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | New web page creation/ Modification | 14/08/2026 | 17/08/2026 | Implement Verification Functionality with Hierarchy-Based Action History | 16.00 | 8 | Completed | Yet To Update | Added loader and used the action master for the dynamic dropdown of the action performed
47 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | New web page creation/ Modification | 19/08/2026 | 19/08/2026 | Develop Mandatory Mobile Number Verification Component | 8.00 | 8 | Completed | Yet To Update | Developed a dedicated Mobile Number Verification component for users. Implemented the mobile verification workflow using OTP-based verification. Integrated the component with the required APIs for OTP generation and validation. Added validation and user messaging to inform users that mobile verification is mandatory.
48 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Query/SP creation/Modification | 20/08/2026 | 20/08/2026 | Implement Database Logic for 2FA, OTP Verification, and User Contact Updates | 8.00 | 8 | Completed | Yet To Update | Developed the database query for OTP generation and storage. Created a dedicated table to maintain the 2FA verification flag/status for users. Implemented database logic to check whether a user is eligible for 2FA validation. Developed the OTP verification query to validate the OTP submitted by the user. Implemented database queries to allow users to update their mobile number and email address.
49 | Bharat Mishra | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Business Logic APIs creation/Changes | 21/08/2026 | 21/08/2026 | Develop APIs for 2FA, OTP Verification, and User Contact Updates | 8.00 | 8 | Completed | Yet To Update | Developed APIs for 2FA eligibility, OTP generation and verification, and user mobile/email updates, integrated them with the database logic, and tested the complete verification workflow.
50 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 01/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 2 | WIP | Yet To Update | Requirement on Mining form , aadhar form and school form
51 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 01/07/2026 | 02/07/2026 | Training and workshop 2nd and 3rd day PM Poshan demonstrated to team at Walmi Campus | 8.00 | 3 | WIP | Yet To Update | 2nd day training of PM Poshan on social audit
52 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 03/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 3 | WIP | Yet To Update | Contant discussion with external stakeholder for requirement enhancements and communicate those requirement upgrades to internal team
53 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 01/07/2026 | 03/07/2026 | Training and workshop 2nd and 3rd day PM Poshan demonstrated to team at Walmi Campus | 8.00 | 5 | Completed | Yet To Update | Completed 3rd day training on PM Poshan social audit in walmi campus
54 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 06/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 6 | WIP | Yet To Update | guided team to onboard betul forms according to master data and verified correct master data for Betul collectorate to finalize
55 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 07/07/2026 | 06/07/2026 | Requirement gathering for Jabalpur Building Inspection Form | 4.00 | 2 | WIP | Yet To Update | Taken requirement from Jabalpur Building Inspection form
56 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 07/07/2026 | 07/07/2026 | Requirement gathering from Chhindwara Collectorate | 12.00 | 4 | WIP | Yet To Update | Requirement gathered from Chhindwara collectorate and did the departmental external meeting
57 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 07/07/2026 | 08/07/2026 | Requirement gathering from Chhindwara Collectorate | 12.00 | 3 | WIP | Yet To Update | Internal team discussion on Chhindwara 6 forms - गोदाम निरीक्षण प्रपत्र आंगनवाड़ी केन्द्र का निरीक्षण प्रपत्र स्वास्थ्य केंद्र निरीक्षण प्रतिवेदन विद्यालय निरीक्षण प्रपत्र is already there, tribal hostel inspection form
58 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 10/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 3 | WIP | Yet To Update | The Betul credentials are created for the state admin level and shared with the Betul collectorate to verify them at UAT environment
59 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 07/07/2026 | 10/07/2026 | Requirement gathering from Chhindwara Collectorate | 12.00 | 3 | WIP | Yet To Update | Chhindwara Master data and form finalized by comparison with other district collectorate forms
60 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 14/07/2026 | Requirement gathering and Analysis & further discussion with internal team & Enhancements into it | 16.00 | 2 | Completed | Yet To Update | All forms created at UAT and Betul Collectorate is checking it
61 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 07/07/2026 | 14/07/2026 | Requirement gathering for Jabalpur Building Inspection Form | 4.00 | 2 | Completed | Yet To Update | Jabalpur unused building inspection form - team has created it after Master data and updated inspection form received
62 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 07/07/2026 | 15/07/2026 | Requirement gathering from Chhindwara Collectorate | 12.00 | 2 | Completed | Yet To Update | All forms updated and moved to UAT and chhindwara collectorate is checking on it
63 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 14/07/2026 | 15/07/2026 | Unused Building Jabalpur Inspection - Department meeting & Internal Meeting Form & Master data | 4.00 | 2 | WIP | Yet To Update | Updated and mailed them to verify the status of Form on UAT
64 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 14/07/2026 | 16/07/2026 | PM Poshan video creation and atttended meeting for Buf fix from fields ( Block officer & VSA Inspector Issues ) Resolutions | 16.00 | 3 | WIP | Yet To Update | PM Poshan Bug fixing and video & department meeting & report creation
65 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 14/07/2026 | 17/07/2026 | PM Poshan video creation and atttended meeting for Buf fix from fields ( Block officer & VSA Inspector Issues ) Resolutions | 16.00 | 6 | WIP | Yet To Update | Resolved issues of PM Poshan inspection form - from VSA BO level in hierarchy users. Created video and updated it on group to complete inspection and connected with development team in meetings
66 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 15/07/2026 | 20/07/2026 | Chhindwara Report corrections | 2.00 | 2 | Completed | Yet To Update | Moved the forms to production
67 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 14/07/2026 | 21/07/2026 | Change request in requirement | 4.00 | 4 | Completed | Yet To Update | Shared data of changes to team and discussed with external department for correcting the remaining changes shared by them
68 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 14/07/2026 | 22/07/2026 | PM Poshan video creation and atttended meeting for Buf fix from fields ( Block officer & VSA Inspector Issues ) Resolutions | 16.00 | 4 | WIP | Yet To Update | Attended meeting and discussed with department about bug in forms
69 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 14/07/2026 | 23/07/2026 | Unused Building Jabalpur Inspection - Department meeting & Internal Meeting Form & Master data | 4.00 | 2 | Completed | Yet To Update | Discussed changes with department and questions & units sqft and other details of photo issue fixed and moved form to prod by dev team
70 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 14/07/2026 | 23/07/2026 | PM Poshan video creation and atttended meeting for Buf fix from fields ( Block officer & VSA Inspector Issues ) Resolutions | 16.00 | 3 | Completed | Yet To Update | PM Poshan issues resolved
71 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 27/07/2026 | 27/07/2026 | Chhindwara forms and reports uat and prod forms & incorporation of changes | 5.00 | 3 | WIP | Yet To Update | Forms changes deployed and Master data corrections incorporated
72 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate - Property Inspection | Property Inspection form | 27/07/2026 | 28/07/2026 | Indore Property form & apk deployment followup | 5.00 | 3 | WIP | Yet To Update | Changes into Property form Apk modification - select correct patch and deployment of and geofencing implementaion proper or not
73 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | MP Cooperative | Inspection form for Mp Cooperative society | 27/07/2026 | 28/07/2026 | MP Cooperative work on change request shared from department Nirikshan form and meeting | 8.00 | 3 | WIP | Yet To Update | MP cooperative Nirikshan old and new form comparison and created changes incorporated document and further implement them
74 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 27/07/2026 | 29/07/2026 | Betul 6 forms changes incorporated and resolved issues of form submissions & virtual calls | 5.00 | 3 | WIP | Yet To Update | Betul collectorate in UAT - able to fill all the forms just, school monitoring form, that was not able to submit other than that every form is working properly now and questions are also fine.
75 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Jabalpur Collectorate | Building Inspection Form for Jabalpur Collectorate | 24/07/2026 | 30/07/2026 | Jabalpur Unused building inspepction form changes and tracking UAT and prod | 3.00 | 3 | Completed | Yet To Update | Live Jabalpur form and report generated and corrected with changes
76 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 27/07/2026 | 31/07/2026 | Chhindwara forms and reports uat and prod forms & incorporation of changes | 5.00 | 2 | Completed | Yet To Update | Chhindwara reports are developed by team and is getting reviewed
77 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 05/08/2026 | 03/08/2026 | Betul Inspection form follow up | 3.00 | 1 | WIP | Yet To Update | Forms to be released in production
78 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 27/07/2026 | 03/08/2026 | Betul 6 forms changes incorporated and resolved issues of form submissions & virtual calls | 5.00 | 2 | Completed | Yet To Update | Betul 5 forms verified on UAT and discussing it with department so that we can onboard them to production
79 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | MP Cooperative | Inspection form for Mp Cooperative society | 27/07/2026 | 03/08/2026 | MP Cooperative work on change request shared from department Nirikshan form and meeting | 8.00 | 5 | Completed | Yet To Update | BRD and change summary documents created and sent to department for verification
80 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate - Property Inspection | Property Inspection form | 27/07/2026 | 04/08/2026 | Indore Property form & apk deployment followup | 5.00 | 2 | Completed | Yet To Update | Internal meeting to get new structured inspection form question deparmtnet wise from external Indore collectorate
81 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 04/08/2026 | 05/08/2026 | Requirement gathering meeting with Team & Indore Collectorate & finalize inspection forms | 16.00 | 4 | WIP | Yet To Update | Internal meeting and External stakeholders discussion on Phase 1 and Phase 2 of Indore inspection implementation and BRD and mock up of forms to team and external stakeholders
82 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 04/08/2026 | 06/08/2026 | Requirement gathering meeting with Team & Indore Collectorate & finalize inspection forms | 16.00 | 3 | WIP | Yet To Update | Connecting with internal team to finalize Divisional level hierarchy in parakh and Action taken report building in parakh
83 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 05/08/2026 | 07/08/2026 | Chhindwara Inspection form follow up | 2.00 | 2 | Completed | Yet To Update | Chhindwara inspection reprot building by team and production release
84 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Guna Collectorate | Guna Ayush health inspection form | 12/08/2026 | 10/08/2026 | Requirement understanding and analysis & gathered Guna Ayush health inspection form and master data | 4.00 | 2 | WIP | Yet To Update | Master data and requirement analysis of Ayush inspection forms and formatting of the form
85 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 11/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 3 | WIP | Yet To Update | Requirement gathered from damoh collectorate on 12 forms and understanding and analysis with team
86 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 12/08/2026 | 12/08/2026 | User manual creation for Phase 1 and Phase 2 implementation for INdore inspecction 17 forms | 14.00 | 5 | WIP | Yet To Update | User manual creation for phase 1
87 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 05/08/2026 | 13/08/2026 | Betul Inspection form follow up | 3.00 | 2 | WIP | Yet To Update | deployed and changes & issues fixed for betul forms - mining form gram panchayt not visible and other changes in the forms for the question changes
88 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 13/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 3 | WIP | Yet To Update | Constant follow up and creation of master data and deployment of Inspecion forms through team meetings
89 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 14/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 3 | WIP | Yet To Update | Conected with department for forms questions and Asset upload bulk upload method and add asset for each form
90 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 04/08/2026 | 17/08/2026 | Requirement gathering meeting with Team & Indore Collectorate & finalize inspection forms | 16.00 | 2 | WIP | Yet To Update | Indore sharing new forms to be implemented. After Phase 2 - Divisional officer login and View feature to divisional officer. Updated User Manual
91 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 18/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 2 | WIP | Yet To Update | following up on damoh forms work - general inspection forms
92 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 04/08/2026 | 20/08/2026 | Requirement gathering meeting with Team & Indore Collectorate & finalize inspection forms | 16.00 | 5 | Completed | Yet To Update | Understood meeting gathering from indore and communicated with them
93 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | CMMI Documentation | CMMI Level Documents | 18/08/2026 | 24/08/2026 | BRDs generic and add on with new enhancements | 12.00 | 5 | WIP | Yet To Update | BRDs according to changes and enhancement updated and created specific docs Generic also created
94 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Requirement gathering and Team Meetings with Indore Collectorate & finalize inspection forms | 12/08/2026 | 24/08/2026 | User manual creation for Phase 1 and Phase 2 implementation for INdore inspecction 17 forms | 14.00 | 3 | WIP | Yet To Update | Created manuals - Indore inspection and District GIS parakh manual updated with enhancements
95 | Dheeraj Motiyani | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Damoh Collectorate 12 Inspection forms | 12/08/2026 | 25/08/2026 | Requirement gathering for Damoh 12 Inspection forms and Team meetings & Departmental meeting for master data for all inspection forms | 14.00 | 3 | Completed | Yet To Update | Shared master data from Damoh should be updated in all 12 CM Jan vishwas
96 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore Collectorate - Property Inspection | Property Inspection form | 01/07/2026 | 01/07/2026 | Asset Survey: Video Recording Restriction and Form Submission Issue Resolution | 16.00 | 8 | WIP | Yet To Update | Implemented video recording restriction in the Asset Survey module. Applied recording constraints as per business requirements. Added validation for recording conditions before allowing video capture. Displayed appropriate validation/error messages for restricted scenarios. Improved user experience by preventing invalid video recordings. Verified video recording functionality across supported use cases.
97 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore Collectorate - Property Inspection | Property Inspection form | 01/07/2026 | 02/07/2026 | Asset Survey: Video Recording Restriction and Form Submission Issue Resolution | 16.00 | 8 | Completed | Yet To Update | Investigated and resolved Asset Survey form submission issues. Fixed form validation and mandatory field checks. Verified and corrected request payload generation according to API specifications. Improved media upload and form submission sequence. Fixed API response handling and error scenarios. Ensured successful submission of form data, location details, and media attachments. Performed regression testing to verify stable submission flow.
98 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 03/07/2026 | 03/07/2026 | Implement Video Compression and Restrict Video Recording Duration to 1 Minute | 8.00 | 8 | Completed | Yet To Update | Implemented video recording duration restriction with a maximum limit of 1 minute. Added automatic recording stop functionality when the time limit is reached. Implemented video compression after recording completion. Optimized video: File size Resolution Bitrate/quality balance Updated video processing flow: Capture video Validate duration Compress video Save optimized file Ensured compressed videos are used across: Upload API Save Draft Completed Form flow Added proper handling for recording, compression, and storage scenarios. Improved video upload performance by reducing file size.
99 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 06/07/2026 | 06/07/2026 | Asset Survey Form Submission Issue | 8.00 | 8 | Completed | Yet To Update | Investigated and resolved Asset Survey form submission issues. Fixed form validation and mandatory field checks. Verified and corrected request payload generation according to API specifications. Improved media upload and form submission sequence. Fixed API response handling and error scenarios. Ensured successful submission of form data, location details, and media attachments. Performed regression testing to verify stable submission flow.
100 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 07/07/2026 | 07/07/2026 | Conditional Questions: Implement Dynamic Sub-Question Addition (Add More) | 8.00 | 8 | Completed | Yet To Update | Complex nested conditional data scenarios require additional handling. Some dependent sub-questions do not update correctly when parent values change dynamically. Request payload mapping for certain multi-level conditional structures needs refinement. Further testing and fixes are in progress for edge cases involving nested/repeated conditional questions.
101 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 08/07/2026 | 08/07/2026 | Mining Site Inspection: Implement Predefined Values in Form Fields and Save As Draft | 16.00 | 8 | WIP | Yet To Update | Implemented predefined value support in Mining Site Inspection form. Added auto-fill functionality for: Text input fields Number fields Other applicable fields Implemented default selection handling for dropdown fields. Mapped predefined data with corresponding form fields. Ensured correct value binding when form loads. Maintained form state without resetting predefined values. Verified validations with auto-filled data.
102 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 08/07/2026 | 09/07/2026 | Mining Site Inspection: Implement Predefined Values in Form Fields and Save As Draft | 16.00 | 8 | Completed | Yet To Update | Added predefined value support in Save As Draft Mining Site Inspection form. Restored saved data for: Input fields Dropdown selections Implemented proper data mapping between saved draft data and dynamic form fields. Maintained selected dropdown values after reopening draft forms. Ensured consistency between: New Form Save As Draft Form Fixed value reset issues during form rendering. Verified form validation and submission flow with restored values.
103 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 10/07/2026 | 10/07/2026 | Indore Collectorate: Non-Survey Property Form, Patch Polygon Integration & Production Release | 8.00 | 8 | Completed | Yet To Update | Completed Indore Collectorate Non-Survey Property Form implementation and required changes. Verified form functionality including: Field handling Validation rules Data processing Submit flow Integrated Patch Polygon API successfully. Implemented polygon data handling: Fetch patch polygon details Parse geometry/path coordinates Display polygon on Google Map Manage polygon selection Attached selected polygon details with form data where required. Performed testing and resolved identified issues. Prepared production builds: Android release build iOS release build Verified production configurations, permissions, and version updates. Successfully uploaded application builds to: Google Play Store Apple App Store
104 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 13/07/2026 | 13/07/2026 | Indore Collectorate: Non-Survey Property Form, Patch Polygon Integration | 8.00 | 8 | Completed | Yet To Update | Completed Indore Collectorate Non-Survey Property Form implementation and required changes. Verified form functionality including: Field handling Validation rules Data processing Submit flow Integrated Patch Polygon API successfully. Implemented polygon data handling: Fetch patch polygon details Parse geometry/path coordinates Display polygon on Google Map Manage polygon selection Attached selected polygon details with form data where required. Performed testing and resolved identified issues.
105 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | New web page creation/ Modification | 14/07/2026 | 14/07/2026 | PM Poshan Form: Gallery Support and Save As Draft Button Visibility | 16.00 | 8 | WIP | Yet To Update | Implemented Gallery image selection in the PM Poshan Form. Added support for selecting images from the device gallery. Integrated gallery images with the existing image handling workflow. Ensured gallery-selected images are supported for: Form submission Save As Draft Offline storage (where applicable) Added image validation and preview functionality. Improved media selection user experience and maintained compatibility with existing camera capture flow.
106 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | New web page creation/ Modification | 14/07/2026 | 15/07/2026 | PM Poshan Form: Gallery Support and Save As Draft Button Visibility | 16.00 | 8 | Completed | Yet To Update | Added Save As Draft button on the last page of the PM Poshan Form. Ensured the button is always visible and accessible. Verified existing Save As Draft functionality works correctly with the updated UI. Ensured draft saving supports both camera-captured and gallery-selected images. Improved the final step user experience by making draft saving easily accessible. Performed testing to verify correct behavior and prevent UI regressions.
107 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 16/07/2026 | 16/07/2026 | MPRRDA Form – Fix Pagination and Camera Issues | 8.00 | 8 | Completed | Yet To Update | The reported issues in the MPRRDA form have been resolved. Pagination Issue: Fixed the pagination logic to ensure correct record display and smooth navigation across all pages while retaining applied filters. Camera Issue: Resolved the camera functionality. Users can now successfully open the camera, capture images, and upload them. Camera permission handling and error messages have also been improved.
108 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 17/07/2026 | 17/07/2026 | Implement Offline Form Save Functionality | 16.00 | 8 | WIP | Yet To Update | Implemented offline form save functionality using the local database (SQLite). Stored complete form information, including: Form fields Dropdown selections Conditional question responses GPS coordinates Date & time Draft status Saved captured media references locally for offline access. Ensured users can save forms without network connectivity. Added validation to maintain data integrity during offline save.
109 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 17/07/2026 | 20/07/2026 | Implement Offline Form Save Functionality | 16.00 | 8 | Completed | Yet To Update | Implemented the initial structure for offline form management. Began development of the offline forms listing and edit functionality. Started synchronization workflow for uploading locally saved forms. Remaining work includes: Completing offline form listing Editing saved offline forms Syncing pending forms with the server Updating local sync status after successful upload End-to-end testing and bug fixes The offline synchronization module is currently under development and will be completed in the next phase.
110 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 21/07/2026 | 21/07/2026 | Implement "Add More" Functionality for Conditional Questions | 16.00 | 8 | WIP | Yet To Update | mplemented the initial Add More functionality for conditional questions. Enabled dynamic creation of multiple conditional question groups. Added support for independent data storage for each added section. Implemented dynamic UI rendering for newly added question groups. Verified basic data entry and navigation for multiple instances.
111 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 21/07/2026 | 22/07/2026 | Implement "Add More" Functionality for Conditional Questions | 16.00 | 8 | Completed | Yet To Update | Work is currently in progress for the remaining implementation, including: Completing edit and delete functionality for dynamically added sections. Applying validation rules for each added question group. Finalizing API payload generation for multiple entries. Integrating with offline save and synchronization workflow. Performing end-to-end testing and resolving identified issues. The feature is partially completed, and the remaining development and testing are still in progress.
112 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 24/07/2026 | 24/07/2026 | Conditional Questions – Part 2: Complete Add More Functionality | 16.00 | 8 | WIP | Yet To Update | Completed Add More functionality for Conditional Questions in the New Form. Implemented dynamic creation of multiple conditional question groups. Added support for: Dynamic question rendering Independent data management for each added section Edit and delete functionality Conditional validation API payload generation Verified successful form submission with multiple Add More entries. Performed functional testing and resolved identified issues. Status: ✅ New Form implementation completed and working successfully.
113 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 24/07/2026 | 27/07/2026 | Conditional Questions – Part 2: Complete Add More Functionality | 16.00 | 8 | Completed | Yet To Update | Started implementing Add More support in the Save As Draft module. Implemented the initial data restoration flow for dynamically added question groups. Began integration of: Dynamic data restoration Edit/update support Validation for restored entries Payload mapping for draft records Currently working on: Complete restoration of all Add More sections Save As Draft update flow Offline compatibility End-to-end testing and bug fixes Status: 🚧 Save As Draft implementation is still in progress.
114 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 28/07/2026 | 28/07/2026 | Conditional Questions: Implement Add More Functionality in Save As Draft Form | 16.00 | 8 | WIP | Yet To Update | Implemented restoration of Add More conditional question groups in the Save As Draft form. Loaded previously saved dynamic entries from local storage/API. Restored: Dynamic question groups Field values Dropdown selections Conditional question responses Implemented dynamic rendering of restored sections. Preserved the original sequence and state of all Add More entries. Verified successful loading of draft data without data loss. All functionalities tested and working as expected.
115 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 28/07/2026 | 29/07/2026 | Conditional Questions: Implement Add More Functionality in Save As Draft Form | 16.00 | 8 | Completed | Yet To Update | Implemented edit and delete functionality for restored Add More sections. Added support for creating new Add More entries after reopening a draft. Applied validation rules to all dynamic sections before saving or submitting. Updated Save As Draft workflow to preserve all Add More data during subsequent saves. Implemented correct API payload generation for both: Save As Draft Final Form Submission Performed end-to-end testing for: Draft restoration Edit and delete operations Draft update Final submission Fixed issues related to dynamic data mapping and payload generation. All functionalities tested and working as expected.
116 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 30/07/2026 | 30/07/2026 | MPRRDA: Radio Button Navigation, Page Transition, and Inspection Summary Confirmation Popup | 16.00 | 8 | WIP | Yet To Update | Updated the radio button selection flow according to the latest business requirements. Implemented automatic navigation to the next page after selecting a radio button. Added support for seamless forward and backward navigation. Preserved selected responses during page transitions. Improved overall inspection workflow and user experience. Performed testing to verify smooth navigation and response retention.
117 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 30/07/2026 | 31/07/2026 | MPRRDA: Radio Button Navigation, Page Transition, and Inspection Summary Confirmation Popup | 16.00 | 8 | Completed | Yet To Update | mplemented a confirmation popup before final inspection submission. Displayed inspection summary including: Total Satisfactory count Total Unsatisfactory count Total answered questions Implemented dynamic calculation of counts based on user selections. Added confirmation and cancel actions before submission. Applied validation to ensure mandatory questions are answered before displaying the popup. Tested summary calculation and submission flow to ensure accurate results.
118 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 03/08/2026 | 03/08/2026 | MPRRDA: Download Data for Offline (SQLite) and Display Geometry from Local Database- Part 1 | 16.00 | 8 | WIP | Yet To Update | Implemented MPRRDA data download functionality. Downloaded and stored: Project details Road information Geometry data Required master data Created and updated SQLite tables for offline storage. Saved geometry coordinates and related metadata in the local database. Implemented data mapping and local persistence. Verified successful offline data download and storage.
119 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 03/08/2026 | 04/08/2026 | MPRRDA: Download Data for Offline (SQLite) and Display Geometry from Local Database- Part 1 | 16.00 | 8 | Completed | Yet To Update | Implemented retrieval of MPRRDA data from the local SQLite database. Displayed offline geometry on Google Map, including: Road polylines Polygon geometries Related map overlays (where applicable) Loaded project information and associated geometry in offline mode. Optimized offline map rendering for better performance. Verified geometry rendering accuracy and offline data consistency. Performed testing to ensure smooth offline map functionality.
120 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 05/08/2026 | 05/08/2026 | MPRRDA: Apply Radius Filter on Offline Road Geometry from SQLite | 8.00 | 8 | Completed | Yet To Update | Implemented radius filtering for MPRRDA road geometry using data stored in the local SQLite database. Retrieved the user's current location and calculated the distance to offline road geometries. Filtered and displayed only the roads falling within the selected radius. Loaded road geometry directly from SQLite without requiring an internet connection. Optimized local database queries and distance calculations for improved performance. Updated Google Map to display only filtered road geometries. Maintained compatibility with the existing road selection and inspection workflow. Verified accurate filtering, offline functionality, and smooth map rendering through testing.
121 | Jameel Khan | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 19/08/2026 | 19/08/2026 | MPRRDA: Implement District Wise Offline Road Data Download Functionality | 8.00 | 8 | Completed | Yet To Update | Implemented district selection workflow for offline road data download. Integrated district-wise road download API. Downloaded and stored: Road details Road geometry (Polyline) District-related metadata Created and updated SQLite tables for offline storage. Implemented data synchronization and duplicate record handling. Added download progress and status management. Implemented offline retrieval of downloaded road data from SQLite. Enabled offline visualization of road geometry on Google Maps. Supported existing road inspection and selection workflows using offline data. Added error handling for API failures, interrupted downloads, and database operations. Performed testing for district-wise downloads, offline access, and data updates.
122 | Krati Pandey | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Districts Reports - 1 | Bug Fixing from Frontend | 24/07/2026 | 24/07/2026 | Vehicle Number Plate Detection | 5.00 | 5 | Completed | Yet To Update | Conducted research on PaddleOCR to evaluate its suitability for OCR-based vehicle number plate recognition and document text extraction. Participated in a technical discussion to review the implementation approach, integration strategy, and expected outcomes. Coordinated with Nikita and requested the preparation of the Vehicle Detection model/file required for further development and integration. This groundwork will support the implementation and testing of the OCR-based detection workflow.
123 | Krati Pandey | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Agar Malwa | Create Agar malwa form and reports | 27/07/2026 | 27/07/2026 | vehicle Detection TFlite implement | 8.00 | 7 | Completed | Yet To Update | Integrated a new TensorFlow Lite (TFLite) model for the Vehicle Detection module to improve object detection accuracy and performance. Updated the inference pipeline to support the new model and validated its output across different vehicle categories. Additionally, enhanced the OCR implementation to achieve more accurate vehicle number plate text recognition. Optimized the detection and recognition workflow, followed by testing to ensure improved reliability and overall system performance.
124 | Krati Pandey | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Agar Malwa | Create Agar malwa form and reports | 27/07/2026 | 28/07/2026 | OCR Improvements | 16.00 | 7 | Completed | Yet To Update | Worked on improving the OCR accuracy and overall text recognition performance. Optimized the OCR processing pipeline to enhance the detection and extraction of text from captured images. Refined the recognition logic to improve reliability across different image qualities and challenging scenarios. Conducted testing to validate the improvements and ensure more accurate OCR results.
125 | Krati Pandey | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Agar Malwa | Create Agar malwa form and reports | 29/07/2026 | 29/07/2026 | Paddle OCR | 5.00 | 5 | Completed | Yet To Update | Installed and configured the Python development environment to support the PaddleOCR workflow. Downloaded the required inference models and converted them into the ONNX format for optimized inference and compatibility. Successfully integrated the converted ONNX models with PaddleOCR. Configured the OCR pipeline and validated the implementation to ensure accurate text detection and recognition. Performed initial testing to verify the end-to-end OCR functionality.
126 | Krati Pandey | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Agar Malwa | Create Agar malwa form and reports | 30/07/2026 | 30/07/2026 | OCR improvement and testing | 3.00 | 3 | Completed | Yet To Update | Enhanced the OCR implementation to improve text recognition accuracy and overall detection performance. Refined the recognition logic to achieve better results across different image qualities and challenging scenarios. Performed comprehensive testing to validate the improvements and ensure consistent OCR output. Verified that the updated implementation provides more reliable and accurate text extraction.
127 | Krati Pandey | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Agar Malwa | Create Agar malwa form and reports | 31/07/2026 | 31/07/2026 | Vehicle Detection Process method enhancement | 3.00 | 3 | Completed | Yet To Update | Integrated the InsertFeedback, GetFeedback, and GetEmergencyContacts APIs for the Department module in the Lokpath application. Implemented the complete API request and response handling using model classes and repository architecture. Updated the UI to allow users to submit feedback, view feedback history, and access emergency contact information. Performed end-to-end testing to ensure accurate data retrieval, successful feedback submission, and seamless user experience.
128 | Krati Pandey | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Agar Malwa | Create Agar malwa form and reports | 03/08/2026 | 04/08/2026 | Implemented Vehicle detection file | 12.00 | 3 | WIP | Yet To Update | Currently integrating the new TFLite model provided by Nikita for the Vehicle Detection module. Updating the detection pipeline and validating the model's performance to ensure accurate and reliable vehicle detection.
129 | Krati Pandey | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Agar Malwa | Create Agar malwa form and reports | 03/08/2026 | 06/08/2026 | Implemented Vehicle detection file | 12.00 | 4.5 | Completed | Yet To Update | Successfully integrated the new TFLite model provided by Nikita into the Vehicle Detection module. Completed the implementation, validated the integration, and generated an APK for testing. The testing build has been shared with the department for verification and feedback.
130 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 01/07/2026 | 01/07/2026 | Betul education form creation and update discussion on mining form and other forms | 8.00 | 8 | Completed | Yet To Update | Betul education form created and update discussion on mining form and other forms
131 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Betul Collectorate | Betul 6 forms Creation & Gathering Requirement | 02/07/2026 | 03/07/2026 | Betula form and sehore form copying from the already built forms. | 8.00 | 8 | Completed | Yet To Update | done Betula form and sehore form copying from the already built forms.
132 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Query/SP creation/Modification | 06/07/2026 | 06/07/2026 | Work flow data structure creation. | 8.00 | 8 | Completed | Yet To Update | Work flow data structure created.
133 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Business Logic APIs creation/Changes | 07/07/2026 | 07/07/2026 | work flow API and query creation | 8.00 | 8 | Completed | Yet To Update | work flow API and query creation done
134 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Chhindwara Collectorate | Inspection Forms total 5 needs to be created | 08/07/2026 | 08/07/2026 | गोदाम निरीक्षण प्रपत्र आंगनवाड़ी केन्द्र का निरीक्षण प्रपत्र स्वास्थ्य केंद्र निरीक्षण प्रतिवेदन forms creation for chhindwara | 8.00 | 8 | Completed | Yet To Update | गोदाम निरीक्षण प्रपत्र आंगनवाड़ी केन्द्र का निरीक्षण प्रपत्र स्वास्थ्य केंद्र निरीक्षण प्रतिवेदन form creation done
135 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | MIning Department | Data Processing | 09/07/2026 | 09/07/2026 | mining department Data processing for inspection | 8.00 | 8 | Completed | Yet To Update | mining department Data processing for inspection and inserted in to asset table
136 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | MIning Department | Report creation/ Modification | 10/07/2026 | 10/07/2026 | Form and Report Creation for Mining department | 8.00 | 8 | Completed | Yet To Update | Form and Report Created for Mining department and deployed to UAT
137 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | New web page creation/ Modification | 13/07/2026 | 13/07/2026 | Bug fixing in Details of Inspection Report | 8.00 | 8 | Completed | Yet To Update | Bug fixed in Details of Inspection Report and deployed to Uat
138 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Technical Support | 14/07/2026 | 14/07/2026 | Technical Support for the PMPsohan Team on their inspection | 16.00 | 8 | WIP | Yet To Update | Supported the inspector in the real time issues or challenges
139 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Technical Support | 14/07/2026 | 15/07/2026 | Technical Support for the PMPsohan Team on their inspection | 16.00 | 8 | Completed | Yet To Update | Supported them and resolve real time queries
140 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | New web page creation/ Modification | 16/07/2026 | 16/07/2026 | Report correction for PMposhan and update verify survey report, test and deploy it to UAT and then to Prod | 16.00 | 8 | WIP | Yet To Update | Report correction and addition of status column in it, updated db query and API and deployed to UAT
141 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | New web page creation/ Modification | 16/07/2026 | 17/07/2026 | Report correction for PMposhan and update verify survey report, test and deploy it to UAT and then to Prod | 16.00 | 8 | Completed | Yet To Update | update the verify survey report and fixed the bugs and then deployed to uat after testing deployed to prod,
142 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | New web page creation/ Modification | 20/07/2026 | 20/07/2026 | Re-assign functionality for rejected surveys | 8.00 | 8 | Completed | Yet To Update | Re-assign functionality for rejected surveys create query , API and updated verify page to have this functionality
143 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Encryption of network layer | 21/07/2026 | 21/07/2026 | Apply encryption of payload and response , so that data travels in network it will be encrypted | 16.00 | 8 | WIP | Yet To Update | Created an interceptors to encrypt the payload and decrypt the response on web
144 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Encryption of network layer | 21/07/2026 | 22/07/2026 | Apply encryption of payload and response , so that data travels in network it will be encrypted | 16.00 | 8 | Completed | Yet To Update | Creation of Middle ware and encryption methodology
145 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Encryption of network layer | 24/07/2026 | 24/07/2026 | Update the encryption methodology to have JWT token implemented | 16.00 | 7 | WIP | Yet To Update | JWT implemented at API level , get and verify
146 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Encryption of network layer | 24/07/2026 | 27/07/2026 | Update the encryption methodology to have JWT token implemented | 16.00 | 8 | Completed | Yet To Update | Implemented at web end deployed as another site for testing
147 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Jabalpur Collectorate | Report creation/ Modification | 28/07/2026 | 28/07/2026 | create the Jabalpur report and deployed | 6.00 | 6 | Completed | Yet To Update | report has been created and deployed.
148 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Query/SP creation/Modification | 28/07/2026 | 28/07/2026 | Bug fixing in query of Get user for mapping and update question so that all the child question should also deleted when their parent question get deleted. | 2.00 | 2 | Completed | Yet To Update | Bug fixed in query of Get user for mapping and update question so that all the child question should also deleted when their parent question get deleted.
149 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 29/07/2026 | 29/07/2026 | Fix the logging to capture the log of disconnectivity of client , log in api also | 8.00 | 8 | Completed | Yet To Update | fixed the logging
150 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Chhindwara Collectorate | Code review and PR merging | 30/07/2026 | 30/07/2026 | Code review and merge the PR and deployment of Web application | 1.00 | 1.00 | Completed | Yet To Update | Merged the PR and deployed to UAT
151 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Business Logic APIs creation/Changes | 30/07/2026 | 30/07/2026 | fix the windows error log writing by APIs | 1.00 | 1 | Completed | Yet To Update | fixed and deployed to UAT
152 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Document Preparation. | 30/07/2026 | 30/07/2026 | deployment of work flow api and Create integration doc , | 6.00 | 6 | Completed | Yet To Update | Deployment done for work flow and Created Integration doc and shared with mobile team
153 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Bug Fixing and Change in Business Logic | 31/07/2026 | 31/07/2026 | Find and Fix the issue in decryption of logic it failing in some APIs | 8.00 | 8 | Completed | Yet To Update | debugged the API code find out the error and fixed it and deployed to development .
154 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Query/SP creation/Modification | 03/08/2026 | 03/08/2026 | update the user table to have govt department and sub department and update the insert , update and get query | 8.00 | 8 | Completed | Yet To Update | altered the table and updated the queries
155 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Business Logic APIs creation/Changes | 04/08/2026 | 04/08/2026 | Update the Insert, Update and Get user APIs and deploy them | 8.00 | 8 | Completed | Yet To Update | Updated the Insert, Update and Get user APIs and deployed them
156 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Query/SP creation/Modification | 05/08/2026 | 05/08/2026 | Create Report query the for Indore collectorate of the form of school department and make it such it that will be visible to heirarchay user as well as to the Department HOD | 8.00 | 8 | Completed | Yet To Update | Created Report query the for Indore collectorate of the form of school department and made it such it that will be visible to heirarchay user as well as to the Department HOD
157 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Query/SP creation/Modification | 06/08/2026 | 06/08/2026 | update the report query for indore school department form and user insert and update query. | 6.00 | 6 | Completed | Yet To Update | updated the report query for indore school department form and user insert and update query.
158 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Staging deployment | 06/08/2026 | 06/08/2026 | code review and deployment to uat for Indore Collectorate work | 2.00 | 2 | Completed | Yet To Update | code reviewed and deployed to uat the Indore Collectorate work
159 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Staging deployment | 07/08/2026 | 07/08/2026 | review the cart addition in indore report and deploy it to staging | 1.00 | 1 | Completed | Yet To Update | reviewed the cart addition in Indore report and deployed it to staging.
160 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | MPRRDA | Report creation/ Modification | 07/08/2026 | 07/08/2026 | MPRRDA road Inspection report creation. | 6.00 | 6 | Completed | Yet To Update | created report for MPRRDA road inspection
161 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | MPRRDA | Staging deployment | 07/08/2026 | 07/08/2026 | deployment of road inspection report to staging | 1.00 | 1 | Completed | Yet To Update | deployed the road inspection report to staging
162 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Business Logic APIs creation/Changes | 10/08/2026 | 10/08/2026 | Indore Workflow of inspection, for HOD of the department . Create API for it | 4.00 | 4 | Completed | Yet To Update | Indore Workflow of inspection, for HOD of the department . Created API for it
163 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Query/SP creation/Modification | 10/08/2026 | 10/08/2026 | Indore Workflow of inspection, for HOD of the department . Create query it | 4.00 | 4 | Completed | Yet To Update | Indore Workflow of inspection, for HOD of the department . query creation done
164 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Query/SP creation/Modification | 11/08/2026 | 11/08/2026 | Create Database query and table creatin for Inspection Action taken report feature in Parakh | 16.00 | 8 | WIP | Yet To Update | Table structure creation done and Create one query to get department wise custom status
165 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Query/SP creation/Modification | 11/08/2026 | 12/08/2026 | Create Database query and table creatin for Inspection Action taken report feature in Parakh | 16.00 | 8 | Completed | Yet To Update | created query to record inspection movement and get inspection movement
166 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Query/SP creation/Modification | 13/08/2026 | 13/08/2026 | Create database query for two factor authentication | 8.00 | 8 | Completed | Yet To Update | created query to verify and get login for 2FA
167 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Business Logic APIs creation/Changes | 14/08/2026 | 14/08/2026 | API and Integration Document creation for 2FA | 8.00 | 8 | Completed | Yet To Update | created APIs for 2FA and Integration Document creation for 2FA
168 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Business Logic APIs creation/Changes | 17/08/2026 | 17/08/2026 | Inspection flow APIs creation | 8.00 | 8 | Completed | Yet To Update | create inspection flow 3 APIs
169 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Code Review and merge , and deployment | 18/08/2026 | 18/08/2026 | Code review and UAT deployment for Inspection ATR flow and 2FA, Betul forms and reports , Indore forms and reports | 2.00 | 2 | Completed | Yet To Update | Reviewed the code and deployed
170 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Rajgarh collectorate | Form and report creation | 18/08/2026 | 18/08/2026 | Rajgarh OBC hostel Inspection report creation | 6.00 | 6 | Completed | Yet To Update | Rajgarh OBC hostel Inspection report creation and UAT deployment
171 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Bhind Collectorate Office | Form and report creation | 19/08/2026 | 19/08/2026 | Create tabel for bhind patient feedback form and insert and get queries | 8.00 | 8 | Completed | Yet To Update | Create db table and insert and get queries for patient feedback form
172 | Madhur Nema | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Bhind Collectorate Office | Form and report creation | 20/08/2026 | 20/08/2026 | Bhind Patient Feedback UI and MIS report creation | 8.00 | 8 | Completed | Yet To Update | Createdd Bhind Patient Feedback UI and MIS report .
173 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 02/07/2026 | 02/07/2026 | Create mining form of Betul Collectorate on UAT | 4.00 | 4 | Completed | Yet To Update | Created a mining form for Betul Collectorate on UAT
174 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | New web page creation/ Modification | 03/07/2026 | 03/07/2026 | Correct the form of JD Inspection for Directorate of T&A department | 8.00 | 8 | Completed | Yet To Update | Corrected the form of the JD Inspection for the Directorate of T&A department, and corrected the form for the Betul Collectorate Mining form
175 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 06/07/2026 | 06/07/2026 | Correct the JD Inspection form for Directorate T&A Department | 8.00 | 8 | Completed | Yet To Update | Corrected the JD Inspection form for the Directorate T&A Department and corrected the Betul Collectorate mining form
176 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 07/07/2026 | 07/07/2026 | Correct the Treasury inspection form for Directorate of T&A department | 8.00 | 8 | Completed | Yet To Update | Corrected the Treasury inspection form for the Directorate of T&A department
177 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Discussion on Parakh | 08/07/2026 | 08/07/2026 | Correct the mining form, create the Non-survey property Detail form and correct the Treasury Form | 8.00 | 8 | Completed | Yet To Update | Corrected the mining form, created the Non-survey property Detail form, and corrected the Treasury Form
178 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 09/07/2026 | 09/07/2026 | Test the Mining form, test the Non-Surveyed property detail form and test the labour department forms | 8.00 | 8 | Completed | Yet To Update | Tested the Mining form, tested the Non-Surveyed property detail form, and tested the labour department forms
179 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Discussion on Parakh | 10/07/2026 | 10/07/2026 | Correct the Chhindwara Collectorate form on the UAT environment. Assign assets for all districts under the Mining Department. | 8.00 | 8 | Completed | Yet To Update | Corrected the Chhindwara Collectorate form on the UAT environment. Assigned assets for all districts under the Mining Department.
180 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Discussion on Parakh | 13/07/2026 | 13/07/2026 | Create the Chhindwara Collectorate "मध्याह्न भोजन निरीक्षण प्रपत्र" and PNRD-SRLM "गैर-कृषि उद्यम सर्वे प्रपत्र" forms. | 8.00 | 8 | Completed | Yet To Update | Created the Chhindwara Collectorate "मध्याह्न भोजन निरीक्षण प्रपत्र" and PNRD-SRLM "गैर-कृषि उद्यम सर्वे प्रपत्र" forms.
181 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | PM Poshan | Training & workshop conducted for District GIS Parakh PM Poshan Social Audit Training | 15/07/2026 | 15/07/2026 | Resolve live production issues reported by PM POSHAN department users. and test the PM POSHAN report | 8.00 | 8 | Completed | Yet To Update | Resolved live production issues reported by PM POSHAN department users. and tested the PM POSHAN report
182 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Discussion on Parakh | 16/07/2026 | 16/07/2026 | Create the MPRRDA Department form and Jabalpur collectorate Form | 8.00 | 8 | Completed | Yet To Update | Created the MPRRDA Department form and Jabalpur Collectorate form
183 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Discussion on Parakh | 17/07/2026 | 17/07/2026 | Correct the Chhindwara Collectorate all forms and Betul Collectorate "mining Lease form" | 8.00 | 8 | Completed | Yet To Update | Corrected the Chhindwara Collectorate all forms and the Betul Collectorate "mining Lease form"
184 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 20/07/2026 | 20/07/2026 | Create the checklist form for "Directive of T&A" Department and test the Betul Collectorate forms | 8.00 | 8 | Completed | Yet To Update | Created the checklist form for the "Directive of T&A" Department and tested the Betul Collectorate forms
185 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Discussion on Parakh | 21/07/2026 | 21/07/2026 | Correct and test the Chhindwara Collectorate forms, and create the 'Checklist' form for the 'Directorate of T&A' Department. | 8.00 | 8 | Completed | Yet To Update | Corrected and tested the Chhindwara Collectorate forms, and created the 'Checklist' form for the 'Directorate of T&A' Department.
186 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 22/07/2026 | 22/07/2026 | Correct and test the Chhindwara Collectorate Forms | 8.00 | 8 | Completed | Yet To Update | Corrected and tested the Chhindwara Collectorate Forms
187 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 24/07/2026 | 24/07/2026 | Test the Betul Collectorate forms and Correct the Froms | 8.00 | 8 | Completed | Yet To Update | Tested the Betul Collectorate forms and corrected the Forms
188 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 27/07/2026 | 27/07/2026 | Test the Indore Property Survey Form, Chhindwara Collectorate Forms, and All Reports | 8.00 | 8 | Completed | Yet To Update | Tested the Indore Property Survey Form, Chhindwara Collectorate Forms, and All Reports
189 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 28/07/2026 | 28/07/2026 | Test the chhindwara collectorate, All reports, correct the Betul collectorate forms and test the Jabalpur collectorate from | 8.00 | 8 | Completed | Yet To Update | Tested the Chhindwara Collectorate, all reports, corrected the Betul Collectorate forms, and tested the Jabalpur Collectorate from
190 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Jabalpur Collectorate | Unit Testing for module | 29/07/2026 | 29/07/2026 | Test the Jabalpur Collectorate form and report for both environment UAT & Web | 8.00 | 8 | Completed | Yet To Update | Tested the Jabalpur Collectorate form and report for both environment UAT & Web
191 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 30/07/2026 | 30/07/2026 | Test the MPRRDA Form on UAT and test the property survey form on production environment | 4.00 | 4 | Completed | Yet To Update | Tested the MPRRDA Form on UAT and tested the property survey form on the production environment
192 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 30/07/2026 | 30/07/2026 | Test the web module all functionality thoroughly and reported bugs on promote | 12.00 | 4 | WIP | Yet To Update | Tested the web module all functionality thoroughly and reported bugs on Promote
193 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 30/07/2026 | 31/07/2026 | Test the web module all functionality thoroughly and reported bugs on promote | 12.00 | 8 | Completed | Yet To Update | Tested the web module all functionality thoroughly and reported bugs on Promote
194 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 03/08/2026 | 03/08/2026 | Test the betul collectorate form on UAT and test the report of Chhindwara collectorate all forms | 8.00 | 8 | Completed | Yet To Update | Tested the betul collectorate form on UAT and tested the report of Chhindwara collectorate all forms
195 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 04/08/2026 | 04/08/2026 | Create Indore Collectorate Forms and Test all the forms on UAT | 16.00 | 8 | WIP | Yet To Update | Created Indore Collectorate Forms on UAT
196 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 04/08/2026 | 05/08/2026 | Create Indore Collectorate Forms and Test all the forms on UAT | 16.00 | 8 | Completed | Yet To Update | Created Indore Collectorate Forms and Tested all the forms on UAT
197 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 06/08/2026 | 06/08/2026 | Correct the Indore Collectorate forms and test them on UAT. Also, test the MPRRDA form changes on UAT. | 16.00 | 8 | WIP | Yet To Update | Corrected the Indore Collectorate forms and tested them on UAT.
198 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 06/08/2026 | 07/08/2026 | Correct the Indore Collectorate forms and test them on UAT. Also, test the MPRRDA form changes on UAT. | 16.00 | 8 | Completed | Yet To Update | Corrected the Indore Collectorate forms and tested them on UAT. Also tested the MPRRDA form changes on UAT.
199 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 10/08/2026 | 10/08/2026 | Create the "महिला एवं बाल विकास विभाग" form for the Indore Collectorate. | 8.00 | 8 | Completed | Yet To Update | Created the "महिला एवं बाल विकास विभाग" form for the Indore Collectorate.
200 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Discussion on Parakh | 11/08/2026 | 11/08/2026 | Create the " खाद वितरण केंद्र निरीक्षण प्रपत्र" form for the All Collectorate. | 8.00 | 8 | Completed | Yet To Update | Created the " खाद वितरण केंद्र निरीक्षण प्रपत्र" form for the All Collectorate.
201 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Discussion on Parakh | 12/08/2026 | 12/08/2026 | Create All the form of damoh Collectorate | 16.00 | 8 | WIP | Yet To Update | Created all the forms of the Damoh Collectorate
202 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Discussion on Parakh | 12/08/2026 | 13/08/2026 | Create All the form of damoh Collectorate | 16.00 | 8 | Completed | Yet To Update | Created all the forms of the Damoh Collectorate
203 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Parakh Enhancement | Manual Testing & prepare testing document | 14/08/2026 | 14/08/2026 | Create the Damoh Collectorate forms, create the users for the Division module, and test the Division module. | 8.00 | 8 | Completed | Yet To Update | Created the Damoh Collectorate forms, created the users for the Division module, and tested the Division module.
204 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore Collectorate | Form and report creation | 17/08/2026 | 17/08/2026 | Test the division Module and District module on UAT | 4.00 | 4 | Completed | Yet To Update | Tested the division Module and District module on UAT
205 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Rajgarh collectorate | Form and report creation | 17/08/2026 | 17/08/2026 | Create the Rajgarh Collectorate “OBC Hostel Inspection Form” and test on UAT | 4.00 | 4 | Completed | Yet To Update | Created the Rajgarh Collectorate “OBC Hostel Inspection Form” and tested on UAT
206 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Form and Report Creation | 18/08/2026 | 18/08/2026 | Create the Damoh Collactorate "jan Vishwash abhiyan" Forms on IAT | 16.00 | 8 | WIP | Yet To Update | Created the Damoh Collectorate "jan Vishwash abhiyan" Forms on IAT
207 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Form and Report Creation | 18/08/2026 | 19/08/2026 | Create the Damoh Collactorate "jan Vishwash abhiyan" Forms on IAT | 16.00 | 8 | Completed | Yet To Update | Created the Damoh Collectorate "jan Vishwash abhiyan" Forms on IAT
208 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Form and Report Creation | 20/08/2026 | 20/08/2026 | Corrected the Damoh Collectorate forms on UAT and created the remaining forms. | 16.00 | 8 | WIP | Yet To Update | Corrected the Damoh Collectorate "Jan Vishwas Abhiyan" Forms
209 | Manisha Dadhore | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Damoh Collectorate | Form and Report Creation | 20/08/2026 | 21/08/2026 | Corrected the Damoh Collectorate forms on UAT and created the remaining forms. | 16.00 | 8 | Completed | Yet To Update | Created the Remaining Forms of Damoh Collectorate on UAT
210 | Neetu Malviya | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore Collectorate - Property Inspection | Form creation and correction | 14/07/2026 | 14/07/2026 | Property Survey Form Update and Submitted Form Rejection Functionality Testing | 16.00 | 8.00 | WIP | Yet To Update | Updated the Property Survey Form for the Indore Collectorate in the Parakh project as per the latest requirements. Verified the updated form fields, validations, data entry process, and overall workflow to ensure the changes were implemented correctly. and Performed testing of the Submitted Form Rejection functionality on the web portal. Verified that submitted forms could be rejected successfully, the rejection status was updated correctly, and the rejected forms reflected the expected behavior in the application
211 | Neetu Malviya | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore Collectorate - Property Inspection | Form creation and correction | 14/07/2026 | 22/07/2026 | Property Survey Form Update and Submitted Form Rejection Functionality Testing | 16.00 | 8.00 | Completed | Yet To Update | Performed corrections to the School Monitoring Form for the Betul Collectorate based on the latest requirements and feedback. Updated the modified form in the UAT environment and verified that all changes were implemented successfully.
212 | Neetu Malviya | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | PM Poshan | Manual Testing & Preparing Document | 17/08/2026 | 17/08/2026 | PM POSHAN Form Workflow and Approval Hierarchy Validation | 16.00 | 8.00 | WIP | Yet To Update | Performed comprehensive testing of the PM POSHAN form to verify form fields, validations, data entry, submission workflow, and overall functionality. Validated the approval hierarchy to ensure that submitted forms were correctly routed through the defined hierarchy at the Block, RO, and State levels. Verified the approval workflow, status updates, user-wise access, and proper movement of forms from one hierarchy level to the next. Ensured that authorized users at each level could view, approve, or take the required action on the forms according to their assigned roles.
213 | Neetu Malviya | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | MP Metro | Manual Testing & Preparing Document | 17/08/2026 | 18/08/2026 | MP MATRO Department and Form Creation | 16.00 | 8.00 | WIP | Yet To Update | Created the MP MATRO Department in the system and configured the required department details and access settings. Developed the associated MP MATRO form based on the defined requirements, including required fields, field types, validations, and form workflow. Performed initial verification of the created department and form to ensure proper configuration, data entry, validation, and submission functionality.
214 | Neetu Malviya | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | MP Metro | Manual Testing & Preparing Document | 17/08/2026 | 19/08/2026 | MP MATRO Department and Form Creation | 16.00 | 8.00 | Completed | Yet To Update | Created and configured the MP MATRO Department in the application as per the project requirements. Set up the required department configuration and created the associated form with appropriate fields, field types, validations, and data collection requirements. Verified the form configuration and ensured that the department and form were properly set up for further use and testing.
215 | Neetu Malviya | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | PM Poshan | Manual Testing & Preparing Document | 17/08/2026 | 20/08/2026 | PM POSHAN Form Workflow and Approval Hierarchy Validation | 16.00 | 8.00 | Completed | Yet To Update | Performed end-to-end testing of the PM POSHAN form to validate form functionality, field behavior, validations, data entry, and submission. Verified the complete approval hierarchy and workflow to ensure that submitted forms were routed correctly through the Block, RO, and State levels.
216 | Neetu Malviya | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Bhind Collectorate Office | Manual Testing and preparing document | 21/08/2026 | 21/08/2026 | Patient Feedback Form and Report Functionality Testing | 8.00 | 8.00 | Completed | Yet To Update | Tested the Patient Feedback functionality and validated the corresponding web reports for accurate data synchronization, rating display, and report generation.
217 | Nilesh Gangrade | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 13/07/2026 | 13/07/2026 | main login page creation and new changes | 16.00 | 8.00 | WIP | Yet To Update | Module: Labour Commissioner Organisation – Login Page Worked on Task: Designed the Login Page as per the latest UI/UX requirements. Updated the complete color scheme and implemented a new theme to match the project branding. Revamped the overall styling of the login page, including layout, typography, buttons, and form elements. Improved the visual hierarchy, spacing, and alignment for a cleaner and more professional government interface. Enhanced the overall look and feel by applying the new design system consistently across the page.
218 | Nilesh Gangrade | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 13/07/2026 | 14/07/2026 | main login page creation and new changes | 16.00 | 8.00 | Completed | Yet To Update | Module: Labour Commissioner Organisation – Compliance and Prosecution Report & Login Page Worked on Task: Worked on the Compliance and Prosecution Report page as per the latest requirements. Designed and refined the filter section for improved search and data filtering. Enhanced the table section with better layout, alignment, and data presentation. Improved spacing, UI consistency, and overall page usability.
219 | Nilesh Gangrade | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 15/07/2026 | 15/07/2026 | Compliance and Prosecution Report page UI changes | 16.00 | 8.00 | WIP | Yet To Update | Module: Labour Commissioner Organisation – Compliance and Prosecution Report Worked on Today’s Task: Worked on the Compliance and Prosecution Report page as per the latest UI requirements. Designed the Download Form section within the report table for better usability and accessibility. Developed the Upload Signed Report popup with a clean and structured UI. Improved the popup layout, form alignment, spacing, and overall user interaction. Refined the filter section with an enhanced layout and better visual consistency.
220 | Nilesh Gangrade | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 15/07/2026 | 16/07/2026 | Compliance and Prosecution Report page UI changes | 16.00 | 8.00 | Completed | Yet To Update | Module: Labour Commissioner Organisation – Filled Prosecutions & Completed Surveys & Inspections Worked on Task: Worked on the Filled Prosecutions and Completed Surveys & Inspections pages. Redesigned the filter section as per the latest UI requirements for improved usability and consistency. Enhanced the table section with a clean layout, better alignment, spacing, and improved data presentation. Implemented the new design by following the same design system and visual theme used on the Login Page to maintain a consistent user experience.
221 | Nilesh Gangrade | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 20/07/2026 | 20/07/2026 | Labour Commissioner Organisation – Establishment Documents table coloum popup | 16.00 | 8.00 | WIP | Yet To Update | Module: Labour Commissioner Organisation – Establishment Documents Worked on Task: Worked on the Establishment Documents page and refined the table interaction flow. Designed and implemented the popup for the Establishment Documents column to display detailed information. Developed the Action column popup with an improved UI and structured layout.
222 | Nilesh Gangrade | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | New web page creation/ Modification | 20/07/2026 | 21/07/2026 | Labour Commissioner Organisation – Establishment Documents table coloum popup | 16.00 | 8.00 | Completed | Yet To Update | Module: Labour Commissioner Organisation – Establishment Inspection Status Worked on Task: Worked on the Establishment Inspection Status page. Completely redesigned the Document Upload – View Popup Modal as per the latest UI requirements.
223 | Nilesh Gangrade | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore - Labour Inspection | New web page creation/ Modification | 29/07/2026 | 29/07/2026 | new changes | 16.00 | 8.00 | WIP | Yet To Update | Module: Labour Commissioner Organisation Worked on Task: Fixed the Login Page image loading issue to ensure all background and UI images display correctly. Improved the Send OTP button by refining its UI, alignment, and interaction for a better user experience. Worked on the Sudden Inspection Report page and implemented the required frontend UI updates. Worked on the Asset Survey Report page and incorporated the latest design changes as per project requirements. Improved layout structure, spacing, alignment, and overall visual consistency across the updated pages.
224 | Nilesh Gangrade | BHOPAL | Parakh (District GIS) | Parakh Customization for MPRRDA & Marketing Federation | 24/07/2026 ¦ 23/08/2026 | Indore - Labour Inspection | New web page creation/ Modification | 29/07/2026 | 30/07/2026 | new changes | 16.00 | 8.00 | Completed | Yet To Update | Module: Labour Commissioner Organisation – Reports Worked on Task: Worked on the Department General Report page and implemented the required frontend UI updates. Enhanced the Details of Survey and Inspection page by refining the layout and improving UI consistency. Worked on the Compliance and Prosecution Report page, focusing on the table popup as per the latest requirements. Updated the popup layout, alignment, spacing, and content presentation to provide a cleaner and more structured interface.
225 | Rini Kanik | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | Meeting and demo | 20/07/2026 | 20/07/2026 | UAT for Labour Compliance & Prosecutions | 2.00 | 2.00 | Completed | Yet To Update | UAT for Labour Compliance & Prosecutions with Bharat. Findings are: 1. When the Inspector uploads the Effective Date and the Compliance Document List, an SMS notification should be sent to the establishment informing them that they must upload the required compliance documents on or before the specified effective date. 2. After the Inspector sets the Effective Date, they should have the option to extend the compliance deadline, if required. 3. Each compliance document should have a maximum file size of 3 MB, and the establishment should be allowed to upload a maximum of 5 documents. 4. When the establishment submits the compliance documents, the final submission should require OTP-based verification. 5. An Edit option should be available for cases where prosecution has already been filed. 6. The Prosecution Filed list should clearly indicate whether the case is a Legacy Case or a Parakh Inspection Case. 7. After the establishment uploads the compliance documents, the Scheduler should review the submission and mark it as one of the following: * Accept – The case will be closed. * Partial Accept – The case will proceed for prosecution. * Not Accept – The case will proceed for prosecution.
226 | Rini Kanik | BHOPAL | Parakh (District GIS) | Parakh Customization for WorkFlow - Indore Collectorate | 23/06/2026 ¦ 22/07/2026 | Indore - Labour Inspection | Meeting and demo | 21/07/2026 | 21/07/2026 | UAT Findings Discussion with Team | 1.00 | 1.00 | Completed | Yet To Update | UAT Findings Discussion with Team