Techno-Commercial Proposal

for MP Cooperative Society Inspection (Nirikshan) Module on ICMIS

MP Cooperative Society — ICMIS Inspection Module (Parakh)

| Madhya Pradesh State Electronics Development Corporation (MPSeDC) State IT Center, 47-A, Arera Hills, Bhopal, M.P. – 462011 |  | Prepared for the Office of the Registrar Cooperative Societies, Government of Madhya Pradesh Phone: +91-755-2518300 URL: www.mpsedc.mp.gov.in |
| --- | --- | --- |

Techno-Commercial Proposal for New Scope of Work   |   Document Version 1.1   |   October 2026

# Contents

Document Control	3

1. Background	4

2. Purpose of this Proposal	4

3. Reference to Existing (Base) System	5

3.1 Existing Components (for reference only)	5

4. Scope of Work	6

5. Functionality List	9

6. Role-wise Access Matrix	10

7. Illustrative Report, Workflow & API Layout	11

8. Methodology & Approach	12

9. Deliverables	12

10. Project Timeline	13

11. Resource & Cost Estimate	14

12. Payment Terms	15

13. Assumptions & Constraints	15

14. Reference Documents	16

15. Contact Persons	16

# Document Control

| Field | Value |
| --- | --- |
| Document Title | MP Cooperative Society ICMIS Inspection (Nirikshan) Module – Techno-Commercial Proposal for New Scope of Work |
| Base Document | Business Specification Document (BSD) – Nirikshan Module v1.0 (May 2026); Previous shared Nirikshan form on 30.07.2026, Approved Final Nirikshan Form, RCS IT Section, 02.10.2026 |
| Prepared For | Office of the Registrar Cooperative Societies (RCS), Co-operation Department, Govt. of Madhya Pradesh |
| Prepared By | MPSeDC — Parakh Team / Business Analysis |
| Trigger References | RCS IT Section email dated 10.09.2026 (Updated Inspection Format & Master Data); RCS Computerization Meeting dated 18.09.2026; Updated Nirikshan Form dated 02.10.2026; Department requirement note (Inspection Report, e-Sign, Login, User List, ICMIS API) |
| Version | 1.1 |
| Status | Submitted for Approval |
| Classification | Commercial in Confidence |

# 1. Background

The Office of the Registrar Cooperative Societies (RCS), Madhya Pradesh, is computerizing the annual inspection (Nirikshan) of Co-operation Department offices through the Integrated Cooperative Management Information System (ICMIS) portal and the Parakh platform. The business process, roles, workflow and report structure have been captured in the Business Specification Document (BSD) for the Nirikshan Module, previously shared Nirikshan form on 30.07.2026, and the approved final format of the Nirikshan Form was shared by the RCS IT Section on 02.10.2026.

Since then the Department has issued an updated Nirikshan Form and Master Data (10.09.2026; updated form dated 02.10.2026), shared UAT feedback, and, following the RCS Computerization Meeting of 18.09.2026, communicated a further set of requirements: an Inspection Report view in the ICMIS Departmental Login, a Custom e-Sign facility, an ICMIS-style Department-only login page, a hierarchy-wise user listing with search, and an API to share inspection reports with ICMIS. The Department has also defined the rules for annual roster creation and assignment among Joint, Deputy and Additional Registrar offices.

Note: This proposal covers the new scope of work shared by the Department, including the development of the Nirikshan form and the end-to-end inspection workflow. Existing screens already available on Parakh (Roster List, Assigned Inspection, View Inspection, Master and User List) are referenced only for context in Section 3 & previously shared Nirikshan Form on 30.07.2026.

# 2. Purpose of this Proposal

This proposal defines the functional scope, delivery approach, timeline and cost for the following new scope of work for the MP Cooperative Inspection Module: (a) publishing inspection reports in the ICMIS Departmental Login, (b) a Custom e-Sign facility for orders and reports (integration with e-Sign facility of MPSeDC), (c) an ICMIS-style Department-only login page, (d) a hierarchy-wise user listing (JR, DR, AR), (e) filteration with keyword search, (f) an API to share inspection reports with ICMIS, (g) annual roster and inspection order management, (g) complete module developed in parakh needs to be re-designed according to ICMIS portal User Interface(UI), (h) customize Parakh login page with ICMIS logo & details, (i) development of the Nirikshan Prativedan (inspection report) form as per the updated format, (h) development of the end-to-end inspection workflow, and (i) masters and user data preparation (RCS Office master & User Template).

# 3. Reference to Existing (Base) System

The Parakh platform already provides the base screens used by the Inspection Module in the UAT environment, as shown in the screenshots shared by the project team. The Nirikshan Form shell (basic details and the Establishment section) opens from the inspector’s Assigned Inspection list. Field-level specification of the form and the process is documented in the BSD and the Updated Nirikshan Form, and is not reproduced here.

## 3.1 Existing Components (for reference only)

| S.No. | Component | Current Status |
| --- | --- | --- |
| 1 | Roster List (Commissioner login) | Available in UAT: order number, status, schedule date, remark, total assigned / pending / ongoing / completed, order copy |
| 2 | Assigned Inspection List (Inspector login) | Available in UAT: order number, office type, division, district, office name, schedule date, status, office order, View action |
| 3 | View Inspection (offices where inspection is conducted) | Screen with summary column groups available; data population pending form development |
| 4 | Master: Create Designation, Create User; User List; Circular/Notification; Reset Password | Available in UAT; user list is not hierarchy-ordered and has no Office Name field |
| 5 | Parakh login page | Existing multi-option design; differs from ICMIS portal |
| 6 | Inspection report hand-off to ICMIS | Not available |

Reference: Refer to the BSD v1.0, the approved Nirikshan Form (30.07.2026) and the Updated Nirikshan Form (02.10.2026) for the complete section structure. The scope of work below lists what is to be developed.

# 4. Scope of Work

The following items are in scope, as per the Department’s requirement note, the business specification, the updated Nirikshan Form and the UAT feedback received:

## SOW-01: Inspection Report in Departmental Login

- Provide a separate “Inspection Report” tab/menu in the ICMIS Departmental Login (alongside Dashboard, Reports and other menus).

- Authorized departmental officers can view and download the inspection reports submitted through the Inspection Module, with filters for Year, Office Name and Status.

- Marked as a priority item by the Department for effective monitoring and review of inspection activities.

## SOW-02: Custom e-Sign Facility

- Provide a Custom e-Sign facility so authorized users can digitally sign the annual inspection order (Commissioner) and the inspection report (Nirikshankarta) as per the prescribed workflow.

- OTP-based signing through the MP State OTP Gateway: OTP valid for 10 minutes, maximum 3 attempts per session.

- Signed PDF carries signer name, designation, timestamp and IP address; every e-sign event is written to an audit log.

- A signed document cannot be edited; changes are handled through a separate Corrigendum (शुद्धिपत्र) process.

## SOW-03: Login Page – Department Option Only

- Provide the Parakh login page in the ICMIS portal design format (colour theme, layout, captcha and OTP flow).

- Display only the “Department” login option; other options are removed/not displayed.

- Align module UI colours with the ICMIS portal (UAT observation: UI colour mismatch between Parakh and ICMIS).

## SOW-04: Hierarchy-wise User Listing with Search

- Display users in the order: JR (Joint Registrar) first, then DR (Deputy Registrar), then AR (Additional Registrar).

- Provide a keyword-based search to quickly locate a particular user.

- Provide the “Office Name” (कार्यालय का नाम) field in the User Master.

## SOW-05: API Integration with ICMIS for Sharing Inspection Reports

- Develop an API to share signed inspection reports with ICMIS.

- Basic payload parameters: Officer ID, Officer Name, Designation, Office ID, User ID and Inspection Report PDF.

- Additional parameters can be added based on further discussion with the receiving (ICMIS) team.

- Secure authentication, request/response logging, retry handling and error reporting for failed transfers.

## SOW-06: Annual Inspection Roster & Order Management

- Commissioner creates the Annual Inspection Roster (draft, inspection year auto-set): selects the Nirikshankarta from the officer list fetched from ICMIS, then the Division, Divisional Office (10 divisions) and multi-selects District Offices (51), with Add / Edit / Delete before final submission.

- Eligibility rules: AR – only AR offices; DR – AR and DR offices; JR – JR, DR and AR offices. An officer is not offered his/her own office, and an office assigned once in a year is removed from the list for other officers (one inspection per office per year; multiple offices per officer allowed).

- An inspector allotted to a Deputy Commissioner office is also allotted the Assistant Commissioner (Audit) and (Administration) offices, as per the inspection order.

- Final Submit locks the roster and triggers OTP e-Sign; the system generates the signed Inspection Order PDF on the Commissioner’s letterhead (order number in the form 2026/ICMIS-RCS/0000n) with the roster table and instruction points.

- The signed order is auto-dispatched to all inspecting officers by email and portal notification, with the order number and roster list.

## SOW-07: Nirikshan Prativedan (Inspection Report) Form Development

- Develop the digital Nirikshan Prativedan form as per the Updated Nirikshan Form (02.10.2026), covering the report sections defined in the BSD (48 sections) organized into tabs (A) to (J): basic details, sanctioned setup, compliance checks, accounts register checklist (18 items), cooperative society data, complaints, court cases, financial banks and credit societies, recovery, audit and IT infrastructure.

- Basic details are auto-filled from the order and masters: Inspecting Officer Name, Office to be Inspected, Office Head Name (not editable) and Inspection Date; District Name is auto-filled in the audit tables.

- Tab-wise Save & Next with sub-sections; “Add Row” provided only where explicitly specified in the format, with tabular alignment and visible scroll bars.

- Auto-calculated fields as per the format: Vacant = Sanctioned − Filled, Pending = A − B, Total = A + B, Recovery % = F / C × 100; validation that Filled + Vacant = Sanctioned.

- Drop-downs from masters: Designation Master in the setup tables and the list of Sections (e.g. 84, 64, 58B) in the recovery-case and court-case tables.

- Pre-fill of available data from ICMIS (society counts, registration status, audit fee), eHRM (attendance) and CJCMS (court cases), where the respective APIs are made available; user can verify and update.

- Draft save at any time (auto-save every 5 minutes), progress percentage, mandatory remarks field per section for analytical observations, and Preview Report with incomplete sections flagged.

- Final Submit with mandatory-field validation, followed by OTP e-Sign (SOW-02) and generation of the signed Nirikshan Prativedan PDF containing all sections, e-signature details and office letterhead.

- UAT feedback incorporated: Election section text correction, audit tab (I) recovery-case sections with Section drop-down, court cases section (J), and ICMIS-aligned UI colours.

## SOW-08: Inspection Workflow, Status Tracking & Notifications

- End-to-end workflow in four phases: (A) Order issuance, (B) Pre-inspection acknowledgement and “Start Inspection”, (C) Report filling, (D) e-Sign and submission, followed by review by the Commissioner / Nodal Officer.

- Status lifecycle: Order Issued → In Progress → Completed, with Overdue flagged automatically by a daily batch after the deadline (current-year reports by 5th April; previous-year pending reports by 31st December).

- Inspector login: Assigned Inspection list with order copy, start-inspection action with start date/time logged; View Inspection list of completed offices.

- Commissioner / Nodal Officer dashboards: total offices assigned, completed, in progress, yet to start, overdue and average days to complete; roster status report with Year and Roster Date filters, pending days, report view and PDF / Excel download; office-level dashboard with Year, Office and Status filters and major issues for completed reports.

- Email and portal notifications at order dispatch, report completion and overdue alerts; Circular/Notification menu retained.

- Corrigendum process for signed reports and an audit log of every e-sign event.

## SOW-09: Masters & Data Preparation

- Inspection Officer master (from existing ICMIS / e-HRMS data), Office master, Office Head master and Designation master as confirmed by the Department.

- Master mapping for “Auto” fields and dependent drop-downs, for example the number of registered Urban Cooperative Banks in a district (Section H).

- Bulk creation of users from the Department’s User List template (First/Last name, Designation, Role, Reporting Officer, District).

# 5. Functionality List

| S.No. | Functionality | Reference | Category |
| --- | --- | --- | --- |
| 1 | Inspection Report tab in ICMIS Departmental Login | SOW-01 | Portal – Priority |
| 2 | Custom e-Sign (orders and reports) | SOW-02 | Security / e-Sign |
| 3 | ICMIS-style login page, Department option only | SOW-03 | UI / Login |
| 4 | Hierarchy-wise user listing (JR → DR → AR) with keyword search | SOW-04 | User Management |
| 5 | API integration with ICMIS for inspection reports | SOW-05 | Integration |
| 6 | Annual roster and inspection order management | SOW-06 | Workflow – Phase A |
| 7 | Nirikshan Prativedan form development | SOW-07 | Form – Phase C / D |
| 8 | Inspection workflow, status tracking and notifications | SOW-08 | Workflow – Phases B to D |
| 9 | Masters and user data preparation | SOW-09 | Masters / Data |

# 6. Role-wise Access Matrix

| Functionality | Commissioner (State Admin) | Nodal Officer | Nirikshankarta (Inspector) |
| --- | --- | --- | --- |
| Create annual roster; issue e-signed inspection order | Yes (OTP e-Sign) | – | – |
| View / download order; start inspection | – | View | Yes |
| Fill Nirikshan Prativedan; save draft; preview | – | – | Yes (assigned offices) |
| Final Submit and e-Sign report | – | – | Yes (OTP) |
| Dashboards, roster status report, PDF / Excel download | Yes (all) | Yes (division) | Own offices |
| Inspection Report tab in ICMIS Departmental Login | Yes (all) | Yes | Own reports |
| Overdue alerts and notifications | Yes | Yes | Yes |
| Hierarchy-wise user list and search | Yes | Yes | – |
| API push of signed report to ICMIS | System-triggered | System-triggered | System-triggered |

Note: Inspection eligibility follows the rule JR → JR/DR/AR offices, DR → DR/AR offices, AR → AR offices. No officer may be assigned his/her own office (Section 4, SOW-06).

# 7. Illustrative Report, Workflow & API Layout

The table below illustrates the Admin Report columns (downloadable in Excel and PDF) for the annual inspection roster:

| Sr. | Inspecting Officer Name & Designation | Allotted Divisional Office | Allotted District Office | Current Status | Pending Days |
| --- | --- | --- | --- | --- | --- |
| 1 | Sample Officer, Joint Commissioner | Sample Division Office | Sample District Office | Not Started / In Progress / Completed / Overdue | From order date |

Inspection status lifecycle used across the dashboards:

| Status | Trigger | Actor / Output |
| --- | --- | --- |
| Order Issued | Roster final submit and e-Sign | Commissioner; signed order PDF dispatched to inspectors |
| In Progress | Inspector clicks “Start Inspection” | Nirikshankarta; start date/time logged; drafts saved |
| Completed | Final Submit and OTP e-Sign of report | Nirikshankarta; signed report PDF; Commissioner / Nodal Officer notified |
| Overdue | Deadline passed and report not completed (daily batch) | System; red flag on dashboard; email alert |

Illustrative payload for sharing a signed inspection report with ICMIS:

| Parameter | Type | Description |
| --- | --- | --- |
| officer_id | String | Unique ID of the inspecting officer |
| officer_name | String | Name of the inspecting officer |
| designation | String | Designation from Designation Master |
| office_id | String | ID of the inspected office (Office Master) |
| user_id | String | Parakh/ICMIS user ID of the officer |
| report_pdf | Base64 / File | Signed inspection report in PDF format |
| (additional) | – | To be added after discussion with the ICMIS team |

Note: Field names, data types and authentication method are illustrative and will be finalized with the ICMIS integration team.

# 8. Methodology & Approach

The work builds on the Parakh inspection screens already available in UAT and the ICMIS portal, and is delivered in the following phases:

- Requirement Confirmation — confirm the requirement note, BSD, updated form and rules with the RCS IT Section (BRD update).

- Design — ICMIS-aligned UI design, role/eligibility model, workflow and status model, e-Sign flow and API contract.

- Development — login page, Inspection Report tab, user listing, roster and order management, Nirikshan form, workflow, e-Sign and ICMIS API.

- Testing — unit, integration and regression testing by MPSeDC, including API testing with the ICMIS team.

- UAT — deployment to the UAT environment for Department sign-off.

- Go-Live — deployment to Production after UAT sign-off.

# 9. Deliverables

- Inspection Report tab in the ICMIS Departmental Login.

- Custom e-Sign facility for inspection orders and reports.

- ICMIS-style login page with Department option only.

- Hierarchy-wise user listing (JR, DR, AR) with keyword search; Office Name in User Master.

- ICMIS integration API with payload documentation.

- Annual roster and inspection order management with signed order PDF and notifications.

- Nirikshan Prativedan form (tabs A to J) with auto-fill, auto-calculation, draft save, preview and signed report PDF.

- Inspection workflow with status tracking, dashboards, overdue alerts, Excel / PDF reports and corrigendum process.

- Masters and user data loaded; updated BRD; UAT support and Department sign-off; Production deployment / Go-Live.

# 10. Project Timeline

The work is estimated for completion in 42 working days from the date of approval and receipt of confirmed masters and API details, as shown below:

| Activity | Duration | Status / Target |
| --- | --- | --- |
| Requirement finalization & Design (BRD update) | 4 days | Day 1–4 from approval |
| Development (Login, Report tab, e-Sign, roster, form, workflow, API) | 24 days | Day 5–28 |
| Internal / Unit testing & API testing | 6 days | Day 29–34 |
| UAT deployment & Department UAT | 6 days | Day 35–40 |
| Production Go-Live | 2 days | Day 41–42 |
| Total | 42 days | Go-Live: Day 42 from approval |

# 11. Resource & Cost Estimate

This work is proposed to be billed on the man-day basis, at the rate of Rs. 12,000/- per man-day plus GST, consistent with the rate applied for earlier MPSeDC portal work. The man-day estimate below is indicative and subject to the Department’s approval; actual billing shall be based on man-days utilized.

| S.No. | Activity | Estimated Man-Days |
| --- | --- | --- |
| 1 | Requirement Analysis, BRD update & Design (BA) | 4 |
| 2 | Login page in ICMIS format (SOW-03) | 2 |
| 3 | Inspection Report tab, dashboard & filters (SOW-01) | 3 |
| 4 | Custom e-Sign facility (SOW-02) | 6 |
| 5 | Hierarchy-wise user listing, search & Office Name in User Master (SOW-04) | 2 |
| 6 | ICMIS API integration (SOW-05) | 5 |
| 7 | Annual roster & inspection order management (SOW-06) | 6 |
| 8 | Nirikshan Prativedan form development (SOW-07) | 14 |
| 9 | Inspection workflow, status tracking & notifications (SOW-08) | 6 |
| 10 | Masters & user data preparation (SOW-09) | 3 |
| 11 | Internal / Unit & API testing | 6 |
| 12 | UAT deployment & Department UAT support | 4 |
| 13 | Deployment & Go-Live support | 1 |
|  | Total | 62 |

| S.No. | Item | Amount (Rs.) |
| --- | --- | --- |
| 1 | Resource Cost (62 man-days × Rs. 12,000/-) | 7,44,000 |
| 2 | GST @ 18% | 1,33,920 |
|  | Grand Total (Estimated) | 8,77,920 |

Note: Figures above are an illustrative estimate for the Department’s evaluation and approval. Final invoicing will reflect actual man-days consumed.

# 12. Payment Terms

- Payment shall be raised on completion and successful Go-Live of the module in Production.

- Billing shall be computed on actual man-days utilized at the approved rate of Rs. 12,000/- per man-day, plus GST as applicable.

- Any scope beyond Section 4 (SOW-01 to SOW-09) shall be treated as a new requirement with its own man-day estimate.

# 13. Assumptions & Constraints

- The work will be built on the existing Parakh platform and ICMIS portal architecture, database and hosting infrastructure — no new infrastructure is required.

- The Department will confirm the Office, Office Head and Designation masters and provide the Inspection Officer master (ICMIS / e-HRMS data) before development of dependent items.

- The ICMIS, eHRM and CJCMS teams will provide API specifications, test environments and credentials; the MP State OTP Gateway will be made available for e-Sign.

- SOW-06 to SOW-09 are based on the BSD, the Department’s functionality sheet, UAT feedback and the updated form, and are subject to final confirmation in the updated BRD.

- The Department will provide timely review and UAT sign-off; any request beyond Section 4 will require a separate estimate.

# 14. Reference Documents

| Document | Reference No. / Date |
| --- | --- |
| Business Specification Document – Nirikshan Module | BSD v1.0, May 2026 |
| Approved final format of Nirikshan Form for MP Cooperative Society on Parakh | RCS IT Section email dated 30.07.2026 |
| Updated Inspection Format and Master Data (RCS Office Master) | RCS IT Section email dated 10.09.2026 |
| Updated Nirikshan Form and UAT change list | Nirikshan Formats dated 02.10.2026; “Before UAT” changes |
| Review and confirmation of masters for Inspection Module | MPSeDC email dated 09.09.2026 |
| RCS Computerization Meeting – Inspection Module status | RCS email dated 17.09.2026; meeting on 18.09.2026 |
| Department requirement note (Inspection Report, e-Sign, Login, User List, API) | MP Cooperative Requirements |
| Parakh UAT screens (Roster List, Assigned Inspection, View Inspection, Master, User List) | Screenshots shared by project team |
| Sample ICMIS UI designs for module development | ICMIS portal screenshots (4 images) |
| MoM of meeting on MP Cooperative changes | MPSeDC email dated 29.06.2026 (meeting 24.06.2026) |

# 15. Contact Persons

| From Office of the Registrar Cooperative Societies | From MPSeDC |
| --- | --- |
| IT Section, O/o Registrar Cooperative Societies, Madhya Pradesh Assistant Commissioner, O/o Registrar Cooperative Societies | Shri Ajeet Pal Singh, Technology Management Consultant Shri Divendra Kumar Ojha, Project Manager Ms. Priya Sharma, IT Consultant Shri Dheeraj Motiyani, Sr. Business Analyst Shri Aman Mishra, Developer Shri Manish Dadhore, Tester |