DISTRICT GIS PARAKH PROJECT STATUS REPORT (PSR) Reporting Period: 01-Jul-2026 to 31-Jul-2026 MPSEDC / MPSSDI — GIS Division

| Date | Version | Description | Prepared By | Approved By |
| --- | --- | --- | --- | --- |
| 01-Aug-2026 | 1.0 | Project Status Report — District GIS Parakh, July 2026 | Dheeraj Motiyani | Dr. Rakesh Dubey |

| Prepared By | Reviewed By | Approved By |
| --- | --- | --- |
| Dheeraj Motiyani Senior Business Analyst, MPSSDI/GIS | Ajeet Pal Singh Technology Management Consultant | Dr. Rakesh Dubey Head, MPSSDI |

| Project | Sponsor / Client | Platform | Report Prepared On |
| --- | --- | --- | --- |
| District GIS Parakh — GIS-Based Dynamic Forms Platform | MPSEDC / Government of Madhya Pradesh (District Collectorates & State Depts.) | UAT: gisuat.mp.gov.in/parakhweb ¦ PROD: geoportal.mp.gov.in/parakhweb | 01-Aug-2026 |

# 1. Executive Summary

During July 2026, the Parakh team logged 927.0 consumed hours across 142 tracked activities — the busiest month in the current cycle — spanning platform-level enhancements, the Indore Labour Inspection module go-live, the PM Poshan Social Audit rollout, and district onboarding across Betul, Chhindwara, Jabalpur, and the Mining and Mandir Nyas departments. Two sprints closed during the month: 'Parakh Customization for WorkFlow – Indore Collectorate' (through 22-Jul) and 'Parakh Customization for MPRRDA & Marketing Federation' (from 24-Jul). Four items reached Production during the month, and 73.2% of July's tracked tasks (104 of 142) were marked Completed by the close of the period.

## 1.1 Overall Project Health

| Dimension | Status | Comment |
| --- | --- | --- |
| Scope | AMBER | Healthy but expanding inflow of new district/department requests (Betul, Chhindwara, Jabalpur, Mining, MP Cooperative, plus a new ATR concept) — scope growth is outpacing formal re-baselining. |
| Schedule | GREEN | Both planned sprints closed on schedule; key go-lives (Indore Property Form, Chhindwara reports, Jabalpur form) delivered within the month as targeted. |
| Resources / Effort | GREEN | 927.0 hrs logged across 11 active resources with reasonably balanced load; no resource over-allocation flagged. |
| Quality / UAT | AMBER | 7 findings logged in the Labour Compliance & Prosecutions UAT (20–21 Jul); PM Poshan live but still in active bug-fixing/re-assign-flow stabilisation. |
| Risk | AMBER | A handful of dependency-driven blockers (Betul School Monitoring form, MP Cooperative BRD sign-off) — see Section 8, Risks & Issues. |

# 2. Key Metrics — July 2026

| Metric | July 2026 |
| --- | --- |
| Total consumed hours (all resources) | 927.0 hrs |
| Total tracked activities / tasks | 142 (104 Completed ¦ 38 WIP — 73.2% completion rate) |
| Districts / Departments actively worked on | 11 — Indore (Labour & Property), Betul, Chhindwara, Jabalpur, PM Poshan, Mining, Mandir Nyas, P&RD, Agar Malwa, MP Cooperative, Parakh Core |
| New / revised requests received via e-mail in July | 9 — Betul ×2, Property Survey Form ×3, Hostel Adoption (Indore), MP Cooperative, PM Poshan role change, Jabalpur Unused Building |
| Production go-lives during the month | 4 — see Section 5, Milestones |
| Sprints closed | 2 — see Section 3, Sprint Status |

# 3. Sprint Status

| Sprint | Duration | Tasks | Hours | Status |
| --- | --- | --- | --- | --- |
| Parakh Customization for WorkFlow – Indore Collectorate | 23-Jun to 22-Jul-2026 | 99 | 673.0 | GREEN |
| Parakh Customization for MPRRDA & Marketing Federation | 24-Jul to 23-Aug-2026 | 43 | 254.0 | GREEN |

Note: the first sprint spans 23-Jun to 22-Jul; hours/tasks above reflect only the July-dated portion of each sprint, consistent with this report's 01–31 Jul reporting window.

# 4. Effort Distribution

## 4.1 By Resource

| Resource | Consumed Hrs | Primary Focus Area (July) |
| --- | --- | --- |
| Jameel Khan | 176.0 | Property/Asset Survey mobile fixes, video compression, conditional 'Add More' questions, offline save, MPRRDA UI |
| Madhur Nema | 167.0 | Betul forms, Mining dept., PM Poshan report/re-assign, workflow engine, JWT encryption |
| Manisha Dadhore | 156.0 | JD/Treasury form corrections, Chhindwara & Betul QA, Jabalpur testing, web-module regression |
| Bharat Mishra | 136.0 | Workflow-mapping component/API, Mining reports, Mandir Nyas login, PM Poshan report, Active Forms API |
| Aman Mishra | 88.0 | Indore Labour establishment login/report/documents module build |
| Dheeraj Motiyani | 83.0 | Requirement gathering (Betul, Jabalpur, Chhindwara), PM Poshan training/workshop & field bug triage |
| Nilesh Gangrade | 64.0 | Labour Commissioner Organisation UI/UX overhaul (login, reports, documents popup) |
| Krati Pandey | 30.0 | Agar Malwa — vehicle detection, TFLite/PaddleOCR implementation |
| Neetu Malviya | 16.0 | Indore Property Survey Form update & rejection-flow testing |
| Arindam Kumar | 8.0 | PM Poshan production support (P&RD Department) |
| Rini Kanik | 3.0 | Labour Compliance & Prosecutions UAT |

## 4.2 By Module / District

| Module / District | Consumed Hrs | Status |
| --- | --- | --- |
| Parakh Enhancement (platform core) | 438.0 | Ongoing |
| Indore – Labour Inspection | 161.0 | Built & entering UAT/stabilisation |
| PM Poshan | 112.0 | Live — bug-fixing & re-assign flow |
| Chhindwara Collectorate | 52.0 | Forms & reports moved to Production |
| Betul Collectorate | 39.0 | WIP — 5 of 6 forms verified for go-live |
| Indore Collectorate – Property Inspection | 35.0 | Live — Non-Survey Property Form released |
| Agar Malwa | 25.0 | WIP — OCR/vehicle detection |
| Jabalpur Collectorate | 25.0 | Completed → Production (30-Jul) |
| Mining Department | 16.0 | Form & report deployed to UAT |
| Mandir Nyas | 8.0 | Login page delivered |
| P&RD Department | 8.0 | PM Poshan production support |
| Districts Reports – 1 | 5.0 | WIP — vehicle-plate detection R&D |
| MP Cooperative | 3.0 | Requirement stage — form change request received |

# 5. Milestones & Production Go-Lives

- 10-Jul: Indore Non-Survey Property Form & Patch Polygon integration released to Production (Android & iOS).

- 24-Jul: Indore Property Survey Form (revised per IMC Commissioner / Addl. Commissioner feedback) confirmed for Production go-live.

- 24–27-Jul: Chhindwara inspection forms and reports moved to Production.

- 29-Jul: Indore Labour establishment/document workflow stabilised in Production.

- 30-Jul: Jabalpur Unused Building Inspection Form released to Production, following the Total Building Area unit (Sq. Ft.) correction.

# 6. District / Department Rollout Status

| District / Module | Hrs (Jul) | RAG | Status This Period |
| --- | --- | --- | --- |
| Parakh Enhancement (platform) | 438.0 | GREEN | Multiple platform features closed: offline save (Phase 1), JWT encryption, workflow engine, 'Add More' conditional questions, Active Forms API. |
| Indore – Labour Inspection | 161.0 | AMBER | Built and entering UAT/stabilisation; 7 UAT findings logged (20–21 Jul) and being worked through. |
| PM Poshan | 112.0 | AMBER | Live in Production; active bug-fixing and role-reassignment (RO → Inspector) flow ongoing. |
| Chhindwara Collectorate | 52.0 | GREEN | Forms & reports moved to Production; report generation work continuing. |
| Betul Collectorate | 39.0 | AMBER | 5 of 6 forms verified for go-live; full rollout blocked pending the School Monitoring form's finalisation. |
| Indore – Property Inspection | 35.0 | GREEN | Live — Non-Survey Property Form released and revised per department feedback. |
| Agar Malwa | 25.0 | AMBER | WIP — OCR/vehicle-detection R&D; TFLite model integrated, PaddleOCR pipeline under test. |
| Jabalpur Collectorate | 25.0 | GREEN | Completed and released to Production (30-Jul). |
| Mining Department | 16.0 | AMBER | Form & report deployed to UAT; awaiting confirmation to proceed to Production. |
| Mandir Nyas | 8.0 | RED | Only the login page delivered this period against a larger statewide BRD scope (Temple & Temple Land Details Form) — schedule risk if not resourced further. |
| P&RD Department | 8.0 | GREEN | PM Poshan production support. |
| MP Cooperative | 3.0 | RED | Requirement stage — change request received; BRD sign-off pending department's final document structure. |

# 7. Scope & Requirement Register

Parakh's cumulative scope is tracked in the District GIS Parakh Consolidated User Story Register (v2.1, 30-Jun to 27-Aug 2026), currently at 177 user stories across 16 modules/districts — Betul, Damoh, Indore, Hostel-School-AWW, Health Facility, GIS Survey-Land, Rural Dev-MGNREGA, Govt Scheme-Welfare, Institutional Dept, Other District, PM Poshan, Asset Survey, CTA Treasury-JD, Workflow Management, Platform Enhancement, and Master Form Standardization.

Unlike Jal Rekha, Parakh does not yet maintain per-story logged actuals — the Register's hours are planning/sizing estimates (Complexity × role-based effort split, following the Jal Rekha estimation methodology), not billed time. Actual July effort is the Date-Wise Time Sheet data captured in Sections 2–4 above.

# 8. Risks & Issues Register

| # | Risk / Issue | District / Module | Impact | Mitigation / Next Step (Owner) |
| --- | --- | --- | --- | --- |
| 1 | Full 6-form Betul go-live is blocked pending the School Monitoring form's finalisation. | Betul | Schedule | Finalise & release the form — target 08-Aug (Madhur Nema / Manisha Dadhore). |
| 2 | MP Cooperative BRD sign-off pending the department's final document structure. | MP Cooperative | Schedule | Incorporate the department's approved Nirikshan form format — target 10-Aug (Aman Mishra). |
| 3 | Offline form-save is only Phase 1 complete — listing, edit and sync (Phase 2) remain outstanding. | Parakh Enhancement | Functional gap | Complete offline listing/edit/sync (Phase 2) — target 20-Aug (Jameel Khan). |
| 4 | PM Poshan role-reassignment requests (Reporting Officer → Inspector) need prompt turnaround to avoid field-level inspection delays. | PM Poshan | Operational | Track requests to closure — ongoing (Dheeraj Motiyani / Madhur Nema). |
| 5 | New Action Taken Report (ATR) + offline-inspection scope added mid-cycle (31-Jul) expands the platform roadmap. | Parakh Enhancement | Scope | Progress ATR design (table structure, action-history query) — target 15-Aug (Madhur Nema). |
| 6 | Indore Weekly Hostel Monitoring Form was requested (13-Jul) but not yet reflected in the July build. | Indore Collectorate | Schedule | Build the form — target 15-Aug (Dheeraj Motiyani / Manisha Dadhore). |
| 7 | Mandir Nyas has only a login page delivered against a much larger statewide BRD scope. | Mandir Nyas | Schedule | Progress full BRD scope (Temple & Temple Land Details Form) in subsequent months. |

# 9. Planned Activities — August 2026

| Action Item | Owner | District / Module | Target Date |
| --- | --- | --- | --- |
| Finalise and release the Betul School Monitoring form | Madhur Nema / Manisha Dadhore | Betul Collectorate | 08-Aug-2026 |
| Complete offline form-save listing, edit and sync workflow (Phase 2) | Jameel Khan | Parakh Enhancement | 20-Aug-2026 |
| Build the Indore Weekly Hostel Monitoring Form (Hostel Adoption Initiative) | Dheeraj Motiyani / Manisha Dadhore | Indore Collectorate | 15-Aug-2026 |
| Progress Betul Tribal Hostel Inspection Form — obtain Tribal Dept. login credentials | Dheeraj Motiyani | Betul Collectorate | 15-Aug-2026 |
| Incorporate MP Cooperative's approved Nirikshan form format into the module | Aman Mishra | MP Cooperative | 10-Aug-2026 |
| Complete JWT-based encryption rollout at web level and verify on test site | Madhur Nema | Parakh Enhancement | 05-Aug-2026 |
| Chhindwara — proceed to report generation and monitor for department feedback | Bharat Mishra / Dheeraj Motiyani | Chhindwara Collectorate | 07-Aug-2026 |
| Share Vehicle Detection (TFLite/OCR) build with department for field testing | Krati Pandey | Agar Malwa | 10-Aug-2026 |
| Progress ATR module design (table structure, action-history query) | Madhur Nema | Parakh Enhancement | 15-Aug-2026 |
| Track PM Poshan field issues and role-reassignment requests to closure | Dheeraj Motiyani / Madhur Nema | PM Poshan | Ongoing |

# 10. Sign-Off

| Prepared By | Reviewed By | Approved By |
| --- | --- | --- |
| Dheeraj Motiyani Senior Business Analyst, MPSSDI/GIS | Ajeet Pal Singh Technology Management Consultant | Dr. Rakesh Dubey Head, MPSSDI |

Next PSR: August 2026 — due first week of September 2026, aligned with the monthly Parakh project review chaired by K.V.S. Choudary (Managing Director, MPSEDC).

Data Sources: Date-Wise Team Time Sheet (01-Jul-2026 to 31-Jul-2026); District GIS Parakh — Monthly Project Review MoM, July 2026; District GIS Parakh Consolidated User Story Register v2.1; District-Level Initiatives (PSR) tracker.