## District Initiatives
S.No. | District/Department | Initiative | Status | More details | Last Status Update date | Action On | Request Received on (Letter / Verbal) | Lettes | Deployed on UAT/Prod | Changes request | District Level SPOC |  | Project Manager | Vertical | OIC | DeGM Name | DeGM Contact Number | Model
1 | Alirajpur | Hostel Survey (Parakh) | Completed | UAT Completed & Went Live (In use by Dept) |  |  | Letter | LetterFromCollector-Alirajpur.pdf |  | y | Virendra Singh Baghel (Joint Collector) | You are welcome! Let me know if you need anything else. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Vineet Vishwkarma | 6260437738 | Hostel Survey (Parakh) General inspection form आवेदन फॉर्म
2 | Chhindwara | Wash on wheel (Parakh) | Completed | UAT Completed & Went Live (In use by Dept) |  |  | Letter | LetterToOnboardParakh-Chindwara.pdf |  |  | Agrim (CEO Jila Panchayat) |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Atul Kumar Sharma | 7898452023 | Wash on wheel (Parakh)
3 | Chhindwara | School Survey (Parakh) | UAT Done - Dependency on Dept | UAT completed. Go Live |  |  | Letter | LetterToOnboardParakh-Chindwara.pdf |  |  | Agrim (CEO Jila Panchayat) |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Atul Kumar Sharma | 7898452023 | Request completion Form School servey Form
5 | Khargone | Inspection Mobile App on (Parakh) | The current collector of Khargone has changed. The new collector will decide whether this project will proceed or not, and if it does, how the work will be carried forward. | The current collector of Khargone has changed. The new collector will decide whether this project will proceed or not, and if it does, how the work will be carried forward. |  |  | Direction by MD / APD Sir | - |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Pramod Pawar | 8989854171
6 | Damoh | School & Hostel Survey (Parakha) | Completed | Go-live |  |  | Letter | Parakh Letter Damoh.pdf |  |  | No Name in Letter |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Mahesh Agrawal | 9893691611 | School & Hostel Survey (Parakha) School monitoring Form
7 | Burhanpur | Inspection Mobile App on (Parakh) | Completed |  |  |  | Letter | PARAKH Burhanpur.pdf |  |  | Bhavya Mittal (Collector) |  | GIS | Dr. Sandeep Goyal
8 | Zila Punchayat , Anuppur | Anuppur Works Management System (Mobile wire frames for WMS) | Work In Progress | Work In Progress |  |  | With COE | - |  |  | - |  | Dr.Rakesh Sir | GIS | Dr. Sandeep Goyal | Vikas Singh | 7697869606 | School & Hostel Survey (Parakha) School monitoring Form
9 | Tikamgarh , Collectorate | Inspection Mobile App on (Parakh) | Using tribal department form | UAT completed. Awaiting approval from the Collectorate to Go Live |  |  | Letter | parakh portal letter tikamgarh.pdf |  |  | Completed |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Pushpendra Tiwari | 7415360791 | Hostel Inspection Form
10 | Dindori , Collectorate | School Survey, Hostel, Anganbadi, PDS Center Extra Inspection App (Parakh) | Completed | UAT Completed & Went Live (In use by Dept) |  |  | Letter | Parakh App dindori.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Deepak Sahu | 9179173987 | Weekly Inspection Form Aaganwadi survey form स्वास्थ्य संस्थाओ का निरीक्षण फॉर्म
11 | Vidisha | Hostel Survey (Parakh) | Completed | UAT Completed & Went Live (In use by Dept) |  |  | Direction by MD / APD Sir | विदिशा जिले में स्_कूलों के निरीक्षण संबंधी APP उपलब्_ध कराने बाबत् तथा तकनीकी सहयोग.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | AMIT AGARWAL | 9893276222 | आकदमिक अवलोकन निरीक्षण फॉर्म
12 | Bhind | Drone Survey | Completed | UAT Completed & Went Live (In use by Dept) |  |  | Letter | Bhind E Khaniz Letter.pdf |  |  | - |  | Anoop Patel | GIS | Dr. Sandeep Goyal | Saurbabh Upadhyay | 9893310941 | छात्रावास निरीक्षण फॉर्म
13 | Chhatarpur Dist | Creation Google form , Login ID Password | they will preparing our form and sending it from the Tikamgarh department, but they have also requested Alirajgarh's Parhak credentials for review. | they will preparing our form and sending it from the Tikamgarh department, but they have also requested Alirajgarh's Parhak credentials for review. |  |  | Letter | Creation Google form for Chattarpur DIst login id 15 01 2025.pdf |  |  | Completed |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Tiwari | 9993551020 | Grocery Store Inspection General Inspection Hostel Inspection Form दुकानों के निरीक्षण की जानकारी फॉर्म
13 | Khandwa | Drone Urban Survey | Drone survey is in process. | Drone survey is in process. |  |  | Direction by ACS Sir | - |  |  | - |  | Anoop Patel | GIS | Dr. Sandeep Goyal | Anil Chandel | 7089189689/ 9926575646
14 | Rewa | Scanning of (Old Revenue / Naksha Record of Rewa (14399 Sheets) | Till now 6 sheets received from district and completed. Reamining sheets are awaited from district. | Work in Progress (Till Date 2793 sheets done) |  |  | Letter | Scanning Old Revenue Naksha of Land Records Rewa.pdf |  |  | - |  | Anoop Patel | GIS | Dr. Sandeep Goyal | Ashish Dubey | 9424468702
4 | Bhopal commissioner office | General Inspection on (Parakh) | Completed | Live |  |  | Letter | Comm. bpl letter for Parakh login.pdf |  |  | Alok (Consultant) MPSEDC |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Vikas Gupta | 7000180080/ 8305303857 | Site Inspection & servey form Hostel Servey Form
15 | Patan | Satellite data based maps for Urban Local Body boundary extension | Survey completed. Data Shared with Department | Survey completed. Data Shared with Department |  |  | Letter | Jabalpur Satellite data Urban Local Body boundary Letter From Dept.pdf |  |  | - |  | Anoop Patel | GIS | Dr. Sandeep Goyal | - | -
16 | Sidhi | Satellite data based maps for Urban Local Body boundary extension | Survey completed. Data Shared with Department | Survey completed. Data Shared with Department |  |  | Letter | Sidhi Satellite data Urban Local Body boundary.pdf |  |  | - |  | Anoop Patel | GIS | Dr. Sandeep Goyal | Manish Kumar Singh | 8120699041/ 7582074124
17 | Sagar | Satellite data based maps for Urban Local Body boundary extension | Survey completed. Data Shared with Department | Survey completed. Data Shared with Department |  |  | Letter | Bina ULB letter for satellte image.pdf |  |  | - |  | Anoop Patel | GIS | Dr. Sandeep Goyal | Rahul Sharma | 7987851221
18 | Narsinghpur | Satellite data based maps for Urban Local Body boundary extension | Survey completed. Data Shared with Department | Survey completed. Data Shared with Department |  |  | Letter | Narsinghpur Satellite data Urban Local Body boundary.pdf |  |  | - |  | Anoop Patel | GIS | Dr. Sandeep Goyal | Ms Kripa Singh | 9131374712
19 | Bhind | Hostel Survey (Parakh) | In Bhind District, the forms are being finalized. | Bhind Collectorate is onboarded. Development work completed. Awaiting list of Hostels from the Collectorate office, so to initiate UAT. |  |  | Letter | PARAKH Hostel Survey Bhind 15.01.2025.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Saurabh Upadhyay | 9893310941
20 | Chhatarpur Dist | Creation Google form , Login ID Password | Request received on 20-01-2025. Department onboarded. A meeting will be scheduled to discuss and finalize the details of the form creation | Live |  |  | Letter | Creation Google form for Chattarpur DIst login id 15 01 2025.pdf |  |  | Completed |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Tiwari | 9993551020
21 | Narmadapuram | Sarthak _Attendance / Parakh | Work In Progress | UAT Completed & Went Live (In use by Dept) |  |  | Letter | Letter to MD_MPSeDC_15_01_2025_Narmadapuram.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Sandeep Chaurasia | 9425966696
22 | Narmadapuram | Hostel Inpection , Adharcard Inpection , aganwadi Inpection, Goverment School Inpection |  |  |  |  | Letter | Inspection Form Letter_Narmadapuram.pdf
23 | Narmadapuram | Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म | Completed | The form has arrived, UAT has been sent, and testing has started. |  |  | Letter | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Sandeep | 9425966696 | Aadhar Inspection Form शाला निरीक्षण प्रपत्र aanganwadi Center Inspection छात्रावास निरीक्षण फॉर्म
24 | rajgarh | छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey | Completed | The form has arrived, UAT has been sent, and testing has started. |  |  | Letter | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal |  |  | छात्रावास निरीक्षण फॉर्म Test Gun Licence survey-InActive Gun Licence Survey
25 | seoni | छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म | Completed |  |  |  | Letter | [5 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Shivhare | 9302469983 | छात्रावास निरीक्षण फॉर्म छात्रावास भोजन गुणवत्ता फॉर्म
#REF! | Saps | LKS Inspection Form | Completed | Go-live | [11 empty] | Rahul tiwari | 9893404034 | LKS Inspection Form
#REF! | Tribale department | जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र | Completed | Work complete |  |  |  | Hostel Survey (Parakha) | [9 empty] | जूनियर छात्रावास /आश्रम निरीक्षण हेतु प्रपत्र
#REF! | SAPS | lnspection Module (Parakh App) | Completed | UAT Completed & Went Live (In use by Dept) |  |  | Letter | SAPS Letter from Dept to MPSEDC_Parakh Inspection.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Nitin Tiwari | 8894278707
#REF! | Satna District | Parakh _Survey Form Adhar Kendra Inspection/Data Collection | Work In Progress | Work completed. Issued for UAT on 13/02/25 |  |  | Letter | Parakh_Portal_Suggestions_District Satna.pdf Collector E governence District Satna.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Yogesh Tiwari | 8085144449
#REF! | Seoni District | Parakh _Survey Form ST/SC hostel | Completed | UAT Completed & Went Live (In use by Dept) |  |  | Letter | Prakhar letter Seoni District.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Shivhare | 9302469983
#REF! | कार्यालय कलेक्टर भोपाल म.प्र | Parakh _App_Hostel Survey | Work In Progress | Work In Progress_ Hostel Survey on Parakh App |  |  | Letter | कार्यालय कलेक्टर भोपाल म.प्र.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | VIKAS GUPTA | 8305303857
#REF! | कार्यालय कलेक्टर (अनुसूचित जाति एवं जनजातीय कार्य विभाग ) भोपाल | Parakh _App_Hostel Survey | Work In Progress | Work In Progress_ Hostel Survey on Parakh App |  |  | Letter | अनुसूचित जाति एवं जनजातीय कार्य विभाग_Hostel Survey.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | VIKAS GUPTA | 8305303857
#REF! | कार्यालय कलेक्टर (पिछड़ा वर्ग तथा अल्पसंख्यक कल्याण ) भोपाल | Parakh _App_Hostel Survey | Work In Progress | Work In Progress_ Hostel Survey on Parakh App |  |  | Letter | पिछड़ा वर्ग तथा अल्पसंख्यक कल्याण_Hostel Survey.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | VIKAS GUPTA | 8305303857
#REF! | Ashoknagar Distrct | Sarthak App_Attendance Marking | Work In Progress | Work In Progress_ Sarthak App_Attendance Marking |  |  | Letter | Sarthak _Attendance Marking_Dist_AshokNagar.pdf |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
#REF! | Rajgarh | lnspection Module (Parakh App) | Completed | UAT Completed & Went Live (In use by Dept) |  |  | Letter |  |  |  | - |  | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
#REF! | PNRD RES | MP MLA CM A CM A+ & Ghoshna Form | [10 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Veertika
#REF! | Jabalpur | Hospital Inspection form | [10 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Sandeep Chaurasia
#REF! | Jabalpur | Grameen Vikas Panchyat Grading live | Completed | UAT Completed and went live | [8 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Sandeep Chaurasia
#REF! | Chhattarpur | Grocery, Hostel , & General Inspection form | [10 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
#REF! | MGNREGA Dynamic Form Creation | lnspection Module (Parakh App) |  | Dynamic Form - Meeting Video Link Meeting Recording Notes | [8 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Kratika Avi sir
#REF! | Bhopal - UADD Department SQM Inspection Form | lnspection Module (Parakh App) |  | Form in UAT. But no call back from the department. Waiting for their confirmation. | [8 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Uday Dharmendra sir
#REF! | Narmadapuram | Health Inspection Form | Completed | [9 empty] | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
#REF! | Vidisha | Hostel Inspection Form | Completed
#REF! | Vidisha | NRC Inspection Form, Primary middle school Inspection Form | Completed
46 | Vidisha | Pharmacist Medical Drug store form, Anganwadi inspection form |  | Need Clarifications form department on few questions |  | District Collectorate |  | Letter Not received
47 | Bhind | Mgnrega work related inspection form | Completed | Completed |  |  |  | Bhind MGNREGA Work Inspection Form
48 | Mandla | PM School, Awas and AAdhar center | Completed | Form and report Deployed | 27/02/2026 | Distrcit collectorate - GIS executive - Ankita Soni 1) to clarify on pm poshan form to incorporate same like mgnrega one 2) one change in 1 question - 270 sq ft related |  | Mandla Mandla PM school PM awas and Aadhar center Inspection forms & Collector letter
49 | Sehore | School Inspection FOrm | Completed | Implemented in UAT. Email sent to District collectorate & GIS executive |  | District Collectorate |  | Sehore School Form
50 | Ayush Department |  |  | Departement onboarded on uat. department to share survey form |  | Subhee Nema |  | Ayush Department Letter
51 | Guna | Anganwadi | Completed | Form created in Uat, Email sent to District collectorate & GIS executive, confirmation required from the District Collectorate & GIS executive |  | Manisha |  | Guna Angawadi letter | done |  | Changes done need UAT confirmation
52 | Health Department | 1. DISTRICT / CIVIL / SUPER SPECIALITY HOSPITAL (जिला / सिविल / सुपर स्पेशियलिटी अस्पताल) 2. COMMUNITY HEALTH CENTRE (सामुदायिक स्वास्थ्य केंद्र (सीएचसी) 3. SUB HEALTH CENTRE (उप स्वास्थ्य केंद्र (एसएचसी) 4. PRIMARY HEALTH CENTRE (प्राथमिक स्वास्थ्य केंद्र (पीएचसी) | Completed | Implemented in prod . chase department for progress |  | Ajeet |  | Depart of Health Letter
53 | School Education Department | form is live but awaiting for autopopulation |  | Implemented in prod . chase department for autopopulation of School list |  | Madhur/ Dheeraj and Altamsah |  |  |  | Changes done on UAT and email sent
54 | Labour Department | Intergration with CIS system for user onboarding , establishment, and form to establishment mapping | Completed | Completed |  | Madhur
55 | MGNREGA PM Poshan Department | This form comes Under Sate coordinator PM Poshan Department Social Audit of schools Scheme | Completed | Deployed to Prod |  | Department |  | PM Poshan Letter
56 | PNRD NRM PMKSY | Inspection on Watershed projects ( project name and related work cost ) |  | Implemented in UAT. Email sent to department, |  | Department
57 | MP Cooperative |  |  | 1) Department Creating the structure of complete document 2) Updating sections and subsections into the format |  | Department Souresh Kulshetra |  | Letter not received
58 | Agar Malwa | Narcotics Drug Form | Completed | Deployed to Prod, email need to be sent | 17/01/2026 | Development team/ Dheeraj |  | Letter for Narcotics drug form | Prod
59 | MPHIDB | Inspection Form | WIP | Form created on UAT |  | Ajeet
60 | Chhindwara | Feedback form | Completed | deployed to Prod , email sent | 17/01/2026 | Manisha |  | Letter - Chhindwara Feedback form | Prod
61 | Ashoknagar Distrct | Hostel Inspection |  | adopted tribal department form |  |  |  | Ashoknagar Letter
62 | Gwalior | School, Hostel, Anganwadi, Health Center | Completed | form/report created and deployed,email sent | 27/01/2026 | Waiting for mail confirmation |  | Gwalior Letter
63 | Gwalior | Aadhar account verification form | Completed | form/report created and deployed,email sent | 17/01/2026 | Waiting for mail confirmation
64 | Burhanpur | Health Inspection form ,निरीक्षण प्रतिवेदन,गोदाम निरीक्षण | Work In Progress | form is live,report is created | 27/01/2026 | Department | Letter | Burhanpur letter |  |  | Mukul
65 | Mandla (On Hold) | मनरेगा (MGNREGA) योजनांतगत नमाण काय के नर ण | Dependency on Dept | Mandla district specific Department is not clear on requirement as conveyed by Ankita | 23/01/2026 | Ankita Soni GIS Executive | Letter | mandla letter |  |  | Ankita Soni
66 | Bhind | 75 वर्ष या उससे अधिक आयुके बिना सन्त लाभार्थियो हेतु मासिक सुविधा मॉनिटरिंग करने के लिए | Completed | form and report is deployed on production, | 2026-02-02 | Sakshi | Letter | Bhind letter
67 | PNRD-MGNREGA | SNA Sparsh अंतर्गत प्रशासकीय मद के भुगतान की जानकारी | Completed | Form is live | 30/01/2026 | Dheeraj,Aman
68 | Rajgarh | School Inspection Form | Work In Progress | Form is created, awaiting for confirmation | 2026-10-01 |  | Letter | Rajgarh Letter
69 | Ashoknagar Distrct | Aganwadi | Completed | Form is live,report is created | 17/03/2026 | Madhur and arindham | Letter | Ashoknagar Letter
70 | Chhindwara | Adhar inspection | Completed | Form is live,report is created,email sent confirmed | 25/02/2025 |  | Letter | Chhindwara
71 | Ujjain Mela | Ujjain Mela | Completed | Form is created and live | 14/02/2026 |  | Letter | Ujjain
72 | Bhopal commissioner office | Hostel Inspection Form(SC/ST category) | Work In Progress | form is same as tribal department. Bhopal Commissioner Office has raised request for creation of the Tribal Inspection Form. This form is same as of the Tribal Hostel Inspection Forms launched by the Tribal Department. The Tribal Dept (Adarsh & Shubham) is aligned with the specific need of the Commissioner Office and the access is granted for the officials to fetch/conduct the Tribal Department's launched forms. | 2026-11-03 |  | Letter | Bhopal Letter | UAT, but alinged with Adarsh / Tribal Dept
73 | PNRD-SRLM | Baseline Survey Form | Completed | Form is live,report is created,email sent and waiting for department confirmation | 23/03/2026 | Department | Letter | SRLM |  | CR-01: Department wants to update SRLM form with other new questions .....
74 | Ujjain | सरकारी स्कूल में शौचालय | Work In Progress | Form is still not finalized from CEO ZP | 13/03/2026 | Sakshi / ON Hold | Letter | Ujjain Letter | Waiting from District Collectorate CEO ZP ( Not finalized - On hold)
75 | Indore | Sugamya Abhiyaan | Completed | Form is created and live on production, report is created | 15/04/2026
76 | Directorate Public Instructions | Hostel Inspection form |  | Form is live,report is created |  | Madhur
77 | Religious and Trust Endowment | Temple and Temple Land Details Form | Work In Progress | Form is created on UAT |  | Bharat/Aman
78 | Bhopal - Food Department | Kharidi Kendra |  | Form received from bhopal collectorate |  | Sakshi / Madhur
79 | Indore Collectorate | Property Inspection | WIP | Form created and Tested | 18/05/2026
80 | Rajgarh Collectorate | Hand-Pump Inspection form | Completed | Form Created & live | 2026-10-06 |  |  |  | Remove Video Functionality
81 | Guna & Gwalior | Patient Feedback Form | Completed | HTML Form and QR Code Created | 02/06//2026
82 | Betul | 6 forms - KGBV , PMPoshan, WCD Anganwadi, School Monitoring, Health form , Mining Form, AAdhar Center form, Tribal Hostel form | Work In Progress | 1) KGBV Form: Verified and approved by the DEO. 2) PM Poshan (PNRD) Form: Department Form verification is completed. Nodal assignment is pending. 3) WCD Form: Currently with the developer team, as modifications are required in Questions 16 and 17. 4) School Monitoring Patra Form: Discussion has been held with the concerned departments. It has been decided to proceed with a single form format for now. If a separate form is required in the future, the department will provide an official request. 5) Health Form: Development and deployment completed; the form is live. 6) Mining Form: Discussion with the department has been completed. Questions and master data have been formatted accordingly and shared. The form is currently awaiting an update from the developer team. 7) Aadhaar Centre Form: Email has already been shared. Awaiting confirmation/update. 8) Tribal Inspection Form: Awaiting login credentials for the Betul Collectorate Tribal Department. | 30/06/2026 | Pending items: 1) WCD form update from the developer team. 2) Update on the Mining form from the developer team. 3) Confirmation/update on the Aadhaar Centre form. 4) login credentials for the Betul Collectorate Tribal Department. AAdhar form taken at the state level - Common form for all districts | 1st Letter Parakh Mining E-Governance letter | 2nd Letter परख एप्_लीकेशन फॉर्मेट
83 | CTA | JD Inspection form and Treasury Inspection form | WIP | Form Created | 20-07-2026 | Pending from CTA Department
84 | Chhindwara | 5 forms - Anganwadi, PMPoshan, Godown, Hostel Monitoring, Health Form, | WIP | Forms are created and Live in Production. Report work is going on | 23-07-2026 | Pending from Chhindwara Collectorate Department & Development team for Report | Letter | Chhindwara Letter for 6 Forms
85 | Jabalpur | Building Inspection Form | WIP | Forms are created and Testing needs to be done | 22-07-2026 | Pending from Jabalpur Collectorate Department | Letter | Unused Building
86 | MPRRD | Road Inspection Form | WIP | In UAT | 22-07-2026 | Dev Team
87 | Mining Department | Mining Inspection Form | Completed | Forms created and Live in Production | 21-07-2026
88 / 57a | MP Cooperative (Changes) | Inspection Form | WIP | 1) Department Recreating the structure of complete document 2) Updating sections and subsections into the format 3) Revamping Inspection and including Rooster of Nirikshan karta Summary Change request document and BRD docuement shared with Deaprtment | 17-07-2026 | Department ICMIS - Devendra, Priya and Jyoti Ma'am. They have to review CRs and BRD dcoument
89 | Indore Inspection forms | Indore 17 forms Departments Finalized forms - | WIP | 1) Phase 1 developed 2) Phase 2 Action taken and Divisional level work under progress | 03-08-2026 & 24-08-2026 | Department to finalize 17 forms Mail sent to dept to check user manuals on 24-08-2026
90 | Rajgarh | OBC Tribal Hostel form | WIP | Form created in UAT. Move to Prod | 17-08-2026 | Department to verify
91 | Damoh | Karyalay Zila Panchayat Form - BBRAMJI, PMAY, 15th Finance Gram Nal Jal Praday Yojana Inspection Form School/Institute Inspection Form Anganwadi Inspection Form Jan Vishwas Abhiyaan - Health Department Govt. Uchit Mulya Ki Dukan Inspection Form Petrol Pump Inspection Form LPG Dealer Inspection Form CM Jan Vishwas Abhiyaan - Farm and Dairy Department Inspection Form Liquor Department Inspection Form Hostel/Ashram Inspection Form Krishi Saakh and Sahkari Samiti Inspection Form | WIP | ZIla Panchayat form created and live in Prod | 14-08-2026 23-08-2026 31 August 2026 | Department sharing master data of other forms and parallely checking if any CR required from department end. Department uploading Asset data (Bulk Upload) Finalized all 12 forms on - ( 23-08-2026) Creating Reports - (31st Aug 2026)
92 | Guna | Ayush Department & Asset Mapping | WIP | Form needs to be created | 2026-12-08 | Team
93 | MP Metro | Plantation Form | WIP | Form Created. First time survey needs to be done by department to collect data & onboard. | 13-08-2026 - 24-08-2026 | Team Madhur Manisha Neetu & Department to verify 24-08-206 Demo - suggested changes -
94 / 83a | CTA - CRs Updates from Department | JD Inspection form and Treasury Inspection form | WIP | Form Created & Updated Changes by Manisha | 13-08-2026 | Pending from CTA Department
95 | Bhind | Patient Feedback form OPD/IPD Patient Satisfaction Survey Forms | WIP | Form copied from Guna form format and new questions to be added for Bhind requirement. QR Code based functionality . Form created. | 17-08-2026 | Department confirmed and Move to Production
96 | Dhar ( Shared by Indore Nidhi) | Jan Vishwas forms like Damoh | WIP | Unformatted Forms recieved from Deaprtment | 17-08-2026 | Word Doc to be provided by Department
97 | Sagar | Jan Vishwas forms like Damoh Regular Physical Inspection under Administrative Control Regular physical inspection of the following government assets coming under administrative control: Government buildings, Schools, Anganwadi centres, Hospitals, Hostels, Drinking water schemes, Structures under construction / already constructed , Inspection Parameters For each building/structure, the inspection should cover: Current status of the building/structure, Availability and condition of: Drinking water facilities, Toilets, Electricity supply, Other basic amenities Action Taken Report (ATR) on Committee Recommendations ATR on the recommendations/observations of the inspection committees, Status of grievance redressal, Name of the responsible department for implementation and follow-up | WIP | Forms same like Damoh CM Jan Vishwas Abhiyaan & ATR on it | 24-08-2026 | Forms not shared from Department
98 | Chhindwara | Gas Godown Inspection Form Fair Price Shop (FPS) Inspection Form | WIP |  | 20-08-2026 | Department to sent word doc & format pdfs with updated questions
99 | Gwalior | Rainwater harvesting structures inspection form. - General Departmental Form. |  |  | 20-08-2026 | Ankita from Gwalior Collectorate Department
100 | CM Jan vishwas | 13 forms release at state level - Master data under District GIS department on Parakh - Generic form at state level | WIP | 18 and 21 ko forms release | 25-08-2026 | Team
101 | Health Department | Total 2 forms - Drug Store Forms - Estimate and Assessemnt 2 forms | WIP | Forms created over UAT | 24-08-2026 | Manisha and Department to verify
Prepare Estimate taking 2 scenarios - CM Jan Vishwas and PM Poshan

## Parakh internal work
S. No | Parakh version | Work/enhancement | Updations | Contact person | Initiate Date | Target Date | Status | Current Status | Priority Level
1 | apk111 | SSO implementation SSO LDAP & Dashboard | Multiple login Issue | Aman |  | 23/12/2025 | done |  | Critical
2 |  | Asset mapping |  | Madhur | 18/12/2025 |  |  |  | medium
3 |  | population of dropdowns via api |  | Jameel | 18/12/2025 |  |  |  | high
4 |  | Auto population - Dynamic way- fields |  | Arindam
5 |  | Parakh mobile app registration approval by adding: with designation |  | Jameel |  |  |  |  | crictical
6 |  | Sync offline
7 |  | Satellite Map on forms and mark pointer |  | Jameel |  |  |  |  | Critical
8 |  | Samagra data bug email |  | Madhur
9 |  | remove inline query |  | madhur |  |  | done
10 |  | scan Parakh api and web on sonar qube |  | madhur |  |  | done
11 |  | coaliation of District admin access |  | Arindham |  |  |  |  | Critical
12 |  | Reports to be made dynamic & link with Dashboard |  | Aman
13 |  | Super admin can Reset Password to Default | [6 empty] | high
14 |  | Change Manrega name to MGNREGA |  | Madhur |  |  | done |  | medium
15 |  | Narsinghpur request - give feature to download blank form ( currently we have to take screenshots of all pages)
16 |  | ATR Report for Tribal
17 |  | Parakh Sprint Creation
Template for frequent forms ( provide facility to download them through Notifications
19 |  | Dynamic Reports Phase 1 |  | Madhur |  |  | Done
20 |  | Please update - example :- At Nodal login level - Collector got changed to new Collector then those credential changes are automatically changing at those places as well where - "old collector has done inspection under his name previously". |  | Madhur
21 |  | 2FA |  | Madhur | 24-08-2026 |  | Done

## MeiTY District
S. No | District | Initiative | Request Received on (Letter / Verbal) | Lettes | District Level SPOC | Current Status | Project Manager | Vertical | OIC | DeGM Name | DeGM Contact Number
1 | Harda | Inspection_Parakh | - | single window 2-1 Harda Parakh.pdf | - | Work in Progress | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
2 | Seoni District | Parakh _Survey Form ST/SC hostel | Letter | Prakhar letter Seoni District.pdf | - | UAT is In-Progress for 1st Inspection form. Development for 2nd Form is in progress. Target 17/02/2025 | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal | Rahul Shivhare | 9302469983
3 | Rajgarh District | Hostel Inspection (Parakh) | Letter | Rajgarh District Hostel Inspection Letter.pdf | - | UAT In-Progress. Work completed on 05-02-2025. | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
4 | Ujjain | उज्जैनी विक्रन, व्यापार मेला 2025 हेतु Geo-tracking software _ Parakh | Letter | उज्जैनी विक्रन, व्यापार मेला 2025 हेतु Geo-tracking software बनाये जाने के संबध मे।.pdf | - | Work in Progress | Ajeet Pal Singh | GIS | Dr. Sandeep Goyal
5 | Seoni District | जिला सिवनी ड्रोन सर्वे कराये जाने के संबंध | Letter | Collector Seoni letter for Drone Survey.pdf |  | Work Done, Data Submited to Department, Also Data Upload in District GIS Portal | Anoop Patel | GIS | Dr. Sandeep Goyal