## Sheet1
Date Wise Time Sheet
Time Sheet entry Date From : 01/08/2026 To 31/08/2026 Current Date & Time : September 17, 2026 at 02:55:24 PM
Sr.No | Resource Name | Resource_Location | Project Name | Sprint Name | Sprint Start Date ¦ End date | Module Name | Activity Name | Task Assign Date | TimeSheet Entry date | Task Name | Assign Hours | Consumed Hrs | Work Status By Resource | Work Status By PM | Action Performed by Resource
1 | ABHINAV SRIVASTAVA | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Asset Mapping | Bug Fixing from Frontend | 10/08/2026 | 10/08/2026 | Adding Length and Direction button to the bottom bar of buffer and layers in MPPHE Angular webportal | 16.00 | 4.00 | WIP | Yet To Update | Adding Length and Direction button to the bottom bar of buffer and layers in MPPHE Angular webportal
2 | ABHINAV SRIVASTAVA | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Asset Mapping | Bug Fixing from Frontend | 10/08/2026 | 11/08/2026 | Adding Length and Direction button to the bottom bar of buffer and layers in MPPHE Angular webportal | 16.00 | 8.00 | Completed | Yet To Update | Adding Length and Direction button to the bottom bar of buffer and layers in MPPHE Angular webportal
3 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Database functions Updation & API Web and Mobile Services | 03/08/2026 | 03/08/2026 | Upgrade target sdk and it's related changes for play console | 8.00 | 8.00 | Completed | Yet To Update | target sdk changes
4 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Loop Functionality | 04/08/2026 | 04/08/2026 | Material Loop bug fixing | 8.00 | 8.00 | Completed | Yet To Update | Bug fixing
5 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Daily Inspection | Production deployment | 20/08/2026 | 20/08/2026 | Image and video permission changes to fix play store warning | 8.00 | 8.00 | Completed | Yet To Update | InProgress
6 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sahbhagita GM | Bug Fixing from Frontend | 24/08/2026 | 24/08/2026 | Google play store compliance issue | 16.00 | 8.00 | WIP | Yet To Update | fix google play compliance issue
7 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sahbhagita GM | Bug Fixing from Frontend | 24/08/2026 | 25/08/2026 | Google play store compliance issue | 16.00 | 8.00 | Completed | Yet To Update | Bug fix, testing and new build deployment
8 | Anand Gour | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara | UI update in existing page | 31/08/2026 | 31/08/2026 | Select image from gallery Dhara issue | 8.00 | 8.00 | Completed | Yet To Update | Bug fix
9 | AWINASH KHARE | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 07/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase (Review) | 3.00 | 3.00 | WIP | Yet To Update | Review of Water Supply & During Construction Review
10 | AWINASH KHARE | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 10/08/2026 | 10/08/2026 | O&M Billing Reset & Meter Reading Approval Tickets Resolution (10-Aug-2026) | 8.00 | 8.00 | Completed | Yet To Update | Scheme_id=95 (Mohanpura) ki meter readings ko teeno tables (Intake, WTP EMF, Village EMF) mein unlock kiya April-May 2026 range ke liye, aur O&M billing side pe scheme ko draft state mein reset kiya. GET_OM_FY_WINDOW function mein scheme_id=109 ke stale orphan row ka bug fix kiya. Multiple MPJN tickets (0028, 0033, 0034, OHT-067-28) ke through GM-approved meter readings unlock/unfreeze ki alag-alag schemes aur months ke liye. April-June 2026 ke Dhara meter readings lock karne ke liye ek official circular draft ki, jo 10-August midnight se effective hui. Get_MeterReading_ApprovalStatus function mein OHT/Village approval columns ke '-' dikhne wale issue ka debugging shuru ki (MIN vs MAX permitted_from logic).
11 | AWINASH KHARE | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 11/08/2026 | Dhara & O&M — Meter Status Logic Fix, User Access Correction & SQC Damoh Production Issues (11-Aug-2026) | 8.00 | 7.00 | Completed | Yet To Update | Fixed the meter_status_id based logic (Functional/Replaced/Not Functional/No Water Supply) for start_reading, end_reading, and total_raw_water_drawn carry-forward/auto-calculation in the Dhara Intake meter reading module. Updated CASE WHEN conditions in both Ins_Up_Intake_meter_reading_daily (INSERT/UPDATE) and Get_Intake_reading_dailyForSurveyWeb (display) functions. Also completed the Apr-Jun backfill/re-approval for scheme_id=95, corrected GM-SQC TL scheme mapping, and resolved SQC SMEC Damoh production access issues (has_dhara_access flag).
12 | AWINASH KHARE | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 20/08/2026 | 31/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase (Review 3) | 3.00 | 3.00 | Completed | Yet To Update | Its Done
13 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 04/08/2026 | Cycle 5 documentation of July and June | 10.00 | 2.00 | WIP | Yet To Update | Documented CR , MOM and PSR - June July
14 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 05/08/2026 | 04/08/2026 | Changes for Meter Reading MF, MNF and NWS documented | 5.00 | 2.00 | WIP | Yet To Update | Changes taken from department. Discussed and understood analysed the Meter reading logics
15 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 04/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 2.00 | WIP | Yet To Update | Nirmal SVS requirement gathered and discussed with internal team and PM.
16 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS dashboard Creation | 04/08/2026 | 05/08/2026 | Mock Up created for Dashboard and updated features suggested by Department | 4.00 | 4.00 | WIP | Yet To Update | SVS Dashboard mock up created and suggested changes to the development team
17 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 05/08/2026 | 06/08/2026 | Changes for Meter Reading MF, MNF and NWS documented | 5.00 | 2.00 | WIP | Yet To Update | connected with OIC rakesh sir for dhara meter reading chnages and fixes
18 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS dashboard Creation | 06/08/2026 | 06/08/2026 | review with Tejas for SVS dashboard | 3.00 | 3.00 | Completed | Yet To Update | review svs dashboard chnages with tejas
19 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 07/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase | 10.00 | 3.00 | WIP | Yet To Update | Workflow meeting and further work requirement gathering meeting with Kapil department jal nigam
20 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 07/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 3.00 | WIP | Yet To Update | Nirmal SVS water quality checks and FTK kit requirement analysis and finalizing acceptable and rejectable range & criteria with stakeholders department and internal team and PM
21 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 10/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase | 10.00 | 3.00 | WIP | Yet To Update | SQC Edit and GM Edit functionality needs to be provided as suggested by department jal nigam
22 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 11/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 2.00 | WIP | Yet To Update | Requirement gathered - Dhara Meter reading MF MNF M Replaceable FE entry only when meter functional and entries are not approved. GM approves entries and are final. Then start and end reading will not change
23 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 11/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 3.00 | WIP | Yet To Update | Team implementing Nirmal range of FTK kit water quality of village water supply
24 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 12/08/2026 | Cycle 5 documentation of July and June | 10.00 | 2.50 | WIP | Yet To Update | Attended and presented CMMI cycle 4 review points with Satyarth Tapan and ranjana in the meeting
25 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 13/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase | 10.00 | 2.00 | WIP | Yet To Update | O&M SQC Edit further functionlity on --- different pages payment, residual, complaint, facilties, final net and abtract payment page
26 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 14/08/2026 | Cycle 5 documentation of July and June | 10.00 | 2.00 | WIP | Yet To Update | Reviewed and discussed changes with team and satyarth for documents
27 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 14/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 3.00 | WIP | Yet To Update | Updating Wireframe with new requirements and changes in the previous screens developed -MVS contractor, Gram sachiv and CEO Block
28 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 17/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 3.00 | WIP | Yet To Update | Updated requirement and wireframe and connected with tteam folr overview of nirmal SVS
29 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 18/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 2.00 | WIP | Yet To Update | Documented these requirements and team implemented.
30 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 18/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 4.00 | WIP | Yet To Update | Added details
31 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 19/08/2026 | Cycle 5 documentation of July and June | 10.00 | 2.00 | WIP | Yet To Update | document review and cycle 5 started june july and august docs
32 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 19/08/2026 | Requirement gathering and creating wireframe and collecting master data | 16.00 | 2.00 | Completed | Yet To Update | implemented nirmal fit functionlaity
33 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 20/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 3.00 | WIP | Yet To Update | Meter reading survey intake wtp oht and bulk web and mobile view
34 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | Cycle 4 Documentation from Jan to June 2026 | 12/08/2026 | 21/08/2026 | CMMI review meeting for Cycle 4 data - https://docs.google.com/spreadsheets/d/1I5mSYQsKy9NE_Bpvi1KwrNQY7fstHskR1z57EtfsjnU/edit?gid=0#gid=0 | 4.00 | 4.00 | Completed | Yet To Update | Updated cycle 5 cmmi docs in jal rekha and parakh
35 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Project Module Initiation Meeting and Requirement gathering | 14/08/2026 | 21/08/2026 | SVS module like Vistrit module of dhara for MVS villages Requirement understanding & analysis | 4.00 | 4.00 | Completed | Yet To Update | Nirmal SVS details and reports FTK Kit finalized and shared
36 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | CMMI Cycle 5 Documentation from June till end | 06/08/2026 | 25/08/2026 | Cycle 5 documentation of July and June | 10.00 | 1.50 | Completed | Yet To Update | updated docs for augist month as well
37 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 24/08/2026 | 25/08/2026 | Water supply during construction phase requirement gathered | 8.00 | 3.50 | WIP | Yet To Update | Meeting with MD sir for reviewing details
38 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Parinam Enhancements | Parinam Dashboard | 20/08/2026 | 26/08/2026 | Requirement gathered for Parinam dashboard | 4.00 | 3.00 | WIP | Yet To Update | Dashboard updates
39 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 11/08/2026 | 27/08/2026 | Regquirement gathering and documentation of Meter functional non functional & replaceable scenario lgoics updation | 14.00 | 3.00 | WIP | Yet To Update | Alignment of Dhara meter for all roles
40 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 27/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase | 10.00 | 2.00 | WIP | Yet To Update | WSDCP steps to wireframe and updates in flow
41 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 05/08/2026 | 28/08/2026 | Changes for Meter Reading MF, MNF and NWS documented | 5.00 | 1.00 | Completed | Yet To Update | updated the tasks
42 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Parinam Enhancements | Parinam Dashboard | 20/08/2026 | 28/08/2026 | Requirement gathered for Parinam dashboard | 4.00 | 1.00 | Completed | Yet To Update | Parinam dashboard updated
43 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 24/08/2026 | 28/08/2026 | Water supply during construction phase requirement gathered | 8.00 | 4.50 | Completed | Yet To Update | Enhancments completed
44 | Dheeraj Motiyani | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Department Meetings | VC with MD sir and training session | 28/08/2026 | 31/08/2026 | Meeting and finalizing O&M billing | 8.00 | 8.00 | Completed | Yet To Update | department and internal meeting
45 | Mukesh Singh | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Database functions Updation & API Web and Mobile Services | 03/08/2026 | 03/08/2026 | Worked on the Material Testing module for RFI reinspection functionality | 8.00 | 8.00 | WIP | Yet To Update | Resolved development issues and implemented database enhancements.
46 | Mukesh Singh | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Development of Web pages and Database functions | 07/08/2026 | 07/08/2026 | Worked on modifying and enhancing the Har Ghar Jal API function as per the updated requirements. | 8.00 | 8.00 | Completed | Yet To Update | Performed data validation and debugging on database tables
47 | Mukesh Singh | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Development of Web pages and Database functions | 19/08/2026 | 12/08/2026 | Worked on the Har Ghar Jal Module Dashboard function and modified it as per the updated requirements. | 8.00 | 8.00 | Completed | Yet To Update | Prepared reports by extracting data using SQL queries
48 | Mukesh Singh | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC (Functional Household Tap Connection) FE Reports | Query/SP creation/Modification | 19/08/2026 | 19/08/2026 | FHTC Dashboard enhancements for FE-level Approved and Rejected status tracking. | 8.00 | 8.00 | Completed | Yet To Update | Created and updated PostgreSQL functions/procedures
49 | Mukesh Singh | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Database functionality to add specific fields into the required tables | 20/08/2026 | 20/08/2026 | SVS Nirmal Water Supply Quality Test. | 8.00 | 8.00 | Completed | Yet To Update | Performed PostgreSQL query development
50 | Neha Soni | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 04/08/2026 | Discussion and UI Creation of SVS Nirmal Module with Tapan SIr and Dheeraj | 8.00 | 8.00 | Completed | Yet To Update | Discussion and UI Creation of SVS Nirmal Module with Tapan SIr and Dheeraj
51 | Neha Soni | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing - FE Login | UAT/Prod/CR Testing | 06/08/2026 | 06/08/2026 | Resolve Material Testing FE Login Production Issue | 1.00 | 1.00 | Completed | Yet To Update | Resolve Material Testing FE Login Production Issue
52 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Anusharavan | Testing | 04/08/2026 | 04/08/2026 | Validated Issue | 2.00 | 2.00 | Completed | Yet To Update | Verified the observation raised on Production. This is not an issue, as all the shared RFIs have already been accepted by the GM. Therefore, they are no longer visible to the contractor under the Re-Inspection list.
53 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Loop Functionality | 04/08/2026 | 04/08/2026 | Testing | 4.00 | 4.00 | Completed | Yet To Update | Tested loop functionality and retested raised issues.
54 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sahbhagita GM | UAT/Prod/CR Testing | 04/08/2026 | 04/08/2026 | Prod Issue-- Block name incorrect | 2.00 | 2.00 | Completed | Yet To Update | Validated block name issue in Sahbhagita Module
55 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Anusharavan | Testing | 05/08/2026 | 05/08/2026 | Report Issue Validation | 2.00 | 2.00 | Completed | Yet To Update | In Anushravan module, user is getting an issue while exporting the Customize Report. Now Its working fine and issue has been closed.
56 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 05/08/2026 | 05/08/2026 | Test Scenario Creation--- Loop Functionality | 6.00 | 6.00 | Completed | Yet To Update | Started analysis and as per understanding I have started creating the test scenarios.
57 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Anusharavan | Testing | 10/08/2026 | 10/08/2026 | Validation of Dashboard Enhancement | 1.00 | 1.00 | Completed | Yet To Update | done
58 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 10/08/2026 | 10/08/2026 | Test Scenarios Creation | 8.00 | 4.00 | WIP | Yet To Update | Started working on writing test scenarios for Cube module
59 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | FHTC Loop functionality implementation | 10/08/2026 | 10/08/2026 | FHTC(Parinam)- Bug Retesting | 2.00 | 2.00 | Completed | Yet To Update | Bug Resting done
60 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Loop Functionality | 10/08/2026 | 10/08/2026 | Material Testing-Bug Retesting | 1.00 | 1.00 | Completed | Yet To Update | Retesting of bug has been completed
61 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 10/08/2026 | 11/08/2026 | Test Scenarios Creation | 8.00 | 4.00 | Completed | Yet To Update | Test Scenario completed
62 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 11/08/2026 | 11/08/2026 | Test Case Creation | 8.00 | 4.00 | WIP | Yet To Update | Started working on creating Test Cases
63 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | Documentation of CMMI and Attneding Audit meeting | 12/08/2026 | 12/08/2026 | CMMIL5 Review Meeting | 2.00 | 2.00 | Completed | Yet To Update | Attended review meeting with Team
64 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Cube Testing CR | Complete Loop run again till FE (Cube Testing Approval) | 11/08/2026 | 12/08/2026 | Test Case Creation | 8.00 | 4.00 | Completed | Yet To Update | completed
65 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sahbhagita GM | UAT/Prod/CR Testing | 12/08/2026 | 12/08/2026 | Prod Issue Validation | 2.00 | 2.00 | Completed | Yet To Update | Validated prod issue and done RCA
66 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Test Case/Scenario Creation | 13/08/2026 | 13/08/2026 | Test Scenarios Creation | 8.00 | 4.00 | WIP | Yet To Update | Stared creating Test Scenarios for Material Testing Loop Functionality
67 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sahbhagita GM | UAT/Prod/CR Testing | 13/08/2026 | 13/08/2026 | Validation of Prod Issue | 4.00 | 4.00 | Completed | Yet To Update | Validated prod issue. Now its working as expected.
68 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Test Case/Scenario Creation | 13/08/2026 | 14/08/2026 | Test Scenarios Creation | 8.00 | 4.00 | Completed | Yet To Update | Test Scenarios has been completed
69 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Internal Testing | 14/08/2026 | 14/08/2026 | Tested SVS Dashboard Report | 2.00 | 2.00 | Completed | Yet To Update | Testing has been performed for SVS Dashboard Report.
70 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Project Module Initiation Meeting and Requirement gathering | 14/08/2026 | 14/08/2026 | SVS New Functionality Discussion | 2.00 | 2.00 | Completed | Yet To Update | Discussed new functionality in SVS.
71 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | FHTC Loop functionality implementation | 17/08/2026 | 17/08/2026 | Test Scenario Creation--Parinam Loop Functionality | 8.00 | 8.00 | Completed | Yet To Update | Test Scenario creation has been done.
72 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | Documentation of CMMI and Attneding Audit meeting | 18/08/2026 | 18/08/2026 | Meeting | 2.00 | 2.00 | Completed | Yet To Update | Internal discussion for upcoming changes in Jal Rekha
73 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 18/08/2026 | 18/08/2026 | Requirement Understanding- SVS Nirmal | 2.00 | 2.00 | Completed | Yet To Update | Understanding of the SVS Nirmal module has been completed.
74 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | User & Role Management | Automation with Selenium | 18/08/2026 | 18/08/2026 | Automation Script Creation for User Access Mapping | 4.00 | 4.00 | Completed | Yet To Update | Worked on automation script for User Access sub module.
75 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | FHTC Loop functionality implementation | 19/08/2026 | 19/08/2026 | Regression Testing | 2.00 | 2.00 | Completed | Yet To Update | Regression performed in Parinam Module
76 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | User & Role Management | Automation with Selenium | 19/08/2026 | 19/08/2026 | Automation Script till Assign Work | 6.00 | 6.00 | Completed | Yet To Update | Script created till Assign Work
77 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC (Functional Household Tap Connection) FE Reports | Test Case Creation | 31/08/2026 | 31/08/2026 | Test Case Update | 4.00 | 4.00 | Completed | Yet To Update | Test case has been updated and completed.
78 | Ranjana Yadav | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sahbhagita GM | UAT/Prod/CR Testing | 31/08/2026 | 31/08/2026 | Prod Validation | 4.00 | 4.00 | Completed | Yet To Update | Worked on prod issue
79 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 03/08/2026 | 03/08/2026 | Task Heading: Contractor Bill Approval – Pending Approval Listing | 8.00 | 8.00 | Completed | Yet To Update | Created new approval page Frm_ContractorBill_ForApproval.aspx for GM bill approval workflow. Added new JavaScript module ContractorBill_ForApproval.js for page-specific functionality. Implemented backend service for GET_PENDING_APPROVALS in the approval workflow. Created required Entity, DTO, DB Helper, Service, and WCF API for pending approval data retrieval. Integrated stored procedure fn_om_bill_approval_workflow with GET_PENDING_APPROVALS query type. Implemented AJAX integration to fetch pending contractor bills based on Financial Year, Scheme, User, and Role. Configured DataTable initialization and binding for pending approval records. Added initial page structure and integrated existing common dropdown filters (Financial Year & Scheme) for approval listing.
80 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 04/08/2026 | 04/08/2026 | GM Approval Workflow – Stage Review & Approval Process | 7.00 | 7.00 | Completed | Yet To Update | Developed GM Stage Review popup for pending bill approvals. Displayed contractor submitted bill details and uploaded documents in review screen. Implemented approval history section to show previous workflow actions. Added dynamic stage-wise controls (remarks, document upload, approve/forward button). Developed ProcessApprovalStage integration for stage-wise approval workflow. Added approval confirmation popup before final submission. Implemented stage-wise validation for mandatory remarks and document upload. Refined popup UI layout and improved document viewing experience.
81 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 04/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase (Review 2) | 3.00 | 1.00 | WIP | Yet To Update | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase (Review)
82 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 05/08/2026 | 05/08/2026 | TL/SQL Approval Page Development | 16.00 | 8.00 | WIP | Yet To Update | Developed TL/SQL approval page using the same workflow structure as GM Review. Implemented pending approval data binding based on workflow stage. Displayed contractor submitted bill details for TL/SQL review. Added document viewing link to open contractor submitted bill and supporting documents. Integrated stage-wise review screen with approval workflow. Performed UI adjustments and navigation improvements for seamless review process. Working on open bill (New Requirment) that is filled by contractor by the query string link but having problem because of that page only make for Contractor.
83 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 05/08/2026 | 06/08/2026 | TL/SQL Approval Page Development | 16.00 | 8.00 | Completed | Yet To Update | Implemented contractor bill redirection from the pending approval page to the TL (SQC) review page while preserving the selected Financial Year, Quarter, and Bill Month. Added functionality to restrict bill access and display only the contractor bill corresponding to the selected quarter and month. Developed document binding functionality to display contractor-uploaded documents and required supporting documents within the approval page. Implemented TL (SQC) Remarks and Recommendation Letter Upload functionality with document validation. Integrated the Forward to GM workflow after successful recommendation document upload and remarks submission. Enhanced approval page UI and data binding for stage-wise review and document verification. Performed end-to-end testing and validation of the TL (SQC) approval workflow, document handling, and stage transition.
84 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 10/08/2026 | 10/08/2026 | Pending Bill Approval Workflow Enhancement (GM and TL SQC Review Module) | 8.00 | 8.00 | Completed | Yet To Update | 1. Contractor Approval Page Access Restriction Removed Frm_ContractorBill_ForApproval.aspx access from the Contractor login to ensure the approval page is available only to authorized workflow roles. 2. Bill View Access Enhancement Enabled the Contractor Bill View functionality for GM (PIU) users. Previously, the bill view link was accessible only to TL (SQC) during the approval workflow. 3. GM Approval Workflow Fix Identified and resolved the issue where the bill was not forwarding after GM review. Updated the service logic to correctly handle stages where document upload is not mandatory, preventing exceptions during approval processing and allowing the workflow to proceed successfully.
85 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 11/08/2026 | 11/08/2026 | Live Issue : O&M Contract Details (GM Page) Scheme Status Save Issue Resolution (Is Full Scheme Under O&M) | 4.00 | 4.00 | Completed | Yet To Update | Investigated issue occurring while saving Scheme Status details. Reproduced the issue by selecting “No” for Is Full Scheme Under O&M. Analyzed the request payload generated during the save operation. Identified that is_full_scheme was being passed as an empty string instead of Boolean false. Reviewed the JavaScript sanitize() function usage in the save request. Identified incorrect application of sanitize() on the Boolean is_full_scheme value. Modified the JavaScript mapping to pass is_full_scheme directly as a Boolean value. Verified that Yes is passed as true and No is passed as false. Tested the Scheme Status save functionality after the modification. Successfully saved the data when Is Full Scheme Under O&M = No. Verified that the issue was resolved without affecting the existing save functionality.
86 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 11/08/2026 | 11/08/2026 | Issue O&M Contract Details Page not load for an particular user of GM Guna | 4.00 | 4.00 | Completed | Yet To Update | Issue Identified: Frm_OMContractDetails.aspx page was throwing a NullReferenceException for a specific user during page load. Root Cause: The user's dist_cd value was found to be NULL in the live database. Code Analysis: Exception was occurring while accessing Session["dist_cd"].ToString() in the Page_Load method. Data Validation: Verified the user's role and corresponding dist_cd value in the live database. Resolution: Corrected the missing dist_cd value for the affected user in the live database. Verification: Re-tested the affected user's login and confirmed that the O&M Contract Details page is loading successfully without any exception. Status: Resolved and Verified.
87 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 12/08/2026 | 12/08/2026 | Live Issue on GM and Contractor Page | 6.00 | 6.00 | Completed | Yet To Update | Live Issue : When GM User login and go to the page : Frm_OMContractDetails then scheme not load for that user . Live Issue : When user download the report of UFW then page show the UFW % , but in downloaded PDF that is not print. So fix the issue.
88 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 12/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase (Review 2) | 3.00 | 2.00 | Completed | Yet To Update | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase (Review 2)
89 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 13/08/2026 | 13/08/2026 | Modification on page : Frm_Bill_Tracking , for "View TimeLine" that is provided by client. | 8.00 | 8.00 | Completed | Yet To Update | Modification : Modification on page : Frm_Bill_Tracking , for "View TimeLine" that is provided by client. Modification on service as per client requirment. Modification on Page for view Timeline and change as per requirement. Create another service as per requirement for filter with quarter also when track the billing Modification on the page for add another filter in the page of the Bill Tracking
90 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 17/08/2026 | 17/08/2026 | Modification on Bill Tracking Page (Frm_Bill_Tracking) – Filter Enhancement | 8.00 | 8.00 | Completed | Yet To Update | Modification : Added "All" option in every filter dropdown (PIU, Scheme, Financial Year, Quarter) on page : Frm_Bill_Tracking, as per client requirement. Modification on Service Layer (GetPIUListForTracking, GetSchemeListForTracking, GetFYListForTracking, GetQuarterListForTracking, GetBillingTrackingReport) to support "All" selection handling. Modification on Database function (fn_om_bill_approval_workflow) for all above queries, to treat "All" selection as no-filter condition at DB level. Fixed cascading dropdown logic (PIU → Scheme → Financial Year → Quarter) on the page, including placeholder vs "All" value conflict. Added new PIU filter parameter in GetBillingTrackingReport service and database function, since PIU-wise data was not restricting properly when Scheme was set to "All". Fixed data validation issue on Search button, where empty selection was incorrectly treated as valid. Modification on page UI for proper alignment of filter dropdowns and Search button in a single row across screen sizes. Tested and verified data accuracy PIU-wise, Scheme-wise, and role-wise (Admin/Contractor/PIU user) after above changes.
91 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 19/08/2026 | 19/08/2026 | Additional Payment (By Upper Level) - Service Creation | 8.00 | 8.00 | Completed | Yet To Update | As per requirement, developed new backend service for Insert, Get and Delete functionality of Additional Payment (By Upper Level) for RA Bill. Analyzed existing Deduction service structure (InsertSummaryDeduction, GetAdditionaldeduction, DELETE_ROW_Summary) to follow same pattern for Payment module. Created DB function query type INSERT_ADDITIONAL_BY_UPPER_LEVEL for inserting additional payment record with role-based validation (only TL/SQC and GM/PIU allowed). Added bill-finalized check in insert flow — payment cannot be added once bill is finalized. Added duplicate entry check on payment type + reason combination for same bill. Created DB function query type GET_ADDITIONAL_PAYMENTS_BY_UPPER_LEVEL to fetch all additional payment records for a given bill. Created DB function query type DELETE_ADDITIONAL_PAYMENT_BY_UPPER_LEVEL with role validation, record-existence check, and bill-finalized check before delete. Created Entity classes: InsertSummaryPayment_ByUpperLevel_Entity, GetAdditionalPayment_ByUpperLevel_Entity, DELETE_ROW_Payment_ByUpperLevel_Entity. Created DTO class GetAdditionalPayment_ByUpperLevel_DTO for mapping payment list response. Implemented DB Helper method InsertSummaryPayment_ByUpperLevel — calls stored procedure fn_om_billing_summary_netpayable with query type INSERT_ADDITIONAL_BY_UPPER_LEVEL. Implemented DB Helper method GetAdditionalPayment_ByUpperLevel — calls stored procedure with query type GET_ADDITIONAL_PAYMENTS_BY_UPPER_LEVEL. Implemented DB Helper method DELETE_ROW_Payment_ByUpperLevel — calls stored procedure with query type DELETE_ADDITIONAL_PAYMENT_BY_UPPER_LEVEL. Implemented Business/Facade layer methods for Insert, Get and Delete additional payment, with proper try-catch and error logging. Added Service Contract (Interface) OperationContract definitions for three new endpoints: /InsertSummaryPayment_ByUpperLevel, /GetAdditionalPayment_ByUpperLevel, /DELETE_ROW_Payment_ByUpperLevel. Verified response structure (Success, Message, StatusCode, Data) consistent with existing Deduction service pattern. Cross-checked and fixed Net Payable calculation query (GET_NET_PAYABLE_BLOCK) — found additional_payments_rs was missing from final_payable_amount_rs calculation while it was correctly included in net_payable_amount_rs; added the missing term so Total Payable Amount reflects Addition entries correctly.
92 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 20/08/2026 | 20/08/2026 | Additional Payment (By Upper Level) - JS & HTML Integration | 8.00 | 8.00 | Completed | Yet To Update | As per new service, developed new method on JS and HTML page for Insert, Get and Delete functionality to the Addition. JS Function: function submitAdditionSummarySheet — Insert new additional payment/addition record with validation and API call. function GetAdditionalPayment_ByUpperLevel — Fetch additional payment list for the bill from API. function GetAdditionalPayment_ByUpperLevelData — Bind fetched additional payment data to DataTable on the page. function DELETE_ROW_Payment_ByUpperLevel — Delete selected additional payment record with confirmation and API call.
93 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 21/08/2026 | 21/08/2026 | O&M Billing – Addition & Deduction Enhancement and Bill Tracking Modification | 8.00 | 8.00 | Completed | Yet To Update | Modified multiple services and database functions to support Addition and Deduction functionality for both Contractor and TL/SQC & GM login levels. Implemented Addition and Deduction visibility on both Contractor and TL/SQC & GM sides. Added validation on the Contractor side to restrict deletion of Addition/Deduction entries added by TL/SQC or GM. Implemented stage-wise validation for TL/SQC and GM, ensuring that once a Deduction is added at a particular approval stage, existing entries cannot be deleted or updated at subsequent stages. Restricted Addition/Deduction modification based on the current bill approval stage, allowing new Addition entries only at the respective active stage. Enhanced Final Abstract Bill functionality to reflect newly added Addition and Deduction entries after bill save and submission. Displayed Addition/Deduction details in the Final Abstract Bill, including added by user, remarks, and Addition/Deduction type. Modified the Bill Tracking page to accommodate the updated Quarter Bill Abstract structure and reflect the latest Addition/Deduction details. Performed end-to-end validation of Addition/Deduction workflow across Contractor, TL/SQC, GM, Final Abstract Bill, and Bill Tracking modules.
94 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 24/08/2026 | 24/08/2026 | Bill Flow Modification & Role-Based Bill Tracking/Approval Enhancement | 8.00 | 8.00 | Completed | Yet To Update | Implemented the Open Bill facility for Kapil based on the assigned user role (Role ID: 15). Configured Bill Tracking and Approval Page access for Role ID: 17 – DYM O&M HQ (DGM). Implemented bill visibility for Role ID: 17, allowing the user to view the bill through the “Open Bill” option in the Approval Flow. Tested the Bill Tracking functionality for Role ID: 17 and identified an issue where the required dropdown values were not loading. Analyzed the dropdown loading issue and identified the role-based data handling/configuration issue. Resolved the dropdown loading issue and verified that the required filters are now loading correctly for Role ID: 17. Performed functional testing of the updated Bill Tracking and Approval Flow to ensure proper bill visibility and role-based access.
95 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 25/08/2026 | 25/08/2026 | Approval Process – Forward/Backward Routing Feature Development | 8.00 | 8.00 | Completed | Yet To Update | Worked on the new requirement for Forward/Backward approval routing to allow authorized users to move the bill to another person/stage when required. Analyzed the existing approval workflow and identified the required changes for supporting dynamic Forward/Backward routes. Designed and implemented the allowed route logic based on the current approval stage and logged-in user. Created a new service GetAllowedRoutes to fetch the valid Forward/Backward routing options. Integrated the GetAllowedRoutes service with the approval process to populate the available routes dynamically. Added a route selection dropdown in the approval process flow for selecting the required Forward/Backward option. Updated Frm_ContractorBill_ForApproval.aspx to accommodate the new route selection and approval workflow changes. Updated ContractorBill_ForApproval.js for handling route selection and integrating the new service with the existing approval flow.
96 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 27/08/2026 | 27/08/2026 | Approval Process – Forward/Backward Routing Feature Development Enhancement | 5.00 | 5.00 | Completed | Yet To Update | Implemented the Backward to Contractor workflow for cases where the bill requires correction or re-editing. Updated the workflow logic to enable the required Edit/Submit functionality for the Contractor after the bill is sent backward. Handled the Contractor re-submission flow so that the bill can continue through the approval process after modification. Updated ContractorBill_ForApproval.js to process the selected Forward/Backward route and corresponding workflow actions. Performed functional testing of the Forward, Backward, and Backward-to-Contractor scenarios and verified the approval flow.
97 | SACHIN KUMAR SONI | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 19/08/2026 | 27/08/2026 | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase (Review 4) | 3.00 | 3.00 | Completed | Yet To Update | Requirement Understanding O&M Workflow Implementation and WSDCP and TRR Phase (Review 4)
98 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Development of Web pages and Database functions | 03/08/2026 | 03/08/2026 | work on SVS Water Supply Monitoring for dash board | 8.00 | 8.00 | Completed | Yet To Update | work on SVS Water Supply Monitoring for dash board
99 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 04/08/2026 | 04/08/2026 | TL- Login O&M BIll Generation Enhancements | 16.00 | 8.00 | WIP | Yet To Update | TL- Login O&M BIll Generation Enhancements
100 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 04/08/2026 | 05/08/2026 | TL- Login O&M BIll Generation Enhancements | 16.00 | 8.00 | Completed | Yet To Update | TL- Login O&M BIll Generation Enhancements Done
101 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | Contractor/GM Login O&M BIll Generation Enhancements | 06/08/2026 | 06/08/2026 | GM- Login O&M BIll Generation Enhancements | 8.00 | 8.00 | Completed | Yet To Update | GM- Login O&M BIll Generation Enhancements Done
102 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | Customized and Summary report changes | 12/08/2026 | 12/08/2026 | Work on FHTC Module for update Field data if no action take. | 8.00 | 8.00 | Completed | Yet To Update | Work on FHTC Module for update Field data if no action take.
103 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sahbhagita | Bug Fixing from Frontend or Database end | 13/08/2026 | 13/08/2026 | Work on Sahbhagita Bug Fixing from Frontend or Database on reports | 8.00 | 8.00 | Completed | Yet To Update | Work on Sahbhagita Bug Fixing from Frontend or Database on reports
104 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 05/08/2026 | 14/08/2026 | Changes for Meter Reading MF, MNF and NWS documented (Review 2) | 3.00 | 3.00 | Completed | Yet To Update | Changes for Meter Reading MF, MNF and NWS documented (Review 2) Done
105 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Nirmal Change Request - Beneficiary Report | Report Issue | 14/08/2026 | 14/08/2026 | Work on Nirmal module Report Issue in TL Login | 5.00 | 5.00 | Completed | Yet To Update | Work on Nirmal module Report Issue in TL Login Done
106 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC (Functional Household Tap Connection) FE Reports | New web page creation/ Modification | 18/08/2026 | 18/08/2026 | FHTC-Module-Work-On-Mobile-Dashboard | 8.00 | 8.00 | Completed | Yet To Update | FHTC-Module-Work-On-Mobile-Dashboard Done
107 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Development of Web pages and Database functions | 19/08/2026 | 19/08/2026 | Work on Nirmal-Module-Work-On-SVS | 16.00 | 8.00 | WIP | Yet To Update | Work on Nirmal-Module-Work-On-SVS
108 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | Development of Web pages and Database functions | 19/08/2026 | 20/08/2026 | Work on Nirmal-Module-Work-On-SVS | 16.00 | 8.00 | Completed | Yet To Update | Work on Nirmal-Module-Work-On-SVS Done
109 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC (Functional Household Tap Connection) FE Reports | Bug Fixing from Frontend or Database end | 21/08/2026 | 21/08/2026 | FHTC-Module-Work-On-Mobile- Data Issue Fix | 8.00 | 8.00 | Completed | Yet To Update | FHTC-Module-Work-On-Mobile- Data Issue Fix
110 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | NIrmal - Change request - WTP, OHT, Beneficiary Report | Nirmal Issues of reading | 24/08/2026 | 24/08/2026 | Work on Nirmal Issues of reading | 16.00 | 8.00 | WIP | Yet To Update | Work on Nirmal Issues of reading
111 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | NIrmal - Change request - WTP, OHT, Beneficiary Report | Nirmal Issues of reading | 24/08/2026 | 25/08/2026 | Work on Nirmal Issues of reading | 16.00 | 8.00 | Completed | Yet To Update | Work on Nirmal Issues of reading
112 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Asset Mapping | Sujalam Bharat API Mapping & Survey Asset data | 27/08/2026 | 27/08/2026 | create Sujalam Bharat API for Mapping & Survey Asset data | 8.00 | 8.00 | Completed | Yet To Update | create Sujalam Bharat API for Mapping & Survey Asset data Done
113 | SUNIL THAKUR | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Asset Mapping | Sujalam Bharat API Mapping & Survey Asset data | 31/08/2026 | 31/08/2026 | Work on Sujalam bharat api | 8.00 | 8.00 | Completed | Yet To Update | Work on Sujalam bharat api
114 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Loop Functionality | 03/08/2026 | 03/08/2026 | Material Testing - add survey uid for OHT name filter. | 8.00 | 8.00 | Completed | Yet To Update | Material Testing: Implemented Survey UID-based OHT name filtering. Completed development, production testing, and deployed successfully.
115 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Database functions Updation & API Web and Mobile Services | 04/08/2026 | 04/08/2026 | All modules of the app were thoroughly tested before deployment. | 8.00 | 8.00 | Completed | Yet To Update | All modules of the app were thoroughly tested before deployment.
116 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Anusharavan | Stage Updation | 05/08/2026 | 05/08/2026 | Dashboard Enhancement and UI Improvements. | 16.00 | 8.00 | WIP | Yet To Update | Enhanced the dashboard by improving the UI, functionality, and overall user experience.
117 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Anusharavan | Stage Updation | 05/08/2026 | 06/08/2026 | Dashboard Enhancement and UI Improvements. | 16.00 | 8.00 | Completed | Yet To Update | Enhanced the dashboard by improving the UI, functionality, and overall user experience.
118 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | FHTC Loop functionality implementation | 07/08/2026 | 07/08/2026 | FHTC(Parinam)- Bug fixing. | 4.00 | 4.00 | Completed | Yet To Update | FHTC(Parinam)- Bug fixing.
119 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Material Testing Change Request | Loop Functionality | 07/08/2026 | 07/08/2026 | Material Testing- Bug fixing. | 4.00 | 4.00 | Completed | Yet To Update | Material Testing- Bug fixing.
120 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | Customized and Summary report changes | 10/08/2026 | 10/08/2026 | FHTC (Parinam) Dashboard ui design. | 8.00 | 8.00 | Completed | Yet To Update | FHTC (Parinam) Dashboard ui design.
121 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | Customized and Summary report changes | 12/08/2026 | 12/08/2026 | FHTC Dashboard ui changes and api integration. | 16.00 | 8.00 | WIP | Yet To Update | FHTC Dashboard ui changes and api integration.
122 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | Customized and Summary report changes | 12/08/2026 | 13/08/2026 | FHTC Dashboard ui changes and api integration. | 16.00 | 8.00 | Completed | Yet To Update | FHTC Dashboard ui changes and api integration.
123 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Cube Testing - FE | Test Case and Test Scenario Creation | 14/08/2026 | 17/08/2026 | Cube Testing- Test case Test Scenario creation. | 8.00 | 8.00 | Completed | Yet To Update | Cube Testing- Test case Test Scenario creation.
124 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | Customized and Summary report changes | 18/08/2026 | 18/08/2026 | FHTC(Parinam)- Complete summary report ui and api integration. | 16.00 | 8.00 | WIP | Yet To Update | FHTC(Parinam)- Complete summary report ui and api integration.
125 | Susheel Kumar Patel | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | FHTC Change request FHTC | Customized and Summary report changes | 18/08/2026 | 19/08/2026 | FHTC(Parinam)- Complete summary report ui and api integration. | 16.00 | 8.00 | Completed | Yet To Update | FHTC(Parinam)- Complete summary report ui and api integration.
126 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Department Meetings | VC with MD sir and training session | 03/08/2026 | 03/08/2026 | VC and Department Meeting with MD Sir and Report checking | 6.00 | 2.00 | Completed | Yet To Update | Attended VC and discussed field issues and action taken to resolve them
127 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Department Meetings | VC with MD sir and training session | 03/08/2026 | 03/08/2026 | VC and Department Meeting with MD Sir and Report checking | 6.00 | 4.00 | WIP | Yet To Update | Meeting with MD sir at Jal Nigam Department. Report checking on readings
128 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Dhara Change Request - GM PIU User/ TL | Meter reading survey for intake, wtp, oht, bulk both for web & mobile view | 05/08/2026 | 03/08/2026 | Changes for Meter Reading MF, MNF and NWS documented (Review) | 2.00 | 2.00 | Completed | Yet To Update | Reviewed and discussed with internal technical team to implement Meter reading changes
129 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS dashboard Creation | 04/08/2026 | 04/08/2026 | SVS dashboard review with BI developer and Business analyst | 3.00 | 3.00 | Completed | Yet To Update | Review with BI dashboard developer and implementation of changes suggested from department into dashboard requirement
130 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 04/08/2026 | Requirement gathering and creating wireframe and collecting master data (Review) | 4.00 | 2.00 | Completed | Yet To Update | Review Nirmal SVS FTK Kit requirement ranges with Jal Nigam department and finalize ranges limits and units of physical and chemical tests of water in Nirmal module
131 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 04/08/2026 | 04/08/2026 | Requirement gathering and creating wireframe and collecting master data (Review) | 4.00 | 2.00 | WIP | Yet To Update | SVS Nirmal water supply wireframe discussion and master creation for data provided from department
132 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 06/08/2026 | Analysis and managing work between resources | 8.00 | 2.00 | WIP | Yet To Update | Analysis of O&M work
133 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 06/08/2026 | 06/08/2026 | Discussed on SVS dashboard and analysis and SVS Nirmal work to implement it | 10.00 | 6.00 | WIP | Yet To Update | SVS Nirmal and Dashboard work to implement
134 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | O&M Billing - Enhancements | O&M Workflow Implementation and WSDCP and TRR Phase requirement gathering | 06/08/2026 | 07/08/2026 | Analysis and managing work between resources | 8.00 | 4.00 | WIP | Yet To Update | Implementation walk through mock up of O&M workflow structure
135 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | SVS Water Supply Monitoring | SVS Nirmal Water Supply details FTK kit requirements | 06/08/2026 | 07/08/2026 | Discussed on SVS dashboard and analysis and SVS Nirmal work to implement it | 10.00 | 4.00 | Completed | Yet To Update | Completed review and implementation analysis meeting with team
136 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | Cycle 4 Documentation from Jan to June 2026 | 10/08/2026 | 11/08/2026 | CMMI review meeting cycle 4 | 3.00 | 3.00 | Completed | Yet To Update | CMMi meeting attaended
137 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sahbhagita Change Request -GM / PM / Reports | Bug Fixing from Frontend or Database end | 11/08/2026 | 11/08/2026 | Sahbhagita internal meeting on Issue of ISA mapping | 3.00 | 3.00 | WIP | Yet To Update | sahbhagita meeting
138 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sopan Change Request - Contractor (Web / Mobile) | Adding Calendar functionality for 2026-27 year option | 12/08/2026 | 11/08/2026 | Functionality implementation and issue check | 2.00 | 2.00 | Completed | Yet To Update | Sopan calendar year issue fix
139 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | NIrmal - Change request - WTP, OHT, Beneficiary Report | Nirmal Issues of reading | 12/08/2026 | 12/08/2026 | Nirmal issue | 4.00 | 4.00 | Completed | Yet To Update | Nirmal design and code issues fix
140 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | CMMI Documents | Cycle 4 Documentation from Jan to June 2026 | 14/08/2026 | 17/08/2026 | CMMI review meeting for Cycle 4 data (Review) | 2.00 | 2.00 | Completed | Yet To Update | cmmi reviewed
141 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Department Meetings | VC with MD sir and training session | 17/08/2026 | 17/08/2026 | VC meeting for Jal rekha | 3.00 | 3.00 | Completed | Yet To Update | meeeting
142 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Anusharavan CR | Internal Testing | 18/08/2026 | 19/08/2026 | RFI verified Anusharavan | 4.00 | 4.00 | Completed | Yet To Update | rfi
143 | TAPAN KHANDELWAL | BHOPAL | Jal Rekha | Jal Rekha/19 | 03/08/2026 ¦ 31/08/2026 | Sahbhagita Change Request -GM / PM / Reports | Bug Fixing from Frontend or Database end | 18/08/2026 | 19/08/2026 | sahbhagita ISA issue fix | 4.00 | 2.00 | WIP | Yet To Update | fix