## Bill_Tracking 01-Sep-2026
Bill Tracking (Aakalan) - Tuesday 01-Sep-2026 15:04:31
S.No. | Zone | PIU | Scheme | OM Start Date | Type Of Bill | RA Bill No | RA Bill Duration | Financial Year | Bill Generation In Progress | Bill Generated | Bill Forwarded To HO | Recommended Amount | Payment Status | Paid Amount | Payment Date | Current Status | Pending Since | Days Pending | Timeline | Final Abstract Bill
1 | Bhopal | Bhopal | Begamganj-Gairatganj | 01-09-2024 | OM RA Bill | RA/1/20/2026-27/Q1/1 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Pending at TL (SQC) | 26-Aug-2026 02:01 PM | 6 | View Timeline | View Consolidated Abstract
2 | Bhopal | Bhopal | Begumganj Ex.-Ii |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
3 | Bhopal | Bhopal | Halali |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
4 | Bhopal | Bhopal | Sagad-Hinotiya Mali | 01-01-2026 | OM RA Bill | RA/50/126/2026-27/Q1/10 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | View Consolidated Abstract
5 | Bhopal | Bhopal | Udaipura | 01-11-2018 | OM RA Bill | RA/12/143/2026-27/Q1/25 | Q1 | 2026-27 | Yes | No | No | - | Not applicable yet | - | - | Bill Generation In Progress (1 of 3 Months) | - | - | - | -
6 | Bhopal | Rajgarh | Bankpura-Kushalpura | 29-07-2024 | OM RA Bill | RA/48/11/2026-27/Q1/10 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
7 | Bhopal | Rajgarh | Gorakhpura | 10-10-2022 | OM RA Bill | RA/53/53/2026-27/Q1/5 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
8 | Bhopal | Rajgarh | Kundaliya |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
9 | Bhopal | Rajgarh | Mohanpura |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
10 | Bhopal | Rajgarh | Pahadgarh |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
11 | Bhopal | Sehore | Mardanpur | 01-01-2018 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
12 | Bhopal | Sehore | Neelkanth-Nasrullaganj | 01-11-2024 | OM RA Bill | RA/13/104/2026-27/Q1/7 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Pending at GM (PIU) | 24-Aug-2026 12:55 PM | 8 | View Timeline | View Consolidated Abstract
13 | Gwalior | Gwalior | Badonkalan | 11-12-2020 | OM RA Bill | RA/31/6/2026-27/Q1/20 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
14 | Gwalior | Gwalior | Basai | 16-08-2021 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
15 | Gwalior | Gwalior | Dathera | 30-11-2023 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
16 | Gwalior | Gwalior | Narhela | 25-11-2019 | OM RA Bill | RA/28/99/2026-27/Q1/1 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
17 | Gwalior | Gwalior | Udgawan | 31-05-2018 | OM RA Bill | RA/37/144/2026-27/Q1/26 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
18 | Indore | Barwani | Talunkhurd | 15-12-2017 | OM RA Bill | RA/8/140/2026-27/Q1/25 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
19 | Indore | Indore | Bagh | 01-03-2026 | OM RA Bill | RA/51/7/2026-27/Q1/2 | Q1 | 2026-27 | Yes | No | No | - | Not applicable yet | - | - | Bill Generation In Progress (1 of 3 Months) | - | - | - | -
20 | Indore | Indore | Nemawar |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
21 | Indore | Indore | Punjapura | 01-09-2017 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
22 | Indore | Indore | Rajond | 01-07-2024 | OM RA Bill | RA/9/121/2026-27/Q1/6 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
23 | Indore | Indore | Rignod |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
24 | Indore | Indore | Roshni | 05-05-2022 | OM RA Bill | RA/6/124/2026-27/Q1/8 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
25 | Indore | Jhabua | Gunawad | 01-08-2023 | OM RA Bill | RA/49/56/2026-27/Q1/8 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
26 | Indore | Khargone | Bagod Nadiya Pipliya | 01-09-2017 | OM RA Bill | RA/42/8/2026-27/Q1/26 | Q1 | 2026-27 | Yes | No | No | - | Not applicable yet | - | - | Bill Generation In Progress (1 of 3 Months) | - | - | - | -
27 | Jabalpur | Chhindwara | Bandol | 17-02-2025 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
28 | Jabalpur | Chhindwara | Jhurki | 01-09-2017 | OM RA Bill | RA/5/66/2026-27/Q1/30 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Pending at TL (SQC) | 14-Aug-2026 11:48 AM | 18 | View Timeline | View Consolidated Abstract
29 | Jabalpur | Chhindwara | Mohkhed | 07-03-2018 | OM RA Bill | RA/7/96/2026-27/Q1/29 | Q1 | 2026-27 | Yes | No | No | - | Not applicable yet | - | - | Bill Generation In Progress (1 of 3 Months) | - | - | - | -
30 | Jabalpur | Chhindwara | Sangamghat |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
31 | Jabalpur | Chhindwara | Siddhaghat | 06-12-2024 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
32 | Jabalpur | Mandla | Bhatera | 07-07-2018 | OM RA Bill | RA/32/23/2026-27/Q1/28 | Q1 | 2026-27 | Yes | No | No | - | Not applicable yet | - | - | Bill Generation In Progress (1 of 3 Months) | - | - | - | -
33 | Jabalpur | Mandla | Devsarra | 01-01-2019 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
34 | Jabalpur | Mandla | Dhuti | 01-01-2019 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
35 | Jabalpur | Mandla | Piparjhari | 01-07-2018 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
36 | Jabalpur | Umaria | Ballaud |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
37 | Jabalpur | Umaria | Damehdi -1 | 01-06-2021 | OM RA Bill | RA/35/31/2026-27/Q1/10 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
38 | Jabalpur | Umaria | Gohparu | 01-09-2021 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
39 | Jabalpur | Umaria | Indwar-1 | 06-06-2025 | OM RA Bill | RA/24/63/2026-27/Q1/8 | Q1 | 2026-27 | Yes | No | No | - | Not applicable yet | - | - | Bill Generation In Progress (1 of 3 Months) | - | - | - | -
40 | Jabalpur | Umaria | Karanpura-1 | 01-12-2022 | OM RA Bill | RA/21/69/2026-27/Q1/17 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
41 | Jabalpur | Umaria | Kirgi | 25-04-2019 | OM RA Bill | RA/22/73/2026-27/Q1/15 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
42 | Jabalpur | Umaria | Manpur | 01-05-2021 | OM RA Bill | RA/23/92/2026-27/Q1/22 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Pending at TL (SQC) | 24-Aug-2026 06:32 PM | 8 | View Timeline | View Consolidated Abstract
43 | Rewa | Rewa | Kandaila |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
44 | Rewa | Sidhi | Majholi | 01-08-2022 | OM RA Bill | RA/40/90/2026-27/Q1/16 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
45 | Sagar | Chhatarpur | Bansujara (Badamalhara) | 01-07-2024 | OM RA Bill | RA/25/13/2026-27/Q1/9 | Q1 | 2026-27 | Yes | No | No | - | Not applicable yet | - | - | Bill Generation In Progress (2 of 3 Months) | - | - | - | -
46 | Sagar | Chhatarpur | Niwadi | 01-04-2020 | OM RA Bill | RA/2/108/2026-27/Q1/21 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
47 | Sagar | Chhatarpur | Niwari Prathvipur-1 | 01-11-2024 | OM RA Bill | RA/27/109/2026-27/Q1/7 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
48 | Sagar | Chhatarpur | Niwari Prathvipur-2 |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
49 | Sagar | Damoh | Byarma | 11-01-2019 | OM RA Bill | RA/45/27/2026-27/Q1/15 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
50 | Sagar | Damoh | Damoh-Patera | 21-02-2025 | OM RA Bill | RA/46/32/2026-27/Q1/5 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
51 | Sagar | Damoh | Jabera-Tendukheda | 26-12-2024 | OM RA Bill | RA/44/65/2026-27/Q1/6 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
52 | Sagar | Panna | Pawai | 04-02-2026 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
53 | Sagar | Sagar | Buxwaha | 01-06-2025 | OM RA Bill | RA/36/26/2026-27/Q1/5 | Q1 | 2026-27 | Yes | No | No | - | Not applicable yet | - | - | Bill Generation In Progress (1 of 3 Months) | - | - | - | -
54 | Sagar | Sagar | Gadakota |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
55 | Sagar | Sagar | Madia | 01-01-2025 | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
56 | Ujjain | Neemuch | Ganga Bavdi | 01-08-2018 | OM RA Bill | RA/43/46/2026-27/Q1/1 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
57 | Ujjain | Ujjain | Agar Malwa |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
58 | Ujjain | Ujjain | Arniya Bahadur | 01-12-2018 | OM RA Bill | RA/17/4/2026-27/Q1/20 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
59 | Ujjain | Ujjain | Indokh |  | OM RA Bill | - | Q1 | 2026-27 | No | No | No | - | Not applicable yet | - | - | Bill Generation Not Started | - | - | - | -
60 | Ujjain | Ujjain | Nagda | 01-10-2021 | OM RA Bill | RA/11/98/2026-27/Q1/15 | Q1 | 2026-27 | No | Yes | No | - | Not applicable yet | - | - | Documents Pending | - | - | - | -
[9 empty] | Bill generation started (Yes/No) | Bill submitted to GM PIU (Yes/No) | [5 empty] | To be discuss with MPSeDC
Not submitted by contractor
Pending with contractor
Pending with SQC (TL)
Pending with GM (PIU)
Pending with GM (O&M)
Pending with Dy M (O&M)
Pending with TL (PMC)

## Aakalan
Points to be discussed with MPSeDC Team
O&M RA bill tracking
Current Status
Not submitted by contractor
Pending with contractor
Pending with SQC (TL)
Pending with GM (PIU)
Pending with GM (O&M)
Pending with Dy M (O&M)
Pending with TL (PMC)
View Timeline
S.No. | RA Bill No. | Pending with | Received on | Forwarded on | Time Taken (in Days) | Remarks
|  | Contractor | -- | 24.05.26 (02:11 pm) | --
|  | GM PIU | 24.05.26 (02:11 pm) | 28.05.26 (05:00 pm) | 4 | Check and submit
|  | TL (SQC) | 28.05.26 (05:00 pm) | 01.06.26 (01:15 pm) | 4
|  | GM PIU | 01.06.26 (01:15 pm) | 02.06.26 (02:05 pm) | 1
|  | Contractor | 02.06.26 (02:05 pm)