## CR Log Jun-Jul 2026
JAL REKHA PROJECT — CHANGE REQUEST LOG ¦ June–July 2026 (Cycle 4, Sprint Jal Rekha/17)
Project: Jal Rekha ¦ Client: Govt. of MP – PHED ¦ Contract: MPSEDC/MPSSDI(GIS)/2025/00423 ¦ Prepared by: Dheeraj Motiyani, Sr. BA ¦ Reviewed by: Tapan Khandelwal, SPM
CR No. | CR Code | CR Raised By | Req. Gathered By | Logging Date | CR Description | Module | Sub-Module | Impact Area | Impact Analysis | Impl. Status | Impl. Date | Approval Status | Priority | Risk Level | Remarks
1 | OMB-JULY-2026-001 | MD Sir / Kapil Sir | Dheeraj Motiyani | 2026-07-01 | Contractor/Firm login – make key document uploads (Submission Letter, Tax Invoice) mandatory before a bill can move out of “Save as Draft” state; draft can be saved with partial data but cannot be forwarded to GM (PIU) until mandatory documents are attached. | O&M Billing | Save as Draft – Mandatory Upload (Contractor) | Contractor/Firm Login – Bill Workflow | Draft-save behaviour unchanged; new gate added only on the Forward action. Mirrors pattern already delivered for Cube Testing and Sahbhagita Mobile Save-as-Draft CRs. | Done | 2026-07-06 | Pending | High | Medium | New CR – raised to align O&M Billing with Cube/Sahbhagita Save-as-Draft pattern.
2 | OMB-JUN-2026-002 | MD Sir | Dheeraj Motiyani | 2026-07-02 | O&M Billing – Residual Pressure & Complaint Redressal screen changes. Pressure Threshold Report format update per OM_RA_Bill_Report.pdf. Complaint Redressal - Is complaint resolved in this month ? Renaming Complaint Redressal page :- Date on which complaint received to contractor, Date on which complaint resolved, Total Days taken in Resolving complaint (Days) | O&M Billing | Residual Pressure & Complaint Redressal | GM PIU / O&M Login – RA Bill | Residual Pressure: columns per OM_RA_Bill_Report.pdf (District, Block, GP, Village, Consumer Name, Mobile, Measured Pressure, Remark, Affected HSCs, Days, Penalty calc). Complaint Redressal: label and status changes. | Done | 2026-07-07 | Pending | Medium | Low | Ref: OM_RA_Bill_Report.pdf – Pressure_Threshold_Report. RA/19/50/2025-26/Q1/1 format.
3 | OMB-JUN-2026-003 | MD Sir | Dheeraj Motiyani | 2026-07-02 | Complaint Redressal Sheet – add Complaint Received Date to Contractor, Event-above-48-hours flag and Penalty Relaxation (Yes/No) fields; document upload as per submeter reading. | O&M Billing | Complaint Redressal Sheet | GM PIU / O&M Login – RA Bill | Auto-derived Event-above-48-hours flag from received/resolved dates. Penalty Relaxation = Yes routes relaxation letter into GM (PIU) document set. | Done | 2026-07-08 | Pending | Medium | Low | New CR – extends Residual Pressure CR (OMB-MAY-2026-020) into the Complaint Redressal tab.
4 | OMB-JUN-2026-004 | MD Sir | Dheeraj Motiyani | 20-Jun-2026 | O&M Billing - Desgin changes portrait to landscape for O&M Report for Abstract Bill | O&M Billing | Abstract Bill – Portrait to Landscape | All Logins – Bill PDF Generation | Report orientation changed from portrait to landscape for Abstract Bill PDF. Impacts GM, SQC, Firm/Contractor bill view and download. Layout redesign required for all table/column headers in Abstract Bill PDF service. | Open |  | Pending | Medium | Low | Ref: RA Bill landscape format request. Landscape layout wider table required for Abstract Bill header + village-wise summary columns.
5 | OMB-JULY-2026-005 |  |  | 2026-07-13 | Naming and formatting of all pages and corrections needed on O&M Contractor login | [5 empty] | 2026-07-14
6 | OMB-JULY-2026-006 |  |  | 2026-07-13 | UFW Report taken from Dhara will be shown on O&M Billling Contractor login Page attached with bill | [5 empty] | 2026-07-15
7 | OMB-JULY-2026-007 |  |  | 2026-07-14 | On Contractor Login Only => Additional document upload by contractor - Firm Letter, Tax Invoice and any other document with remark mandatory - ( on New page - "View Bills") | [5 empty] | 2026-07-16
8 | OMB-JULY-2026-008 |  |  | 2026-07-14 | FHTC & Sahbhagita Bug Fix and API Service and External API Updations in both modules
9 | OMB-MAY-2026-006 | MD Sir | Dheeraj Motiyani | 01-Jun-2026 | O&M Billing – Workflow Redesign: Firm → GM PIU → TL SQC → GM PIU → GM O&M → DGM → TL PMC → CFO → CA → P.D. → MD. | O&M Billing | Billing Workflow Redesign | Firm, GM PIU, TL SQC, GM O&M, All Hierarchy | Two workflow paths defined. “Manage Bill” option used for GM PIU. “View Pending Bills” accessible before Pending stage. Ref: O&M_Billing_Workflow diagrams and process flow PDF. | In Progress |  | Pending | High | High | Use Manage Page (not old flow). Refer O&M Billing Workflow PDF + JPEG diagrams.
10 | OMB-MAY-2026-002 | MD Sir / Kapil Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – Contractor Generate Bill: Abstract generation from Contractor login. Select Bill → Generate Abstract → With all villages, scheme (Dhara readings, Master Module tables and UFW Approved report and other documents with Abstract bill ) | O&M Billing | Contractor Bill – Abstract | Contractor Login – Bill Workflow | Abstract screen added under Contractor login for RA billing. Links to selected bill and tags all villages. GM/SQC approval chain unaffected. | In Progress |  | Pending | High | Medium | Abstract linked to 8th Bill; Tag all villages flag needed.
11 | OMB-JUN-2026-003 | MD Sir | Dheeraj Motiyani | 18-Jun-2026 | Sahbhagita – Village-wise and Combined Activity abstract report; Category filter (Village/Combined/All); quarterly RA Bill numbering (RA/1–RA/12) reflected on abstract header. | Sahbhagita | Abstract Bill – Category Filter | GM PIU / Contractor Login – Abstract Report | Reuses Sahbhagita Category(V/C/A) filter logic for the O&M Abstract report; RA numbering aligned to the RA(1)-RA(12) cycle used in Sahbhagita. | Open |  | Pending | High | Medium | New CR – aligns O&M Abstract Bill with Sahbhagita Village/Combined activity structure.
| OMB-MAY-2026-005 | MD Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – Bill PDF consolidation: approx. 19–20 documents merged into one PDF (GM, SQC, Firm, Form 27A, MB, Abstract). 3-month combined PDF for static docs; monthly for variable docs. | O&M Billing | Bill PDF Merge – All Documents | All Logins – Bill Generation | Merged PDF includes: 1.GM letter, 2.SQC letter, 3.Firm docs, 4.Form 27A, 5.MB, 6.Abstract. Static docs = 1 copy for 3 months; variable = per month. Total ~19–20 docs. | In Progress |  | Approved | High | Medium | Landscape issue in O&M Bill PDF also fixed in this CR.
| OMB-MAY-2026-008 | MD Sir | Dheeraj Motiyani | 03-Jun-2026 | O&M Billing – Contractor mistakes visible to SQC/TL and GM. Show all records on all IDs for GM and SQC. Merge PDF of all O&M documents. | O&M Billing | Contractor Mistake Visibility & PDF Merge | GM, SQC, TL Logins | Contractor error entries visible across SQC/TL and GM logins. All records shown on all IDs. O&M merged PDF available per bill. | Open |  | Pending | Medium | Medium | Related to Bill PDF CR (OMB-MAY-2026-005). SQC 7L/4–GM mapping check needed.
| OMB-MAY-2026-015 | MD Sir | Dheeraj Motiyani | 09-Jun-2026 | O&M Billing – Document Upload Screen: Firm: Firm Submission Letter, Tax Invoice, Any Other (Multiple). TL/SQC: SQC Recommendation Letter, Third Party Water Quality Test Report (Multiple + Remark). GM PIU: PIU Recommendation Letter, Signed Form 27A, Signed Scanned MB, Signed Abstract, Signed Monthly Bill Sheet (Multiple), Any Other Docs (Multiple + Remark). | O&M Billing | Document Upload Screen Design | Firm, TL/SQC, GM PIU Logins | Upload UI: Download + View PDF buttons per doc type. Multiple upload for Water Quality Test Report, Monthly Bill Sheet, Any Other Docs. Remark field for selected doc types. | In Progress |  | Approved | High | Medium | Ref: Handwritten wireframe (Contractor/Firm, TL SQC, GM PIU sections). Upload + Download + View PDF per doc.
| OMB-MAY-2026-003 | MD Sir / Kapil Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – GST No. Integration with O&M Billing Jal Rekha portal. GST number to be captured and linked at firm/contractor level. | O&M Billing | GST Integration | Contractor / GM PIU Login | GST No. field added at contractor master level. Appears on bill PDF and abstract. Rakesh Sir to validate GST API/manual entry approach. | Open |  | Pending | Medium | Low | GST No. (150/215) – Rakesh Sir to confirm data source.
| OMB-MAY-2026-001 | MD Sir / Kapil Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – E-Sign Integration via CDAC for all parties (Firm/FE-eSign, Web & Mobile). CDAC integration for e-sign on Bill, Submission Letter, and Tax Invoice. FE (e-sign) → Web & Mobile flow. | O&M Billing | E-Sign – CDAC Integration | Web & Mobile – Bill Workflow | CDAC API integration required. Affects Firm, FE, TL, GM PIU login flows. Bill PDF and submission letter to carry e-sign. System-generated bill – physical sign NOT required. | Open |  | Pending | High | High | CDAC Rakesh Sir to coordinate. FE (e-sign) ↔ Web/Mobile dual flow.
| OMB-MAY-2026-004 | MD Sir | Dheeraj Motiyani | 22-May-2026 | O&M Billing – TL Recommendation Letter to be E-Office generated (system-generated). TL (PMC) → E-Office → Account Office Jal Rekha. | O&M Billing | TL Recommendation Letter – E-Office | TL (PMC) & Account Office Login | TL recommendation letter generated from E-Office system, not manual upload. Integration with Account Office Jal Rekha to be established. | Open |  | Pending | High | High | TL SQC integration also required. E-Office API/link to be confirmed.
| OMB-MAY-2026-014 | MD Sir | Dheeraj Motiyani | 08-Jun-2026 | O&M Billing (Aaklan) – GM (PIU Login) & GM (O&M) / Deputy O&M: View Pending Bills and Manage Bills. Bills already generated shown in table. | O&M Billing (Aaklan) | Pending Bills View – GM Logins | GM PIU & GM O&M Login | GM PIU: View Pending Bills, Manage Bill under O&M. GM O&M: View Pending Bills + Manage Bill. Already generated bills shown in table. Ref: 18-Jun handwritten flow. | In Progress |  | Approved | High | Medium | Aaklan module O&M section. GM PIU & GM O&M/Deputy flows defined.
| SHB-JUN-2026-004 | MD Sir | Dheeraj Motiyani | 18-Jun-2026 | Sahbhagita – Report: Category → Activity. Village Wise (32/27 activities) & Combined (22). Filter: V, C, A. Category V/C/A cross-filter. Ref: Sahbhagita_master_activity_matched.xlsx. | Sahbhagita | Activity Report – Village/Combined Category Filter | Sahbhagita Report Module | Report shows Village Wise (32 listed, 27 unique) and Combined (22). Category filter: V=Village, C=Combined, A=All. Sub-activity linked. Ref: Sahbhagita master activity doc. | In Progress |  | Approved | High | Medium | Village 32/27 activities; Combined 22; V/C/A cross-filter. Ref master activity matched xlsx.
| SHB-MAY-2026-007 | MD Sir | Dheeraj Motiyani | 01-Jun-2026 | Sahbhagita – Multi-select dropdown for bill selection. RA(1) to RA(12) bill range with Withhold Bills option. | Sahbhagita | Multi-Select Bill Dropdown | Sahbhagita Login – Bill Management | Sahbhagita module: multi-select in bill dropdown. RA Bill range RA(1)–RA(12). Withhold Bills toggle added. | Open |  | Pending | Medium | Low | Generate Abstract → Select Bill → Tag all villages. Village-wise & Combined Activities in scope.
| SHB-MAY-2026-013 | MD Sir | Dheeraj Motiyani | 04-Jun-2026 | Sahbhagita – Hyperlink: Village Name → Village Activity Document Preview popup. Two hyperlinks: (1) Village Name, (2) Village Activity Document (Reviewed) & Other Column names | Sahbhagita | Hyperlink – Village Activity Document Preview | Sahbhagita Report View | Village Name clickable hyperlink. On click: popup showing Village Activity Document with preview. Two separate hyperlink areas. | In Progress |  | Approved | Medium | Low | Popup with village activity doc preview.
| SHB-MAY-2026-012 | MD Sir | Dheeraj Motiyani | 04-Jun-2026 | Sahbhagita – Future Scope: Photo Scan → Face/Background AI Model (CP Manager). Video option. Duplicate/Repeated photo detection → flag message to CP Manager. | Sahbhagita | AI Photo Verification – CP Manager | CP Manager Login | Photo/video capture at CP Manager login. AI model (face + background). Duplicate/repeated → show flag: “Already Used Before”. Future scope item. | Open |  | Pending | Low | High | Future scope. AI model (Photo Scan face + background). Video in scope.
| CUBE-JUN-2026-005 | MD Sir | Dheeraj Motiyani | 16-Jun-2026 | Cube Testing – Cube ID get generated before image upload; Show rejected data to Contractor. | Cube Testing | Cube ID Generation & Rejected-Data Visibility | Contractor Login – Cube Inspection | Cube ID no longer depends on a successful image upload. Rejected inspection records surfaced back to Contractor login for correction and resubmission. | Completed | 2026-07-08 | Approved | Medium | Low | Delivered per MoM 16-Jun-2026, Point 2.
| CUBEMAT-JUN-2026-007 | MD Sir | Dheeraj Motiyani | 20-Jun-2026 | Material testing & Cube testing - cycle loop runs 2nd time after rejction from GM. FE to GM to contractor back to GM again to SQC TPIA then to FE again (if new FE added) | Material testing and cube testing | Re-Inspection Loop (2nd Cycle – After GM Rejection) | Contractor, FE, GM, SQC, TPIA Logins – Cube & Material Testing | Second cycle loop triggered after GM rejects result: FE → GM → Contractor → GM → SQC/TPIA → FE (if new FE added). Loop re-runs with same RFI structure but new inspection data. Applies to both Cube Testing and Material Testing modules. | Open |  | Pending | High | High | 2nd loop post-rejection: FE → GM → Contractor → GM → SQC → TPIA → FE (new). Complex state machine; must retain original submission data alongside new loop data.
| CUBEMAT-JUN-2026-008 | MD Sir | Dheeraj Motiyani | 20-Jun-2026 | Material testing & Cube testing - cycle loop run - Image optional in RFI 2nd time loop (in Cube and Material testing) | Material testing and cube testing | RFI 2nd Loop – Image Upload Optional | Contractor & FE Logins – RFI Second Cycle | During RFI second-time cycle loop (re-inspection), image/photo upload marked as optional (not mandatory) for both Cube Testing and Material Testing. Mandatory on first cycle; optional on subsequent loops. DB flag added per loop iteration. | Open |  | Pending | Medium | Low | Image optional flag must not apply to 1st cycle. CR depends on CUBEMAT-JUN-2026-007 (loop CR) being implemented first.
| MSTR-JUN-2026-006 | MD Sir | Dheeraj Motiyani | 18-Jun-2026 | Master – Lock Scheme Master, Village Master and OHT Master entries once linked to live transactions (Dhara, O&M Billing, Asset Mapping); GM (PIU) side all details lock. | Master | Scheme / Village / OHT Master – Entry Lock | GM PIU Login – Master Data | Record becomes read-only once tagged/used in a Dhara report, O&M Billing entry or Asset Mapping (BISAC) record. Further correction routed through a controlled change/relaxation flow rather than direct edit. | Open |  | Pending | High | High | Extends the Dhara approved-report lock principle (CR OMB/DHARA-MAY-2026-009) to the Master data layer.
| DHARA-MAY-2026-009 | MD Sir | Dheeraj Motiyani | 03-Jun-2026 | Dhara– Approved report data entry should NOT change once approved. UI lock for GM PIU. GM PIU/TL can ADD (not edit). GM can add new penalty point on Contractor bill. | Dhara | Approved Report Lock – Entry Freeze | GM PIU Login – Report Approval | Once GM PIU approves Dhara report, entry locked across all logins. GM PIU/TL can add info but cannot edit Contractor data. Penalty by GM is addable on top. | In Progress |  | Approved | High | High | GM can add new point (Penalty applied). Cannot edit existing Contractor-generated bill data.
| DHARA-MAY-2026-021 | MD Sir | Dheeraj Motiyani | 01-Jun-2026 | O&M Billing – Mandatory options & go-live on 19th June across all logins: (1) Remark, (2) Photo Upload, (3) Forward, (4) Backward Options. | Dhara | Non-Mandatory Options – Go Live 19-Jun | All Logins – Dhara Module | mandatory options (Remark, Photo Upload, Forward, Backward) enabled on 19-Jun across all logins. These actions do NOT block submission if not filled. | In Progress |  | Approved | High | Low | Go-live 19-Jun-2026 confirmed. Non-mandatory: Remark, Photo Upload, Forward, Backward.

## Module Summary
CR Module Summary – June–July 2026 ¦ Jal Rekha Project
Module | No. of CRs | Completed | In Progress | Open | Total Effort (Hrs)
O&M Billing | 12 | 0 | 4 | 8 | 280
O&M Billing (Aaklan) | 1 | 0 | 1 | 0 | 24
Sahbhagita | 4 | 0 | 2 | 2 | 40
Cube Testing | 1 | 1 | 0 | 0 | 16
Master | 1 | 0 | 0 | 1 | 12
Dhara | 2 | 1 | 1 | 0 | 32
Material & Cube Testing (Loop) | 2 | 0 | 0 | 2 | 32
TOTAL | 23 | 2 | 8 | 13 | 436