## Version History
Date | Version | Description | Prepared by | Reviewed & approved by
2025-01-03 | 1 | Size base Estimation Model First baseline | SEPG Team | SEPG Head
2026-06-01 | 1.4 | Cycle 4 (Jan-May 2026) Size based Estimation - All modules updated | SEPG Team | SEPG Head
2026-06-17 | 2.0 | Cycle 4 Estimation corrected – All module Size and Effort values updated per CMMI L5 size-based estimation guidelines. Productivity=0.18 pt/hr; VAF=1.01; Risk=5%; PM=10%. Sizes: ANS=26, AST=9, BHR=23, CUBE=69, DHR=89, FHTC=53, MST=38, MAT=51, NRM=22, O&M=96, SAH=10, SVS=11. All hardcoded Size/TotalCount cells converted to Excel formulas. Complexity distributions recalibrated per Guidelines sheet. | SEPG Team | SEPG Head
2026-08-11 | 1.0 | Cycle 5 (June-July 2026) Size based Estimation - New workbook covering all 22 modules per the Consolidated User Story Register (107 stories) and CR Log. Methodology inherited from Cycle 4 V2.0: Productivity=0.18 pt/hr, VAF=1.01 (Total rating=36, retained from Cycle 4 baseline, not re-scored), Risk=5%, PM=10%. Complexity per story derived from its logged Effort (hrs) in the User Story Register: <=8 hrs=Low(1), 9-16 hrs=Medium(3), >16 hrs=High(5). Actual Consumed Hrs per module sourced from the Date-Wise Time Sheet (Cycle 5, Jun-Jul 2026) via Module Name mapping; unmapped generic timesheet entries (Dashboard/DevOps/Meetings, 59 hrs) are shown separately and excluded from module actuals. | Mr. Dheeraj Motiyani | Mr. Tapan Khandelwal

## Cycle 5 Summary
JAL REKHA - CYCLE 5 (JUNE-JULY 2026) SIZE-BASED ESTIMATION SUMMARY
Prepared by: Mr. Dheeraj Motiyani, Sr. Business Analyst ¦ Basis: Consolidated User Story Register + Date-Wise Time Sheet (Cycle 5)
Sr. No. | Module | User Stories | Total Size (Points) | Planned Effort (Man-hrs) | Actual Consumed Hrs (Timesheet) | Variance (Man-hrs) | US Register Effort (hrs)
1 | O&M Billing – Aaklan | 17 | 37 | 238.7528 | 325 | -86.2472 | 218
2 | Sahbhagita | 11 | 19 | 122.6028 | 271 | -148.3972 | 104
3 | Dhara (Reports, Corrections, Disputes) | 8 | 14 | 90.3389 | 112 | -21.6611 | 82
4 | Vistrit (Master Module) | 5 | 5 | 32.2639 | 0 | 32.2639 | 34
5 | FHTC Parinam | 5 | 11 | 70.9806 | 108 | -37.0194 | 56
6 | BISAC / NIC Asset Integration | 3 | 11 | 70.9806 | 0 | 70.9806 | 52
7 | e-Sign via CDAC (Aadhaar) | 4 | 16 | 103.2444 | 0 | 103.2444 | 82
8 | Anusharavan (June CR) | 3 | 3 | 19.3583 | 70 | -50.6417 | 18
9 | Cube Testing (June CR) | 5 | 7 | 45.1694 | 345 | -299.8306 | 38
10 | SVS Water Supply Monitoring (June CR) | 4 | 4 | 25.8111 | 105 | -79.1889 | 20
11 | Vistrit OTP & Validation | 2 | 2 | 12.9056 | 0 | 12.9056 | 12
12 | CMMI Documentation | 2 | 10 | 64.5278 | 200 | -135.4722 | 100
13 | O&M Billing Workflow Module (Multi-Level Approval Chain) | 16 | 48 | 309.7333 | 30 | 279.7333 | 0
14 | Material Testing | 3 | 9 | 58.075 | 141 | -82.925 | 42
15 | Nirmal Module | 4 | 4 | 25.8111 | 32 | -6.1889 | 28
16 | AI Module - FHTC Tap Connection Detection | 3 | 15 | 96.7917 | 147 | -50.2083 | 104
17 | Master Data Module | 3 | 5 | 32.2639 | 16 | 16.2639 | 30
18 | Asset Mapping (BISAC) | 2 | 6 | 38.7167 | 16 | 22.7167 | 22
19 | Bharosa (Factory Testing) | 2 | 2 | 12.9056 | 7 | 5.9056 | 14
20 | Daily Inspection | 2 | 4 | 25.8111 | 20 | 5.8111 | 18
21 | Sopan | 1 | 3 | 19.3583 | 8 | 11.3583 | 10
22 | QA - User & Role Management Automation | 2 | 4 | 25.8111 | 10 | 15.8111 | 20
| GRAND TOTAL (Cycle 5, 22 modules) | 107 | 239 | 1542.2139 | 1963 | -420.7861 | 1104
Notes:
1. Complexity per user story is derived from its logged Effort (hrs) in the Consolidated User Story Register: <=8 hrs = Low (weight 1), 9-16 hrs = Medium (weight 3), >16 hrs = High (weight 5). This is an assumption made to fit story-level data into the CMMI size-based model; it has not been independently re-scored against the Guidelines sheet element-by-element.
2. Productivity (0.18 pt/hr), VAF (1.01, factor Total=36) and Risk (5%) / PM (10%) loadings are retained unchanged from the Cycle 4 V2.0 baseline per SEPG guidelines.
3. "Actual Consumed Hrs" is aggregated from the Date-Wise Time Sheet (Cycle 5, Jun-Jul 2026) by Module Name, mapped to each estimation sheet. Timesheet entries logged under generic buckets (Dashboard, AzureDevOps, Department Meetings - 59 hrs total) are not attributable to a single module and are excluded from the module rows above; see the "Unmapped Timesheet Hours" row below.
4. Vistrit, Vistrit OTP & Validation, BISAC/NIC Asset Integration and e-Sign via CDAC did not have a distinctly labelled Module Name in the Cycle 5 timesheet (their effort is likely embedded within Dhara / O&M Billing Workflow timesheet entries); Actual Consumed Hrs for these four modules is shown as 0 rather than estimated.
5. "US Register Effort (hrs)" is the sum of the Effort (hrs) column already logged against each story in the Consolidated User Story Register - shown as an independent cross-check against the size-based Planned Effort, not an input to it.
6. The 16 O&M Billing Workflow stories are carried forward unchanged from the Cycle 4 register and have no logged Cycle 5 Effort (hrs) figure (US Register Effort shows 0); complexity for these was defaulted to Medium. The module nonetheless shows 30 actual timesheet hours in Cycle 5 (workflow discussion/requirement-gathering per the June/July MoM), so its Planned-vs-Actual variance should be read with this in mind.
| Unmapped Timesheet Hours (Dashboard/DevOps/Meetings) |  |  |  | 59
| Grand Total Timesheet Hours (all entries, Cycle 5) |  |  |  | 2022

## Master
Estimation Elements
New Development | Enhancement and customization
Web Page / Screen with no of input fields | Web Page / Screen with no of input fields
Type of exit scenario | Type of exit scenario
No of Validation on the fields | No of Validation on the fields
No of Prefilled fields | No of Prefilled fields
No of API Integrations | No of API Integrations
No API integrations for saving the data | No API integrations for saving the data
Queries or Business rules for the application | Queries or Business rules for the application
No of Integration | No of Integration
mobile App-UI | mobile App-UI
Data Migration | Data Migration
Reports | Reports
Complexity | Type of work | VAF Rating
Low | New Development | 5 | 5 - Very Strong Influence
Medium | Enhancement and customization | 4 | 4 - Strong Influence
High |  | 3 | 3 - Average Influence
Complex |  | 2 | 2 - Moderate Influence
|  | 1 | 1- Slight Influence
|  | 0 | 0 - No Influence
Effort Distribution Guidelines
| Effort Distribution | Cost
|  | Min | Max
Business Analyst | 15% | 4000 | 6000
Solution Architecht | 10% | 6000 | 8000
Developer / Data Scientist | 40% | 3000 | 5000
Tester | 20% | 2500 | 5000
Project Manager | 10% | 8000 | 10000
Infrastructure Setup | 5% | 3000 | 5000
Business Analyst | 15%
Solution Architecht | 10%
Developer / Data Scientist | 40%
Tester | 20%
Project Manager | 10%
Infrastructure Setup | 5%

## Baseline Productivity
Type of work | Calculated Productivity | Targated Productivity | Unit
Development & Enhancement |  | 0.179 | Point / per hour
|  | 1 Point | 5.5866
~5.6 hours

## Guidelines
| Complexity | 1 | 3 | 5
Work Type | Component | Low | Medium | High
Development | Web Page / Screen with no of input fields | 10 | 10-15 | > 15 | Elements Label Graph Tile Grid Pop-up Drop Down Data Entery Field Button Custom Built element |  |  | 1
| Type of exit scenario | 1 | 1 to 2 | >3 |  | label | text box
| No of Validation on the fields | 1 to 5 | 5 To 10 | >10 |  | button
| No of Prefilled fields | 10 to 30 | 30 to 50 | >50 |  | drop down
| No of API Integrations | 2 | 2 to 5 | > 5 |  | checkbox
| No API integrations for saving the data | 3 | 3 to 5 | >5 |  | aadhar
| Queries or Business rules for the application | No validation or business rules. One data store | No validation or business rules. Up to 3 data stores | Validation or business rules involved. Multiple data stores |  | samagra integration
| No of Integration | 2 | 2 to 5 | >5 |  | report
| mobile App-UI | Static screen | Screen with 2-4 internal components | Screen with external components |  | MObile app
| Data Migration | Master Table | Table with data errors and involves Data validation and cleansing | Table with relationship with data errors and requires data validation and cleansing |  | submit
| Reports | tabular report. <10 columns. 1 data source Elements( Table, PIE chart, Report count: 1-2 | 2-3 data source. Simple (Pie/Bar) chart Elements( Stack,Line etc.) Report type: 3-5 | >3 data source. Multiple complex graphs Elements( Doughnut, Trend analysis etc.) Report type: More than 5 |  | clear
reset
Code element Data Tranformation Data Pre-processing Custom Build element API creation for UI\UX API Integration

## OM Billing Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | O&M Billing – Aaklan - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
O&M Billing – Abstract Report Generation | US-OM-C5-001 | As a GM and Contractor user, I want the Abstract Report auto-generated and available for download from the O&M Billing module so that billing summaries are formally captured without manual preparation. | 0 | 0 | 1 | 5 | High | Done | Sprint 17 | 20
O&M Billing – Contractor Mistake Correction by SQC/TL → GM | US-OM-C5-002 | As a TL (SQC/CSC), I want the ability to add or edit bill data fields on behalf of the Contractor before forwarding to GM so that contractor data entry mistakes are corrected without returning the full bill. | 0 | 1 | 0 | 3 | High | Done | Sprint 17 | 16
O&M Billing – Show All Records on All IDs (GM, SQC) | US-OM-C5-003 | As a GM (PIU) user, I want all O&M billing records from all contractor/firm submissions visible on GM and SQC login so that I do not miss any bill regardless of which login it was submitted from. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
O&M Billing – Merge PDF of All O&M Bill Documents | US-OM-C5-004 | As a GM and Contractor user, I want all O&M bill documents (approx. 19–20 documents per bill: GM, SQC, Firm, Form 27A, MB, Abstract, etc.) merged into a single PDF for a 3-month consolidated bill so that submission to higher authorities is a single file. | 0 | 1 | 0 | 3 | High | Done | Sprint 17 | 16
O&M Billing – Power Consumption: Contractor & GM Side Changes | US-OM-C5-005 | As a Contractor and GM user, I want the Power Consumption tab updated to include Contract Details (Basic Detail, Intermediate Raw Water Demand) and correct calculation logic so that electricity cost billing is accurate. | 0 | 0 | 1 | 5 | High | In Progress | Sprint 17-18 | 24
O&M Billing – Two New Columns in Water Supply During Construction Bill | US-OM-C5-006 | As a GM user, I want two new columns added to the Water Supply During Construction Bill so that construction-phase water supply data is captured completely. | 1 | 0 | 0 | 1 | Medium | In Progress | Sprint 17 | 8
O&M Billing – O&M Villages: Construction Approval Status | US-OM-C5-007 | As a GM user, I want O&M Villages to include villages where Water Supply During Construction is under consideration or approved so that construction-phase billing is inclusive and accurate. | 1 | 0 | 0 | 1 | Medium | In Progress | Sprint 18 | 8
O&M Billing – Aaklan Contractor Dispute: Dhara Data Discrepancy Window | US-OM-C5-008 | As a Contractor, I want a time-bound window to check Dhara meter reading data and raise a discrepancy before the O&M bill is finalised so that billing disputes are pre-empted and Dhara data is used as the authoritative source. | 0 | 1 | 0 | 3 | High | In Progress | Sprint 18 | 16
O&M Billing – GM: Pump Transformer 10% Deduction Logic | US-OM-C5-009 | As a GM user, I want the consolidated bill to automatically apply a 10% deduction on the total amount when the Pump Transformer column is marked YES so that penalty deductions are system-enforced. | 1 | 0 | 0 | 1 | High | In Progress | Sprint 18 | 8
O&M Billing Workflow – e-Sign via CDAC (Contractor & GM) | US-OM-C5-010 | As a Contractor and GM user, I want all O&M Bill documents digitally signed using e-Sign via CDAC (Aadhaar-based) so that the bill submission process is legally compliant and paperless. | 0 | 0 | 1 | 5 | High | In Progress | Sprint 17-18 | 40
O&M Billing – GM (PIU) Login: Bill PDF (19–20 Docs) & 3-Month Consolidation | US-OM-C5-011 | As a GM (PIU) user, I want to view and download a consolidated Bill PDF comprising 19–20 documents for a 3-month bill cycle so that I can submit a single complete document package to GM (O&M). | 0 | 1 | 0 | 3 | High | Done | Sprint 17 | 12
O&M Billing – Sahbhagita Generate Abstract: Select RA Bill & Tag All | US-OM-C5-012 | As a Sahbhagita PM user, I want to generate an Abstract report by selecting a specific RA Bill number and tagging all activities to that bill so that Sahbhagita billing is linked to O&M billing cycles. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
O&M Billing – Landscape Issue Fix in O&M Bill Layout | US-OM-C5-013 | As a GM user, I want the Landscape orientation issue in the O&M Bill PDF resolved so that all pages print and display correctly without layout distortion. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 4
O&M Billing – LGD Code Integration: LG Directory → MPSQC | US-OM-C5-014 | As a system admin, I want LGD Code integration from the LG Directory into MPSQC (Revenue Portal) so that O&M village and scheme data is aligned with national LGD codes. | 1 | 0 | 0 | 1 | Medium | In Progress | Sprint 18 | 8
O&M Billing - Residual Pressure & Complaint Redressal Report Format | US-OM-C5-015 | As a GM (PIU)/O&M user, I want the Residual Pressure report reformatted to the OM_RA_Bill_Report.pdf column layout and the Complaint Redressal screen relabeled with resolution status, so that pressure exceptions and complaint outcomes are captured in the department-approved format. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
O&M Billing - Complaint Redressal: 48-Hour Flag & Penalty Relaxation | US-OM-C5-016 | As a GM (PIU)/O&M user, I want the Complaint Redressal sheet to capture the received date, auto-flag complaints unresolved beyond 48 hours, and support a Penalty Relaxation (Yes/No) field with document upload, so that penalty calculation and relaxation are auditable. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 6
O&M Billing - GST Number Integration | US-OM-C5-017 | As a Contractor and GM (PIU) user, I want my GST number captured at the firm/contractor level and reflected on the bill PDF and abstract, so that generated bills are GST-compliant. | 1 | 0 | 0 | 1 | Medium | Open | Sprint 18 | 8
TOTAL O&M BILLING – AAKLAN ESTIMATION (CYCLE 5) | [5 empty] | 37 |  |  |  | 218
| Total Count |  |  |  |  | 37 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 37 | Point | [5 empty] | Data Communications |  | 0
| Effort | 205.5556 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 238.7528 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 250.6904 | 226.8151 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 325 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -86.2472 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 218 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Sahbhagita Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Sahbhagita - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Sahbhagita – RA Bill for ISA (replacing CP Manager) | US-SAH-C5-001 | As an ISA Manager user, I want RA Bill functionality moved from CP Manager to ISA Manager login so that ISA-specific billing is role-accurate and ISA can raise bills independently. | 0 | 1 | 0 | 3 | High | Done | Sprint 17 | 12
Sahbhagita – Village-wise & Combined Activity Report | US-SAH-C5-002 | As a GM and ISA user, I want Sahbhagita reports available in both Village-wise and Combined Activity views so that activity tracking is possible at both individual village and aggregate levels. | 0 | 1 | 0 | 3 | High | Done | Sprint 17 | 16
Sahbhagita – Master Activity List Update (22 Combined + 32 Village-wise) | US-SAH-C5-003 | As a system admin, I want the Sahbhagita master activity list updated to the finalised 22 Combined Activities and 32 Village-wise Activities so that all ISA submissions are mapped to the correct master. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
Sahbhagita – Photo Scan AI: Face & Background Detection (CP Manager Review) | US-SAH-C5-004 | As a CP Manager, I want an AI-based photo scan to detect duplicate face and background at the time of CP Manager review so that fraudulent or repeated activity submissions are flagged automatically. | 0 | 0 | 1 | 5 | Medium | In Progress | Sprint 18 | 20
Sahbhagita – Hyperlink: Village Name → Village Activity → Document Preview | US-SAH-C5-005 | As a GM and ISA user, I want a hyperlink on Village Name in the Sahbhagita report that drills down to Village Activity list and then opens Document Preview popup so that I can review all field evidence without leaving the report. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
Sahbhagita – RA Bill: RA(1) till RA(12) Withhold Bills | US-SAH-C5-006 | As a PM user, I want RA Bill numbers from RA(1) to RA(12) to be supported, with the ability to withhold specific RA Bills so that billing cycles are properly managed per ISA contract. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
Sahbhagita – Customised Report (ISA – Mainly Contractor Convention) | US-SAH-C5-007 | As an ISA user, I want a customised Sahbhagita report primarily aligned to the contractor-convention billing structure so that ISA RA bills are correctly mapped to MPJN billing norms. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
Sahbhagita – Save as Draft for Video, Image & Document (Mobile CR) | US-SAH-C5-008 | As an FE mobile user, I want Save as Draft functionality for activity submissions that include video, image, and document uploads so that field evidence can be captured in stages without losing partial submissions. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
Sahbhagita - Pagination on Approval Pages | US-SAH-C5-009 | As an ISA Manager/CP Manager, I want the Sahbhagita approval listing pages paginated, so that I can review and approve activity records in manageable batches instead of one long scrolling page. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 6
Sahbhagita - FE Visibility Scoped to Assigned ISA | US-SAH-C5-010 | As an ISA user, I want to see only the Field Executives (FE) specifically mapped to my ISA, so that I don't have to sift through FE records belonging to other ISAs. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 6
Sahbhagita - Self-Service Password Reset for ISA Login | US-SAH-C5-011 | As an ISA user, I want a self-service password reset option on my login, so that I can regain access without waiting on the admin team. | 1 | 0 | 0 | 1 | Low | Done | Sprint 17 | 4
TOTAL SAHBHAGITA ESTIMATION (CYCLE 5) | [5 empty] | 19 |  |  |  | 104
| Total Count |  |  |  |  | 19 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 19 | Point | [5 empty] | Data Communications |  | 0
| Effort | 105.5556 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 122.6028 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 128.7329 | 116.4726 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 271 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -148.3972 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 104 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Dhara Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Dhara (Reports, Corrections, Disputes) - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Dhara – Report Corrections (Approved Village MWSR, DWSR, OHT) | US-DHR-C5-001 | As a GM user, I want Dhara report corrections applied to Approved Village MWSR, DWSR, and OHT report pages so that report data is accurate and error-free for O&M billing purposes. | 0 | 1 | 0 | 3 | High | Done | Sprint 17 | 16
Dhara – Report Format Standardisation (27 May 2026 Format) | US-DHR-C5-002 | As a GM user, I want Dhara reports standardised to the approved format of 27 May 2026 so that all Dhara reports across all logins have consistent column layout, headers, and data ordering. | 0 | 1 | 0 | 3 | High | Done | Sprint 17 | 12
Dhara – Approved Reports & Contractor Dispute Window | US-DHR-C5-003 | As a Contractor user, I want to view GM-approved Dhara meter reading reports and raise a dispute within a defined time window so that incorrect meter data is challenged before O&M billing is finalised. | 0 | 1 | 0 | 3 | High | In Progress | Sprint 17-18 | 16
Dhara – New Dhara Reports Visible on All Jal Rekha Logins | US-DHR-C5-004 | As a CGM, PMU, and higher official user, I want the new Dhara reports (MWSR, DWSR, OHT, UFW) visible on all Jal Rekha logins (not just GM) so that scheme water supply data is accessible at all governance levels. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
Dhara – Dhara Entry Lock (Approved Data Should Not Change) | US-DHR-C5-005 | As a GM user, I want approved Dhara meter reading entries locked from further changes so that billing data integrity is maintained after GM approval. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
Dhara – OHT/WTP/Intake Base Capacity Column in Report | US-DHR-C5-006 | As a GM user, I want OHT, WTP, and Intake Base Capacity columns added to the relevant Dhara reports so that water supply adequacy can be assessed against infrastructure capacity. | 1 | 0 | 0 | 1 | Medium | In Progress | Sprint 18 | 8
Dhara - Approved Report Data Correction (Agreed with Kapil Sir) | US-DHR-C5-007 | As a GM (PIU) user, I want the previously identified data discrepancies in the Approved Report corrected as agreed with Kapil Sir, so that approved data accurately reflects the correct figures before it is used downstream for O&M billing. | 1 | 0 | 0 | 1 | High | Done | Sprint 18 | 8
Dhara - Non-Mandatory Remark, Photo Upload, Forward & Backward Options | US-DHR-C5-008 | As a user on any Jal Rekha login, I want the Remark, Photo Upload, Forward and Backward options in Dhara to be available but not mandatory, so that I can use them when relevant without being blocked from submitting. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 6
TOTAL DHARA (REPORTS, CORRECTIONS, DISPUTES) ESTIMATION (CYCLE 5) | [5 empty] | 14 |  |  |  | 82
| Total Count |  |  |  |  | 14 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 14 | Point | [5 empty] | Data Communications |  | 0
| Effort | 77.7778 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 90.3389 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 94.8558 | 85.8219 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 112 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -21.6611 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 82 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Vistrit Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Vistrit (Master Module) - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Vistrit – WTP Meter Mapping: New Columns (Date, Scheme, PIU, Meter Name) | US-VST-C5-001 | As a GM user, I want new columns – Date, Scheme, PIU, and Meter Name (e.g., Narela-WTP-01) – added to WTP Meter Mapping and Intake Mapping so that asset identification is standardised. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
Vistrit – OTP Verification for GM Edit/Delete on Scheme, OHT, Bulk Master | US-VST-C5-002 | As a system admin, I want OTP verification applied to GM login when performing Edit or Delete operations on Scheme Village Mapping, OHT Mapping, and Bulk Consumer Mapping so that master data changes are authenticated. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
Vistrit – Scheme Village Mapping: Testing/Permitted Field Validation & Census Population | US-VST-C5-003 | As a data admin, I want validation applied to Testing and Permitted fields in Scheme Village Mapping and Census Population left open at all levels so that mapping data quality is enforced without blocking census entries. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 6
Vistrit – OHT Deactivate Bug Fix (OHT Not Visible in FE Login) | US-VST-C5-004 | As an FE user, I want OHTs that are deactivated in Vistrit but active in FE login to be correctly displayed so that field engineers do not miss active OHTs due to a master data deactivation bug. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
Vistrit – WTP Meter Naming Convention Standardisation | US-VST-C5-005 | As a system admin, I want WTP Meter names standardised to a consistent naming convention (e.g., Narela-WTP-01) across the Vistrit Master module so that meter asset identification is uniform. | 1 | 0 | 0 | 1 | Low | Done | Sprint 17 | 4
TOTAL VISTRIT (MASTER MODULE) ESTIMATION (CYCLE 5) | [5 empty] | 5 |  |  |  | 34
| Total Count |  |  |  |  | 5 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 5 | Point | [5 empty] | Data Communications |  | 0
| Effort | 27.7778 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 32.2639 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 33.8771 | 30.6507 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 0 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 32.2639 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 34 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## FHTC Parinam Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | FHTC Parinam - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
FHTC Parinam – Nasamajh Family Head ID & Add Connection | US-FHTC-C5-001 | As a Contractor user, I want to access Family Head ID for Nasamajh (uncategorised) families with an upper cap of 3 household connections per family and add tap connections for them so that all eligible households including uncategorised families are covered. | 0 | 1 | 0 | 3 | High | In Progress | Sprint 17 | 16
FHTC Parinam – FE Name Shown in Reports | US-FHTC-C5-002 | As a GM user, I want the FE (Field Engineer) name to appear in FHTC Parinam reports so that inspection accountability is traceable at the individual FE level. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 4
FHTC Parinam – Contractor Search Option | US-FHTC-C5-003 | As a Contractor user, I want a search option on the FHTC Parinam Contractor login page so that I can locate specific tap connection records quickly across large datasets. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 4
FHTC Parinam – Samagra API Integration for Household Data | US-FHTC-C5-004 | As a system developer, I want Samagra API integrated with FHTC Parinam so that household data (Family Head ID, Member ID, address) is auto-fetched from the state Samagra citizen database without manual entry. | 0 | 0 | 1 | 5 | High | In Progress | Sprint 17-18 | 24
FHTC Parinam - Multiple Surveys per Samagra ID | US-FHTC-C5-005 | As an FE/GM (PIU) user, I want the system to allow more than one survey to be recorded against the same FHTC Samagra ID, so that genuine repeat/revisit surveys aren't blocked by a false duplicate restriction. | 1 | 0 | 0 | 1 | Medium | UAT Done | Sprint 18 | 8
TOTAL FHTC PARINAM ESTIMATION (CYCLE 5) | [5 empty] | 11 |  |  |  | 56
| Total Count |  |  |  |  | 11 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 11 | Point | [5 empty] | Data Communications |  | 0
| Effort | 61.1111 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 70.9806 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 74.5296 | 67.4315 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 108 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -37.0194 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 56 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## BISAC Integration Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | BISAC / NIC Asset Integration - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
BISAC – NIC Asset ID Mapping (Asset & Junction Mapping) | US-BISAC-C5-001 | As a system admin, I want NIC Asset IDs integrated with BISAC for Junction-to-Junction Map, Asset Mapping, and Pipeline Tracking so that Jal Rekha asset data is aligned with the national GIS system. | 0 | 0 | 1 | 5 | High | In Progress | Sprint 18 | 24
BISAC – Pipeline Mapping with BISAC Junction Data | US-BISAC-C5-002 | As a project manager, I want pipeline asset data mapped using BISAC Junction-to-Junction track data so that complete pipeline route and network is visualised on the Jal Rekha GIS portal. | 0 | 0 | 1 | 5 | High | In Progress | Sprint 18 | 20
BISAC – Village LGD Code Integration (Village without LGD = Habitation) | US-BISAC-C5-003 | As a data admin, I want BISAC LGD Code logic applied so that villages without an LGD Code are automatically classified as Habitations so that data quality is maintained across BISAC and LGD master sources. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
TOTAL BISAC / NIC ASSET INTEGRATION ESTIMATION (CYCLE 5) | [5 empty] | 11 |  |  |  | 52
| Total Count |  |  |  |  | 11 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 11 | Point | [5 empty] | Data Communications |  | 0
| Effort | 61.1111 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 70.9806 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 74.5296 | 67.4315 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 0 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 70.9806 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 52 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## eSign CDAC Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | e-Sign via CDAC (Aadhaar) - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
e-Sign CDAC – FE e-Sign via Mobile/Web (All Logins) | US-ESIGN-C5-001 | As a Field Engineer, I want to e-Sign inspection records and reports using CDAC Aadhaar-based e-Sign so that digital signatures are legally valid and the system is fully paperless. | 0 | 0 | 1 | 5 | High | In Progress | Sprint 17-18 | 30
e-Sign CDAC – Contractor/Firm e-Sign for O&M Bill Documents | US-ESIGN-C5-002 | As a Contractor user, I want to e-Sign the O&M Bill Submission Letter, Abstract, and Tax Invoice using CDAC e-Sign so that bill submission is legally compliant without physical signatures. | 0 | 0 | 1 | 5 | High | In Progress | Sprint 17-18 | 20
e-Sign CDAC – TL (PMC) Recommendation Letter (E-Office Generated) | US-ESIGN-C5-003 | As a TL (PMC) user, I want to generate and e-Sign the Recommendation Letter as an E-Office generated document via CDAC so that the PMC review is formally certified. | 0 | 1 | 0 | 3 | Medium | In Progress | Sprint 18 | 16
e-Sign CDAC – TL (SQC) & TL (PMC) Account Office Jal Rekha Integration | US-ESIGN-C5-004 | As a TL (SQC) and TL (PMC) user, I want CDAC e-Sign integrated with Jal Rekha Account Office workflow so that billing documents are routed and signed digitally through the Account Office system. | 0 | 1 | 0 | 3 | Medium | In Progress | Sprint 18 | 16
TOTAL E-SIGN VIA CDAC (AADHAAR) ESTIMATION (CYCLE 5) | [5 empty] | 16 |  |  |  | 82
| Total Count |  |  |  |  | 16 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 16 | Point | [5 empty] | Data Communications |  | 0
| Effort | 88.8889 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 103.2444 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 108.4067 | 98.0822 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 0 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 103.2444 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 82 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Anusharavan Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Anusharavan (June CR) - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Anusharavan – Multi-Date in Report: FE RFI Submission Date & Block Name | US-ANS-C5-001 | As a GM user, I want the Anusharavan RFI report to include multiple dates (FE RFI Submission Date alongside inspection date) and Block Name column so that inspection traceability is enhanced. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
Anusharavan – OHT Search Option During RFI | US-ANS-C5-002 | As a Contractor and FE user, I want an OHT search option during the RFI creation process so that the correct OHT can be quickly identified without scrolling through large dropdown lists. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 6
Anusharavan – Remove Mandatory GPS/Village for Intake, WTP, MBR, RWPM, CWPM | US-ANS-C5-003 | As a Contractor user, I want District, Block, GP, and Village selection to be non-mandatory for Intake, WTP, MBR, RWPM, and CWPM components during RFI creation so that non-site-specific components can be registered without location barrier. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 4
TOTAL ANUSHARAVAN (JUNE CR) ESTIMATION (CYCLE 5) | [5 empty] | 3 |  |  |  | 18
| Total Count |  |  |  |  | 3 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 3 | Point | [5 empty] | Data Communications |  | 0
| Effort | 16.6667 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 19.3583 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 20.3263 | 18.3904 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 70 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -50.6417 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 18 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Cube Testing Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Cube Testing (June CR) - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Cube Testing – Show Rejected Data to Contractor | US-CUBE-C5-001 | As a Contractor user, I want to see rejected cube test records in my login so that I can re-submit or address the rejection reason without contacting GM separately. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 6
Cube Testing – Cube ID Generated Before Image Upload | US-CUBE-C5-002 | As a Contractor user, I want the Cube Test ID to be generated first before uploading images so that images are linked to a confirmed Cube ID and cannot be submitted without a valid record. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 6
Cube Testing – Filter Bed Sub-Component Under WTP | US-CUBE-C5-003 | As a Contractor user, I want 'Filter Bed' added as a sub-component under the WTP component in the Cube Testing module so that filter bed quality testing is properly recorded. | 1 | 0 | 0 | 1 | Low | Done | Sprint 17 | 4
Cube Testing - Re-Inspection Loop (2nd Loop after GM Rejection) | US-CUBE-C5-004 | As an FE/GM/Contractor/SQC/TPIA user, I want a working re-inspection loop so a rejected cube record cycles back through FE to GM to Contractor, back to GM, then SQC/TPIA, then to a newly assigned FE if applicable, so that corrections are fully re-verified through the quality chain. | 0 | 1 | 0 | 3 | High | Done | Sprint 18 | 16
Cube Testing - Optional Image Upload on Second RFI Loop | US-CUBE-C5-005 | As an FE/Contractor user, I want image upload to be optional (not mandatory) on the second RFI loop pass for Cube Testing, so that minor re-inspection corrections aren't blocked by recapturing images already provided the first time. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 18 | 6
TOTAL CUBE TESTING (JUNE CR) ESTIMATION (CYCLE 5) | [5 empty] | 7 |  |  |  | 38
| Total Count |  |  |  |  | 7 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 7 | Point | [5 empty] | Data Communications |  | 0
| Effort | 38.8889 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 45.1694 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 47.4279 | 42.911 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 345 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -299.8306 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 38 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## SVS Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | SVS Water Supply Monitoring (June CR) - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
SVS – Bilingual Conversion (Hindi/English) for Water Supply Entry Page | US-SVS-C5-001 | As an MP government user, I want the SVS Daily Water Supply entry page to support bilingual labels (Hindi and English) and report column headers to be in Hindi so that GP-level users can operate in their native language. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
SVS – Login-Specific District, Block, GP Auto-Selection | US-SVS-C5-002 | As a GP or Block-level user, I want District, Block, and GP pre-selected according to my login credentials so that I do not need to manually navigate the location hierarchy on every submission. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 4
SVS – Additional Reason for NO Supply & Spelling Correction | US-SVS-C5-003 | As a GP user, I want one additional reason option added to the NO supply dropdown and any spelling errors in existing reason options corrected so that supply failure recording is accurate. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 4
SVS – Remove JJM ID and Village Status Fields | US-SVS-C5-004 | As a PHE department stakeholder, I want the JJM ID field and Village Status field removed from the SVS Daily Water Supply monitoring form so that the form is simplified to current operational requirements. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 4
TOTAL SVS WATER SUPPLY MONITORING (JUNE CR) ESTIMATION (CYCLE 5) | [5 empty] | 4 |  |  |  | 20
| Total Count |  |  |  |  | 4 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 4 | Point | [5 empty] | Data Communications |  | 0
| Effort | 22.2222 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 25.8111 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 27.1017 | 24.5206 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 105 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -79.1889 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 20 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Vistrit OTP Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Vistrit OTP & Validation - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Vistrit – OTP Verification on Scheme/OHT/Bulk Master (GM Edit/Delete) | US-VST-OTP-C5-001 | As a GM user, I want OTP verification required before performing Edit or Delete on Scheme Village Mapping, OHT Mapping, and Bulk Consumer Master so that unauthorised master data changes are prevented. | 1 | 0 | 0 | 1 | High | Done | Sprint 17 | 8
Vistrit – Scheme Village Mapping: Duplicate Village Validation | US-VST-OTP-C5-002 | As a data admin, I want duplicate village mapping validation applied across schemes so that a village is not accidentally mapped to multiple schemes resulting in data conflicts. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 4
TOTAL VISTRIT OTP & VALIDATION ESTIMATION (CYCLE 5) | [5 empty] | 2 |  |  |  | 12
| Total Count |  |  |  |  | 2 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 2 | Point | [5 empty] | Data Communications |  | 0
| Effort | 11.1111 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 12.9056 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 13.5508 | 12.2603 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 0 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 12.9056 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 12 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## CMMI Doc Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | CMMI Documentation - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
CMMI Doc – Cycle 5 Data Collection (June 2026) | US-CMMI-C5-001 | As a SEPG team member, I want to initiate and maintain data collection for Cycle 5 (June–July 2026) so that project performance metrics are captured for CMMI Level 5 audit preparation. | 0 | 0 | 1 | 5 | High | In Progress | Sprint 17-18 | 40
CMMI Doc – Streamline Documentation for Cycle 5 Modules | US-CMMI-C5-002 | As a quality manager, I want CMMI documentation streamlined for all Cycle 5 modules (O&M Billing Workflow, Sahbhagita, Dhara, e-Sign, BISAC) so that audit artifacts are consistent and complete for CMMI L5 standards. | 0 | 0 | 1 | 5 | High | In Progress | Sprint 17-18 | 60
TOTAL CMMI DOCUMENTATION ESTIMATION (CYCLE 5) | [5 empty] | 10 |  |  |  | 100
| Total Count |  |  |  |  | 10 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 10 | Point | [5 empty] | Data Communications |  | 0
| Effort | 55.5556 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 64.5278 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 67.7542 | 61.3014 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 200 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -135.4722 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 100 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## OM Billing Workflow Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | O&M Billing Workflow Module - Multi-Level Approval Chain. Note: the 16 stories on this sheet are carried forward unchanged from the Cycle 4 (Jan-May 2026) register (no Cycle 5 Effort figure was separately logged against them), but the workflow remained an active discussion/effort item in Cycle 5 per the June/July MoM and Date-Wise Time Sheet (30 hrs actual, Jun-Jul 2026).
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
O&M Billing Workflow – Firm Bill Submission | US-OMWF-C4-001 | As a Firm/Contractor, I want to generate the O&M bill along with submission letter and supporting documents (electricity bills, PHE test reports, tax invoice) so that the billing process can begin with complete documentation. | 0 | 1 | 0 | 3 | High | Done | Sprint 12 | 0
O&M Billing Workflow – GM (PIU) Forward to TL (CSC) | US-OMWF-C4-002 | As a GM (PIU), I want to review the firm-submitted bill and forward it to TL (CSC) so that the bill proceeds for committee-level scrutiny. | 0 | 1 | 0 | 3 | High | Done | Sprint 12 | 0
O&M Billing Workflow – TL (CSC) Review & Recommendation | US-OMWF-C4-003 | As a TL (CSC/SQC), I want to add or edit bill data and provide a recommendation letter so that GM (PIU) receives a vetted bill for final data entry. | 0 | 1 | 0 | 3 | High | Done | Sprint 12-13 | 0
O&M Billing Workflow – GM (PIU) Final Data Entry & Signed Document Upload | US-OMWF-C4-004 | As a GM (PIU), I want to add/edit final bill data and upload the signed MB, signed abstract, signed bill sheet, Form 27A, and relaxation letter so that the bill is certified and ready for O&M escalation. | 0 | 1 | 0 | 3 | High | Done | Sprint 13 | 0
O&M Billing Workflow – GM (O&M) to TL (PMC) Routing | US-OMWF-C4-005 | As a GM (O&M), I want the bill forwarded from GM (PIU) to be routed to TL (PMC) for recommendation with supporting documents so that the bill undergoes project management consultant review. | 0 | 1 | 0 | 3 | High | Done | Sprint 13 | 0
O&M Billing Workflow – DGM (O&M) Review | US-OMWF-C4-006 | As a DGM (O&M), I want to review bills recommended by TL (PMC) so that I can validate billing accuracy before passing the order. | 0 | 1 | 0 | 3 | High | Done | Sprint 13-14 | 0
O&M Billing Workflow – GM (O&M) Pass Order & HO Letter Upload | US-OMWF-C4-007 | As a GM (O&M), I want to upload the Pass Order copy (signed by DGM O&M) and the signed letter received from HO so that the bill is certified for regional CGM-level processing. | 0 | 1 | 0 | 3 | High | Done | Sprint 14 | 0
O&M Billing Workflow – CGM Regional Office Routing | US-OMWF-C4-008 | As a CGM (Regional Office user), I want to receive and process O&M bills routed from GM (O&M) for my respective region so that regional-level billing escalation is managed correctly. | 0 | 1 | 0 | 3 | High | Done | Sprint 14 | 0
O&M Billing Workflow – CA Financial Review | US-OMWF-C4-009 | As a CA (Chartered Accountant/Finance reviewer), I want to review the financial accuracy of bills forwarded from CGM so that billing figures are validated before CFO sign-off. | 0 | 1 | 0 | 3 | High | Done | Sprint 14 | 0
O&M Billing Workflow – CFO Sign-off | US-OMWF-C4-010 | As a CFO, I want to review CA-approved bills and provide financial sign-off so that the bill is cleared for Project Director review. | 0 | 1 | 0 | 3 | High | Done | Sprint 15 | 0
O&M Billing Workflow – P.D. Review | US-OMWF-C4-011 | As a Project Director (P.D.), I want to review CFO-approved bills so that I can endorse them for final MD approval. | 0 | 1 | 0 | 3 | High | Done | Sprint 15 | 0
O&M Billing Workflow – MD Final Approval | US-OMWF-C4-012 | As an MD (Managing Director), I want to give final approval on bills that have passed through the complete approval chain so that payment processing can be initiated. | 0 | 1 | 0 | 3 | High | Done | Sprint 15 | 0
O&M Billing Workflow – Manage Bill (View Pending Bills) | US-OMWF-C4-013 | As any workflow-stage user (GM PIU, TL CSC, GM O&M, TL PMC, DGM O&M, CGM, CA, CFO, P.D., MD), I want a 'Manage' page showing all bills pending at my login so that I can take timely action without searching across modules. | 0 | 1 | 0 | 3 | High | Done | Sprint 13-14 | 0
O&M Billing Workflow – Document Upload Hub (Multi-Document Per Bill) | US-OMWF-C4-014 | As any workflow user, I want a consolidated document section on each bill (Firm Submission Letter, SQC/TL Recommendation, PIU Recommendation, Signed Abstract, Signed Monthly Bill Sheet, Tax Invoice, Form 27A, Third Party Water Quality Test Report, Signed Scanned MB, and Any Other Documents) so that all certifications are traceable in one place. | 0 | 1 | 0 | 3 | High | Done | Sprint 13 | 0
O&M Billing Workflow – GM (PIU) Login Screen Structure | US-OMWF-C4-015 | As a GM (PIU) user, I want the O&M login dashboard organised into Contractor/Firm view, View Pending Bills, and Manage sections so that I can navigate the bill workflow efficiently. | 0 | 1 | 0 | 3 | Medium | Done | Sprint 14 | 0
O&M Billing Workflow – End-to-End Workflow Testing | US-OMWF-C4-016 | As a QA engineer, I want end-to-end testing of the complete O&M Billing Workflow (Firm → GM PIU → TL CSC → GM PIU → GM O&M → TL PMC → DGM O&M → GM O&M → CGM → CA → CFO → P.D. → MD) so that the multi-level approval chain functions correctly across all 13 roles. | 0 | 1 | 0 | 3 | High | WIP | Sprint 15-16 | 0
TOTAL O&M BILLING WORKFLOW MODULE (MULTI-LEVEL APPROVAL CHAIN) ESTIMATION (CYCLE 5) | [5 empty] | 48 |  |  |  | 0
| Total Count |  |  |  |  | 48 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 48 | Point | [5 empty] | Data Communications |  | 0
| Effort | 266.6667 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 309.7333 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 325.22 | 294.2467 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 30 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 279.7333 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 0 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Material Testing Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Material Testing - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Material Testing - Re-Inspection Loop (2nd Loop after GM Rejection) | US-MAT-C5-001 | As an FE/GM/Contractor/SQC/TPIA user, I want the same re-inspection loop implemented for Cube Testing to also work for Material Testing, so that rejected material test records can be corrected and re-verified through the full approval chain. | 0 | 1 | 0 | 3 | High | In Progress | Sprint 18 | 16
Material Testing - Optional Image Upload on Second RFI Loop | US-MAT-C5-002 | As an FE/Contractor user, I want image upload to be optional on the second (re-inspection) RFI loop pass for Material Testing, consistent with Cube Testing, so that minor corrections aren't blocked by re-capturing images. | 1 | 0 | 0 | 1 | Medium | Open | Sprint 18 | 6
Material Testing - GM/Contractor Login Database & API Enhancements | US-MAT-C5-003 | As a system developer, I want the Material Testing database functions and web/mobile API services updated for GM and Contractor logins, so that the re-inspection loop and related business logic work reliably end-to-end. | 0 | 0 | 1 | 5 | Medium | In Progress | Sprint 18 | 20
TOTAL MATERIAL TESTING ESTIMATION (CYCLE 5) | [5 empty] | 9 |  |  |  | 42
| Total Count |  |  |  |  | 9 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 9 | Point | [5 empty] | Data Communications |  | 0
| Effort | 50 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 58.075 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 60.9787 | 55.1713 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 141 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -82.925 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 42 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Nirmal Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Nirmal Module - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Nirmal - Beneficiary Report Issue Fix | US-NRM-C5-001 | As a Nirmal module user, I want the reported issue in the Beneficiary Report resolved, so that beneficiary data displays correctly across the Nirmal inner pages. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
Nirmal - Contractor Login Report Counting Bug Fix | US-NRM-C5-002 | As a Contractor user, I want the Nirmal report counting issue on my login corrected, so that reported totals reflect the actual number of records. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 6
Nirmal - FE Mobile Reports Validation & Bug Fixes | US-NRM-C5-003 | As a Field Executive, I want the Nirmal Reports on my mobile login validated and any bugs fixed, so that the data I submit and view in the field is accurate. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
Nirmal - Test Scenario and Test Case Creation | US-NRM-C5-004 | As a QA engineer, I want documented test scenarios and test cases for the Nirmal Change Request, so that regression coverage is in place for future releases. | 1 | 0 | 0 | 1 | Low | Done | Sprint 17 | 6
TOTAL NIRMAL MODULE ESTIMATION (CYCLE 5) | [5 empty] | 4 |  |  |  | 28
| Total Count |  |  |  |  | 4 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 4 | Point | [5 empty] | Data Communications |  | 0
| Effort | 22.2222 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 25.8111 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 27.1017 | 24.5206 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 32 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -6.1889 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 28 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## AI Module FHTC Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | AI Module - FHTC Tap Connection Detection - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
AI Module - Tap & Person Detection Predictive Model | US-AI-C5-001 | As a project data scientist, I want a machine learning predictive model built for tap and person detection on FHTC connection photos, so that tap connection evidence can be automatically verified instead of relying solely on manual review. | 0 | 0 | 1 | 5 | High | Done | Sprint 17 | 40
AI Module - Tap Connection Buffer Region Validation (LLM/Pretrained Model Integration) | US-AI-C5-002 | As a project data scientist, I want the tap connection monitoring buffer region validated using an LLM-assisted identification approach and an integrated human-pretrained model, so that tap identification accuracy improves in ambiguous or edge-case images. | 0 | 0 | 1 | 5 | High | Done | Sprint 17 | 32
AI Module - FHTC Data Processing & Model Training Pipeline | US-AI-C5-003 | As a project data scientist, I want a repeatable data processing pipeline (including YOLOv8-based tap identification) for FHTC tap connection images, so that new field data can be efficiently prepared for model training and retraining. | 0 | 0 | 1 | 5 | Medium | Done | Sprint 17 | 32
TOTAL AI MODULE - FHTC TAP CONNECTION DETECTION ESTIMATION (CYCLE 5) | [5 empty] | 15 |  |  |  | 104
| Total Count |  |  |  |  | 15 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 15 | Point | [5 empty] | Data Communications |  | 0
| Effort | 83.3333 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 96.7917 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 101.6312 | 91.9521 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 147 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | -50.2083 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 104 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Master Data Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Master Data Module - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Master - Lock Scheme/Village/OHT Master Once Linked to Live Transactions | US-MSTR-C5-001 | As a GM (PIU) user, I want Scheme Master, Village Master and OHT Master entries to become locked once linked to live Dhara, O&M Billing or Asset Mapping transactions, so that master data can't be altered in a way that silently breaks downstream billing and reporting. | 0 | 1 | 0 | 3 | High | Open | Sprint 18 | 16
Master - Dhara Mapped Summary Report Search Debugging & Enhancement | US-MSTR-C5-002 | As a GM (PIU) user, I want the search functionality on the Dhara Mapped Summary report (used in Abstract report generation) debugged and enhanced, so that I can reliably locate the mapped records I need. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 8
Master - Village Deletion Restriction & Database Validation Message | US-MSTR-C5-003 | As a data admin, I want village deletion restricted with a clear database validation message when a village is in use, so that master data integrity is preserved and users understand why a deletion is blocked. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 17 | 6
TOTAL MASTER DATA MODULE ESTIMATION (CYCLE 5) | [5 empty] | 5 |  |  |  | 30
| Total Count |  |  |  |  | 5 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 5 | Point | [5 empty] | Data Communications |  | 0
| Effort | 27.7778 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 32.2639 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 33.8771 | 30.6507 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 16 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 16.2639 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 30 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Asset Mapping Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Asset Mapping (BISAC) - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Asset Mapping - SQC/TPIA Contractor Data & Report on Web | US-AST-C5-001 | As an SQC/TPIA/Contractor user, I want Asset Mapping data and reports available on the web portal, so that I can review and verify asset mapping records without relying solely on the mobile app. | 0 | 1 | 0 | 3 | Medium | Done | Sprint 17 | 12
Asset Mapping - API Integration & Frontend Bug Fixes | US-AST-C5-002 | As a system developer, I want Asset Mapping API integrations completed and identified frontend bugs fixed, so that asset data flows correctly between the mobile app, web portal, and BISAC integration. | 0 | 1 | 0 | 3 | Low | Done | Sprint 17 | 10
TOTAL ASSET MAPPING (BISAC) ESTIMATION (CYCLE 5) | [5 empty] | 6 |  |  |  | 22
| Total Count |  |  |  |  | 6 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 6 | Point | [5 empty] | Data Communications |  | 0
| Effort | 33.3333 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 38.7167 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 40.6525 | 36.7808 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 16 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 22.7167 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 22 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Bharosa Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Bharosa (Factory Testing) - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Bharosa - Item Master Duplicate Dropdown Entry Fix | US-BHR-C5-001 | As a Bharosa Factory Testing (Web) user, I want the duplicate data entry issue in the item master dropdown fixed, so that I don't select or record duplicate item entries during factory testing. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 18 | 6
Bharosa - Factory Testing Mobile Bug Fixes | US-BHR-C5-002 | As a Bharosa Factory Testing (Mobile) user, I want identified bugs in the mobile factory testing flow fixed, so that factory test submissions are reliable in the field. | 1 | 0 | 0 | 1 | Medium | Done | Sprint 18 | 8
TOTAL BHAROSA (FACTORY TESTING) ESTIMATION (CYCLE 5) | [5 empty] | 2 |  |  |  | 14
| Total Count |  |  |  |  | 2 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 2 | Point | [5 empty] | Data Communications |  | 0
| Effort | 11.1111 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 12.9056 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 13.5508 | 12.2603 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 7 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 5.9056 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 14 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Daily Inspection Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Daily Inspection - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Daily Inspection - Role-Based Report Modifications | US-DIN-C5-001 | As an SQC/TPIA/Contractor/GM/CGM/TL user, I want the Daily Inspection Report module modified to reflect the correct fields and views for my role, so that daily inspection data is relevant and actionable for each reviewer level. | 0 | 1 | 0 | 3 | Medium | Done | Sprint 17 | 12
Daily Inspection - Mobile App Bug Fixes | US-DIN-C5-002 | As a field user, I want identified bugs in the Daily Inspection mobile app fixed, so that daily inspection entries can be submitted reliably from the field. | 1 | 0 | 0 | 1 | Low | Done | Sprint 17 | 6
TOTAL DAILY INSPECTION ESTIMATION (CYCLE 5) | [5 empty] | 4 |  |  |  | 18
| Total Count |  |  |  |  | 4 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 4 | Point | [5 empty] | Data Communications |  | 0
| Effort | 22.2222 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 25.8111 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 27.1017 | 24.5206 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 20 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 5.8111 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 18 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## Sopan Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | Sopan - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
Sopan - Calendar Functionality for 2026-27 | US-SOP-C5-001 | As a Contractor (Web/Mobile), I want a calendar feature reflecting the 2026-27 calendar year on my Sopan login, so that I can plan and track activities against the correct project calendar year. | 0 | 1 | 0 | 3 | Medium | Open | Sprint 18 | 10
TOTAL SOPAN ESTIMATION (CYCLE 5) | [5 empty] | 3 |  |  |  | 10
| Total Count |  |  |  |  | 3 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 3 | Point | [5 empty] | Data Communications |  | 0
| Effort | 16.6667 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 19.3583 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 20.3263 | 18.3904 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 8 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 11.3583 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 10 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36

## QA Automation Est C5
| Type Of Work | Development | Enhancement and Customization (CR-driven)
| Project Name | Jal Rekha
| Remark | QA - User & Role Management Automation - Cycle 5 (June-July 2026)
| Basis | Consolidated User Story Register (Cycle 5) + Date-Wise Time Sheet (Cycle 5)
|  |  | Volume/Count of elements |  |  |  | Guidelines
Module + sub Module | User Story ID | Elements (User Story Description - Refer Guidelines) | Low Complexity | Medium complexity | High Complexity | Size | Priority | Status | Sprint | US Register Effort (hrs)
|  |  | 1 | 3 | 5
QA Automation - Selenium Scripts for User Login & Registration | US-QA-C5-001 | As a QA engineer, I want automated Selenium scripts for User Login and User Registration flows, so that regression testing of core access functionality is faster and repeatable across releases. | 0 | 1 | 0 | 3 | Medium | Done | Sprint 17 | 16
QA Automation - Internal Review Process for Automation Testing | US-QA-C5-002 | As a quality manager, I want a recurring internal review meeting for automation testing progress, so that automation coverage and defects are tracked consistently across sprints. | 1 | 0 | 0 | 1 | Low | Done | Sprint 17-18 | 4
TOTAL QA - USER & ROLE MANAGEMENT AUTOMATION ESTIMATION (CYCLE 5) | [5 empty] | 4 |  |  |  | 20
| Total Count |  |  |  |  | 4 |  |  | Value added factors
| Productivity | 0.18 | [6 empty] | Factor |  | Rating
| Size | 4 | Point | [5 empty] | Data Communications |  | 0
| Effort | 22.2222 | Man hours | [5 empty] | Distributed Data Processing |  | 0
| VAF | 1.01 | [6 empty] | Performance |  | 0
| Risk contingency | 0.05 | [6 empty] | Heavily used Configuration |  | 3
| Project Management | 0.1 | [6 empty] | Transaction Rate |  | 4
| Total Planned Effort | 25.8111 | Man hours | [5 empty] | Online Data Entry |  | 3
[9 empty] | End-User Efficiency |  | 2
| Permissible Range (Man hours) | 27.1017 | 24.5206 | [5 empty] | Online Update |  | 1
| Actual Consumed Hrs (Timesheet, Cycle 5) | 10 | Man hours | [5 empty] | Complex Processing |  | 3
| Variance (Planned - Actual) | 15.8111 | Man hours | [5 empty] | Reusability |  | 4
| US Register Total Effort (hrs, cross-check) | 20 | Man hours | [5 empty] | Installation Ease |  | 4
[9 empty] | Operational Ease |  | 4
[9 empty] | Multiple Sites |  | 4
[9 empty] | Facilitate Change |  | 4
[9 empty] | Total |  | 36